## Work_Completion_Browse638587240
Work Completion Browse
Project : GANGA ALTUS
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 24487 Records 1 to 24487
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
PWD license Charges | N/C | N/C | Kone Elevator (I) Pvt. Ltd | 1004 | 2024-05-31 | D Bldg.-Lift License Charges | 1 | 31600 | 0 | 31600 | 0 | 2024-06-01 | PWD Licensse Charges for D Building lift. | 100 |  | 107880 | 2024-06-01 | 31600 | 2024-06-03 18:01 | 0 | ANAND PUNDLIK JADHAV
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg Stilt Fl Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P3 Floor Staircase Ceiling Putty - 205.22 Sq.Ft | 184.698 | 1.25 | 0 | 230.8725 | 41.56 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5294.5075 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 3rd Fl-Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- Ground Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 5th Fl-Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 2nd Fl-Lobby Staircase Ceiling Putty | 33 | 1.25 | 0 | 41.25 | 7.42 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5484.13 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P1 Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 1st Fl-Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P1 Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 3rd Fl-Lobby Staircase Ceiling Putty | 33 | 1.25 | 0 | 41.25 | 7.42 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5484.13 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 2nd Fl-Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 4th Fl-Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P3 Floor Staircase Ceiling Putty - 205.22 Sq.Ft | 184.698 | 1.25 | 0 | 230.8725 | 41.56 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5294.5075 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P5 Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 5th Fl-Lobby Staircase Ceiling Putty | 33 | 1.25 | 0 | 41.25 | 7.42 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5484.13 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P5 Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 1st Fl-Lobby Staircase Ceiling Putty | 33 | 1.25 | 0 | 41.25 | 7.42 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5484.13 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- Ground Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P2 Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D- P2 Floor Staircase Ceiling Putty - 203.44 Sq.Ft | 183.096 | 1.25 | 0 | 228.87 | 41.2 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on ceiling for D-Bldg Parking Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5296.51 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg Stilt Fl Lobby Staircase Ceiling Putty | 189.414 | 1.25 | 0 | 236.7675 | 42.62 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5288.6125 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg Stilt Fl Lobby Staircase Wall Putty | 547.614 | 1.25 | 0 | 684.5175 | 123.22 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on wall for D-Bldg Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -4840.8625 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg Stilt Fl Lobby Staircase Wall Putty | 547.614 | 1.25 | 0 | 684.5175 | 123.22 | 2024-06-12 | Labour charges for Applying 2nd Coat Putty on wall for D-Bldg Fire Staircase-1 | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -4840.8625 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1005 | 2024-06-03 | D-Bldg 4th Fl-Lobby Staircase Ceiling Putty | 33 | 1.25 | 0 | 41.25 | 7.42 | 2024-06-12 | Labour charges for Applying 1st Coat Putty on ceiling for D-Bldg Fire Staircase-1 Painting work. | 100 |  | 108486 | 2024-06-22 | 5525.38 | 2024-06-27 15:20 | -5484.13 | SHUBHAM SURENDRA BAHADUR SINGH
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 24th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 12th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 5th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P5 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 20th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 6th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 13th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 21st Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 16th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 17th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 19th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 10th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 2nd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 15th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 7th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 3rd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 4th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P3 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P2 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 11th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 23rd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 22nd Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 8th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 14th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg P1 Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg Stilt Fl Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg LG Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 1st Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 18th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg 9th Fl-Lobby Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges for Granite with polish including transportation, loading & unloading of Material. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 1006 | 2024-06-04 | D-Bldg Ground Floor Lift Cladding Work | 59.13 | 110.7 | 0 | 6545.691 | 0 | 2024-07-24 | Material supply charges of Granite with Polish including transportation, loading & unloading of material for D-Bldg Parking Lift cladding work. | 100 |  | 109397 | 2024-07-29 | 202916.39 | 2024-08-05 14:01 | -196370.699 | PAPPU BAGELA
Total Station Point marking- | N/C | N/C | TANGENT SURVEYORS | 103 | 2020-09-26 | D-Building Point Mark | 2 | 4500 | 0 | 9000 | 0 | 2020-10-22 | Building Point marking as per Revised Setting out plan | 100 |  | 87878 | 2020-10-22 | 9000 | 2020-10-28 18:02 | 0 | VECTOR SURVEYORS
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-23 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-29 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-24 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-27 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-26 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-28 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Door Shutter fixing - | N/C | N/C | ATISH WARILAL KUMAR | 104 | 2020-09-26 | F-Bldg Carpentary Work Shop No-25 | 1 | 600 | 0 | 600 | 0 | 2022-10-29 | Labour Charges for- F Building Shops toilet Door Shutter fixing work | 100 |  | 96850 | 2022-10-31 | 4200 | 2022-12-03 10:56 | -3600 | ATISH WARILAL KUMAR
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1302-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1304-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1801-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1101-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1701-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1402-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1004-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1503-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1002-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1301-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1601-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1702-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1704-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1303-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1501-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1803-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1804-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1202-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1502-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1504-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1602-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1603-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1102-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1104-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1203-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1604-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1201-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1204-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1404-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1001-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1003-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1802-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1401-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1403-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1103-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting Work 3" BCE | N/C | N/C | VIRAJ CONSTRUCTION AND SERVICES | 1041 | 2024-07-04 | E-1703-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2024-07-13 | Labour charges for 3 inch Dia. Vertical Core Cutting work for E-Bldg Dry Balcony area. | 100 |  | 109093 | 2024-07-15 | 25200 | 1900-01-01 | -24500 | VIRAJ CONSTRUCTION AND SERVICES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 155 | 0 | 775000 | 139500 | 2021-12-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92881 | 2021-12-29 | 1187610 | 2022-01-06 15:03 | -412610 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2662.5 | 155 | 0 | 412687.5 | 74283.76 | 2021-11-22 12:54 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92427 | 2021-11-23 | 1237544.8 | 2021-12-04 12:26 | -824857.3 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking Footing & Column | 7823.33 | 32 | 0 | 250346.56 | 45062.38 | 2021-04-14 | E Bldg Substructure Work Footing & Column | 100 |  | 89901 | 2021-04-19 | 250346.56 | 2021-04-20 14:58 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5321.66 | 155 | 0 | 824857.3 | 148474.32 | 2021-11-22 12:54 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92427 | 2021-11-23 | 1237544.8 | 2021-12-04 12:26 | -412687.5 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12227 | 10 | 0 | 122270 | 22008.6 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571829 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
RCC Beam | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking RCC Beam | 15646.66 | 15 | 0 | 234699.9 | 42245.98 | 2021-03-23 | E Bldg Substructure Work RCC Beam | 100 |  | 89477 | 2021-03-24 | 234699.9 | 2021-03-26 16:19 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1900 | 140 | 0 | 266000 | 47880 | 2021-09-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91732 | 2021-09-29 | 842940 | 2021-10-07 17:08 | -576940 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 165 | 0 | 825000 | 148500 | 2022-01-25 17:03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93223 | 2022-01-27 | 1967012.85 | 2022-02-09 14:33 | -1142012.85 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2141.37 | 140 | 0 | 299791.8 | 53962.52 | 2021-11-02 10:43 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92307 | 2021-11-02 | 299791.8 | 2021-11-23 15:45 | 0 | VNE INFRA PROJECTS P LTD
Dressing, Levelling & Cleaning | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking Dressing Levelling &Cleaning | 15464.66 | 5.41 | 0 | 83663.8106 | 15065.06 | 2021-01-21 | E Bldg Substructure Work- Dressing,Levelling & Cleaning | 100 |  | 88779 | 2021-01-23 | 412274.6 | 2021-01-27 18:17 | -328610.7894 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5325 | 155 | 0 | 825375 | 148567.5 | 2021-11-30 09:51 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92755 | 2021-12-17 | 1083450 | 2021-12-17 12:23 | -258075 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5321.29 | 165 | 0 | 878012.85 | 158042.32 | 2022-01-25 17:03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93223 | 2022-01-27 | 1967012.85 | 2022-02-09 14:33 | -1089000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1600 | 165 | 0 | 264000 | 47520 | 2022-01-25 17:03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93223 | 2022-01-27 | 1967012.85 | 2022-02-09 14:33 | -1703012.85 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2662 | 155 | 0 | 412610 | 74269.8 | 2021-12-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92881 | 2021-12-29 | 1187610 | 2022-01-06 15:03 | -775000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1200 | 140 | 0 | 168000 | 30240 | 2021-09-04 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91429 | 2021-09-04 | 463540 | 2021-09-07 16:52 | -295540 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1665 | 155 | 0 | 258075 | 46453.5 | 2021-11-30 09:51 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92755 | 2021-12-17 | 1083450 | 2021-12-17 12:23 | -825375 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2889 | 140 | 0 | 404460 | 72802.8 | 2021-07-23 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 90971 | 2021-07-24 | 482693 | 2021-07-30 13:25 | -78233 | VNE INFRA PROJECTS P LTD
PCC | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking PCC Work | 7823.3 | 10 | 0 | 78233 | 14081.94 | 2021-07-23 | E Bldg Substructure Work PCC Work | 100 |  | 90971 | 2021-07-24 | 482693 | 2021-07-30 13:25 | -404460 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4121 | 140 | 0 | 576940 | 103849.2 | 2021-09-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91732 | 2021-09-29 | 842940 | 2021-10-07 17:08 | -266000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3184 | 140 | 0 | 445760 | 80236.8 | 2021-10-12 17:12 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92012 | 2021-10-12 | 1190740.6 | 2021-10-16 13:26 | -744980.6 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking Footing & Column | 7823.33 | 32 | 0 | 250346.56 | 45062.38 | 2021-01-21 | E Bldg Substructure Work Footing & Column | 100 |  | 88779 | 2021-01-23 | 412274.6 | 2021-01-27 18:17 | -161928.04 | VNE INFRA PROJECTS P LTD
PCC | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking PCC Work | 7823.33 | 10 | 0 | 78233.3 | 14082 | 2021-01-21 | E Bldg Substructure Work PCC Work | 100 |  | 88779 | 2021-01-23 | 412274.6 | 2021-01-27 18:17 | -334041.3 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5321.29 | 140 | 0 | 744980.6 | 134096.5 | 2021-10-12 17:12 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92012 | 2021-10-12 | 1190740.6 | 2021-10-16 13:26 | -445760 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2111 | 140 | 0 | 295540 | 53197.2 | 2021-09-04 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91429 | 2021-09-04 | 463540 | 2021-09-07 16:52 | -168000 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Podium Floor-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC W | 6626.32 | 255.45 | 0 | 1692693.444 | 304684.82 | 2022-03-17 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 94258 | 2022-04-08 | 1692693.44 | 2022-04-15 10:51 | 0.004 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Podium Floor-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC W | 8282.9 | 10 | 0 | 82829 | 14909.22 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -611270 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1665 | 140 | 0 | 233100 | 41958 | 2021-11-02 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92330 | 2021-11-03 | 233100 | 2021-12-04 12:24 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 4591 | 155 | 0 | 711605 | 128088.9 | 2022-03-17 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 94255 | 2022-04-08 | 711605 | 2022-04-15 10:50 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 6360.729 | 155 | 0 | 985912.995 | 177464.34 | 2022-05-11 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 94756 | 2022-05-11 | 985913 | 2022-05-21 11:12 | -0.005 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 7949.174 | 10 | 0 | 79491.74 | 14308.52 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800547.48 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 1589.7032 | 155 | 0 | 246403.996 | 44352.72 | 2022-08-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -633635.224 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 7949.174 | 10 | 0 | 79491.74 | 14308.52 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800547.48 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 750 | 145 | 0 | 108750 | 19575 | 2022-08-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -771289.22 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 7950 | 10 | 0 | 79500 | 14310 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800539.22 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 7950 | 10 | 0 | 79500 | 14310 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800539.22 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 1787 | 155 | 0 | 276985 | 49857.3 | 2021-11-22 12:56 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92428 | 2021-11-23 | 276985 | 2021-12-04 12:25 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 4060 | 145 | 0 | 588700 | 105966 | 2022-01-11 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93095 | 2022-01-12 | 588700 | 2022-01-28 12:55 | 0 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 7949.174 | 10 | 0 | 79491.74 | 14308.52 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800547.48 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 822 | 155 | 0 | 127410 | 22933.8 | 2022-08-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -752629.22 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 5386 | 145 | 0 | 780970 | 140574.6 | 2022-02-09 15:21 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93411 | 2022-02-10 | 780970 | 2022-02-23 17:55 | 0 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between Parking Footing & Column | 10509.22 | 28 | 0 | 294258.16 | 52966.46 | 2020-11-05 | Substructure Work Footing & Column | 100 |  | 88071 | 2020-11-06 | 336295.04 | 2020-11-09 18:41 | -42036.88 | VNE INFRA PROJECTS P LTD
Dressing, Levelling & Cleaning | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between Parking Dressing Levelling &Cleaning | 10509.22 | 4 | 0 | 42036.88 | 7566.64 | 2020-11-05 | Substructure Work-Dressing,Levelling & Cleaning | 100 |  | 88071 | 2020-11-06 | 336295.04 | 2020-11-09 18:41 | -294258.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 1787 | 145 | 0 | 259115 | 46640.7 | 2021-05-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 90342 | 2021-05-27 | 259115 | 2021-06-01 10:42 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 1787 | 145 | 0 | 259115 | 46640.7 | 2021-07-23 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91030 | 2021-07-30 | 259115 | 2021-09-20 16:42 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 2130 | 145 | 0 | 308850 | 55593 | 2021-08-23 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91711 | 2021-09-29 | 308850 | 2021-09-29 13:09 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 6360 | 205 | 0 | 1303800 | 234684 | 2022-06-06 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95003 | 2022-06-06 | 1303800 | 2022-06-20 16:23 | 0 | VNE INFRA PROJECTS P LTD
Trimix Work | N/C | N/C | JAI SAIRAM CONSTRUCTION | 120 | 2020-11-27 | Tower D Grade Slab Trimix Work | 2750 | 10 | 0 | 27500 | 0 | 2021-02-06 | Trimix Concreting Work | 100 |  | 88936 | 2021-02-08 | 27500 | 2021-02-10 17:06 | 0 | S.S. PADMAKAR
Trimix Work | N/C | N/C | JAI SAIRAM CONSTRUCTION | 120 | 2020-11-27 | D-Bldg Parking LGF Grade Slab Trimix Work | 1736 | 10 | 0 | 17360 | 3124.8 | 2022-08-04 | Trimix Concreting Work | 100 |  | 95814 | 2022-08-05 | 17360 | 2022-08-16 11:42 | 0 | JAI SAIRAM CONSTRUCTION
Trimix Work | N/C | N/C | JAI SAIRAM CONSTRUCTION | 120 | 2020-11-27 | D - LG Floor Parking Trimix work | 2166 | 10 | 0 | 21660 | 3898.8 | 2023-07-14 | Labour Charges for Trimix flooring work including Groove cutting filling work | 100 |  | 100699 | 2023-07-15 | 45307.2 | 2023-08-30 11:55 | -23647.2 | JAI SAIRAM CONSTRUCTION
Trimix Work - BC | N/C | N/C | JAI SAIRAM CONSTRUCTION | 120 | 2020-11-27 | F-Bldg LG Fl Parking Trimix Work | 2364.72 | 10 | 0 | 23647.2 | 4256.5 | 2023-07-14 | Labour Charges for Trimix Flooring work including Groove Cutting and Filling work. | 100 |  | 100699 | 2023-07-15 | 45307.2 | 2023-08-30 11:55 | -21660 | JAI SAIRAM CONSTRUCTION
Perma Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 122 | 2020-12-08 | Retaining Wall - Waterproofing Work | 160.3333 | 12 | 0 | 1923.9996 | 346.32 | 2022-08-25 | Bldg F Retaining wall Waterproofing work. vertical RCC retaining wall waterproofing Treatment | 100 |  | 95994 | 2022-08-26 | 1924 | 2022-12-03 11:02 | -0.0004 | AQUARIUS WATERPROOFING
Perma Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 122 | 2020-12-08 | D-Bldg Parking Ret Wall Waterproofing Work | 3055.1667 | 12 | 0 | 36662.0004 | 6599.16 | 2021-02-09 | Waterproofing Treatment for Vertical RCC Retaining wall incl Cleaning and Grinding all vertical surface,Removing all binding wire and nails from RCC wall,Open All cold Concrete joint in V shape and treat by perma polycreate plus SBR Bond | 100 |  | 89059 | 2021-02-23 | 36662 | 2021-02-23 13:08 | 0.0004 | AQUARIUS WATERPROOFING
Perma Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 122 | 2020-12-08 | E-Bldg Parking Retaining Wall Waterproofing | 1084 | 12 | 0 | 13008 | 2341.44 | 2021-10-08 | Bldg-E Retaining wall Waterproofing work. Vertical RCC Retaining Wall Waterproofing Treatment. | 100 |  | 91939 | 2021-10-09 | 13008 | 2022-01-28 18:11 | 0 | AQUARIUS WATERPROOFING
Perma Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 122 | 2020-12-08 | Retaining Wall - Waterproofing Work | 952 | 10 | 0 | 9520 | 1713.6 | 2022-03-02 | Bldg F Retaining wall Waterproofing work. Horizontal RCC retaining wall waterproofing Treatment | 100 |  | 96430 | 2022-09-30 | 9520 | 2023-01-17 18:17 | 0 | AQUARIUS WATERPROOFING
Perma Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 123 | 2020-12-08 | E-Bldg Parking Retaining Wall Waterproofing | 1084 | 30 | 0 | 32520 | 5853.6 | 2021-10-08 | Material Supply for Bldg-E Retaining wall Waterproofing work. Vertical RCC Retaining Wall Waterproofing Treatment. | 100 |  | 91944 | 2021-10-09 | 32520 | 2022-01-28 18:12 | 0 | AQUARIUS WATERPROOFING
Perma Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 123 | 2020-12-08 | Retaining Wall - Waterproofing Work | 160.3667 | 30 | 0 | 4811.001 | 865.98 | 2022-08-25 | Bldg F Retaining wall Waterproofing work. vertical RCC retaining wall waterproofing Treatment | 100 |  | 95995 | 2022-08-26 | 4811 | 2022-12-03 11:03 | 0.001 | AQUARIUS WATERPROOFING
Perma Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 123 | 2020-12-08 | Retaining Wall - Waterproofing Work | 952 | 27 | 0 | 25704 | 4626.72 | 2022-03-02 | Bldg F Retaining wall Waterproofing work. Horizontal RCC retaining wall waterproofing Treatment | 100 |  | 96431 | 2022-09-30 | 25704 | 2022-12-03 10:51 | 0 | AQUARIUS WATERPROOFING
Perma Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 123 | 2020-12-08 | D-Bldg Parking Ret Wall Waterproofing Work | 3055.1667 | 30 | 0 | 91655.001 | 16497.9 | 2021-02-09 | Material Supply for Waterproofing Treatment for Vertical RCC Retaining wall with NEOPROOF RC-202 plus 50 GSM Coating on entire RCC Retaining wall from back filling side | 100 |  | 89058 | 2021-02-23 | 91655 | 2021-02-23 13:09 | 0.001 | AQUARIUS WATERPROOFING
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 18.5 | 450 | 0 | 8325 | 0 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For Individual labour Registration Bill No-O-00040, dated-02/03/2021 | 89554 | 2021-03-29 | 8325 | 2021-03-30 13:03 | 0 | VISION MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 11.5 | 450 | 0 | 5175 | 931.5 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For Individual labour Registration Bill No-O-00043, dated-02/03/2021 | 89552 | 2021-03-29 | 5175 | 2021-03-30 13:03 | 0 | VISION MANAGEMENT SERVICES
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall PCC Work (L) | 7 | 250 | 0 | 1750 | 315 | 2020-12-28 | D Building Parking Area Retaining wall PCC Work for Raft with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting & unloading of material from store to required place in Contractor scope | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -511497 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 890.62 | 450 | 0 | 400779 | 72140.22 | 2020-12-28 | D Bldg Parking Area Shuttering work for Retaining wall | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -112468 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 6726 | 7.5 | 0 | 50445 | 9080.1 | 2020-12-28 | D Bldg Parking Area Reinforcement Work for Retaining wall for Fixing reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBSdrawing | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -462802 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 6.6667 | 450 | -0.02 | 3000.015 | 540 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For BOCW Act Registration Bill No-O-00042, dated-02/03/2021 | 89553 | 2021-03-29 | 3000 | 2021-03-30 13:03 | 0.015 | VISION MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Ret Wall Raft Work(L) | 30.74 | 400 | 0 | 12296 | 2213.28 | 2020-12-28 | D Bldg Parking Area Shuttering Work for Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -500951 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Ret Wall Raft Work(L) | 1532 | 7.5 | 0 | 11490 | 2068.2 | 2020-12-28 | D Bldg Parking Area Reinforcement work Fixing reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -501757 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Ret Wall Raft Work(L) | 21 | 250 | 0 | 5250 | 945 | 2020-12-28 | D Bldg Parking Area RCC work for Raft of specified grade of concrete including compaction by vibrator, with proper line level and roughening them if special finish is to be provided.Loading, shifting & unloading of material in Contractor Scope | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -507997 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 110.292 | 250 | 0 | 27573 | 4963.14 | 2020-12-28 | D Bldg Parking Area RCC work for Retaining wall of specified grade of concrete including all Reinforcement, shuttering (bothside), strutting, propping, concreting with compaction and removal of form etc completed as per drawing. | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -485674 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall PCC Work (L) | 9.16 | 400 | 0 | 3664 | 659.52 | 2020-12-28 | D Bldg Parking Area Retaining wall Shuttering work for PCC Raft | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -509583 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 21.1111 | 450 | 0 | 9499.995 | 1710 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For BOCW Act Registration Bill No-O-00039, dated-02/03/2021 | 89555 | 2021-03-29 | 9500 | 2021-03-30 13:04 | -0.005 | VISION MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall PCC For Retaining Wall Raft(L) | 3.24 | 400 | 0 | 1296 | 233.28 | 2021-04-19 | E Bldg Parking Area Retaining wall Shuttering work for Raft with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -231808.5 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall RCC (L) | 822.6667 | 7.5 | 0 | 6170.0003 | 1110.6 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Reinforcement work with Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -226934.4997 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Raft for Retaining Wall (L) | 349.3333 | 7.5 | 0 | 2619.9997 | 471.6 | 2021-04-19 | E Bldg Parking Area Retaining wall Reinforcement work for Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230484.5003 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall Raft (L) | 358 | 7.5 | 0 | 2685 | 483.3 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Reinforcement work with Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230419.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall RCC (L) | 156.46 | 450 | 0 | 70407 | 12673.26 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Shuttering work with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -162697.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 29.54 | 250 | 0 | 7385 | 1329.3 | 2021-04-19 | E Bldg Parking Area RCC Retaining wall of specified grade of concrete including compaction by vibrator,with proper line level and roughening them if special finish is to be provided Loading,shifting & unloading of material in Contractor scope. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -225719.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall Raft (L) | 9.97 | 250 | 0 | 2492.5 | 448.66 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Concrete work with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading,shifting & unloading of material from store to required place to be done by contractor | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230612 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Raft for Retaining Wall (L) | 9.4 | 250 | 0 | 2350 | 423 | 2021-04-19 | E Bldg Parking Area Retaining wall RCC work for Raft with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting & unloading of material from store to required place in contractor scope | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230754.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall PCC (L) | 4.31 | 400 | 0 | 1724 | 310.32 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Shuttering work with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -231380.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall PCC For Retaining Wall Raft(L) | 2.84 | 250 | 0 | 710 | 127.8 | 2021-04-19 | E Bldg Parking Area Retaining wall PCC Work for Raft with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting & unloading of material from store to required place in Contractor scope. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -232394.5 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 1657.4667 | 7.5 | 0 | 12431.0002 | 2237.58 | 2021-04-19 | E Bldg Parking Area Retaining wall Reinforcement work for Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -220673.4997 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall PCC (L) | 3.7 | 250 | 0 | 925 | 166.5 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Concrete work with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading,shifting & unloading of material from store to required place to be done by contractor | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -232179.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Raft for Retaining Wall (L) | 12.96 | 400 | 0 | 5184 | 933.12 | 2021-04-19 | E Bldg Parking Area Retaining wall Shuttering work for RCC Raft with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -227920.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 236.3 | 450 | 0 | 106335 | 19140.3 | 2021-04-19 | E Bldg Parking Area Retaining wall Shuttering work for Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -126769.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall RCC (L) | 19.56 | 250 | 0 | 4890 | 880.2 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Concrete work with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading,shifting & unloading of material from store to required place to be done by contractor | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -228214.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall Raft (L) | 13.75 | 400 | 0 | 5500 | 990 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Shuttering work with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -227604.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 17.8 | 250 | 0 | 4450 | 801 | 2021-07-23 | E Bldg Parking Area RCC Retaining wall of specified grade of concrete including compaction by vibrator,with proper line level and roughening them if special finish is to be provided Loading,shifting & unloading of material in Contractor scope. | 100 |  | 90973 | 2021-07-24 | 74406 | 2021-07-30 13:25 | -69956 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 781.0667 | 7.5 | 0 | 5858.0003 | 1054.44 | 2021-07-23 | E Bldg Parking Area Retaining wall Reinforcement work for Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 90973 | 2021-07-24 | 74406 | 2021-07-30 13:25 | -68547.9998 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 142.44 | 450 | 0 | 64098 | 11537.64 | 2021-07-23 | E Bldg Parking Area Retaining wall Shuttering work for Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 90973 | 2021-07-24 | 74406 | 2021-07-30 13:25 | -10308 | VNE INFRA PROJECTS P LTD
Pump Hiring for RMC-BC | N/C | N/C | PRISM JOHNSON LIMITED (SUPPLIER) | 153 | 2021-03-04 | D-Bldg RCC Work RMC Pump Charges | 269 | 190 | 0 | 51110 | 0 | 2021-03-23 | Pumping Charges for Concreting work | 100 |  | 93788 | 2022-03-11 | 51110 | 2022-03-11 14:17 | 0 | PRISM JOHNSON LIMITED (SUPPLIER)
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | E-Parking Excavation work | 1466 | 60 | 0 | 87960 | 0 | 2023-12-22 | Substructure Excavation work by Bucket & Shifting Inside | 100 | near well side Ramp Area | 104101 | 2023-12-25 | 109950 | 2024-01-02 11:44 | -21990 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | E-Parking Excavation work | 1466 | 15 | 0 | 21990 | 0 | 2023-12-22 | Spreading & Levelling Work | 100 |  | 104101 | 2023-12-25 | 109950 | 2024-01-02 11:44 | -87960 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | D&E Podium Excavation work | 83.58 | 15 | 0 | 1253.7 | 225.66 | 2021-03-23 | Spreading & Levelling Work | 100 |  | 89476 | 2021-03-24 | 112812.7 | 2021-03-30 13:00 | -111559 | SS ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | E-Parking Excavation work | 866.1333 | 60 | 0 | 51967.998 | 9354.24 | 2021-03-23 | Substructure Excavation work by Bucket & Shifting Inside | 100 |  | 89476 | 2021-03-24 | 112812.7 | 2021-03-30 13:00 | -60844.702 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | E-Parking Excavation work | 1050.9333 | 15 | 0 | 15763.9995 | 2837.52 | 2021-03-23 | Spreading & Levelling Work | 100 |  | 89476 | 2021-03-24 | 112812.7 | 2021-03-30 13:00 | -97048.7005 | SS ENTERPRISES
Excavation By Needle | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | E-Parking Excavation work | 184.82 | 210 | 0 | 38812.2 | 6986.2 | 2021-03-23 | Substructure Excavation work by Needle & Shifting Inside | 100 |  | 89476 | 2021-03-24 | 112812.7 | 2021-03-30 13:00 | -74000.5 | SS ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 155 | 2021-03-05 | D&E Podium Excavation work | 83.58 | 60 | 0 | 5014.8 | 902.66 | 2021-03-23 | Substructure Excavation work by Bucket & Shifting Inside | 100 |  | 89476 | 2021-03-24 | 112812.7 | 2021-03-30 13:00 | -107797.9 | SS ENTERPRISES
Levelling Work | N/C | N/C | SS ENTERPRISES | 180 | 2021-04-09 | E-Bldg Plinth murum back filling | 2504.44 | 30 | 0 | 75133.2 | 13523.98 | 2021-05-08 | Levelling Work in between Footing/column | 100 |  | 90161 | 2021-05-08 | 225399.6 | 2021-06-11 12:08 | -150266.4 | SS ENTERPRISES
Murum Filling (avail earth in site) | N/C | N/C | SS ENTERPRISES | 180 | 2021-04-09 | E-Bldg Plinth murum back filling | 2504.44 | 60 | 0 | 150266.4 | 27047.96 | 2021-05-08 | E Bldg Plinth Murum Backfilling work (Shifting inside) | 100 |  | 90161 | 2021-05-08 | 225399.6 | 2021-06-11 12:08 | -75133.2 | SS ENTERPRISES
Murum Filling (avail earth in site) | N/C | N/C | SS ENTERPRISES | 180 | 2021-04-09 | E-Bldg Plinth murum back filling | 2504.44 | 60 | 0 | 150266.4 | 27047.96 | 2021-08-29 | E Bldg Plinth Murum Backfilling work (Shifting inside) | 100 |  | 91343 | 2021-08-30 | 150266.4 | 2021-09-25 12:26 | 0 | SS ENTERPRISES
Levelling Work | N/C | N/C | SS ENTERPRISES | 180 | 2021-04-09 | E-Bldg Plinth murum back filling | 2504 | 30 | 0 | 75120 | 13521.6 | 2021-09-07 | Levelling Work in between Footing/column | 100 |  | 91444 | 2021-09-07 | 75120 | 2021-09-25 12:26 | 0 | SS ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P3-Fl RCC Parapet Wall (L) | 31.125 | 500 | 0 | 15562.5 | 2801.26 | 2022-10-04 | Labour charges for Shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -33653.28 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Shops pardi RCC work (L) | 421 | 450 | 0 | 189450 | 34101 | 2021-05-18 | D Bldg Shop Pardi Shuttering Work | 100 |  | 94807 | 2022-05-18 | 201499.5 | 2022-05-27 11:15 | -12049.5 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Shops pardi RCC work (L) | 737 | 7.5 | 0 | 5527.5 | 994.96 | 2021-05-18 | D Bldg Shop Pardi Reinforcement Work | 100 |  | 94807 | 2022-05-18 | 201499.5 | 2022-05-27 11:15 | -195972 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P1-Fl RCC Parapet Wall (L) | 31.125 | 500 | 0 | 15562.5 | 2801.26 | 2022-10-04 | Labour charges for Shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -33653.28 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P1-Fl RCC Parapet Wall (L) | 47.22 | 8 | 0 | 377.76 | 68 | 2022-10-04 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48838.02 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P2-Fl RCC Parapet Wall (L) | 31.125 | 500 | 0 | 15562.5 | 2801.26 | 2022-10-04 | Labour charges for Shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -33653.28 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P1-Fl RCC Parapet Wall (L) | 1.55 | 300 | 0 | 465 | 83.7 | 2022-10-04 | Labour charges for Concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48750.78 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P3-Fl RCC Parapet Wall (L) | 47.22 | 8 | 0 | 377.76 | 68 | 2022-10-04 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48838.02 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P3-Fl RCC Parapet Wall (L) | 1.55 | 300 | 0 | 465 | 83.7 | 2022-10-04 | Labour charges for Concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48750.78 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P2-Fl RCC Parapet Wall (L) | 47.22 | 8 | 0 | 377.76 | 68 | 2022-10-04 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48838.02 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P2-Fl RCC Parapet Wall (L) | 1.55 | 300 | 0 | 465 | 83.7 | 2022-10-04 | Labour charges for Concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48750.78 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | E-Bldg Shops RCC Work | 620 | 7.5 | 0 | 4650 | 837 | 2021-10-09 | E-Building Shop Pardi Reinforcement work (Fe 500). | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -399192 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | E-Bldg Shops RCC Work | 442.38 | 450 | 0 | 199071 | 35832.78 | 2021-10-09 | E-Building Shop Pardi Shuttering work. | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -204771 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | D&E Podium Shops RCC Work | 534 | 7.5 | 0 | 4005 | 720.9 | 2021-10-09 | D & E Building Podium Shop Pardi Reinforcement work (Fe 500). | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -399837 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | D&E Podium Shops RCC Work | 20.67 | 300 | 0 | 6201 | 1116.18 | 2021-10-09 | D & E Building Podium Shop Pardi Concrete work. | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -397641 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | E-Bldg Shops RCC Work | 22.55 | 300 | 0 | 6765 | 1217.7 | 2021-10-09 | E-Building Shop Pardi Cocreting work (M 50). | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -397077 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | D&E Podium Shops RCC Work | 407 | 450 | 0 | 183150 | 32967 | 2021-10-09 | D & E Building Podium Shop Pardi Shuttering work. | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -220692 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Shops pardi RCC work (L) | 21.74 | 300 | 0 | 6522 | 1173.96 | 2021-05-18 | D Bldg Shop Pardi Concreting Work (M 25) | 100 |  | 94807 | 2022-05-18 | 201499.5 | 2022-05-27 11:15 | -194977.5 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-02-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93787 | 2022-03-11 | 870064 | 2022-03-11 15:52 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2023-08-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 101491 | 2023-08-28 | 250980 | 2023-09-12 12:51 | -125490 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 101.682 | 140 | 0 | 14235.48 | 2562.38 | 2023-08-30 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | SAFETY NET REMOVING WORK | 101522 | 2023-08-30 | 14235.48 | 2023-09-12 12:52 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 402.5 | 120 | 0 | 48300 | 0 | 2023-07-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100859 | 2023-07-26 | 48300 | 2023-07-27 11:44 | 0 | PAWAR SHIVAPPA TARANAIK
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-12-09 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97320 | 2022-12-10 | 468496 | 2022-12-24 10:48 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 2146.4 | 150 | 0 | 321960 | 57952.8 | 2023-02-15 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98205 | 2023-02-15 | 321960 | 2023-02-24 11:37 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-31st Slab RCC Built-up Area (L) | 188.1013 | 190.642 | -0.01 | 35860.008 | 6454.8 | 2024-06-20 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab, Beam, Staircase & All Shear walls. | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -3008550.202 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-02-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93787 | 2022-03-11 | 870064 | 2022-03-11 15:52 | -435032 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 3385.536 | 130 | 0 | 440119.68 | 79221.54 | 2022-05-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94816 | 2022-05-20 | 880239.36 | 2022-06-20 16:24 | -440119.68 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398020.96 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2023-01-03 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97618 | 2023-01-04 | 468496 | 2023-01-23 18:34 | 0 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 168 | 10 | 0 | 1680 | 0 | 2024-06-10 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108270 | 2024-06-10 | 3360 | 1900-01-01 | -1680 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 272.5 | 10 | 0 | 2725 | 0 | 2024-05-19 | Quantity Differance Charges for Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall. | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -37440 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 168 | 10 | 0 | 1680 | 0 | 2024-06-10 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108270 | 2024-06-10 | 3360 | 1900-01-01 | -1680 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-08 16:34 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92654 | 2021-12-09 | 903528 | 2021-12-23 17:53 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 3764.7 | 130 | 0 | 489411 | 88093.98 | 2022-01-25 16:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93222 | 2022-01-27 | 978822 | 2022-01-28 17:45 | -489411 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 3764.7 | 130 | 0 | 489411 | 88093.98 | 2022-01-25 16:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93222 | 2022-01-27 | 978822 | 2022-01-28 17:45 | -489411 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 4231.92 | 120 | 0 | 507830.4 | 91409.48 | 2021-09-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91572 | 2021-09-18 | 507830.4 | 2021-09-20 16:40 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 71.4286 | 140 | 0 | 10000.004 | 0 | 2023-08-12 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 101223 | 2023-08-12 | 10000 | 2023-08-12 14:26 | 0.004 | PAWAR SHIVAPPA TARANAIK
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 106.6233 | 150 | 0 | 15993.495 | 2878.84 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2985078.865 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 768.7692 | 130 | 0 | 99939.996 | 17989.2 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2901132.364 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 82.334 | 140 | 0 | 11526.76 | 2074.82 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2989545.6 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 65.038 | 140 | 0 | 9105.32 | 1638.96 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991967.04 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-01-28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98204 | 2023-02-15 | 501960 | 2023-02-20 15:36 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99004 | 2023-04-06 | 501960 | 2023-04-11 17:44 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-03-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98615 | 2023-03-11 | 501960 | 2023-03-29 11:34 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-12 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99129 | 2023-04-12 | 501960 | 2023-04-13 12:05 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 3346 | 140 | 0 | 468440 | 84319.2 | 2022-09-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96297 | 2022-09-20 | 468440 | 2022-10-04 12:00 | 0 | VNE INFRA PROJECTS P LTD
Sorting & Shifting Work | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Sorting & Shifting mockup,checking & rework(1st Floor) | 8366 | 75 | 0 | 627450 | 112941 | 2021-09-04 | Sorting And Shifting Mockup , Checking & Rework (1St Floor) | 100 |  | 91435 | 2021-09-06 | 627450 | 2021-09-07 17:26 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 147.95 | 120 | 0 | 17754 | 3195.72 | 2022-02-07 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Horizontal Safety net fixing Work | 93383 | 2022-02-08 | 17754 | 2022-02-24 14:42 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 329.336 | 140 | 0 | 46107.04 | 8299.26 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -734032.94 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 260.152 | 140 | 0 | 36421.28 | 6555.84 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -743718.7 | VNE INFRA PROJECTS P LTD
RCC Work -Dld | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace LMR OHWT | 0.1192 | 1678594 | 0 | 200088.4048 | 36015.92 | 2024-04-12 17:05 | Top Terrace LMR OHWT RCC Work | 100 |  | 106898 | 2024-04-15 | 200088.4 | 1900-01-01 | 0.0048 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-11-02 11:30 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92323 | 2021-11-02 | 803136 | 2021-12-04 12:21 | -301176 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 877.7571 | 140 | 0.01 | 122885.994 | 22119.48 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | for Internal handing over | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -623620.006 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 2509.8 | 120 | 0 | 301176 | 54211.68 | 2021-11-02 11:30 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92323 | 2021-11-02 | 803136 | 2021-12-04 12:21 | -501960 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 198.29 | 140 | 0 | 27760.6 | 4996.9 | 2023-01-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Debit for horrizontal safety net fixing work | 97935 | 2023-01-25 | 27760.6 | 2023-02-27 15:41 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 305.0467 | 150 | 0 | 45757.005 | 8236.26 | 2023-05-18 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Debit for horizontal safety net removing work on 9th Floor and fixing work on 19th floor | 99700 | 2023-05-18 | 45757.01 | 2023-06-15 13:02 | -0.005 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 100 | 130 | 0 | 13000 | 2340 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -767139.98 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 260.152 | 140 | 0 | 36421.28 | 6555.84 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -743718.7 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 4231.92 | 130 | 0 | 550149.6 | 99026.92 | 2021-12-30 17:57 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92919 | 2021-12-31 | 880469.2 | 2022-01-06 15:04 | -330319.6 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 313.83 | 130 | 0 | 40797.9 | 7343.62 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -739342.08 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-31st Slab RCC Built-up Area (L) | 3475 | 190.642 | 0 | 662480.95 | 119246.58 | 2023-08-31 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab, Beam, Staircase & All Shear walls. | 100 |  | 101541 | 2023-09-01 | 662480.95 | 2023-09-12 12:51 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-09-04 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91430 | 2021-09-04 | 501960 | 2021-09-07 16:52 | 0 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 7766 | 10 | 0 | 77660 | 13978.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2966750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398656.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 2509.8 | 140 | 0 | 351372 | 63246.96 | 2022-08-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95925 | 2022-08-19 | 1053808 | 2022-08-24 11:17 | -702436 | VNE INFRA PROJECTS P LTD
Lintel Casting work | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Lintel casting for 3 BHK Flats (Stilt to 5th Floor) | 12 | 500 | 0 | 6000 | 1080 | 2023-10-11 | Labour charges for Lintel Binding, Shuttering and Concrete casting work for D-Bldg 3 BHK Flats from Stilt Floor to 5th Floor. | 100 |  | 102540 | 2023-10-12 | 6000 | 1900-01-01 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-01-11 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93096 | 2022-01-12 | 870064 | 2022-01-28 12:55 | -435032 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-03-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94393 | 2022-04-14 | 870064 | 2022-04-22 13:04 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-07-28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100893 | 2023-07-29 | 501960 | 2023-08-24 10:17 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-03-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94393 | 2022-04-14 | 870064 | 2022-04-22 13:04 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 369 | 140 | 0 | 51660 | 9298.8 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -694846 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-10-09 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% Bill Released against Internal Handover | 102481 | 2023-10-10 | 257749 | 1900-01-01 | -199187 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-10-09 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% Bill Released against Internal Handover | 102481 | 2023-10-10 | 257749 | 1900-01-01 | -199187 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 2509.8 | 140 | 0 | 351372 | 63246.96 | 2022-09-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96202 | 2022-09-10 | 351372 | 2022-09-15 16:40 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 1200 | 150 | 0 | 180000 | 32400 | 2023-02-15 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98203 | 2023-02-15 | 180000 | 2023-02-24 11:38 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 25.5 | 140 | 0 | 3570 | 642.6 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2997502.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 65.038 | 150 | 0 | 9755.7 | 1756.02 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991316.66 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 325.19 | 150 | 0 | 48778.5 | 8780.14 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2952293.86 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 213.83 | 130 | 0 | 27797.9 | 5003.62 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2973274.46 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 65.038 | 140 | 0 | 9105.32 | 1638.96 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991967.04 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 325.19 | 150 | 0 | 48778.5 | 8780.14 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2952293.86 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 418.3 | 120 | 0 | 50196 | 9035.28 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2950876.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 436.75 | 120 | 0 | 52410 | 9433.8 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2948662.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 74429.28 | 2022-06-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95529 | 2022-07-16 | 936992 | 2022-07-22 11:41 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-06-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95529 | 2022-07-16 | 936992 | 2022-07-22 11:41 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 1671 | 140 | 0 | 233940 | 42109.2 | 2022-08-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95925 | 2022-08-19 | 1053808 | 2022-08-24 11:17 | -819868 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-08-16 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95925 | 2022-08-19 | 1053808 | 2022-08-24 11:17 | -585312 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92624 | 2021-12-07 | 903528 | 2021-12-11 12:29 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 260.152 | 140 | 0 | 36421.28 | 6555.84 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -743718.7 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 325.19 | 140 | 0 | 45526.6 | 8194.78 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -734613.38 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98416 | 2023-03-01 | 501960 | 2023-03-14 18:27 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 3385.536 | 130 | 0 | 440119.68 | 79221.54 | 2022-05-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94816 | 2022-05-20 | 880239.36 | 2022-06-20 16:24 | -440119.68 | VNE INFRA PROJECTS P LTD
RCC Work -Dld | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace LMR OHWT | 0.029 | 1678594 | 0 | 48679.226 | 0 | 2024-04-12 16:52 | Top Terrace LMR OHWT RCC Work | 100 | OHWT REINFORCEMENT WORK | 106899 | 2024-04-15 | 48679.23 | 2024-06-10 11:28 | -0.004 | MOURYA AWADHESH KUMAR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 1632.2429 | 140 | 0 | 228514.006 | 41132.52 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2815896.204 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 8366 | 10 | 0 | 83660 | 15058.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2960750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 7563.84 | 10 | 0 | 75638.4 | 13614.92 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2968771.81 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 836.6 | 130 | 0 | 108758 | 19576.44 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -298718 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 8031.84 | 10 | 0 | 80318.4 | 14457.32 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2964091.81 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 1321.5 | 10 | 0 | 13215 | 2378.7 | 2024-06-20 19:27 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -3031195.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-07-22 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95627 | 2022-07-23 | 936992 | 2022-08-04 10:36 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 708.5 | 140 | 0 | 99190 | 17854.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2945220.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 183.3333 | 120 | 0 | 21999.996 | 3960 | 2022-07-02 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95360 | 2022-07-04 | 22000 | 2022-07-14 11:43 | -0.004 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 203.364 | 150 | 0 | 30504.6 | 5490.82 | 2023-08-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Safety net fixing work on 22nd floor(28th slab) | 101492 | 2023-08-28 | 30504.6 | 2023-09-12 12:50 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-31st Slab RCC Built-up Area (L) | 3346.4 | 190.642 | 0 | 637964.3888 | 114833.6 | 2023-09-15 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab, Beam, Staircase & All Shear walls. | 100 |  | 101897 | 2023-09-15 | 637964.39 | 2023-09-20 12:01 | -0.0012 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 130.78 | 120 | 0 | 15693.6 | 2824.84 | 2022-08-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95827 | 2022-08-08 | 15693.6 | 2022-08-27 12:59 | 0 | GREEN SAFETY SOLUTIONS
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 4183 | 140 | 0 | 585620 | 105411.6 | 2022-10-20 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96827 | 2022-10-20 | 819840 | 2022-11-08 10:41 | -234220 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2023-08-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 101491 | 2023-08-28 | 250980 | 2023-09-12 12:51 | -125490 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 1673 | 140 | 0 | 234220 | 42159.6 | 2022-10-20 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96827 | 2022-10-20 | 819840 | 2022-11-08 10:41 | -585620 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 500 | 140 | 0 | 70000 | 12600 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -676506 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-07-22 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95627 | 2022-07-23 | 936992 | 2022-08-04 10:36 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 396.1714 | 140 | 0 | 55463.996 | 9983.52 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2988946.214 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 392.8 | 140 | 0 | 54992 | 9898.56 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2989418.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | 1875 | 75 | 0 | 140625 | 25312.5 | 2023-10-09 | Top Terrace LMR OHWT Parapet Wall Pergola And Elevation | 100 |  | 102481 | 2023-10-10 | 257749 | 1900-01-01 | -117124 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 4231.92 | 120 | 0 | 507830.4 | 91409.48 | 2021-09-24 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91655 | 2021-09-25 | 507830.4 | 2021-10-07 17:04 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92624 | 2021-12-07 | 903528 | 2021-12-11 12:29 | -451764 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-10-09 14:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91993 | 2021-10-12 | 1003920 | 2021-10-16 13:27 | -501960 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-10-09 14:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91993 | 2021-10-12 | 1003920 | 2021-10-16 13:27 | -501960 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99083 | 2023-04-10 | 501960 | 2023-04-11 17:44 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 247.8286 | 140 | 0 | 34696.004 | 6245.28 | 2023-01-16 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Debit for vertical safety net fixing & removing (for 14th floor) | 97809 | 2023-01-16 | 34696 | 2023-01-31 11:59 | 0.004 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-13 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99157 | 2023-04-13 | 501960 | 2023-04-14 11:50 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-08-23 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91297 | 2021-08-24 | 501960 | 2021-09-03 17:16 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398656.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 836.6 | 130 | 0 | 108758 | 19576.44 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -298718 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398020.96 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 1045.75 | 140 | 0 | 146405 | 26352.9 | 2022-08-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95992 | 2022-08-25 | 146405 | 2022-08-27 13:01 | 0 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 7766 | 10 | 0 | 77660 | 13978.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2966750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-07-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100732 | 2023-07-17 | 501960 | 2023-07-29 10:57 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-06-23 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100259 | 2023-06-23 | 501960 | 2023-06-27 14:21 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 75 | 130 | 0 | 9750 | 1755 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -397726 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-08 16:34 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92654 | 2021-12-09 | 903528 | 2021-12-23 17:53 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 65.038 | 150 | 0 | 9755.7 | 1756.02 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991316.66 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 418.3 | 120 | 0 | 50196 | 9035.28 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2950876.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 2540.92 | 130 | 0 | 330319.6 | 59457.52 | 2021-12-30 17:57 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92919 | 2021-12-31 | 880469.2 | 2022-01-06 15:04 | -550149.6 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 325.19 | 140 | 0 | 45526.6 | 8194.78 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -734613.38 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 313.83 | 120 | 0 | 37659.6 | 6778.72 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -742480.38 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 260.152 | 150 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 260.152 | 150 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 7563.84 | 10 | 0 | 75638.4 | 13614.92 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2968771.81 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 753 | 130 | 0 | 97890 | 17620.2 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -309586 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-01-11 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93096 | 2022-01-12 | 870064 | 2022-01-28 12:55 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 316.618 | 140 | 0 | 44326.52 | 7978.78 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2956745.84 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 128.5 | 140 | 0 | 17990 | 3238.2 | 2024-02-03 15:29 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2983082.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 836.6 | 130 | 0 | 108758 | 19576.44 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2892314.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 65.038 | 140 | 0 | 9105.32 | 1638.96 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991967.04 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | 5625 | 75 | 0 | 421875 | 75937.5 | 2024-02-03 15:00 | Top Terrace LMR OHWT Parapet Wall Pergola And Elevation | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2579197.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 325.19 | 150 | 0 | 48778.5 | 8780.14 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2952293.86 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2942510.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 336.6 | 140 | 0 | 47124 | 8482.32 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2953948.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946057.4 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 686 | 120 | 0 | 82320 | 14817.6 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -325156 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946057.4 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 761.6 | 130 | 0 | 99008 | 17821.44 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2902064.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 170.4714 | 140 | 0 | 23865.996 | 4295.88 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2977206.364 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 234.9667 | 120 | 0 | 28196.004 | 5075.28 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2972876.356 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2942510.36 | VNE INFRA PROJECTS P LTD
RCC Work -Dld | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace LMR OHWT | 0.75 | 1678594 | 0 | 1258945.5 | 226610.2 | 2024-02-03 15:00 | Top Terrace LMR OHWT RCC Work | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -1742126.86 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 10.86 | 140 | 0 | 1520.4 | 273.68 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2999551.96 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 169.2308 | 130 | 0 | 22000.004 | 3960 | 2022-08-04 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Safety net Fixing ( Flat no -1306,1307,1308,1301) Vertical safety net joint Below Brecket. | 95780 | 2022-08-04 | 22000 | 2022-08-16 11:41 | 0.004 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | For Part 1 | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -244546 | VNE INFRA PROJECTS P LTD
Earthing work(m+l)- BC | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 203 | 2021-05-20 | Earthing Work | 10 | 4000 | 0 | 40000 | 7200 | 2021-11-25 | Earthing Work (M+L) for Tower Crane-3 Nos,125 KVA DG-3 Nos,60 KVA DG-2 Nos & Steel yard Cutting & Bending Machine-2 Nos) | 100 |  | 92462 | 2021-11-25 | 40000 | 2021-11-25 17:28 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-23- | 80.776 | 20 | 0 | 1615.52 | 290.8 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44530.52 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-24 | 3.08 | 20 | 0 | 61.6 | 11.08 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46084.44 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-26 | 84.992 | 20 | 0 | 1699.84 | 305.98 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44446.2 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-23- | 147.096 | 20 | 0 | 2941.92 | 529.54 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -43204.12 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-28 | 82.408 | 20 | 0 | 1648.16 | 296.66 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44497.88 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-27 | 1.816 | 20 | 0 | 36.32 | 6.54 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.72 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-27 | 152.336 | 20 | 0 | 3046.72 | 548.4 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -43099.32 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-28 | 3.08 | 20 | 0 | 61.6 | 11.08 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46084.44 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-25 | 187.83 | 20 | 0 | 3756.6 | 676.18 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -42389.44 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-24 | 152.336 | 20 | 0 | 3046.72 | 548.4 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -43099.32 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-24 | 82.472 | 20 | 0 | 1649.44 | 296.9 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44496.6 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-27 | 82.408 | 20 | 0 | 1648.16 | 296.66 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44497.88 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-26 | 3.096 | 20 | 0 | 61.92 | 11.14 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46084.12 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-29 | 1.816 | 20 | 0 | 36.32 | 6.54 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.72 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-25 | 3.08 | 20 | 0 | 61.6 | 11.08 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46084.44 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-29 | 80.856 | 20 | 0 | 1617.12 | 291.08 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44528.92 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-23- | 3.104 | 20 | 0 | 62.08 | 11.18 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46083.96 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-25 | 1.824 | 20 | 0 | 36.48 | 6.56 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.56 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-29 | 3.104 | 20 | 0 | 62.08 | 11.18 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46083.96 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-23- | 1.816 | 20 | 0 | 36.32 | 6.54 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.72 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-24 | 1.824 | 20 | 0 | 36.48 | 6.56 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.56 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-29 | 18.654 | 20 | 0 | 373.08 | 67.16 | 2022-04-04 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 94148 | 2022-04-05 | 16923.59 | 2022-04-15 11:40 | -16550.51 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-26 | 19.698 | 20 | 0 | 393.96 | 70.92 | 2022-04-04 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 94148 | 2022-04-05 | 16923.59 | 2022-04-15 11:40 | -16529.63 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-23- | 18.387 | 20 | 0 | 367.74 | 66.2 | 2022-04-04 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 94148 | 2022-04-05 | 16923.59 | 2022-04-15 11:40 | -16555.85 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-28 | 18.783 | 20 | 0 | 375.66 | 67.62 | 2022-04-04 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 94148 | 2022-04-05 | 16923.59 | 2022-04-15 11:40 | -16547.93 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-27 | 19.042 | 20 | 0 | 380.84 | 68.56 | 2022-04-04 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 94148 | 2022-04-05 | 16923.59 | 2022-04-15 11:40 | -16542.75 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-25 | 82.408 | 20 | 0 | 1648.16 | 296.66 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -44497.88 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-24 | 19.042 | 20 | 0 | 380.84 | 68.56 | 2022-04-04 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 94148 | 2022-04-05 | 16923.59 | 2022-04-15 11:40 | -16542.75 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-27 | 3.08 | 20 | 0 | 61.6 | 11.08 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46084.44 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-26 | 1.832 | 20 | 0 | 36.64 | 6.6 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.4 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-29 | 149.232 | 20 | 0 | 2984.64 | 537.24 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -43161.4 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-28 | 150.264 | 20 | 0 | 3005.28 | 540.96 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -43140.76 | PAPPU BAGELA
Vitrified Skirting work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-28 | 1.824 | 20 | 0 | 36.48 | 6.56 | 2022-03-20 | Fixing Vitrified Skirting 600 X 600 with proper line and level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg Shop loft Mezzanine slab | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -46109.56 | PAPPU BAGELA
Vitrified Flooring work | N/C | N/C | PAPPU BAGELA | 207 | 2021-05-31 | F-Bldg Shops Flooring & Tiling Shop No-26 | 157.584 | 20 | 0 | 3151.68 | 567.3 | 2022-03-20 | Fixing Vitrified Flooring 600 X 600 with proper line level, proper joint filling, right angle including acid wash etc. complete as per drawing in F-Bldg | 100 |  | 93959 | 2022-03-21 | 46146.04 | 1900-01-01 | -42994.36 | PAPPU BAGELA
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg OPD+Com Area Rolling Shutter Work | 127.5 | 70 | 0 | 8925 | 1606.5 | 2023-07-10 | Labour Charges for Fixing of Hand Operated Rolling Shutter including C R Strip, MS Bracket, Round Coil pipe 42mm,Galvanized part no red oxide MS Paint with red oxide, L bottom,Side Guide & Ball Bearing. | 100 |  | 100613 | 2023-07-11 | 27195 | 2023-08-14 14:33 | -18270 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-23 | 144.41 | 72 | 0 | 10397.52 | 1871.56 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -67201.92 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-26 | 153.43 | 72 | 0 | 11046.96 | 1988.46 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -66552.48 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bdlg Rolling Shutter Shop No-28 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-24 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg OPD+Com Area Rolling Shutter Work | 52.5 | 70 | 0 | 3675 | 661.5 | 2023-07-10 | Labour Charges for Fixing of Hand Operated Rolling Shutter including C R Strip, MS Bracket, Round Coil pipe 42mm,Galvanized part no red oxide MS Paint with red oxide, L bottom,Side Guide & Ball Bearing. | 100 |  | 100613 | 2023-07-11 | 27195 | 2023-08-14 14:33 | -23520 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-25 | 153.43 | 72 | 0 | 11046.96 | 1988.46 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -66552.48 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-29 | 151.39 | 72 | 0 | 10900.08 | 1962.02 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -66699.36 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-27 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-23 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-25 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-29 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg OPD+Com Area Rolling Shutter Work | 208.5 | 70 | 0 | 14595 | 2627.1 | 2023-07-10 | Labour Charges for Fixing of Hand Operated Rolling Shutter including C R Strip, MS Bracket, Round Coil pipe 42mm,Galvanized part no red oxide MS Paint with red oxide, L bottom,Side Guide & Ball Bearing. | 100 |  | 100613 | 2023-07-11 | 27195 | 2023-08-14 14:33 | -12600 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-26 | 1 | 400 | 0 | 400 | 72 | 2024-05-09 17:33 | Labour charges for - Gear Box | 100 |  | 107498 | 2024-05-13 | 2800 | 1900-01-01 | -2400 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bdlg Rolling Shutter Shop No-28 | 160.84 | 72 | 0 | 11580.48 | 2084.48 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -66018.96 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-27 | 160.84 | 72 | 0 | 11580.48 | 2084.48 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -66018.96 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 210 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-24 | 153.43 | 72 | 0 | 11046.96 | 1988.46 | 2022-04-16 | Labour Charges for Fixing of Rolling Shutter for F Building Shops. | 100 |  | 94433 | 2022-04-16 | 77599.44 | 2022-06-18 16:25 | -66552.48 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-27 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg OPD+Com Area Rolling Shutter Work | 208.5 | 155 | 0 | 32317.5 | 5817.16 | 2023-07-10 | Material Supply Charges of Hand Operated Rolling Shutter (Size-7.5ft x 10.5), Total 4 Nos. | 100 |  | 100612 | 2023-07-11 | 60217.5 | 2023-08-14 14:33 | -27900 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-26 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-29 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-25 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-23 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-24 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-29 | 151.39 | 168 | 0 | 25433.52 | 4578.04 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -155631.84 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bdlg Rolling Shutter Shop No-28 | 160.84 | 168 | 0 | 27021.12 | 4863.8 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -154044.24 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg OPD+Com Area Rolling Shutter Work | 52.5 | 155 | 0 | 8137.5 | 1464.76 | 2023-07-10 | Material Supply charges of Hand Operated Rolling Shutter (size- 5ft x 10.5ft) Total- 1 No. | 100 |  | 100612 | 2023-07-11 | 60217.5 | 2023-08-14 14:33 | -52080 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg OPD+Com Area Rolling Shutter Work | 127.5 | 155 | 0 | 19762.5 | 3557.26 | 2023-07-10 | Material Supply charges of Hand Operated Rolling Shutter (size- 5ft x 8.5ft) Total- 3 Nos. | 100 |  | 100612 | 2023-07-11 | 60217.5 | 2023-08-14 14:33 | -40455 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-26 | 153.43 | 168 | 0 | 25776.24 | 4639.72 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -155289.12 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-24 | 153.43 | 168 | 0 | 25776.24 | 4639.72 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -155289.12 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-27 | 160.84 | 168 | 0 | 27021.12 | 4863.8 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -154044.24 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-25 | 153.43 | 168 | 0 | 25776.24 | 4639.72 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -155289.12 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bdlg Rolling Shutter Shop No-28 | 1 | 3600 | 0 | 3600 | 648 | 2024-06-02 | Material Supply For- Gear Box | 100 |  | 107922 | 2024-06-03 | 104400 | 2024-06-15 11:51 | -100800 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 211 | 2021-06-09 | F-Bldg Rolling Shutter Shop No-23 | 144.41 | 168 | 0 | 24260.88 | 4366.96 | 2022-04-16 | Material Supply for - Rolling Shutter of F- Building Shops | 100 |  | 94434 | 2022-04-16 | 181065.36 | 2022-05-13 12:37 | -156804.48 | BHAGYALAXMI ENTERPRISES
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-08-10 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 95863 | 2022-08-10 | 10000 | 2022-08-27 13:11 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2021-08-23 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 91299 | 2021-08-24 | 10000 | 2021-10-11 14:07 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-11-09 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | 17th Floor | 97000 | 2022-11-10 | 10000 | 2022-11-16 11:36 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-01-31 17:38 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 93297 | 2022-02-01 | 10000 | 2022-02-14 16:39 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 200 | 100 | 0 | 20000 | 0 | 2022-01-01 13:36 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 92940 | 2022-01-01 | 20000 | 2022-01-28 18:01 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-01-14 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 93124 | 2022-01-15 | 10000 | 2022-02-10 12:43 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-05-31 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | For 23rd floor Point Marking | 99855 | 2023-05-31 | 10000 | 2023-06-15 13:07 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-07-31 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 100925 | 2023-07-31 | 10000 | 2023-08-14 14:32 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-05-18 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 94813 | 2022-05-19 | 10000 | 2022-06-18 15:54 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-07-09 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 95872 | 2022-08-11 | 10000 | 2022-08-11 12:03 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-09-21 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 96714 | 2022-10-12 | 20000 | 2022-10-12 16:44 | -10000 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-09-21 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 96714 | 2022-10-12 | 20000 | 2022-10-12 16:44 | -10000 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-03-10 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | For 20th floor marking | 98614 | 2023-03-10 | 10000 | 2023-03-29 11:17 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-02-13 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | For 19 th floor | 98177 | 2023-02-13 | 10000 | 2023-03-29 11:17 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-01-06 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | 18th floor point | 97672 | 2023-01-06 | 10000 | 2023-01-31 11:44 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2021-10-03 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 91825 | 2021-10-04 | 10000 | 2021-10-11 14:08 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-02-08 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 93399 | 2022-02-09 | 10000 | 2022-03-07 14:18 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-04-11 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | For 21st floor marking | 99127 | 2023-04-12 | 10000 | 1900-01-01 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-04-18 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | for 22nd floor point marking | 99212 | 2023-04-18 | 10000 | 2023-04-24 10:51 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2022-03-20 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 93965 | 2022-03-21 | 10000 | 2022-03-24 12:35 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 100 | 100 | 0 | 10000 | 0 | 2023-06-27 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 | For 23 rd floor Point Marking | 100310 | 2023-06-28 | 10000 | 2023-07-26 12:19 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 216 | 2021-06-18 | D-Total Station Point Marking | 300 | 100 | 0 | 30000 | 0 | 2021-11-23 11:50 | D Bldg Total Station Point Marking from 1st Floor upto last floor | 100 |  | 92435 | 2021-11-24 | 30000 | 2021-12-23 17:44 | 0 | VECTOR SURVEYORS
Excavation By Needle | N/C | N/C | SS ENTERPRISES | 219 | 2021-06-21 | F-Excavation Work | 64.05 | 210 | 0 | 13450.5 | 2421.1 | 2021-08-29 | Excavation work by Needle in earth soft / hard rock up to required depth including removing the excavated material all leads and lifts, stacking and spreading with in site boundary with all tool, machinery & Equipments | 100 |  | 91342 | 2021-08-30 | 243238.5 | 2021-09-25 12:24 | -229788 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 219 | 2021-06-21 | F-Excavation Work | 3060.6667 | 15 | 0 | 45910.0005 | 8263.8 | 2021-08-29 | Spreading & Levelling Work for F Bldg | 100 |  | 91342 | 2021-08-30 | 243238.5 | 2021-09-25 12:24 | -197328.4995 | SS ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 219 | 2021-06-21 | F-Excavation Work | 3064.6333 | 60 | 0 | 183877.998 | 33098.04 | 2021-08-29 | Excavation work by Bucket in earth, soils of all types, sand, gravel and soft murum up to required depth including removing the excavated material all leads and lifts, stacking and spreading with in site boundary with all tool, machinery & Equipments | 100 |  | 91342 | 2021-08-30 | 243238.5 | 2021-09-25 12:24 | -59360.502 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 22 | 2020-03-13 | Tower D Excavation, Shifting, Levelling | 3532.9333 | 15 | 0 | 52993.9995 | 9538.92 | 2022-06-09 | Charges for Excavated materail spreading and levelling work. | 100 |  | 95060 | 2022-06-10 | 52994 | 2022-08-27 13:08 | -0.0005 | SS ENTERPRISES
Excavation By Needle (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 22 | 2020-03-13 | Tower D Excavation, Shifting, Levelling | 3319.93 | 225 | 0 | 746984.25 | 134457.16 | 2020-10-06 | Substructure Excavation work by Needle & Shifting inside including Levelling of Excavated material after unloading. | 100 |  | 87646 | 2020-10-07 | 835891.25 | 2020-11-09 17:43 | -88907 | SS ENTERPRISES
Excavation By Bucket (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 22 | 2020-03-13 | Tower D Excavation, Shifting, Levelling | 928.2667 | 75 | 0 | 69620.0025 | 12531.6 | 2020-10-06 | Substructure Excavation work by Bucket & Shifting inside,including Levelling of Excavated material after unloading | 100 |  | 87646 | 2020-10-07 | 835891.25 | 2020-11-09 17:43 | -766271.2475 | SS ENTERPRISES
Excavation By Needle (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 22 | 2020-03-13 | Tower D Excavation, Shifting, Levelling | 85.72 | 225 | 0 | 19287 | 3471.66 | 2020-10-06 | Substructure Excavation work by Needle & Shifting inside,including Levelling of Excavated material after unloading | 100 |  | 87646 | 2020-10-07 | 835891.25 | 2020-11-09 17:43 | -816604.25 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 22 | 2020-03-13 | Tower D Excavation, Shifting, Levelling | 5862.39 | 15 | 0 | 87935.85 | 0 | 2024-04-22 13:01 | Charges for Excavated Material spresding & Levelling work. | 100 |  | 107127 | 2024-04-29 | 87935.85 | 2024-05-21 12:26 | 0 | SHIVAM ENTERPRISES
Murum Filling (avail earth in site) | N/C | N/C | SS ENTERPRISES | 22 | 2020-03-13 | Tower D Excavation, Shifting, Levelling | 1738.52 | 90 | 0 | 156466.8 | 28164.02 | 2021-03-25 | Murum Filling Work up to Grid Slab | 100 |  | 89515 | 2021-03-25 | 156466.8 | 2021-03-30 12:56 | 0 | SS ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-13th Refuge slab rcc work with scaffolding. | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2022-05-09 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 94732 | 2022-05-09 | 67640.32 | 2022-08-17 15:12 | -33820.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-8th Refuge slab rcc work with scaffolding. | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2022-05-09 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 94732 | 2022-05-09 | 67640.32 | 2022-08-17 15:12 | -33820.16 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P3-Fl RCC Parapet Wall (L) | 68.09 | 8 | 0 | 544.72 | 98.04 | 2022-10-04 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73719.44 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-23rd Refuge slab rcc work with scaffolding | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2023-08-01 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 100933 | 2023-08-01 | 67640.32 | 2023-08-09 12:17 | -33820.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-28th Refuge slab rcc work with scaffolding | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2023-08-01 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 100933 | 2023-08-01 | 67640.32 | 2023-08-09 12:17 | -33820.16 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P1-Fl RCC Parapet Wall (L) | 47.01 | 500 | 0 | 23505 | 4230.9 | 2022-10-04 | Labour charges for Shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -50759.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-18th Refuge slab rcc work with scaffolding. - 96.08 Sq. | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2022-06-29 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 95284 | 2022-06-29 | 33820.16 | 2022-08-17 15:12 | 0 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P2-Fl RCC Parapet Wall (L) | 2.35 | 300 | 0 | 705 | 126.9 | 2022-10-04 | Labour charges for Concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73559.16 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P3-Fl RCC Parapet Wall (L) | 2.35 | 300 | 0 | 705 | 126.9 | 2022-10-04 | Labour charges for Concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73559.16 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P2-Fl RCC Parapet Wall (L) | 47.01 | 500 | 0 | 23505 | 4230.9 | 2022-10-04 | Labour charges for Shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -50759.16 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P1-Fl RCC Parapet Wall (L) | 68.09 | 8 | 0 | 544.72 | 98.04 | 2022-10-04 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73719.44 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P2-Fl RCC Parapet Wall (L) | 68.09 | 8 | 0 | 544.72 | 98.04 | 2022-10-04 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73719.44 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P3-Fl RCC Parapet Wall (L) | 47.01 | 500 | 0 | 23505 | 4230.9 | 2022-10-04 | Labour charges for Shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -50759.16 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P1-Fl RCC Parapet Wall (L) | 2.35 | 300 | 0 | 705 | 126.9 | 2022-10-04 | Labour charges for Concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73559.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg Shops Mezzanine Floor RCC Work (L) | 1205 | 92.5 | 0 | 111462.5 | 20063.26 | 2022-05-19 | Labour Charges for- E Building shops mezzanine floor RCC Slab & Beam work. | 100 |  | 94815 | 2022-05-20 | 111462.5 | 2022-06-20 16:24 | 0 | VNE INFRA PROJECTS P LTD
Excavation By Needle | N/C | N/C | SS ENTERPRISES | 23 | 2020-03-13 | E-Bldg Excavation work | 777.99 | 210 | 0 | 163377.9 | 29408.02 | 2021-03-23 | Substructure Excavation work by Needle & Shifting Inside | 100 |  | 89475 | 2021-03-24 | 369306.75 | 2021-03-30 12:59 | -205928.85 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 23 | 2020-03-13 | E-Bldg Excavation work | 3368.11 | 15 | 0 | 50521.65 | 9093.9 | 2021-03-23 | Spreading & Levelling Work | 100 |  | 89475 | 2021-03-24 | 369306.75 | 2021-03-30 12:59 | -318785.1 | SS ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 23 | 2020-03-13 | E-Bldg Excavation work | 2590.12 | 60 | 0 | 155407.2 | 27973.3 | 2021-03-23 | Substructure Excavation work by Bucket & Shifting Inside | 100 |  | 89475 | 2021-03-24 | 369306.75 | 2021-03-30 12:59 | -213899.55 | SS ENTERPRISES
JCB Charges BC | N/C | N/C | SS ENTERPRISES | 23 | 2020-03-13 | Tower E Excavation, Shifting, Levelling | 6 | 800 | 0 | 4800 | 864 | 2020-10-02 | JCB for E Bldg. Plot Cleaning & Levelling Work | 100 |  | 91173 | 2021-08-12 | 4800 | 2021-08-13 19:19 | 0 | SS ENTERPRISES
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 0.252 | 160000 | 0 | 20160 | 0 | 2021-10-21 13:44 | After Delivery of Strand | 50 |  | 92158 | 2021-10-22 | 40240 | 2021-10-26 16:58 | -20080 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 0.251 | 160000 | 0 | 20080 | 0 | 2021-10-21 14:08 | After Delivery of Strand | 50 |  | 92158 | 2021-10-22 | 40240 | 2021-10-26 16:58 | -20160 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.209 | 160000 | 0 | 96720 | 17409.6 | 2022-02-15 18:21 | Balance After Stressing | 50 |  | 93499 | 2022-02-16 | 232960 | 2022-02-23 17:49 | -136240 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.703 | 160000 | 0 | 136240 | 24523.2 | 2022-02-15 18:21 | After Delivery of Strand | 50 |  | 93499 | 2022-02-16 | 232960 | 2022-02-23 17:49 | -96720 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.216 | 160000 | 0 | 97280 | 17510.4 | 2021-10-28 15:38 | After Delivery of Strand | 50 |  | 92273 | 2021-10-29 | 97280 | 2021-11-23 15:46 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.719 | 160000 | 0 | 137520 | 24753.6 | 2021-11-25 14:31 | Balance After Stressing | 50 |  | 92461 | 2021-11-25 | 137520 | 2021-12-11 12:28 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work Rate diff. | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 8.037 | 2586.378 | 0 | 20786.72 | 3741.6 | 2022-06-29 | Charges for Rate differnace for Post tensioning work for 1st PT Slab, 2nd PT Slab pour 1 & 2, 4th PT Slab,5th PT Slab & Subtracting the excess amount of 3rd PT Slab. | 100 |  | 95309 | 2022-06-30 | 20786.72 | 2022-07-13 12:08 | -1.4e-05 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.703 | 160000 | 0 | 136240 | 24523.2 | 2022-05-21 | After Delivery of Strand | 50 |  | 94838 | 2022-05-21 | 136240 | 2022-07-02 11:23 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.703 | 160000 | 0 | 136240 | 24523.2 | 2022-04-21 | Balance After Stressing | 50 |  | 94522 | 2022-04-22 | 136240 | 2022-05-12 14:37 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.703 | 160000 | 0 | 136240 | 24523.2 | 2022-06-14 | Balance After Stressing | 50 |  | 95086 | 2022-06-14 | 136240 | 2022-06-20 16:32 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.703 | 160000 | 0 | 136240 | 24523.2 | 2022-03-16 | Balance After Stressing | 50 |  | 93902 | 2022-03-17 | 136240 | 2022-03-22 11:32 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.209 | 160000 | 0 | 96720 | 17409.6 | 2021-12-31 12:11 | After Delivery of Strand | 50 |  | 92920 | 2021-12-31 | 96720 | 2022-01-06 16:58 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 234 | 2021-06-28 | F-PT(Post Tensioning Work) PT (Post Tensioning Work) | 1.703 | 160000 | 0 | 136240 | 24523.2 | 2022-04-06 | After Delivery of Strand | 50 |  | 94191 | 2022-04-06 | 136240 | 2022-04-13 19:12 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Fastner (L) - SOSB | N/C | N/C | PATILS FABRICATORS | 235 | 2021-06-30 | D-Bldg Fab Work Near Material Lift | 80 | 60 | 0 | 4800 | 864 | 2022-09-03 | Chemical Fastner Fixing for MS Beam Support for Slab | 100 |  | 96119 | 2022-09-03 | 4800 | 2022-09-15 17:07 | 0 | R.T.S. STEEL SERVICES
Fabrication work (L) | N/C | N/C | PATILS FABRICATORS | 235 | 2021-06-30 | D-Bldg Fab Work Near Material Lift | 472.7 | 21.6 | 0 | 10210.32 | 1837.86 | 2022-08-04 | Fabrication Work for Fixing of ISMB 150 & Angle 50 x 5 for MS Beam Support for slab | 100 |  | 95807 | 2022-08-05 | 14357.52 | 2022-09-15 17:07 | -4147.2 | R.T.S. STEEL SERVICES
Fabrication work (L) | N/C | N/C | PATILS FABRICATORS | 235 | 2021-06-30 | D-Bldg Fab Work Near Material Lift | 144 | 28.8 | 0 | 4147.2 | 746.5 | 2022-08-04 | Fabrication Work for Fixing of MS Plate (300 x 300 x 10mm) for MS Beam Support for slab | 100 |  | 95807 | 2022-08-05 | 14357.52 | 2022-09-15 17:07 | -10210.32 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | PATILS FABRICATORS | 236 | 2021-06-30 | D-Bldg Fab Work Near Material Lift | 472.7 | 54 | 0 | 25525.8 | 4594.64 | 2022-08-04 | Material Supply for Fabrication Work for ISMB 150 & Angle 50 x 5 for MS Beam Support for slab | 100 |  | 95816 | 2022-08-05 | 35893.8 | 2022-09-15 17:07 | -10368 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | PATILS FABRICATORS | 236 | 2021-06-30 | D-Bldg Fab Work Near Material Lift | 144 | 72 | 0 | 10368 | 1866.24 | 2022-08-04 | Material Supply for Fabrication Work for MS Plate (300 x 300 x 10mm) for MS Beam Support for slab | 100 |  | 95816 | 2022-08-05 | 35893.8 | 2022-09-15 17:07 | -25525.8 | R.T.S. STEEL SERVICES
Unloading work-SO | N/C | N/C | SWAPNIL SHARAD SONAWANE | 242 | 2021-07-19 | D-Bldg LG Floor 5" Blockwork | 1 | 3200 | 0 | 3200 | 0 | 2021-08-12 | Unloading of Tiles | 100 |  | 91170 | 2021-08-12 | 13200 | 2021-08-12 11:52 | -10000 | SWAPNIL SHARAD SONAWANE
Unloading work-SO | N/C | N/C | SWAPNIL SHARAD SONAWANE | 242 | 2021-07-19 | D-Bldg LG Floor 5" Blockwork | 1 | 10000 | 0 | 10000 | 0 | 2021-08-12 | Unloading Of Mivan Shuttering Material | 100 |  | 91170 | 2021-08-12 | 13200 | 2021-08-12 11:52 | -3200 | SWAPNIL SHARAD SONAWANE
Unloading of AAC Blocks | N/C | N/C | SWAPNIL SHARAD SONAWANE | 242 | 2021-07-19 | D-Bldg LG Floor 5" Blockwork | 1900 | 2 | 0 | 3800 | 0 | 2021-08-12 | Unloading of AAC Blocks | 100 |  | 91169 | 2021-08-12 | 3800 | 2021-08-12 11:54 | 0 | SWAPNIL SHARAD SONAWANE
Unloading of AAC Blocks | N/C | N/C | SWAPNIL SHARAD SONAWANE | 242 | 2021-07-19 | D-Bldg LG Floor 5" Blockwork | 915 | 3 | 0 | 2745 | 0 | 2022-05-28 | Unloading of AAC Blooks. | 100 |  | 94885 | 2022-05-28 | 2745 | 2022-05-28 10:47 | 0 | SWAPNIL SHARAD SONAWANE
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-4th Slab RCC Built-up Area (L) | 3263.677 | 140 | 0 | 456914.78 | 82244.66 | 2022-04-06 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 94193 | 2022-04-06 | 913830.75 | 2022-04-13 18:59 | -456915.97 | RITU ENTERPRISES
Schedule & Quality | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-1st Slab RCC Built-up Area (L) | 4000 | 2.5 | 0 | 10000 | 1800 | 2024-02-05 | Schedule & Quality for RCC Work | 100 | Rework for OTIS lift lintel casting | 105314 | 2024-02-13 | 10000 | 1900-01-01 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-4th Slab RCC Built-up Area (L) | 575.9 | 140 | 0 | 80626 | 14512.68 | 2022-08-25 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 95993 | 2022-08-25 | 322510 | 2022-09-06 11:21 | -241884 | RITU ENTERPRISES
Hacking Work | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-Bldg OHWT+LMR Built-Up Area Qty Difference | 461.75 | 2.5 | 0 | 1154.375 | 207.78 | 2022-10-08 | Labour charges for Hacking work after Deshuttering for OHWT & LMR F-Building. | 100 |  | 96626 | 2022-10-10 | 73880.01 | 2022-10-15 11:44 | -72725.635 | RITU ENTERPRISES
Schedule & Quality | No category | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-Bldg OHWT+LMR Built-Up Area Qty Difference | 461.75 | 2.5 | 0 | 1154.375 | 207.78 | 2022-10-08 | Schedule and Quality of RCC Work for OHWT & LMR F-Building. | 100 |  | 96626 | 2022-10-10 | 73880.01 | 2022-10-15 11:44 | -72725.635 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-Bldg OHWT+LMR Built-Up Area Qty Difference | 461.75 | 155 | 0 | 71571.25 | 12882.82 | 2022-10-08 | Labour charges for RCC work for LMR and OHWT for F-Building. | 100 |  | 96626 | 2022-10-10 | 73880.01 | 2022-10-15 11:44 | -2308.76 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-4th Slab RCC Built-up Area (L) | 3263.6855 | 140 | 0 | 456915.97 | 82244.88 | 2022-04-06 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 94193 | 2022-04-06 | 913830.75 | 2022-04-13 18:59 | -456914.78 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-5th Slab RCC Built-up Area (L) | 3071.704 | 160 | 0 | 491472.64 | 88465.08 | 2022-05-27 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 94895 | 2022-05-28 | 982944 | 2022-06-09 12:43 | -491471.36 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-5th Slab RCC Built-up Area (L) | 3071.696 | 160 | 0 | 491471.36 | 88464.84 | 2022-05-27 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 94895 | 2022-05-28 | 982944 | 2022-06-09 12:43 | -491472.64 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-5th Slab RCC Built-up Area (L) | 767.926 | 160 | 0 | 122868.16 | 22116.26 | 2022-08-04 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 95824 | 2022-08-06 | 429411 | 2022-08-16 11:06 | -306542.84 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-5th Slab RCC Built-up Area (L) | 767.924 | 160 | 0 | 122867.84 | 22116.22 | 2022-08-04 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 95824 | 2022-08-06 | 429411 | 2022-08-16 11:06 | -306543.16 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-LMR OHWT RCC | 500 | 367.35 | 0 | 183675 | 33061.5 | 2022-07-28 | RCC Work for LMR, OHWT | 100 |  | 95824 | 2022-08-06 | 429411 | 2022-08-16 11:06 | -245736 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-2nd Slab RCC Built-up Area (L) | 3839.62 | 130 | 0 | 499150.6 | 89847.1 | 2022-01-05 13:02 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 93006 | 2022-01-05 | 998302.5 | 2022-01-10 15:50 | -499151.9 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-2nd Slab RCC Built-up Area (L) | 3839.63 | 130 | 0 | 499151.9 | 89847.34 | 2022-01-05 13:02 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 93006 | 2022-01-05 | 998302.5 | 2022-01-10 15:50 | -499150.6 | RITU ENTERPRISES
Dressing, Levelling & Cleaning | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-Excavation & Cleaning | 7679.25 | 5 | 0 | 38396.25 | 0 | 2021-10-04 14:50 | Dressing, Levelling & Cleaning work for Substructure RCC Work | 100 |  | 91894 | 2021-10-06 | 591302.25 | 2021-10-09 18:57 | -552906 | RITU ENTERPRISES
PCC | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-PCC | 7679.25 | 4 | 0 | 30717 | 0 | 2021-10-04 14:50 | PCC work for Substructure RCC Work i.e. below footings & Beam | 100 |  | 91894 | 2021-10-06 | 591302.25 | 2021-10-09 18:57 | -560585.25 | RITU ENTERPRISES
Footing & Column | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-Footing & Column | 7679.25 | 45 | 0 | 345566.25 | 0 | 2021-10-04 14:50 | RCC Work for Footing & Column upto Plinth (Shuttering, Reinforcement, Concreting & Deshuttering work etc) | 100 |  | 91894 | 2021-10-06 | 591302.25 | 2021-10-09 18:57 | -245736 | RITU ENTERPRISES
RCC Beam | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-Plinth Beam | 7679.25 | 23 | 0 | 176622.75 | 0 | 2021-10-04 14:50 | RCC work for Plinth Beam (Shuttering, Reinforcement, Concreting & Deshuttering work etc.) | 100 |  | 91894 | 2021-10-06 | 591302.25 | 2021-10-09 18:57 | -414679.5 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-1st Slab RCC Built-up Area (L) | 3839.62 | 130 | 0 | 499150.6 | 89847.1 | 2021-12-06 12:01 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 92742 | 2021-12-15 | 998302.5 | 2021-12-15 18:11 | -499151.9 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-1st Slab RCC Built-up Area (L) | 3839.63 | 130 | 0 | 499151.9 | 89847.34 | 2021-12-06 12:01 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 92742 | 2021-12-15 | 998302.5 | 2021-12-15 18:11 | -499150.6 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-3rd Slab RCC Built-up Area (L) | 3263.677 | 140 | 0 | 456914.78 | 0 | 2022-02-21 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 93555 | 2022-02-22 | 913830.75 | 2022-02-24 14:17 | -456915.97 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-3rd Slab RCC Built-up Area (L) | 575.9 | 140 | 0 | 80626 | 14512.68 | 2022-08-25 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 95993 | 2022-08-25 | 322510 | 2022-09-06 11:21 | -241884 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-4th Slab RCC Built-up Area (L) | 575.9 | 140 | 0 | 80626 | 14512.68 | 2022-08-25 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 95993 | 2022-08-25 | 322510 | 2022-09-06 11:21 | -241884 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-3rd Slab RCC Built-up Area (L) | 575.9429 | 140 | -0.01 | 80632.006 | 14513.76 | 2022-08-25 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 95993 | 2022-08-25 | 322510 | 2022-09-06 11:21 | -241877.994 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 243 | 2021-07-21 | F-3rd Slab RCC Built-up Area (L) | 3263.6855 | 140 | 0 | 456915.97 | 0 | 2022-02-21 | Construction of RCC work for columns, beams, Slab, Lift Pardi, Lintels, Chajja, cantilevers, staircase incl. all Reinforcement, Centering and shuttering, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 93555 | 2022-02-22 | 913830.75 | 2022-02-24 14:17 | -456914.78 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | RITU ENTERPRISES | 252 | 2021-08-31 | Retaining Wall RCC Work(L) | 280.05 | 500 | 0 | 140025 | 0 | 2021-10-09 13:44 | Shuttering for Retaining wall - Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 91943 | 2021-10-09 | 167866.35 | 2021-10-09 18:57 | -27841.35 | RITU ENTERPRISES
Concreting Work-Dev | N/C | N/C | RITU ENTERPRISES | 252 | 2021-08-31 | Retaining Wall RCC Work(L) | 41.7 | 250 | 0 | 10425 | 0 | 2021-10-09 13:44 | RCC Retaining Wall Concreting of specified grade including compaction by vibrator, with proper line level and roughening them if special finish is to be provided.Loading,shifting,unloading of estimated raw material from store in Contractors Scope | 100 |  | 91943 | 2021-10-09 | 167866.35 | 2021-10-09 18:57 | -157441.35 | RITU ENTERPRISES
Reinforcement Work-Dev | N/C | N/C | RITU ENTERPRISES | 252 | 2021-08-31 | Retaining Wall RCC Work(L) | 2322.18 | 7.5 | 0 | 17416.35 | 0 | 2021-10-09 13:44 | Reinforcement for Retaining wall-Fixing in position reinforcement of various diameters for construction including Cutting & Bending as per BBS/drawing,Shifting to the Required place from steel yard fixing in position etc. complete as per final drawing. | 100 |  | 91943 | 2021-10-09 | 167866.35 | 2021-10-09 18:57 | -150450 | RITU ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 910.2 | 200 | 0 | 182040 | 32767.2 | 2022-02-07 | RMC Pump Rental Charges for RCC Work- JAN-2022 | 100 |  | 93384 | 2022-02-08 | 182040 | 2022-03-29 12:20 | 0 | LOTUS ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 1200 | 200 | 0 | 240000 | 43200 | 2021-10-01 | RMC Pump Rental Charges for RCC Work - SEPT-2021 | 100 |  | 91793 | 2021-10-02 | 240000 | 2021-10-11 14:06 | 0 | LOTUS ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 1200 | 200 | 0 | 240000 | 43200 | 2022-01-04 10:40 | RMC Pump Rental Charges for RCC Work - DEC-2021 | 100 |  | 92962 | 2022-01-04 | 240000 | 2022-01-28 17:05 | 0 | LOTUS ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 1200 | 200 | 0 | 240000 | 43200 | 2021-11-08 | RMC Pump Rental Charges for RCC Work - OCT-2021 | 100 |  | 92340 | 2021-11-09 | 240000 | 2021-11-22 18:31 | 0 | LOTUS ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 1200 | 200 | 0 | 240000 | 43200 | 2022-03-02 | RMC Pump Rental Charges for RCC Work- FEB-2022 | 100 |  | 93683 | 2022-03-02 | 240000 | 2022-03-24 12:09 | 0 | LOTUS ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 890.32 | 200 | 0 | 178064 | 32051.52 | 2021-09-21 | RMC Pump Rental Charges for RCC Work - AUG-2021 | 100 |  | 91606 | 2021-09-21 | 178064 | 2021-09-22 10:46 | 0 | LOTUS ENTERPRISES
Pump Hiring for RMC-BC | N/C | N/C | LOTUS ENTERPRISES | 254 | 2021-09-02 | D-Bldg RCC Work RMC Pump Charges | 1200 | 200 | 0 | 240000 | 43200 | 2021-12-02 | RMC Pump Rental Charges for RCC Work - NOV-2021 | 100 |  | 92564 | 2021-12-02 | 240000 | 2021-12-11 12:28 | 0 | LOTUS ENTERPRISES
Blockwork 5" - BC - | GLAZING SERVICES | N/C | SUNIL KUMAR | 258 | 2021-09-07 | D-Bldg parking floor blockwork (L) | 377 | 14 | 0 | 5278 | 0 | 2022-07-05 | D-Building Parking Floor Staircase wall Blockwork (125 mm thick wall). | 100 | Meter room Block work | 95400 | 2022-07-06 | 5278 | 2022-08-27 13:03 | 0 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | SUNIL KUMAR | 258 | 2021-09-07 | D-Bldg parking floor blockwork (L) | 600 | 14 | 0 | 8400 | 0 | 2022-03-20 | D-Building Parking Floor Staircase wall Blockwork (125 mm thick wall). | 100 |  | 95959 | 2022-08-23 | 8400 | 2022-08-27 13:09 | 0 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | SUNIL KUMAR | 258 | 2021-09-07 | D-Bldg parking floor blockwork (L) | 1000 | 14 | 0 | 14000 | 0 | 2022-01-17 | D-Building Parking Floor Staircase wall Blockwork (125 mm thick wall). | 100 |  | 93140 | 2022-01-18 | 14000 | 2022-02-09 16:13 | 0 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | SUNIL KUMAR | 258 | 2021-09-07 | D-Bldg parking floor blockwork (L) | 467 | 14 | 0 | 6538 | 0 | 2021-10-09 | D-Building Parking Floor Staircase wall Blockwork (125 mm thick wall). | 100 |  | 91957 | 2021-10-11 | 6538 | 1900-01-01 | 0 | SUNIL KUMAR
Blockwork 5" - BC - | GLAZING SERVICES | N/C | SUNIL KUMAR | 258 | 2021-09-07 | D-Bldg parking floor blockwork (L) | 417 | 14 | 0 | 5838 | 0 | 2022-05-06 | D-Building Parking Floor Staircase wall Blockwork (125 mm thick wall). | 100 |  | 94701 | 2022-05-07 | 5838 | 2022-08-27 13:03 | 0 | K RAMU RATHOD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 6.227 | 300 | 0 | 1868.1 | 336.26 | 2023-08-30 | Labour charges for concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101523 | 2023-08-30 | 5604.3 | 2023-09-12 12:51 | -3736.2 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 6.227 | 300 | 0 | 1868.1 | 336.26 | 2023-08-30 | Labour charges for concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101523 | 2023-08-30 | 5604.3 | 2023-09-12 12:51 | -3736.2 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 144.45 | 8 | 0 | 1155.6 | 208 | 2022-10-06 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -156238.2 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 144.45 | 8 | 0 | 1155.6 | 208 | 2022-10-06 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -156238.2 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 4.98 | 300 | 0 | 1494 | 268.92 | 2022-10-06 | Labour charges for concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -155899.8 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 124.54 | 500 | 0 | 62270 | 11208.6 | 2023-08-29 | Labour charges for shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -129592.72 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 124.54 | 500 | 0 | 62270 | 11208.6 | 2023-08-29 | Labour charges for shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -129592.72 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 210.53 | 8 | 0 | 1684.24 | 303.16 | 2023-08-29 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -190178.48 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 210.53 | 8 | 0 | 1684.24 | 303.16 | 2023-08-29 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -190178.48 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 10 | 500 | 0 | 5000 | 0 | 2023-08-31 | Labour charges for shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101534 | 2023-08-31 | 5000 | 2023-09-01 10:58 | 0 | PAWAR SHIVAPPA TARANAIK
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 99.63 | 500 | 0 | 49815 | 8966.7 | 2022-10-06 | Labour charges for shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -107578.8 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 99.63 | 500 | 0 | 49815 | 8966.7 | 2022-10-06 | Labour charges for shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -107578.8 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 4.98 | 300 | 0 | 1494 | 268.92 | 2022-10-06 | Labour charges for concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -155899.8 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 144.45 | 8 | 0 | 1155.6 | 208 | 2022-10-06 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -156238.2 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 4.98 | 300 | 0 | 1494 | 268.92 | 2022-10-06 | Labour charges for concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -155899.8 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 99.63 | 500 | 0 | 49815 | 8966.7 | 2022-10-06 | Labour charges for shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -107578.8 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 210.53 | 8 | 0 | 1684.24 | 303.16 | 2023-08-29 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -190178.48 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 124.54 | 500 | 0 | 62270 | 11208.6 | 2023-08-29 | Labour charges for shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -129592.72 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 6.227 | 300 | 0 | 1868.1 | 336.26 | 2023-08-30 | Labour charges for concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101523 | 2023-08-30 | 5604.3 | 2023-09-12 12:51 | -3736.2 | VNE INFRA PROJECTS P LTD
Breaking Work - Dld | N/C | N/C | SHREE GURUDATTA ENTERPRISES (Prop. Datta Dhawale) | 265 | 2021-09-14 | Hard Rock breaking work | 2 | 4000 | 0 | 8000 | 1440 | 2021-10-19 22:58 | Breaking of Hardrock by Tractor breaker, used for Lift footing and E & F Bldg combined footing & in triangular portion of F-Building. | 100 |  | 92126 | 2021-10-20 | 8000 | 2021-10-26 16:35 | 0 | SHREE GURUDATTA ENTERPRISES (Prop. Datta Dhawale)
Core Cutting Work | N/C | N/C | AVCON TECHNICS PVT LTD | 274 | 2021-09-28 | Parking Ret Wall Podium & E-Bldg RW Core Cutting Work | 3 | 2000 | 0 | 6000 | 1080 | 2021-10-09 14:59 | Core Cutting work in Parking Retaining wall, Podium & E-Bldg RW. | 100 |  | 91994 | 2021-10-12 | 6000 | 2022-01-20 16:00 | 0 | AVCON TECHNICS PVT LTD
Levelling Work | N/C | N/C | SS ENTERPRISES | 278 | 2021-10-16 | F-Bldg Back Filling Work | 3860.7 | 30 | 0 | 115821 | 20847.78 | 2021-12-25 | Levelling work. | 100 |  | 92843 | 2021-12-27 | 347463 | 2022-03-19 11:50 | -231642 | SS ENTERPRISES
Murum Filling (avail earth in site) | N/C | N/C | SS ENTERPRISES | 278 | 2021-10-16 | F-Bldg Back Filling Work | 3860.7 | 60 | 0 | 231642 | 41695.56 | 2021-12-25 | F-Bldg Back Filling work upto Plinth level 95.55. Excavated Average level-90.812. | 100 |  | 92843 | 2021-12-27 | 347463 | 2022-03-19 11:50 | -115821 | SS ENTERPRISES
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-29 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-28 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-24 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-26 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-25 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-27 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Brickbat W/P. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 291 | 2021-11-29 | F-Bldg Toilet Brickbat waterproofing work Shop No-23 | 0.8 | 1000 | 0 | 800 | 0 | 2022-03-20 | Brickbat Waterproofing work for F- Building (Shops) | 100 |  | 93961 | 2022-03-21 | 5600 | 2022-03-24 12:38 | -4800 | SHINDE PLUMBING CONTRACTOR
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 303 | 2021-12-09 | Rework Steel rebaring work | 18 | 210 | 0 | 3780 | 680.4 | 2021-12-25 | F Bldg Steel Rebarring work. Steel Rebars 16mm dia bars at 5 inch depth. | 100 |  | 96639 | 2022-10-10 | 6740 | 2022-10-12 11:03 | -2960 | AVCON TECHNICS PVT LTD
Rebaring work 20mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 303 | 2021-12-09 | Rework Steel rebaring work | 8 | 250 | 0 | 2000 | 360 | 2021-12-25 | Steel Rebarring work in F Bldg. Steel rebarring 20mm dia Bars at a depth of 5 inch. | 100 |  | 96639 | 2022-10-10 | 6740 | 2022-10-12 11:03 | -4740 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 303 | 2021-12-09 | Rework Steel rebaring work | 8 | 120 | 0 | 960 | 172.8 | 2021-12-25 | F Bldg Steel Rebarring work. Steel Rebars 12mm dia bars at 5 inch depth. | 100 |  | 96639 | 2022-10-10 | 6740 | 2022-10-12 11:03 | -5780 | AVCON TECHNICS PVT LTD
GI Sheet Fixing (L) | N/C | N/C | DILIP MARUTI MANDAVAKAR | 304 | 2021-12-09 | Fabrication Work-for garbage chute | 520 | 4 | 0 | 2080 | 0 | 2021-12-24 | GI Sheet Fixing. | 100 |  | 92828 | 2021-12-25 | 7582 | 2022-01-28 17:48 | -5502 | DILIP MARUTI MANDAVAKAR
Fabrication work (L) | N/C | N/C | DILIP MARUTI MANDAVAKAR | 304 | 2021-12-09 | Fabrication Work-for garbage chute | 246.3333 | 12 | 0 | 2955.9996 | 0 | 2021-12-24 | Horizontal pipe 50 mm for garbage chute ground floor to 25th floor. | 100 |  | 92828 | 2021-12-25 | 7582 | 2022-01-28 17:48 | -4626.0004 | DILIP MARUTI MANDAVAKAR
Fabrication work (L) | N/C | N/C | DILIP MARUTI MANDAVAKAR | 304 | 2021-12-09 | Fabrication Work-for garbage chute | 205 | 12 | 0 | 2460 | 0 | 2022-09-27 | Vertical pipe 40 mm for garbage chute ground floor to 25th floor. | 100 |  | 96397 | 2022-09-28 | 2460 | 2022-10-17 10:58 | 0 | PARTH ENTERPRISES
Tapping Screw- Den | N/C | N/C | DILIP MARUTI MANDAVAKAR | 304 | 2021-12-09 | Fabrication Work-for garbage chute | 156 | 2.5 | 0 | 390 | 0 | 2021-12-24 | Tapping screw. | 100 |  | 92828 | 2021-12-25 | 7582 | 2022-01-28 17:48 | -7192 | DILIP MARUTI MANDAVAKAR
Fabrication work (L) | N/C | N/C | DILIP MARUTI MANDAVAKAR | 304 | 2021-12-09 | Fabrication Work-for garbage chute | 155 | 12 | 0 | 1860 | 0 | 2023-10-06 | Vertical pipe 40 mm for garbage chute ground floor to 25th floor. | 100 |  | 102432 | 2023-10-09 | 1860 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
Fabrication work (L) | N/C | N/C | DILIP MARUTI MANDAVAKAR | 304 | 2021-12-09 | Fabrication Work-for garbage chute | 179.6667 | 12 | 0 | 2156.0004 | 0 | 2021-12-24 | Vertical pipe 40 mm for garbage chute ground floor to 25th floor. | 100 |  | 92828 | 2021-12-25 | 7582 | 2022-01-28 17:48 | -5425.9996 | DILIP MARUTI MANDAVAKAR
Core Cutting 4" -DSP | N/C | N/C | YASHWANT ENTERPRISES | 310 | 2021-12-09 | Concrete breaking & core cutting work | 50 | 300 | 0 | 15000 | 2700 | 2022-01-29 | Core Cutting work for Slab Cutting | 100 |  | 93251 | 2022-01-29 | 15000 | 2022-02-10 12:21 | 0 | SHINDE PLUMBING CONTRACTOR
Concrete Breaking work-DER | N/C | N/C | YASHWANT ENTERPRISES | 310 | 2021-12-09 | Concrete breaking & core cutting work | 8.01 | 5000 | 0 | 40050 | 0 | 2022-01-06 16:11 | Concrete breaking work (Incl.Cutting & Crushing work for Material lift | 100 |  | 93027 | 2022-01-06 | 40050 | 2022-01-10 15:31 | 0 | RAHUL V. THORAT
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-29 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-28 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-25 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-24 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-26 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-29 | 1 | 1800 | 0 | 1800 | 324 | 2022-10-10 | Internal Plumbing CP & Sanitary Fitting. | 100 |  | 96640 | 2022-10-10 | 1800 | 2022-10-17 11:01 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-24 | 1 | 1800 | 0 | 1800 | 0 | 2023-11-06 | Internal Plumbing CP & Sanitary Fitting. | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -6800 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-25 | 0.2 | 2000 | 0 | 400 | 0 | 2023-11-06 | External Plumbing Work | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -8200 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-23 | 1 | 2000 | 0 | 2000 | 0 | 2023-11-06 | External Plumbing Work | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -6600 | SHINDE PLUMBING CONTRACTOR
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-23 | 1 | 1800 | 0 | 1800 | 0 | 2023-11-06 | Internal Plumbing CP & Sanitary Fitting. | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -6800 | SHINDE PLUMBING CONTRACTOR
Int Plumbing CP & Sanitary Fittings. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-25 | 1 | 1800 | 0 | 1800 | 0 | 2023-11-06 | Internal Plumbing CP & Sanitary Fitting. | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -6800 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-24 | 0.2 | 2000 | 0 | 400 | 0 | 2023-11-06 | External Plumbing Work | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -8200 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-29 | 0.2 | 2000 | 0 | 400 | 0 | 2023-11-06 | External Plumbing Work | 100 |  | 103315 | 2023-11-06 | 8600 | 2023-12-11 14:16 | -8200 | SHINDE PLUMBING CONTRACTOR
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-27 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-29 | 0.8 | 2000 | 0 | 1600 | 0 | 2022-10-14 | External Plumbing Work | 100 |  | 96766 | 2022-10-15 | 9600 | 1900-01-01 | -8000 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-27 | 0.8 | 2000 | 0 | 1600 | 0 | 2022-10-14 | External Plumbing Work | 100 |  | 96766 | 2022-10-15 | 9600 | 1900-01-01 | -8000 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-28 | 0.8 | 2000 | 0 | 1600 | 0 | 2022-10-14 | External Plumbing Work | 100 |  | 96766 | 2022-10-15 | 9600 | 1900-01-01 | -8000 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-26 | 0.8 | 2000 | 0 | 1600 | 0 | 2022-10-14 | External Plumbing Work | 100 |  | 96766 | 2022-10-15 | 9600 | 1900-01-01 | -8000 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-24 | 0.8 | 2000 | 0 | 1600 | 0 | 2022-10-14 | External Plumbing Work | 100 |  | 96766 | 2022-10-15 | 9600 | 1900-01-01 | -8000 | SHINDE PLUMBING CONTRACTOR
External Plumbing Work - BRE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-25 | 0.8 | 2000 | 0 | 1600 | 0 | 2022-10-14 | External Plumbing Work | 100 |  | 96766 | 2022-10-15 | 9600 | 1900-01-01 | -8000 | SHINDE PLUMBING CONTRACTOR
Int Plumbing PPRC Work. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 311 | 2021-12-10 | F-Bldg Plumbing Work Shop No-23 | 1 | 1200 | 0 | 1200 | 216 | 2022-01-24 18:07 | Internal Plumbing PPRC work. | 100 |  | 93200 | 2022-01-25 | 8400 | 2022-02-10 12:24 | -7200 | SHINDE PLUMBING CONTRACTOR
Granite Riser (L)- BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 314.752 | 40 | 0 | 12590.08 | 2266.22 | 2022-04-04 | F Bldg Shops Staircase Granite Work. Granite Riser. | 100 |  | 94149 | 2022-04-05 | 26576.8 | 2022-04-15 10:54 | -13986.72 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Int Flooring Work | 1083.014 | 18 | 0 | 19494.252 | 0 | 2023-08-12 18:03 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 101244 | 2023-08-14 | 47849.87 | 2023-08-17 11:26 | -28355.618 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Skirting Work | 294.0225 | 22 | 0 | 6468.495 | 0 | 2023-08-12 18:06 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 101244 | 2023-08-14 | 47849.87 | 2023-08-17 11:26 | -41381.375 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Skirting Work | 458.53 | 22 | 0 | 10087.66 | 0 | 2023-09-22 17:06 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 102041 | 2023-09-22 | 48073.24 | 2023-10-11 11:16 | -37985.58 | PAPPU BAGELA
Flooring work- cc | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 3rd Floor Toilet Flooring Work | 100.69 | 21 | 0 | 2114.49 | 0 | 2024-07-24 16:29 | Labour charges for Fixing of Toilet Flooring (300 x 300) for 3rd floor Common Unisex Toilet-1 & 2. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -73220.83 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | Stilt Floor Stilt Floor Granite Umbra Patti | 5 | 45 | 0 | 225 | 0 | 2024-07-24 16:30 | Labour charges for Granite Cutting & Fixing work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75110.32 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Int Flooring Work | 2110.31 | 18 | 0 | 37985.58 | 0 | 2023-09-22 17:06 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 102041 | 2023-09-22 | 48073.24 | 2023-10-11 11:16 | -10087.66 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | Stilt Floor Stilt Floor Granite Umbra Patti | 5 | 10 | 0 | 50 | 0 | 2024-07-24 16:30 | Labour charges for Granite Edge Polish work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75285.32 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | Stilt Floor Granite Work (M) | 3 | 110.7 | 0 | 332.1 | 0 | 2024-07-24 16:30 | Material Supply charges for Granite for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75003.22 | PAPPU BAGELA
Granite work (M) | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | 3rd Floor Granite Work (M) | 3 | 110.7 | 0 | 332.1 | 0 | 2024-07-24 16:30 | Material Supply charges for Granite for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75003.22 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Int Flooring Work | 841.8 | 18 | 0 | 15152.4 | 0 | 2024-04-14 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 106792 | 2024-04-15 | 15152.4 | 1900-01-01 | 0 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Floor Toilet Flooring Work | 57.54 | 2 | 0 | 115.08 | 0 | 2024-07-24 16:23 | Charges for- Schedule & Quality of Ceramic flooring work of F Building toilets. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75220.24 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | 3rd Floor Stilt Floor Granite Umbra Patti | 5 | 10 | 0 | 50 | 0 | 2024-07-24 16:30 | Labour charges for Granite Edge Polish work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75285.32 | PAPPU BAGELA
Granite Riser (L)- BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 78.688 | 40 | 0 | 3147.52 | 0 | 2024-04-22 17:12 | F Bldg Shops Staircase Granite Work. Granite Riser. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -76690.48 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Floor Toilet Flooring Work | 135.2857 | 17 | 0 | 2299.8569 | 0 | 2024-04-22 11:12 | Labour Charges for- Ceramic flooring (300 x 300mm) fixing & floor guard laying work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -77538.1431 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 934.41 | 10 | 0 | 9344.1 | 0 | 2024-04-22 17:12 | F Bldg Shops Staircase Granite Work. Granite Edge Polish. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -70493.9 | PAPPU BAGELA
Granite Double Patti.-BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 77.704 | 45 | 0 | 3496.68 | 0 | 2024-04-22 17:12 | F Bldg Shops Staircase Granite Work. Granite Double Patti. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -76341.32 | PAPPU BAGELA
Granite Tappa (L) - BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 93.638 | 50 | 0 | 4681.9 | 0 | 2024-04-22 17:12 | F Bldg Shops Staircase Granite Work. Granite Tappa. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -75156.1 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Fl -Int Flooring Work | 2513.394 | 18 | 0 | 45241.092 | 0 | 2024-07-24 16:23 | Labour Charges for- Vitrified flooring fixing & Floor Guard laying with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -30094.228 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | 3rd Floor Stilt Floor Granite Umbra Patti | 5 | 45 | 0 | 225 | 0 | 2024-07-24 16:30 | Labour charges for Granite Cutting & Fixing work for Granite Umbra patti at Stilt & 3rd Floor office area between both staircase. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -75110.32 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Floor Toilet Dado | 344.1 | 23 | 0 | 7914.3 | 0 | 2024-07-24 16:23 | Labour charges for Fixing of 300 x 600 mm Dado tile (Lucia DK) for F-Bldg Common Toilet,Gents Toilet,Ladies Toilet,OPD Toilet,Unisex Toilet,Pantry Toilet,Room Toilet,Doctors Toilet,etc. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -67421.02 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Int Flooring Work | 4035.21 | 2 | 0 | 8070.42 | 0 | 2024-04-07 | Labour Charges for- Floor Guard removing & Acid Wash work. | 100 |  | 106651 | 2024-04-08 | 8070.42 | 2024-04-30 15:23 | 0 | A R CLEANING SERVICS
Granite Tappa (L) - BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 374.552 | 50 | 0 | 18727.6 | 3370.96 | 2022-03-20 | F Bldg Shops Staircase Granite Work. Granite Tappa. | 100 |  | 93960 | 2022-03-21 | 18727.6 | 1900-01-01 | 0 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Floor Toilet Dado | 842.3304 | 23 | 0 | 19373.5992 | 0 | 2023-08-12 18:38 | Labour charges for Fixing of 300 x 600 mm Dado tile (Lucia DK) for F-Bldg Common Toilet,Gents Toilet,Ladies Toilet,OPD Toilet,Unisex Toilet,Pantry Toilet,Room Toilet,Doctors Toilet,etc. | 100 |  | 101244 | 2023-08-14 | 47849.87 | 2023-08-17 11:26 | -28476.2708 | PAPPU BAGELA
Granite Double Patti.-BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 310.816 | 45 | 0 | 13986.72 | 2517.6 | 2022-04-04 | F Bldg Shops Staircase Granite Work. Granite Double Patti. | 100 |  | 94149 | 2022-04-05 | 26576.8 | 2022-04-15 10:54 | -12590.08 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Floor Toilet Flooring Work | 283.14 | 2 | 0 | 566.28 | 0 | 2024-04-22 11:12 | Charges for- Schedule & Quality of Ceramic flooring work of F Building toilets. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -79271.72 | PAPPU BAGELA
Granite Champher Polish BCo | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 934.41 | 20 | 0 | 18688.2 | 0 | 2024-04-22 17:12 | F Bldg Shops Staircase Granite Work. Granite Champher Polish. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -61149.8 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Int Flooring Work | 4035.21 | 2 | 0 | 8070.42 | 0 | 2024-04-22 11:12 | Labour Charges for- Schedule & Quality of F Building vitrified flooring work. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -71767.58 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg LG Floor Toilet Dado | 221.75 | 23 | 0 | 5100.25 | 0 | 2024-04-22 11:12 | Labour charges for Fixing of 300 x 600 mm Dado tile (Lucia DK) for F-Bldg Common Toilet,Gents Toilet,Ladies Toilet,OPD Toilet,Unisex Toilet,Pantry Toilet,Room Toilet,Doctors Toilet,etc. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -74737.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Floor Toilet Dado | 799.0196 | 23 | 0 | 18377.4508 | 0 | 2024-04-22 11:12 | Labour charges for Fixing of 300 x 600 mm Dado tile (Lucia DK) for F-Bldg Common Toilet,Gents Toilet,Ladies Toilet,OPD Toilet,Unisex Toilet,Pantry Toilet,Room Toilet,Doctors Toilet,etc. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -61460.5492 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg LG Floor Toilet Flooring Work | 37.35 | 17 | 0 | 634.95 | 0 | 2024-04-22 11:12 | Labour Charges for- Ceramic flooring (300 x 300mm) fixing & floor guard laying work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -79203.05 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg LG Floor Toilet Flooring Work | 37.35 | 2 | 0 | 74.7 | 0 | 2024-04-22 11:12 | Charges for- Schedule & Quality of Ceramic flooring work of F Building toilets. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -79763.3 | PAPPU BAGELA
Granite Cutting & fixing (L) | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Granite Work | 9.91 | 50 | 0 | 495.5 | 0 | 2024-04-22 17:12 | F Bldg Shops Staircase Granite Work. Granite Cutting and Fixing. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -79342.5 | PAPPU BAGELA
Skirting Fixing - AIE | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Fl- Skirting Work | 220.9175 | 22 | 0 | 4860.185 | 0 | 2024-04-22 11:12 | Labour Charges for- Vitrified Skirting fixing work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 107108 | 2024-04-25 | 79838 | 2024-05-15 14:39 | -74977.815 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 1st Floor Toilet Flooring Work | 147.8543 | 17 | 0 | 2513.5231 | 0 | 2023-08-12 18:51 | Labour Charges for- Ceramic flooring (300 x 300mm) fixing & floor guard laying work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 101244 | 2023-08-14 | 47849.87 | 2023-08-17 11:26 | -45336.3469 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 3rd Floor Toilet Dado | 553.53 | 23 | 0 | 12731.19 | 0 | 2024-07-24 16:29 | Labour charges for Fixing of Dado (300 x 600) for 3rd floor Common Unisex Toilet-1 & 2. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -62604.13 | PAPPU BAGELA
Schedule & Quality | No category | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Fl -Int Flooring Work | 2513.394 | 2 | 0 | 5026.788 | 0 | 2024-07-24 16:23 | Labour Charges for- Schedule & Quality of F Building vitrified flooring work. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -70308.532 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 312 | 2021-12-10 | F-Bldg 2nd Floor Toilet Flooring Work | 57.54 | 17 | 0 | 978.18 | 0 | 2024-07-24 16:23 | Labour Charges for- Ceramic flooring (300 x 300mm) fixing & floor guard laying work with proper line, level, right angle & joint filling.Transportation of raw material from store to required working place to be done by contractor scope. | 100 |  | 109401 | 2024-07-29 | 75335.32 | 1900-01-01 | -74357.14 | PAPPU BAGELA
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg 2nd Floor Blockwork | 171.12 | 18 | 0 | 3080.16 | 554.42 | 2023-09-20 | Charges for Construction of 6 Inch Blockwork for 2nd floor internal walls in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb,right angle at corner with proper joint filling etc complete. | 100 |  | 102005 | 2023-09-21 | 3080.16 | 2023-09-30 12:14 | 0 | JAI SEVALAL CONSTRUCTION
PCC Work | N/C | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg Shop Stairacse Tappa PCC Work | 947.7 | 4 | 0 | 3790.8 | 0 | 2022-01-17 | Pcc Work. | 100 |  | 93139 | 2022-01-18 | 69293.67 | 2022-02-09 14:46 | -65502.87 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg Shops 5" Blockwork | 2020.698 | 18 | 0 | 36372.564 | 0 | 2022-01-17 | 5" Blockwork for F Bldg Shops Walls. | 100 |  | 93139 | 2022-01-18 | 69293.67 | 2022-02-09 14:46 | -32921.106 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Tar Plaster | 530.67 | 15 | 0 | 7960.05 | 0 | 2022-01-17 | Tar Plaster BC | 100 |  | 93139 | 2022-01-18 | 69293.67 | 2022-02-09 14:46 | -61333.62 | K RAMU RATHOD
Tappa Brickwork | N/C | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Brickwork | 314.75 | 50 | 0 | 15737.5 | 0 | 2022-01-17 | Tappa Brickwork | 100 |  | 93139 | 2022-01-18 | 69293.67 | 2022-02-09 14:46 | -53556.17 | K RAMU RATHOD
Brickwork 4" BC | N/C | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg Shop Stairacse Tappa Brickwork | 301.82 | 18 | 0 | 5432.76 | 0 | 2022-01-17 | 4' Brickwork for Shop Staircase Tappa. | 100 |  | 93139 | 2022-01-18 | 69293.67 | 2022-02-09 14:46 | -63860.91 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg 2nd Floor Blockwork | 1463.7778 | 18 | 0 | 26348.0004 | 0 | 2022-09-26 | Charges for Construction of 6 Inch Blockwork for 2nd floor internal walls in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb,right angle at corner with proper joint filling etc complete. | 100 |  | 96377 | 2022-09-27 | 26348 | 2022-10-03 11:15 | 0.0004 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | D-Bldg 7th Floor 2BHK Flat Near Refuge Area Blockwork | 159.072 | 18 | 0 | 2863.296 | 0 | 2023-07-04 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100459 | 2023-07-05 | 10385.72 | 2023-07-26 12:25 | -7522.424 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | D-Bldg 2nd Floor 2BHK Flat Near Refuge Area Blockwork | 198.84 | 18 | 0 | 3579.12 | 0 | 2023-07-04 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100459 | 2023-07-05 | 10385.72 | 2023-07-26 12:25 | -6806.6 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | D-Bldg 12th Floor 2BHK Flat Near Refuge Area Blockwork | 159.072 | 18 | 0 | 2863.296 | 0 | 2023-07-04 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100459 | 2023-07-05 | 10385.72 | 2023-07-26 12:25 | -7522.424 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 314 | 2021-12-10 | F-Bldg Shops 5" Blockwork | 60 | 18 | 0 | 1080 | 0 | 2023-07-04 | 5" Blockwork for F Bldg Shops Walls. | 100 |  | 100459 | 2023-07-05 | 10385.72 | 2023-07-26 12:25 | -9305.72 | K RAMU RATHOD
3M Base Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 100 | 60 | 0 | 6000 | 1080 | 2022-02-12 16:35 | 3M Base Plate | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -73910 | HARISH CHANDRA JADHAV ELECTRICALS
6M Base Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 66 | 110 | 0 | 7260 | 1306.8 | 2022-02-12 16:35 | 6M Base Plate. | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -72650 | HARISH CHANDRA JADHAV ELECTRICALS
2M Base Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 80 | 50 | 0 | 4000 | 720 | 2022-02-12 16:35 | 2M Base Plate | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -75910 | HARISH CHANDRA JADHAV ELECTRICALS
4M Base Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 50 | 70 | 0 | 3500 | 630 | 2022-02-12 16:35 | 4M Base Plate | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -76410 | HARISH CHANDRA JADHAV ELECTRICALS
12M Base Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 15 | 270 | 0 | 4050 | 729 | 2022-02-12 16:35 | 12 Model Base Plate. | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -75860 | HARISH CHANDRA JADHAV ELECTRICALS
Dummy Junction Box | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 100 | 370 | 0 | 37000 | 6660 | 2022-02-12 16:35 | Dummy Juction Box | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -42910 | HARISH CHANDRA JADHAV ELECTRICALS
Dummy Junction Box Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 100 | 120 | 0 | 12000 | 2160 | 2022-02-12 16:35 | Dummy junction box plate | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -67910 | HARISH CHANDRA JADHAV ELECTRICALS
8M Base Plate | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 318 | 2021-12-11 | Mivan floor Electrical work (L) | 50 | 122 | 0 | 6100 | 1098 | 2022-02-12 16:35 | 8M Base Plate. | 100 |  | 93447 | 2022-02-12 | 79910 | 2022-03-11 12:52 | -73810 | HARISH CHANDRA JADHAV ELECTRICALS
Base Plate Fitting | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 319 | 2021-12-11 | Mivan floor Electrical work (L) | 4 | 4500 | 0 | 18000 | 3240 | 2022-02-12 17:51 | Base Plate Fitting Myone 3BHK Flat. | 100 |  | 93449 | 2022-02-12 | 50891 | 2022-03-07 19:15 | -32891 | HARISH CHANDRA JADHAV ELECTRICALS
Plate Fitting | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 319 | 2021-12-11 | Mivan floor Electrical work (L) | 100 | 60 | 0 | 6000 | 1080 | 2022-02-12 17:51 | Plate Fitting. | 100 |  | 93449 | 2022-02-12 | 50891 | 2022-03-07 19:15 | -44891 | HARISH CHANDRA JADHAV ELECTRICALS
Base Plate Fitting | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 319 | 2021-12-11 | Mivan floor Electrical work (L) | 4 | 3750 | 0 | 15000 | 2700 | 2022-02-12 17:51 | Base Plate Fixing of Myone Flat 2BHK x 5 x750 | 100 |  | 93449 | 2022-02-12 | 50891 | 2022-03-07 19:15 | -35891 | HARISH CHANDRA JADHAV ELECTRICALS
Contractor Profit-Mkt | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 319 | 2021-12-11 | Mivan floor Electrical work (L) | 1 | 11891 | 0 | 11891 | 2140.38 | 2022-02-12 17:51 | Contractor Profit Mkt | 100 |  | 93449 | 2022-02-12 | 50891 | 2022-03-07 19:15 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 323 | 2021-12-16 | F-Bldg Mezzanine Slab (L) | 886 | 82.5 | 0 | 73095 | 13157.1 | 2022-01-04 11:47 | F- Bldg , RCC Slab ( Mezzanine Slab) | 100 |  | 92963 | 2022-01-04 | 73095 | 2022-01-20 15:50 | 0 | RITU ENTERPRISES
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P5 Floor Sand Face Plaster-Full Ht On Blockwork | 111.45 | 20 | 0 | 2229 | 401.22 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -43239.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P3 Floor Sand Face Plaster-Full Ht On Blockwork | 185 | 20 | 0 | 3700 | 666 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -41768.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P2 Floor Sand Face Plaster-Full Ht On Blockwork | 162 | 20 | 0 | 3240 | 583.2 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -42228.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg Ground Floor Sand Face Plaster-Full Ht On Blockwork | 181.1 | 20 | 0 | 3622 | 651.96 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -41846.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P1 Floor Sand Face Plaster-Full Ht On Blockwork | 162 | 20 | 0 | 3240 | 583.2 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -42228.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg Ground Floor Sand Face Plaster-Full Ht On Blockwork | 760.08 | 20 | 0 | 15201.6 | 2736.28 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -30266.6 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P5 Floor Sand Face Plaster-Full Ht On Blockwork | 506.81 | 20 | 0 | 10136.2 | 1824.52 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -35332 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg Ground Floor Sand Face Plaster-Full Ht On Blockwork | 723.28 | 20 | 0 | 14465.6 | 2603.8 | 2023-12-28 15:01 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 104220 | 2024-01-01 | 64000.8 | 2024-02-05 11:36 | -49535.2 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P5 Floor Sand Face Plaster-Full Ht On Blockwork | 444.36 | 20 | 0 | 8887.2 | 1599.7 | 2023-12-28 15:01 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 104220 | 2024-01-01 | 64000.8 | 2024-02-05 11:36 | -55113.6 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P3 Floor Sand Face Plaster-Full Ht On Blockwork | 118.14 | 20 | 0 | 2362.8 | 425.3 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -43105.4 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P2 Floor Sand Face Plaster-Full Ht On Blockwork | 86.83 | 20 | 0 | 1736.6 | 312.58 | 2024-03-04 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 106962 | 2024-04-19 | 45468.2 | 2024-04-25 11:29 | -43731.6 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P2 Floor Sand Face Plaster-Full Ht On Blockwork | 646.6 | 20 | 0 | 12932 | 2327.76 | 2023-12-28 15:01 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 104220 | 2024-01-01 | 64000.8 | 2024-02-05 11:36 | -51068.8 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P3 Floor Sand Face Plaster-Full Ht On Blockwork | 739.2 | 20 | 0 | 14784 | 2661.12 | 2023-12-28 15:01 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 104220 | 2024-01-01 | 64000.8 | 2024-02-05 11:36 | -49216.8 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 329 | 2021-12-28 | D-Bldg P1 Floor Sand Face Plaster-Full Ht On Blockwork | 646.6 | 20 | 0 | 12932 | 2327.76 | 2023-12-28 15:01 | Labour Charges for Sand Face plaster work with scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using chicken mesh etc complete. | 100 |  | 104220 | 2024-01-01 | 64000.8 | 2024-02-05 11:36 | -51068.8 | JAI SEVALAL CONSTRUCTION
Unloading work-SO | N/C | N/C | SWAPNIL SHARAD SONAWANE | 330 | 2021-12-29 | D-Bldg LG Floor 5" Blockwork | 1 | 30460 | 0 | 30460 | 0 | 2022-01-06 |  | 100 |  | 93025 | 2022-01-06 | 30460 | 2022-01-06 12:03 | 0 | SWAPNIL SHARAD SONAWANE
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-12-29 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 104238 | 2024-01-01 | 10000 | 2024-02-09 11:07 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-02-08 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 98097 | 2023-02-08 | 10000 | 2023-02-20 15:36 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-10-10 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 102491 | 2023-10-11 | 10000 | 2023-11-07 13:58 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-04-18 | Total Station Point Marking for E Bldg P5+25 Floor | 100 | For 7 th floor point marking | 99213 | 2023-04-18 | 10000 | 2023-04-24 10:48 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2022-09-26 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 96370 | 2022-09-26 | 10000 | 2022-10-03 11:03 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2022-10-21 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 96839 | 2022-10-21 | 10000 | 2022-11-16 11:38 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2024-02-05 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 105076 | 2024-02-05 | 10000 | 2024-02-19 15:18 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-08-14 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 101256 | 2023-08-14 | 10000 | 2023-09-04 11:48 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-06-27 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 100299 | 2023-06-27 | 10000 | 2023-07-19 11:57 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2024-01-13 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 104554 | 2024-01-15 | 10000 | 1900-01-01 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-11-24 | Total Station Point Marking for E Bldg P5+25 Floor | 100 | For 19th floor Marking | 103494 | 2023-11-25 | 10000 | 2023-12-22 11:36 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-09-16 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 102030 | 2023-09-22 | 10000 | 2023-10-17 13:03 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2024-01-20 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 104684 | 2024-01-22 | 10000 | 2024-02-19 15:19 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-09-01 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 101542 | 2023-09-01 | 10000 | 2023-10-11 11:03 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2024-03-18 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 106216 | 2024-03-18 | 10000 | 2024-03-23 12:16 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-12-13 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 104020 | 2023-12-18 | 10000 | 2024-02-09 11:07 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-04-08 | Total Station Point Marking for E Bldg P5+25 Floor | 100 | For 6th floor point marking | 99054 | 2023-04-08 | 10000 | 2023-04-24 10:49 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-07-27 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 100876 | 2023-07-28 | 10000 | 2023-08-14 14:34 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-09-29 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 102137 | 2023-09-30 | 10000 | 2023-10-17 13:03 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-02-27 | Total Station Point Marking for E Bldg P5+25 Floor | 100 | for 5th floor point marking | 98373 | 2023-02-27 | 10000 | 2023-03-29 11:16 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-11-08 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 103390 | 2023-11-08 | 10000 | 2023-11-22 11:29 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-05-31 | Total Station Point Marking for E Bldg P5+25 Floor | 100 | For 9 th floor point marking | 99854 | 2023-05-31 | 10000 | 2023-06-22 13:52 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-05-05 | Total Station Point Marking for E Bldg P5+25 Floor | 100 | For 8th Floor point marking | 99450 | 2023-05-05 | 10000 | 2023-05-16 12:28 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-01-12 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 97761 | 2023-01-12 | 10000 | 2023-01-31 11:44 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2022-07-09 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 95873 | 2022-08-11 | 10000 | 2022-08-11 12:06 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 355 | 2022-01-20 | Total Station Survey E-Bldg Total station survey | 100 | 100 | 0 | 10000 | 0 | 2023-10-23 | Total Station Point Marking for E Bldg P5+25 Floor | 100 |  | 102925 | 2023-10-23 | 10000 | 2023-11-06 16:13 | 0 | VECTOR SURVEYORS
Gypsum Plaster (L) | N/C | N/C | SHAHID RAJA KHAN | 365 | 2022-01-24 | F-Shops Common area gypsum plaster. | 544.048 | 9.5 | 0 | 5168.456 | 0 | 2022-03-17 | Gypsum Plaster at Shop Pardi | 100 |  | 93919 | 2022-03-17 | 18723.77 | 2022-03-22 11:18 | -13555.314 | SHAHID RAJA KHAN
Gypsum Plaster (L) | N/C | N/C | SHAHID RAJA KHAN | 365 | 2022-01-24 | F-Shops Common area gypsum plaster. | 135.0526 | 9.5 | 0 | 1282.9997 | 0 | 2022-10-01 | Gypsum Plaster at Shop Pardi | 100 |  | 96479 | 2022-10-03 | 3905 | 2022-10-17 11:08 | -2622.0003 | SHAHID RAJA KHAN
Gypsum Plaster (M) | GLAZING SERVICES | N/C | SHAHID RAJA KHAN | 366 | 2022-01-24 | F-Shops Common area gypsum plaster. | 680.06 | 9.5 | 0 | 6460.57 | 0 | 2022-03-17 | Gypsum Plaster of Shop Pardi | 100 | Invoice no -202122PUN7441 | 93935 | 2022-03-18 | 25673.66 | 2022-03-30 13:56 | -19213.09 | NKV HOME DEPOT
Concrete Breaking..-Dld | N/C | N/C | PATIL CONSTRUCTION | 367 | 2022-01-29 | D-Bldg-Toilet Ledge wall cutting work | 15 | 3000 | 0 | 45000 | 0 | 2022-05-25 | Labour Charges for- D-Bldg Toilet Ledge Wall Cutting, Breaking, Grinding. | 100 |  | 94861 | 2022-05-26 | 45000 | 2022-06-09 15:10 | 0 | B R ENTERPRISES
Concrete Breaking..-Dld | N/C | N/C | PATIL CONSTRUCTION | 367 | 2022-01-29 | D-Bldg-Toilet Ledge wall cutting work | 1 | 3000 | 0 | 3000 | 0 | 2022-10-11 | Labour Charges for- D-Bldg Toilet Ledge Wall Cutting, Breaking, Grinding. | 100 |  | 96701 | 2022-10-12 | 3000 | 1900-01-01 | 0 | B R ENTERPRISES
Concrete Breaking..-Dld | N/C | N/C | PATIL CONSTRUCTION | 367 | 2022-01-29 | D-Bldg-Toilet Ledge wall cutting work | 22 | 3000 | 0 | 66000 | 0 | 2022-10-10 | Labour Charges for- D-Bldg Toilet Ledge Wall Cutting, Breaking, Grinding. | 100 |  | 96661 | 2022-10-11 | 66000 | 2022-10-15 11:41 | 0 | B R ENTERPRISES
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-707-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1603-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1407-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-907-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-801-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-802-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1607-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-807-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-808-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1303-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37585.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1202-2BHK(Near Refuse Area) Electrical Work | 1 | 12683 | -0.05 | 4439.05 | 799.02 | 2022-08-10 | PVC Conduiting for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37577.35 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1308-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37585.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1307-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37585.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1301-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37052.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1305-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37052.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1304-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37585.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1306-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37052.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1302-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-08-10 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95870 | 2022-08-11 | 42016.4 | 2022-08-27 12:55 | -37052.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1007-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-104-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1104-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1107-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1204-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1304-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-904-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-706-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-706-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1603-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2003-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1102-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-805-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-806-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-101-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1101-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1203-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1203-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1302-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-902-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-805-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1608-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1601-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1602-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1605-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1902-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1904-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1004-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1804-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2006-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1803-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2101-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1602-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1806-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1903-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1901-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2008-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1605-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1607-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1705-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1907-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2104-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2004-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2107-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2007-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2002-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2105-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1801-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2108-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1908-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2001-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1902-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2102-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1906-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2106-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1802-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1905-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1206-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-07-20 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95570 | 2022-07-21 | 27650 | 2022-08-10 11:51 | -22686.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1203-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-07-20 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95570 | 2022-07-21 | 27650 | 2022-08-10 11:51 | -23219.35 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1205-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-07-20 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95570 | 2022-07-21 | 27650 | 2022-08-10 11:51 | -22686.3 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1405-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1404-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1008-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1408-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1501-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1506-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1101-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1407-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1503-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-705-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1607-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-103-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1101-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1103-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-808-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-707-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1904-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-703-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-602-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1608-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1804-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1106-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1206-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-801-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-804-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-602-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-603-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-604-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1508-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1703-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1005-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-105-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1508-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1703-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1006-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1006-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-106-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1206-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-704-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-605-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1804-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1008-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-104-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1204-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-903-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-803-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1207-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-07-20 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95570 | 2022-07-21 | 27650 | 2022-08-10 11:51 | -23219.35 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1105-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1001-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1002-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1401-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1505-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2201-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2203-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2308-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2202-2BHK(Near Refuse Area) Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2023-07-21 | PVC Conduiting for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2307-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2301-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2208-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2304-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2205-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-504-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-906-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-801-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-003-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-004-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-205-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-605-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-606-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-305-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-107-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-307-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-502-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1108-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1007-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1102-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1006-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1003-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1005-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1406-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1508-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1707-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1805-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1904-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2003-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2005-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1706-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1704-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1701-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1807-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1808-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2103-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-05-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1603-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-407-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-701-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-706-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-006-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-105-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-408-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-007-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-108-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-501-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-901-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-805-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-202-2BHK(Near Refuse Area) Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2022-02-21 | PVC Conduiting for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370285.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-203-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-204-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-403-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-603-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-604-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-703-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-301-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-904-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-308-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-602-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-607-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-708-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-302-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-503-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-005-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-707-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-106-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-207-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-508-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-903-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-008-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-206-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-406-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-507-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-601-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-608-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-702-2BHK(Near Refuse Area) Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2022-02-21 | PVC Conduiting for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370285.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-101-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-303-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-304-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-802-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-803-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-804-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-208-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-401-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-808-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-705-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-402-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-104-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-505-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1201-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-07-02 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95344 | 2022-07-04 | 4963.7 | 2022-08-10 11:47 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1208-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-07-20 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95570 | 2022-07-21 | 27650 | 2022-08-10 11:51 | -23219.35 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-908-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-102-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-103-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-506-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-001-3BHK Flat Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-002-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-201-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-404-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-405-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-807-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-806-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-704-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-306-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1402-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1403-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1004-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1103-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1107-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1502-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1504-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1507-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-09-27 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 96394 | 2022-09-28 | 75154.8 | 2022-10-15 11:36 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1104-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70724.15 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1106-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-06-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95141 | 2022-06-18 | 75154.8 | 2022-06-27 18:23 | -70191.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2407-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -33146.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2204-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2306-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2405-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -32613.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2302-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2303-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2401-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -32613.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2408-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -33146.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2403-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -33146.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2402-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -32613.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2406-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -32613.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2404-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-10-03 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 102215 | 2023-10-04 | 37577.4 | 2023-11-01 14:24 | -33146.75 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-902-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-907-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -370294.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-905-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2022-02-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 93551 | 2022-02-22 | 374724.7 | 2022-02-24 13:21 | -369761 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2206-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2207-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -70199.5 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2305-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-07-21 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 100804 | 2023-07-22 | 74630.15 | 2023-08-09 12:24 | -69666.45 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1601-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1606-3BHK Electrical Work | 1 | 14182 | 0 | 4963.7 | 893.46 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -219976.05 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1702-2BHK(Near Refuse Area) Electrical Work | 1 | 12683 | 0 | 4439.05 | 799.02 | 2023-03-17 | PVC Conduiting for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220500.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1703-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1708-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1604-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1608-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2023-03-17 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 99393 | 2023-05-03 | 224939.75 | 2023-05-16 12:29 | -220509.1 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1001-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-101-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-102-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-606-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-607-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-608-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1604-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1604-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1106-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1107-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-905-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-906-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-708-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-601-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-606-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1003-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-108-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1104-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1108-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1201-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1205-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-901-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-807-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-704-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-601-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1401-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-803-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-2003-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1208-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1301-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1102-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1103-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-103-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-107-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1105-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1208-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-908-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1002-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-102-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1001-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1605-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-806-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1002-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1302-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-902-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-804-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1003-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1108-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1205-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1301-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-907-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1007-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-105-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1201-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1303-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1303-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-901-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-705-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-708-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1008-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1308-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-802-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-604-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-605-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-108-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-905-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1204-2BHK Electrical Work | 1 | 12659 | 0 | 4430.65 | 797.52 | 2022-07-20 | PVC Conduiting work for RCC Shear Wall & Slab | 35 |  | 95570 | 2022-07-21 | 27650 | 2022-08-10 11:51 | -23219.35 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-906-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-701-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-703-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-603-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1407-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1005-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-106-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1105-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1207-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1307-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1308-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-608-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1401-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1601-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1602-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1902-3BHK Electrical Work | 1 | 14182 | 0 | 3545.5 | 638.2 | 2024-05-17 | Switch & Socket Fixing Work | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605330.9 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1004-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1304-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-904-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-908-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-607-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-903-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-107-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1207-2BHK Electrical Work | 1 | 12659 | 0 | 3164.75 | 569.66 | 2024-05-17 | Switch Socket Fixing | 25 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605711.65 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-1307-2BHK Electrical Work | 1 | 12659 | 0 | 3797.7 | 683.58 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -605078.7 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-701-3BHK Electrical Work | 1 | 14182 | 0 | 4254.6 | 765.82 | 2024-05-17 | Internal Wiring Work | 30 |  | 107658 | 2024-05-20 | 608876.4 | 1900-01-01 | -604621.8 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-002-3BHK Electrical Work | 0.2962 | 14182 | -0.21 | 1260.2125 | 0 | 2023-10-11 | Internal Wiring Work | 30 | Debit for Shivappa Pawar (Housekeeping ) | 102553 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1259.7875 | PAWAR SHIVAPPA TARANAIK
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 369 | 2022-02-02 | D-001-3BHK Flat Electrical Work | 0.2962 | 14182 | -0.21 | 1260.2125 | 0 | 2023-10-11 | Internal Wiring Work | 30 | Debit for Shivappa Pawar (Housekeeping ) | 102553 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1259.7875 | PAWAR SHIVAPPA TARANAIK
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-803-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-402-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1104-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-902-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-607-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1904-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40088 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1206-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40068.25 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1902-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-604-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1201-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -39616 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1203-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40422.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1902-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40068.25 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1207-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1904-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-603-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1506-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-21 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22614.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1503-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-21 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22359.75 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1501-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-21 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -21553.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1505-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-21 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -21553.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1507-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-21 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22806.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1507-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-21 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22025.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1504-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-21 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22359.75 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1507-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-21 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22359.75 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1501-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-21 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22801.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1504-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-21 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22806.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1501-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-21 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22005.75 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1808-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35508.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1306-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35364.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1802-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34116.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1805-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34116.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1806-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34569 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1801-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35177.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-808-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1303-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-402-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-508-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1507-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-21 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22945.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1503-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-21 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22806.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1505-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-21 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22614.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1504-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-21 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22025.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1503-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-21 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22945.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1504-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-21 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22945.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1501-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-21 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22614.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1505-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-21 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22005.75 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1503-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-21 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22025.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1506-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-21 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -21553.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1506-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-21 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22801.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-606-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-701-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1801-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35364.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1802-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35364.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-803-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-502-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26329.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1107-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-701-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1104-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-807-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-807-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-808-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-707-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-806-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-504-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27721.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-502-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26781.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-201-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26781.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-503-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27135.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-503-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27721.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1508-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-705-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-707-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1303-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1204-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-902-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-808-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1104-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-705-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1107-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-706-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1303-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-807-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-301-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -23704.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-301-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24765.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-305-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24952.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-303-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24176.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-308-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -25096.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-304-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24957.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-303-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24510.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-304-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24510.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-308-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24176.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-404-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24176.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-404-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24957.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1603-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-14 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107239 | 2024-04-30 | 3312.75 | 2024-05-03 13:17 | -2756.75 | AAKRUTI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-403-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19493.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1102-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19488.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1102-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19301.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1102-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18693 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-405-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18693 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-405-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19301.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-405-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19488.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1102-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18240.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-403-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19632.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-706-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1508-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1204-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-402-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-707-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1104-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1107-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-806-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-402-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-803-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-705-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-508-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-606-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-701-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-607-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25255.5 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-604-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-03-17 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25841.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-605-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-03-17 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25697.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-502-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27577.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1001-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26781.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-201-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27577.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-502-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27390.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-503-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27582.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1204-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-902-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-806-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-902-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-508-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-808-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-806-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-701-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-705-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1107-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1204-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-706-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63889.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-803-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-606-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63702.75 | TEJASHREE ENTERPRISES
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-27 | 300 | 6.5 | 0 | 1950 | 351 | 2024-05-14 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 108984 | 2024-07-10 | 5850 | 2024-07-11 10:30 | -3900 | TEJASHREE ENTERPRISES
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-28 | 300 | 6.5 | 0 | 1950 | 351 | 2024-05-14 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 108984 | 2024-07-10 | 5850 | 2024-07-11 10:30 | -3900 | TEJASHREE ENTERPRISES
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-26 | 300 | 6.5 | 0 | 1950 | 351 | 2024-05-14 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 108984 | 2024-07-10 | 5850 | 2024-07-11 10:30 | -3900 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-906-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-906-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-802-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-904-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-904-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-704-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-506-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-507-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-901-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-805-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-908-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-908-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-505-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-507-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-801-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-804-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-901-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-901-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-905-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-704-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-906-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-908-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-704-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-804-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-401-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17531 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-708-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18470.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-604-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24921.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-603-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-03-17 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25841.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1307-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -7707 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1308-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -8292.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-608-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25255.5 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-602-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-03-17 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25697.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-608-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-03-17 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25841.25 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-607-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24921.25 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-108-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2023-09-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10544.25 | PATHAN HABIB MEHATAB
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-105-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2023-09-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -9291.25 | PATHAN HABIB MEHATAB
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-107-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2023-09-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10544.25 | PATHAN HABIB MEHATAB
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-107-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2023-09-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -9763.25 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-108-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2023-09-18 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10097.5 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-308-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24510.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-305-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -23704.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-301-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24156.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-301-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24952.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-307-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24957.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-202-2BHK(Near Refuse Area) Internal Painting Work | 511 | 0.75 | 0 | 383.25 | 68.98 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27755 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-306-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27390.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-504-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27582.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 548 | 1 | 0 | 548 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18501.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-504-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26801.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 1609 | 1 | 0 | 1609 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17440.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 1609 | 1 | 0 | 1609 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17440.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1203-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40088 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 1137 | 1 | 0 | 1137 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17912.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-408-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18331.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1004-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19493.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-302-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19488.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-403-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18712.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1004-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19632.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-302-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19301.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-302-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18240.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1004-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19047 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-302-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18693 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1004-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18712.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-405-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -18240.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-403-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104265 | 2024-01-01 | 20049.75 | 2024-01-16 15:02 | -19047 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1304-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12435 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1601-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12291 | SHAHI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1607-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11849.25 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1602-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12291 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-207-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2023-10-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10544.25 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-104-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2023-10-18 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10097.5 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-101-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2023-10-18 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -9743.5 | PATHAN HABIB MEHATAB
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-104-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2023-10-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10544.25 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-207-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2023-10-18 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10097.5 | PATHAN HABIB MEHATAB
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-104-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2023-10-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -9763.25 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-207-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2023-10-18 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10683.25 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-104-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2023-10-18 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10683.25 | PATHAN HABIB MEHATAB
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-207-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2023-10-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -9763.25 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1602-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11495.25 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1607-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12435 | SHAHI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1601-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11495.25 | SHAHI ENTERPRISES
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-23 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-29 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-29 | 721.0769 | 6.5 | 0 | 4686.9999 | 0 | 2022-09-13 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -2504.1602 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-23 | 294.6 | 6.5 | 0 | 1914.9 | 0 | 2023-10-09 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 102488 | 2023-10-11 | 3839.55 | 2023-11-25 11:31 | -1924.65 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-24 | 296.1 | 6.5 | 0 | 1924.65 | 0 | 2023-10-09 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 102488 | 2023-10-11 | 3839.55 | 2023-11-25 11:31 | -1914.9 | YUGESH KUMAR
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1307-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -8292.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1602-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15327 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1601-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15327 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1308-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-14 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108396 | 2024-06-17 | 1112 | 2024-08-05 13:42 | -556 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1307-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-14 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108396 | 2024-06-17 | 1112 | 2024-08-05 13:42 | -556 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-604-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25702.25 | BHARAT KASHINATH KARCHE
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-24 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-504-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27135.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1001-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27577.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-202-2BHK(Near Refuse Area) Internal Painting Work | 511 | 1 | 0 | 511 | 91.98 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27627.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-202-2BHK(Near Refuse Area) Internal Painting Work | 1554 | 0.75 | 0 | 1165.5 | 209.8 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26972.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-306-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26329.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-201-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27390.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-306-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-01-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27577.25 | RUSHIYOGI ENTERPRISES
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-602-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-907-2BHK Internal Painting Work | 1069.6 | 1 | 0 | 1069.6 | 192.52 | 2024-05-09 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107497 | 2024-05-13 | 2139.2 | 2024-06-03 12:36 | -1069.6 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1108-2BHK Internal Painting Work | 1069.6 | 1 | 0 | 1069.6 | 192.52 | 2024-05-09 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107497 | 2024-05-13 | 2139.2 | 2024-06-03 12:36 | -1069.6 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-108-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2023-09-18 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10683.25 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-107-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2023-09-18 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10683.25 | PATHAN HABIB MEHATAB
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-108-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2023-09-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -9763.25 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-107-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2023-09-18 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10097.5 | PATHAN HABIB MEHATAB
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-105-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2023-09-18 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -9743.5 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-105-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2023-09-18 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10539.25 | PATHAN HABIB MEHATAB
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-105-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2023-09-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 101947 | 2023-09-20 | 11100.25 | 2023-09-30 12:09 | -10352.25 | PATHAN HABIB MEHATAB
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 548 | 1 | 0 | 548 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18501.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-02-20 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18632.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 1137 | 1 | 0 | 1137 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17912.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1802-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35177.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1805-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35177.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-702-2BHK(Near Refuse Area) Internal Painting Work | 1554 | 1 | 0 | 1554 | 279.72 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34371.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1304-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11849.25 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1604-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12435 | SHAHI ENTERPRISES
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-27 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-28 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-29 | 230 | 4.5 | 0 | 1035 | 0 | 2022-09-13 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6156.16 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-24 | 101.1 | 4.5 | 0 | 454.95 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16945.2 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-26 | 104.1 | 4.5 | 0 | 468.45 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16931.7 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-28 | 102.6 | 4.5 | 0 | 461.7 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16938.45 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-24 | 296.1 | 6.5 | 0 | 1924.65 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15475.5 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-27 | 101.4 | 4.5 | 0 | 456.3 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16943.85 | YUGESH KUMAR
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-702-2BHK(Near Refuse Area) Internal Painting Work | 1554 | 0.75 | 0 | 1165.5 | 209.8 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34760.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1605-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11495.25 | SHAHI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1407-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11849.25 | SHAHI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-306-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-01-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26781.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1001-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-01-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -27390.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1001-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26329.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-201-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26329.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-503-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26801.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-202-2BHK(Near Refuse Area) Internal Painting Work | 1554 | 1 | 0 | 1554 | 279.72 | 2024-01-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104860 | 2024-01-29 | 28138.25 | 2024-02-19 15:21 | -26584.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-205-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-10-31 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18326.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-103-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-10-31 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17550.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-206-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-10-31 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18326.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-206-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-10-31 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18139.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-208-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-10-31 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18470.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-103-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-10-31 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18331.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-205-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-10-31 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18139.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-205-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-10-31 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17531 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-204-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-10-31 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18331.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-204-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-10-31 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17885 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-205-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-10-31 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17078.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-307-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24510.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-404-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -25096.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-404-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24510.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-303-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -25096.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-305-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24765.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-303-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24957.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-102-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2022-05-31 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 94960 | 2022-06-02 | 4474.75 | 2022-06-27 18:25 | -3118 | YUGESH KUMAR
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-707-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-807-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-16 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -64033.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1303-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63113.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-706-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-03-16 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -62641.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-106-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-09 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103800 | 2023-12-11 | 4474.75 | 1900-01-01 | -3913.75 | CITY PAINTS
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-106-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-09 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103800 | 2023-12-11 | 4474.75 | 1900-01-01 | -3726.75 | CITY PAINTS
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-25 | 238.6667 | 4.5 | 0 | 1074.0002 | 0 | 2023-05-02 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 99385 | 2023-05-03 | 6625 | 2023-05-16 12:30 | -5550.9999 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-25 | 854 | 6.5 | 0 | 5551 | 0 | 2023-05-02 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 99385 | 2023-05-03 | 6625 | 2023-05-16 12:30 | -1074 | YUGESH KUMAR
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1805-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35364.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-406-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18139.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1601-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16388 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1304-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15799 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1608-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15799 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1607-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15799 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1602-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16388 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1605-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16388 | SHAHI ENTERPRISES
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-25 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
Premium Emulsion Paint Rate Diff. BC | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-26 | 104.94 | 2 | 0 | 209.88 | 0 | 2022-09-13 | Labour charges for Rate Difference for Painting work for Height Greater than 3m. | 100 |  | 96247 | 2022-09-14 | 7191.16 | 2022-09-26 10:45 | -6981.28 | YUGESH KUMAR
2nd Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-301-3BHK Internal Painting Work | 748 | 1.25 | 0 | 935 | 168.3 | 2024-06-07 | Labour Charges for- 2nd Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -7774.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-203-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2023-10-20 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102837 | 2023-10-20 | 3312.75 | 2023-10-28 11:42 | -2895.75 | BUDDHRAJ MANJHI
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-203-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2023-10-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 102837 | 2023-10-20 | 3312.75 | 2023-10-28 11:42 | -2310 | BUDDHRAJ MANJHI
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-203-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2023-10-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102837 | 2023-10-20 | 3312.75 | 2023-10-28 11:42 | -2756.75 | BUDDHRAJ MANJHI
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-203-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2023-10-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102837 | 2023-10-20 | 3312.75 | 2023-10-28 11:42 | -1975.75 | BUDDHRAJ MANJHI
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-602-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25510.25 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-607-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25702.25 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-602-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24449.25 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-603-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24921.25 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-603-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25702.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-604-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25255.5 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-605-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24901.5 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-601-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24449.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-601-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-03-17 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25697.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-603-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25255.5 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-608-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25702.25 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-605-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25510.25 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-605-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24449.25 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-608-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-03-17 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24921.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-601-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24901.5 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-601-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -25510.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-602-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-03-17 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107250 | 2024-05-02 | 26258.25 | 2024-05-06 12:39 | -24901.5 | BHARAT KASHINATH KARCHE
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-23 | 350 | 6.5 | 0 | 2275 | 0 | 2023-10-04 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 102266 | 2023-10-05 | 6692 | 2023-11-25 11:31 | -4417 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-23 | 235.1111 | 4.5 | 0 | 1057.9999 | 0 | 2023-10-04 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 102266 | 2023-10-05 | 6692 | 2023-11-25 11:31 | -5634 | YUGESH KUMAR
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1608-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11849.25 | SHAHI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1604-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-04-24 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -11849.25 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1608-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12435 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1407-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12435 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1605-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-04-24 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107130 | 2024-04-29 | 12852 | 1900-01-01 | -12291 | SHAHI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1804-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-101-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2023-10-18 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10539.25 | PATHAN HABIB MEHATAB
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-101-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2023-10-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -10352.25 | PATHAN HABIB MEHATAB
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-101-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2023-10-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 102791 | 2023-10-19 | 11100.25 | 2023-11-06 15:45 | -9291.25 | PATHAN HABIB MEHATAB
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2003-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2003-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-25 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2003-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1804-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1804-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-25 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-501-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-505-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-501-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-505-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-506-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-801-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-903-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-801-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-908-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-505-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-506-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-407-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17885 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-401-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18326.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-708-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18331.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-407-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18470.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-708-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17550.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-708-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17885 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-408-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18470.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-401-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18139.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-407-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-30 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18331.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-406-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17531 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-704-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-506-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-801-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-903-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-905-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-507-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-905-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-906-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-901-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-904-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65772 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1604-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16580 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1607-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16580 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1605-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15327 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1608-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16580 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1304-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16580 | SHAHI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1407-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-04-18 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -16580 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1407-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15799 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1604-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-04-18 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106992 | 2024-04-22 | 17136 | 1900-01-01 | -15799 | SHAHI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1307-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -7372.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-204-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-10-31 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17550.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-206-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-10-31 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17531 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-103-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-10-31 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17885 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-208-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-10-31 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18331.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-208-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-10-31 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17885 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-206-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-10-31 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17078.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-103-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-10-31 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18470.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-204-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-10-31 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -18470.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-208-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-10-31 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103119 | 2023-10-31 | 18887.75 | 2023-11-08 16:34 | -17550.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1508-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-24 | 354 | 6.5 | 0 | 2301 | 0 | 2023-10-04 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 102266 | 2023-10-05 | 6692 | 2023-11-25 11:31 | -4391 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-24 | 235.1111 | 4.5 | 0 | 1057.9999 | 0 | 2023-10-04 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 102266 | 2023-10-05 | 6692 | 2023-11-25 11:31 | -5634 | YUGESH KUMAR
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-507-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-802-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-501-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1804-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-25 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2003-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-25 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-106-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-09 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103800 | 2023-12-11 | 4474.75 | 1900-01-01 | -3118 | CITY PAINTS
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-23 | 294.6 | 6.5 | 0 | 1914.9 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15485.25 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-23 | 101.1 | 4.5 | 0 | 454.95 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16945.2 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-25 | 102.3 | 4.5 | 0 | 460.35 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16939.8 | YUGESH KUMAR
Premium Emulsion Paint (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Premium Emulsion Paint- On Ceiling Shop No-29 | 99 | 4.5 | 0 | 445.5 | 0 | 2022-04-16 | Labour Charges for- F- Building Shop Interrnal Painting (Premium Emulsion Paint) | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -16954.65 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-27 | 316.5 | 6.5 | 0 | 2057.25 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15342.9 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-26 | 292.2 | 6.5 | 0 | 1899.3 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15500.85 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-28 | 309.6 | 6.5 | 0 | 2012.4 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15387.75 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-25 | 366 | 6.5 | 0 | 2379 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15021.15 | YUGESH KUMAR
Satin Matt Paint- (L) | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | F-Bldg Satin Matt Paint- On Wall Shop No-29 | 309.3 | 6.5 | 0 | 2010.45 | 0 | 2022-04-16 | Lbour Charges for- F Building Internal Painting Work for Sattin Matt Paint | 100 |  | 94439 | 2022-04-16 | 17400.15 | 2022-04-22 13:06 | -15389.7 | YUGESH KUMAR
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1808-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35369.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-702-2BHK(Near Refuse Area) Internal Painting Work | 511 | 0.75 | 0 | 383.25 | 68.98 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35542.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1306-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34569 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1805-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34569 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1401-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -39616 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1201-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40068.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1201-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40864 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1201-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1203-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-601-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-608-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 356 | 1 | 0 | 356 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18693.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1902-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -39616 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1208-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40422.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1902-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40864 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1203-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1904-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-02-20 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17693 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1206-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -39616 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1207-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41008 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1806-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35177.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1306-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35177.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-702-2BHK(Near Refuse Area) Internal Painting Work | 511 | 1 | 0 | 511 | 91.98 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35414.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1808-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34588.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2204-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34923 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1801-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34116.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1806-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34116.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1807-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34588.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1802-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34569 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2204-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35369.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1306-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34116.75 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2204-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-22 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34588.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1508-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63448 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-606-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-03-16 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63094 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-102-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2022-05-31 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 94960 | 2022-06-02 | 4474.75 | 2022-06-27 18:25 | -2665.75 | YUGESH KUMAR
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-102-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2022-05-31 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 94960 | 2022-06-02 | 4474.75 | 2022-06-27 18:25 | -3726.75 | YUGESH KUMAR
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-102-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2022-05-31 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 94960 | 2022-06-02 | 4474.75 | 2022-06-27 18:25 | -3913.75 | YUGESH KUMAR
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-508-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-03-17 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106960 | 2024-04-19 | 64450.75 | 2024-04-25 11:27 | -63894.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1807-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34923 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1806-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35364.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1808-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34923 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-2204-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35508.75 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1807-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-06-22 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35369.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1801-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-22 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -34569 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1807-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-06-22 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108511 | 2024-06-24 | 35925.75 | 2024-08-05 13:42 | -35508.75 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-408-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2023-12-30 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17885 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-802-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-804-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66357.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-802-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-804-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-903-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66218.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-905-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-805-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-02-23 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65418 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-904-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-805-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-02-23 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66213.75 | TEJASHREE ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-805-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 134.64 | 2024-02-23 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -66026.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-903-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -65437.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-501-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2024-02-23 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105581 | 2024-02-26 | 66774.75 | 2024-03-18 12:10 | -64965.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1308-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-06-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -7707 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1308-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-06-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -7372.75 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-301-3BHK Internal Painting Work | 1809 | 1.25 | 0 | 2261.25 | 407.02 | 2024-06-07 | Labour Charges for- 2nd Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108185 | 2024-06-10 | 8709.75 | 2024-06-15 11:50 | -6448.5 | RUSHIYOGI ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-305-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2023-12-07 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24156.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-307-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24176.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-304-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -25096.25 | RUSHIYOGI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-307-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2023-12-07 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -25096.25 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-308-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 100.08 | 2023-12-07 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24957.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-304-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-07 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103801 | 2023-12-11 | 25513.25 | 2023-12-22 11:35 | -24176.25 | RUSHIYOGI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-106-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-09 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 103800 | 2023-12-11 | 4474.75 | 1900-01-01 | -2665.75 | CITY PAINTS
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1506-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 244.22 | 2024-06-21 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22005.75 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1505-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2024-06-21 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 108556 | 2024-06-24 | 23362.5 | 2024-06-28 20:04 | -22801.5 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-406-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 100.98 | 2023-12-30 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -18326.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-408-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17550.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-406-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17078.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-401-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 325.62 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17078.75 | TEJASHREE ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-407-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2023-12-30 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 104264 | 2024-01-01 | 18887.75 | 2024-03-18 12:11 | -17550.75 | TEJASHREE ENTERPRISES
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1603-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 180.5 | 2024-03-14 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 107239 | 2024-04-30 | 3312.75 | 2024-05-03 13:17 | -2310 | AAKRUTI ENTERPRISES
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1603-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 240.66 | 2024-03-14 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107239 | 2024-04-30 | 3312.75 | 2024-05-03 13:17 | -1975.75 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1603-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 75.06 | 2024-03-14 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 107239 | 2024-04-30 | 3312.75 | 2024-05-03 13:17 | -2895.75 | AAKRUTI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-02-20 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18632.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-02-20 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17693 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1008-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-02-20 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18047 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-02-20 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18488.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-02-20 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17693 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-02-20 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18047 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 100 | 1 | 0 | 100 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18949.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 356 | 1 | 0 | 356 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18693.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-02-20 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18488.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-02-20 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18488.75 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 548 | 1 | 0 | 548 | 0 | 2024-02-20 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -18501.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1006-3BHK Internal Painting Work | 1609 | 1 | 0 | 1609 | 0 | 2024-02-20 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 105582 | 2024-02-26 | 19049.75 | 2024-03-12 14:17 | -17440.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1207-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40088 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1401-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40068.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1203-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41008 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1207-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1205-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40068.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1401-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40864 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1205-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1007-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1205-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -39616 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1206-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1206-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1205-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40864 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1206-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40864 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1205-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1208-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-04-12 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40088 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-607-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1201-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1208-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-603-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-604-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-605-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1208-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41008 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1902-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-602-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1401-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-605-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1401-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-601-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1208-2BHK Internal Painting Work | 1337 | 0.25 | 0 | 334.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41090.75 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1002-3BHK Internal Painting Work | 748 | 0.25 | 0 | 187 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41238 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-608-2BHK Internal Painting Work | 556 | 0.25 | 0 | 139 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for Ceiling Paint.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41286 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1207-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40422.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1904-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-04-12 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40422.25 | BHARAT KASHINATH KARCHE
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1904-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-04-12 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -41008 | BHARAT KASHINATH KARCHE
Cleaning work.- BRE | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-1005-3BHK Internal Painting Work | 1809 | 0.25 | 0 | 452.25 | 0 | 2024-04-12 | Labour Charges for- Final Cleaning work for OBD Paint of Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 106779 | 2024-04-15 | 41425 | 2024-04-30 15:25 | -40972.75 | BHARAT KASHINATH KARCHE
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-14th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-08-17 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 95913 | 2022-08-18 | 13000 | 2022-08-27 12:55 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-18th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-03 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 99394 | 2023-05-03 | 78000 | 2023-05-16 12:29 | -65000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-20th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-03 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 99394 | 2023-05-03 | 78000 | 2023-05-16 12:29 | -65000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-19th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-03 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 99394 | 2023-05-03 | 78000 | 2023-05-16 12:29 | -65000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-21st Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-03 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 99394 | 2023-05-03 | 78000 | 2023-05-16 12:29 | -65000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-16th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-03 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 99394 | 2023-05-03 | 78000 | 2023-05-16 12:29 | -65000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-13th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-07-01 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 95327 | 2022-07-02 | 26000 | 2022-08-04 10:44 | -13000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-11th Floor | 1 | 13000 | 0 | 13000 | 0 | 2022-03-20 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93964 | 2022-03-21 | 13000 | 2022-03-24 12:36 | 0 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-4th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-9th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-5th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-22nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-07-21 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 100803 | 2023-07-22 | 26000 | 1900-01-01 | -13000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-8th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-1st Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-7th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-17th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-03 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 99394 | 2023-05-03 | 78000 | 2023-05-16 12:29 | -65000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-15th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-09-27 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 96395 | 2022-09-28 | 13000 | 2022-10-15 11:35 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-24th Floor | 1 | 13000 | 0 | 13000 | 0 | 2024-07-30 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 109559 | 2024-08-05 | 26000 | 1900-01-01 | -13000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-25th Floor | 1 | 13000 | 0 | 13000 | 0 | 2024-07-30 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 109559 | 2024-08-05 | 26000 | 1900-01-01 | -13000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-23rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-07-21 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 100803 | 2023-07-22 | 26000 | 1900-01-01 | -13000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-10th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-2nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-3rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-6th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-02-23 18:06 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 93567 | 2022-02-23 | 130000 | 2022-03-11 12:11 | -117000 | SHINDE PLUMBING CONTRACTOR
Sleeve Fixing Work | No category | N/C | SHINDE PLUMBING CONTRACTOR | 374 | 2022-02-10 | Sleeve Fixing Work-12th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-07-01 | Sleeve fixing work for AC, Fire fighting and Plumbing etc in D-Bldg | 100 |  | 95327 | 2022-07-02 | 26000 | 2022-08-04 10:44 | -13000 | HARISH CHANDRA JADHAV ELECTRICALS
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 3rd Floor Blockwork | 1421.9 | 18 | 0 | 25594.2 | 0 | 2022-09-26 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -73241 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 1st Floor Blockwork | 2780 | 18 | 0 | 50040 | 0 | 2023-01-02 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 97590 | 2023-01-03 | 50040 | 2023-01-23 18:39 | 0 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 2nd Floor Blockwork Amendment Qty | 200 | 18 | 0 | 3600 | 648 | 2024-01-23 | Charges for Construction of 6 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 104746 | 2024-01-23 | 7500 | 2024-02-05 11:35 | -3900 | JAI SEVALAL CONSTRUCTION
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 3rd Floor Blockwork Amendment Qty | 1447.74 | 18 | 0 | 26059.32 | 4690.68 | 2023-09-09 11:38 | Charges for Construction of 6 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 101801 | 2023-09-11 | 26059.32 | 2023-09-30 12:15 | 0 | JAI SEVALAL CONSTRUCTION
Rough Plaster - SO | N/C | N/C | K RAMU RATHOD | 375 | 2022-02-10 | 3rd Fl Toilet Internal Rough Coat (tar) Plaster | 195 | 20 | 0 | 3900 | 702 | 2024-01-23 | Labour Charges for Tar Plaster work for F-Bldg 3rd Floor Common Toilet area before Dado work. | 100 |  | 104746 | 2024-01-23 | 7500 | 2024-02-05 11:35 | -3600 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F- Bldg Stilt Floor Blockwork | 50 | 18 | 0 | 900 | 0 | 2023-05-08 | Labour Charges for- 5 Inch Blockwork for F Building | 100 |  | 99532 | 2023-05-09 | 33478 | 2023-06-10 10:38 | -32578 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F- Bldg Stilt Floor Blockwork | 632.625 | 20 | 0 | 12652.5 | 0 | 2022-07-05 | Labour Charges for- 8 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 95398 | 2022-07-06 | 47031.6 | 2022-08-27 13:33 | -34379.1 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F- Bldg Stilt Floor Blockwork | 1909.95 | 18 | 0 | 34379.1 | 0 | 2022-07-05 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 95398 | 2022-07-06 | 47031.6 | 2022-08-27 13:33 | -12652.5 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg LG Floor Blockwork | 1973.2778 | 18 | 0 | 35519.0004 | 0 | 2023-03-18 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 | Having QTY-1973.3 Sq.Ft. | 98822 | 2023-03-20 | 35519 | 2023-03-30 12:48 | 0.0004 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-27 | 101.82 | 20 | 0 | 2036.4 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -13805.6 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-26 | 102.03 | 20 | 0 | 2040.6 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -13801.4 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-25 | 118.04 | 20 | 0 | 2360.8 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -13481.2 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-23 | 143.71 | 20 | 0 | 2874.2 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -12967.8 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg LG Floor Blockwork | 259.6667 | 18 | 0 | 4674.0006 | 0 | 2023-05-08 | Labour Charges for- 5 Inch Blockwork for F Building. | 100 |  | 99532 | 2023-05-09 | 33478 | 2023-06-10 10:38 | -28803.9994 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 1st Floor Blockwork | 3000 | 18 | 0 | 54000 | 0 | 2022-12-14 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 97381 | 2022-12-14 | 58037.04 | 2022-12-23 11:28 | -4037.04 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg LG Floor Blockwork | 263.875 | 20 | 0 | 5277.5 | 949.96 | 2024-02-12 | Labour Charges for- 8 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 105279 | 2024-02-12 | 5277.5 | 2024-03-01 11:45 | 0 | JAI SEVALAL CONSTRUCTION
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 1st Floor Blockwork | 539.6667 | 18 | 0 | 9714.0006 | 0 | 2023-05-08 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 99532 | 2023-05-09 | 33478 | 2023-06-10 10:38 | -23763.9994 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-29 | 102.13 | 20 | 0 | 2042.6 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -13799.4 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-24 | 107.72 | 20 | 0 | 2154.4 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -13687.6 | K RAMU RATHOD
Tar Plaster-BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | Toilet- Internal wall tar plaster Shop No-28 | 116.65 | 20 | 0 | 2333 | 0 | 2022-07-23 | Labour Charges for- F Building Shops toilet internal tar plaster work. | 100 |  | 95637 | 2022-07-25 | 15842 | 2022-08-27 13:10 | -13509 | K RAMU RATHOD
Sand face Plaster- cc | N/C | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Shops Shutter beam sand face plaster | 78.6 | 20 | 0 | 1572 | 0 | 2022-12-09 | Shop Shutter beam plaster work for F shop | 100 |  | 97326 | 2022-12-10 | 3772 | 1900-01-01 | -2200 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 2nd Floor Blockwork Amendment Qty | 694 | 18 | 0 | 12492 | 0 | 2023-03-06 | Charges for Construction of 6 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 98546 | 2023-03-08 | 12492 | 2023-03-23 11:05 | 0 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 1st Floor Blockwork | 247.5 | 18 | 0 | 4455 | 0 | 2023-05-08 | Labour Charges for- 5 Inch Blockwork for F Building. | 100 |  | 99532 | 2023-05-09 | 33478 | 2023-06-10 10:38 | -29023 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 2nd Floor Blockwork Amendment Qty | 45.8333 | 18 | 0 | 824.9994 | 0 | 2023-05-08 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 99532 | 2023-05-09 | 33478 | 2023-06-10 10:38 | -32653.0006 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg LG Floor Blockwork | 645.5 | 20 | 0 | 12910 | 0 | 2023-05-08 | Labour Charges for- 8 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 99532 | 2023-05-09 | 33478 | 2023-06-10 10:38 | -20568 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg LG Floor Blockwork | 379.68 | 18 | 0 | 6834.24 | 1230.16 | 2023-09-20 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 102006 | 2023-09-21 | 6834.24 | 2023-09-30 12:14 | 0 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- cc | N/C | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Shops Shutter beam sand face plaster | 314.4 | 20 | 0 | 6288 | 0 | 2022-02-21 | Shop Shutter beam plaster work for F shop | 100 |  | 95958 | 2022-08-23 | 33288 | 2022-08-27 13:04 | -27000 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 3rd Floor Blockwork | 54.1667 | 18 | 0 | 975.0006 | 0 | 2022-09-26 | Labour Charges for- 5 Inch Blockwork for F Building. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -97860.1994 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 2nd Floor Blockwork | 1421.9 | 18 | 0 | 25594.2 | 0 | 2022-09-26 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -73241 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 2nd Floor Blockwork | 54.1667 | 18 | 0 | 975.0006 | 0 | 2022-09-26 | Labour Charges for- 5 Inch Blockwork for F Building. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -97860.1994 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F- Bldg Stilt Floor Blockwork | 636 | 18 | 0 | 11448 | 0 | 2022-09-26 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -87387.2 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg Terrace Floor Blockwork | 14.1 | 18 | 0 | 253.8 | 0 | 2022-09-26 | Labour Charges for- 5 Inch Blockwork for F Building. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -98581.4 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 3rd Floor Blockwork | 348.1 | 20 | 0 | 6962 | 0 | 2022-09-26 | Labour Charges for- 8 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -91873.2 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg 2nd Floor Blockwork | 348.1 | 20 | 0 | 6962 | 0 | 2022-09-26 | Labour Charges for- 8 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -91873.2 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg Terrace Floor Blockwork | 809 | 18 | 0 | 14562 | 0 | 2022-09-26 | Labour Charges for- 6 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -84273.2 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg Terrace Floor Blockwork | 275.45 | 20 | 0 | 5509 | 0 | 2022-09-26 | Labour Charges for- 8 Inch AAC Blockwork with proper line,level,plumb and right angle. | 100 |  | 96376 | 2022-09-27 | 98835.2 | 2022-10-03 11:16 | -93326.2 | K RAMU RATHOD
Blockwork 6" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 375 | 2022-02-10 | F-Bldg Above Terrace Floor LMR & OHWT Blockwork | 224.28 | 18 | 0 | 4037.04 | 0 | 2022-12-14 | Charges for Construction of 6 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 97381 | 2022-12-14 | 58037.04 | 2022-12-23 11:28 | -54000 | K RAMU RATHOD
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-08 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16594 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-08 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -15052.6 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-12-08 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16749.2 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-08 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -15511.6 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-08 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16287.6 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-08 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16094.6 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-08 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16287.6 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 541.2 | 1 | 0 | 541.2 | 97.42 | 2023-12-08 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16323.4 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 230.8 | 1 | 0 | 230.8 | 41.54 | 2023-12-08 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16633.8 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-08 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -15511.6 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2003-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-25 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1308-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46173 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1306-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45844 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1308-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45397 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1307-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46173 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2204-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46073.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2204-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45397 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1003-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27848 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1105-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27655 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1101-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -26613 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1108-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1101-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-20 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27655 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1004-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18499.8 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19582.2 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1102-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19082.8 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1501-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12140 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1505-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12004 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1206-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1206-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1501-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -11098 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1501-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12140 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1501-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12004 | SHUBHAM SURENDRA BAHADUR SINGH
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1505-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12525 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1201-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1401-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1904-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1205-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1207-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1004-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19275.8 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19490.4 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1207-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1203-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1904-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1904-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1401-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2024-04-12 | Labour Charges for- Ceiling Touch up work | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43652 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1902-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1206-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1205-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1904-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 0 | 2024-04-12 | Labour Charges for- Wall touch up work. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43360.5 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21526.1 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -20692.5 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-06-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95143 | 2022-06-18 | 1340.8 | 2022-06-27 18:27 | -724.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-702-2BHK(Near Refuse Area) Flat Putty Work (L) | 399.7 | 1 | 0 | 399.7 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21742.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21059.7 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21059.7 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21680.5 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.401 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 172.8 | 2023-11-25 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103499 | 2023-11-27 | 16960 | 2023-12-11 14:22 | -16000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.403 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-11-25 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 103499 | 2023-11-27 | 16960 | 2023-12-11 14:22 | -9960 | SHREE RAM INTERIOR & DECORATORS
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-703-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-701-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-903-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1006-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1005-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.807 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-02-17 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -17110.6 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.405 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-06-16 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -21264 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23061.6 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23528 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23682.4 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23682.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.404 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-06-16 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -21744 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23061.6 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.104 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.502 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-06-16 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -21264 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.504 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-06-16 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -21744 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -22694.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-06-16 | Labour Charges for- Wall touch up work. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23419.2 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23528 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1802-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1801-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46365 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1806-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46365 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1801-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1805-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2204-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46173 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -19049 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.805 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-02-17 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -16630.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-701-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-901-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 947.1 | 0.5 | 0 | 473.55 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67315.65 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-207-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 947.1 | 1 | 0 | 947.1 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66842.1 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1104-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1201-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1202-2BHK(Near Refuse Area) Putty Work (L) | 1168 | 0.5 | 0 | 584 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13634 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1208-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 403.9 | 0.5 | 0 | 201.95 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67587.25 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1205-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1105-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21704.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1108-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21743.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-807-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1508-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1303-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-05-09 | Labour Charges for- Wall touch up work. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21182 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-901-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1107-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-903-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1104-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-15 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-807-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-908-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-901-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54032.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1508-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54341 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-902-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-903-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-807-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-203-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24390.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.705 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-12-09 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103802 | 2023-12-11 | 31240 | 2023-12-25 15:41 | -23040 | A K INTERIOR CONTRACTOR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21704.5 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-807-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-904-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54032.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46007.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.408 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-07-22 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -22600.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-07-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24770 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-07-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24384.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-07-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -23551.2 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-104-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-07-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -23918.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-07-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -23551.2 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-07-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -23551.2 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.402 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-07-22 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -22120.8 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.403 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-07-22 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -22600.8 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-104-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-07-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -23918.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-07-22 | Labour Charges for- Wall touch up work. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24459.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-07-22 | Labour Charges for- Wall touch up work. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24459.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-07-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -23918.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-07-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24539.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-07-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24692.8 | YUGESH KUMAR
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1102 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-12-08 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103804 | 2023-12-11 | 21600 | 1900-01-01 | -13400 | SHREE RAM INTERIOR & DECORATORS
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-07-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24770 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.401 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-07-22 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -22120.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-07-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24692.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1105-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -26613 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-703-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27848 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-703-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-20 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27848 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1003-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1103-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-703-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.105 Dhar Core Work-(L) (3BHK) | 0.17 | 4800 | 0 | 816 | 146.88 | 2023-09-20 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -32216 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.107 Dhar Core Work-(L) (2BHK) | 0.125 | 4000 | 0 | 500 | 90 | 2023-09-20 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -32532 | SHREE RAM INTERIOR & DECORATORS
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1802-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46365 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1802-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1306-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2204-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45397 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1307-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46173 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2204-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46461.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1308-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46173 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1802-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45844 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1801-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1802-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1806-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1307-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45397 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2204-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46173 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1307-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45397 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1806-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1306-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46365 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1308-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46461.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1106-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -26613 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1003-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1106-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -26613 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1106-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27655 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1106-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-20 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27655 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1806-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1508-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-05-09 | Labour Charges for- Wall touch up work. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21182 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2003-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-05-09 | Labour Charges for- Wall touch up work. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21182 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 405 | 1 | 0 | 405 | 72.9 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21453.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 270 | 1 | 0 | 270 | 48.6 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21588.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1108-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-09 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -20505.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 362 | 1 | 0 | 362 | 65.16 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21496.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 543 | 1 | 0 | 543 | 97.74 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21315.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21704.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1203-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1207-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1205-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1401-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1207-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1401-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1203-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43460 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1201-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1902-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2024-04-12 | Labour Charges for- Ceiling Touch up work | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43652 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19582.2 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19698.8 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1102-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18040.8 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1004-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19275.8 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1603-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107238 | 2024-04-30 | 2895 | 2024-05-03 13:16 | -1542 | AAKRUTI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1603-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-03-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 107238 | 2024-04-30 | 2895 | 2024-05-03 13:16 | -2606.5 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1603-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107238 | 2024-04-30 | 2895 | 2024-05-03 13:16 | -2318 | AAKRUTI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18499.8 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19490.4 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19082.8 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1603-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-03-14 | Labour Charges for- Wall touch up work. | 100 |  | 107238 | 2024-04-30 | 2895 | 2024-05-03 13:16 | -2218.5 | AAKRUTI ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.107 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-09-20 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -26032 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.108 Dhar Core Work-(L) (2BHK) | 0.125 | 4000 | 0 | 500 | 90 | 2023-09-20 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -32532 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.105 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-09-20 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -24832 | SHREE RAM INTERIOR & DECORATORS
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -59018 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58400.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58921.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1804-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-25 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1105-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -26613 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2003-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-25 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19737.4 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19275.8 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1102-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19082.8 | RUSHIYOGI ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.403 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 144 | 2023-11-25 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 103499 | 2023-11-27 | 16960 | 2023-12-11 14:22 | -16160 | SHREE RAM INTERIOR & DECORATORS
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-07-22 | Labour Charges for- Wall touch up work. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24459.6 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-104-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-07-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24539.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45486.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1405-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.401 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-11-25 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103499 | 2023-11-27 | 16960 | 2023-12-11 14:22 | -8760 | SHREE RAM INTERIOR & DECORATORS
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18224 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-12-09 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103805 | 2023-12-11 | 516.4 | 1900-01-01 | -154 | CITY PAINTS
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -16989 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18224 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1001-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-01-25 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18031 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -17448 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1602-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42584 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1407-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1608-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1608-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1607-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1604-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43201.5 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1605-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43105 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1605-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42720 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1607-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43201.5 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1605-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42720 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1608-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43201.5 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1607-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1407-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43201.5 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1601-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -41678 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1604-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1607-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42813.5 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1608-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24390.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -23556.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -23924 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.705 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-12-09 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103802 | 2023-12-11 | 31240 | 2023-12-25 15:41 | -29320 | A K INTERIOR CONTRACTOR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.202 Dhar Core work-(L) (2BHK) Near Refuge | 0.18 | 7000 | 0 | 1260 | 0 | 2023-10-11 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102550 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260 | PAWAR SHIVAPPA TARANAIK
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 0.1537 | 8200 | -0.34 | 1260.34 | 0 | 2023-10-11 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102550 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1259.66 | PAWAR SHIVAPPA TARANAIK
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2023-12-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103805 | 2023-12-11 | 516.4 | 1900-01-01 | -362.4 | CITY PAINTS
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1306-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1801-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45844 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1805-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45844 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1801-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1806-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1802-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1805-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1805-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46365 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1806-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45844 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1805-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-905-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-906-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-903-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-908-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1307-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46461.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21704.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21088.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 362 | 1 | 0 | 362 | 65.16 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21496.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21743.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-808-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21743.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1108-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-701-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21088.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21088.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 362 | 1 | 0 | 362 | 65.16 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21496.5 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45486.8 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46007.8 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.506 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-12-12 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -26000 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28264 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28418.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27430.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27430.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.008 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.104 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.108 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.107 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1408-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.206 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.306 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1408-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30956.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1402-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30475 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1403-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1402-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30475 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.405 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-11-02 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103250 | 2023-11-04 | 28840 | 2023-11-22 11:29 | -26920 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.406 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-11-02 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103250 | 2023-11-04 | 28840 | 2023-11-22 11:29 | -26920 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.406 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-11-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103250 | 2023-11-04 | 28840 | 2023-11-22 11:29 | -20640 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.404 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-11-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 103250 | 2023-11-04 | 28840 | 2023-11-22 11:29 | -21840 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.404 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 288 | 2023-11-02 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 103250 | 2023-11-04 | 28840 | 2023-11-22 11:29 | -27240 | SHREE RAM INTERIOR & DECORATORS
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1404-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.405 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-11-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103250 | 2023-11-04 | 28840 | 2023-11-22 11:29 | -20640 | SHREE RAM INTERIOR & DECORATORS
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 154 | 0.5 | 0 | 77 | 0 | 2023-09-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 101946 | 2023-09-20 | 644.2 | 1900-01-01 | -567.2 | PATHAN HABIB MEHATAB
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -23924 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 362.4 | 0.5 | 0 | 181.2 | 0 | 2023-09-18 | Labour Charges for- Wall touch up work. | 100 |  | 101946 | 2023-09-20 | 644.2 | 1900-01-01 | -463 | PATHAN HABIB MEHATAB
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 115.4 | 0.5 | 0 | 57.7 | 0 | 2023-09-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 101946 | 2023-09-20 | 644.2 | 1900-01-01 | -586.5 | PATHAN HABIB MEHATAB
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-10-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29323.1 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-10-31 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29108.5 | RUSHIYOGI ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.305 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-10-31 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -27765.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-10-31 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -27873.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-10-31 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -28332.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 173.1 | 0.5 | 0 | 86.55 | 15.58 | 2023-10-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29598.95 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-10-31 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -28332.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 405.9 | 0.5 | 0 | 202.95 | 36.54 | 2023-10-31 | Labour Charges for- Wall touch up work. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29482.55 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-10-31 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29108.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1103-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27848 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.002 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.004 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.304 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.003 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.305 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.103 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.202 Dhar Core work-(L) (2BHK) Near Refuge | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.102 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.303 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.205 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.204 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27797.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46007.8 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1707-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1405-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-12-09 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 103802 | 2023-12-11 | 31240 | 2023-12-25 15:41 | -24240 | A K INTERIOR CONTRACTOR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1105-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1207-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.307 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 0 | 2023-10-19 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102836 | 2023-10-20 | 24299.66 | 2023-10-28 11:42 | -22699.66 | BUDDHRAJ MANJHI
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.203 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-10-19 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102836 | 2023-10-20 | 24299.66 | 2023-10-28 11:42 | -23499.66 | BUDDHRAJ MANJHI
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 0.8463 | 8200 | 0 | 6939.66 | 0 | 2023-10-19 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 102836 | 2023-10-20 | 24299.66 | 2023-10-28 11:42 | -17360 | BUDDHRAJ MANJHI
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.203 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 0 | 2023-10-19 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102836 | 2023-10-20 | 24299.66 | 2023-10-28 11:42 | -17299.66 | BUDDHRAJ MANJHI
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.307 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 0 | 2023-10-19 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102836 | 2023-10-20 | 24299.66 | 2023-10-28 11:42 | -17299.66 | BUDDHRAJ MANJHI
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-10-19 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 102836 | 2023-10-20 | 24299.66 | 2023-10-28 11:42 | -23339.66 | BUDDHRAJ MANJHI
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.802 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-02-17 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -16630.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-902-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 1268.4 | 1 | 0 | 1268.4 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18242.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1003-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-904-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-808-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1006-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1008-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1001-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-807-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-901-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-702-2BHK(Near Refuse Area) Flat Putty Work (L) | 1168 | 0.5 | 0 | 584 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28072.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1004-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-902-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1003-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-202-2BHK(Near Refuse Area) Putty Work (L) | 571 | 1 | 0 | 571 | 102.78 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18230 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1001-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18031 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -16989 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-202-2BHK(Near Refuse Area) Putty Work (L) | 1460 | 1 | 0 | 1460 | 262.8 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -17341 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18031 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -16989 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1001-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-01-25 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -16989 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -17448 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1807-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -9361.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1808-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -9361.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-702-2BHK(Near Refuse Area) Flat Putty Work (L) | 1460 | 1 | 0 | 1460 | 262.8 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108539 | 2024-06-24 | 2031 | 1900-01-01 | -571 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1808-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-14 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -8297 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1808-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-14 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -9073 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1807-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-14 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -8297 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1808-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -8297 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1808-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -9073 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1807-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-14 | Labour Charges for- Wall touch up work. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -8973.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-702-2BHK(Near Refuse Area) Flat Putty Work (L) | 571 | 1 | 0 | 571 | 102.78 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108539 | 2024-06-24 | 2031 | 1900-01-01 | -1460 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1808-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-14 | Labour Charges for- Wall touch up work. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -8973.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1607-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1605-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42584 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1605-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -41678 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1407-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1601-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42720 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1407-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42813.5 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1604-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1002-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -17936 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1005-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-02-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -17936 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1006-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18978 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1002-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18978 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1007-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-02-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18395 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1005-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -17936 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1007-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18395 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1002-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-02-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -17936 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1006-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-02-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -17936 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1005-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18978 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1008-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18395 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1008-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-02-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -18395 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1007-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -19171 | BHARAT KASHINATH KARCHE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1601-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43105 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1604-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67019.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-207-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-104-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1108-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1205-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1203-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1202-2BHK(Near Refuse Area) Putty Work (L) | 456.8 | 0.5 | 0 | 228.4 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13989.6 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12374.8 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12567.8 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12990.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12874.2 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12567.8 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24544.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24544.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -23556.8 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1604-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42813.5 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1608-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42813.5 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1602-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -41678 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1304-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43201.5 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1602-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -41678 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1407-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1605-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -41678 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1602-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42720 | SHAHI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1602-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-04-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -43105 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1601-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -41678 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1604-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47902.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.601 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -45638.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47068.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47436 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.605 Dhar Core Work-(L) (3BHK) | 1 | 4800 | 0 | 4800 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -43718.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -48056.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-808-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1508-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-907-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1508-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-905-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54032.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-904-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-902-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 1268.4 | 1 | 0 | 1268.4 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18242.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-907-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-908-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-908-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1007-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-807-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1007-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1008-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.207 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-202-2BHK(Near Refuse Area) Putty Work (L) | 1168 | 0.5 | 0 | 584 | 0 | 2023-01-10 | Labour Charges for- Wall touch up work. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42156.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.202 Dhar Core work-(L) (2BHK) Near Refuge | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 346.2 | 1 | 0 | 346.2 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42394.1 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42586.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42586.3 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-06-16 | Labour Charges for- Wall touch up work. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23602.8 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.102 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 135.3 | 1 | 0 | 135.3 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42605 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-104-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42469.7 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-07-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24692.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-07-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24770 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-905-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-903-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-904-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-907-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-907-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 811.8 | 1 | 0 | 811.8 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13012.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-07-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13516 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.307 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-07-14 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -11424 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 811.8 | 1 | 0 | 811.8 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13012.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 346.2 | 1 | 0 | 346.2 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13477.8 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.308 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-07-14 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -11424 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-07-14 | Labour Charges for- Wall touch up work. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13282.8 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-07-14 | Labour Charges for- Wall touch up work. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13282.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 346.2 | 1 | 0 | 346.2 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13477.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 1087.2 | 1 | 0 | 1087.2 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -12736.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-07-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13593.2 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1308-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45397 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1801-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1805-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -44938 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1308-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46073.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1804-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1804-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-25 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-07-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13516 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-07-14 | Labour Charges for- Wall touch up work. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13099.2 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2003-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-02-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44927 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45486.8 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1903-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1405-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -20692.5 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.803 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-02-02 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -19742.1 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-702-2BHK(Near Refuse Area) Flat Putty Work (L) | 1168 | 1 | 0 | 1168 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -20974.1 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21680.5 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-801-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21526.1 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.801 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-02-02 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -19262.1 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-06-17 | Labour Charges for- Wall touch up work. | 100 |  | 95143 | 2022-06-18 | 1340.8 | 2022-06-27 18:27 | -616 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.804 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-02-02 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -19742.1 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-701-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -20692.5 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-701-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21526.1 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21526.1 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21680.5 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -21059.7 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2023-02-02 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97998 | 2023-02-03 | 22142.1 | 2023-02-09 11:09 | -20692.5 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.106 Dhar Core Work-(L) (3BHK) | 0.17 | 4800 | 0 | 816 | 146.88 | 2023-09-20 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -32216 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.106 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-09-20 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -24832 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.108 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-09-20 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102011 | 2023-09-21 | 33032 | 2023-11-01 14:48 | -26032 | SHREE RAM INTERIOR & DECORATORS
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47436 | YUGESH KUMAR
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.505 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-12-30 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 104261 | 2024-01-01 | 10120 | 2024-01-16 14:57 | -1920 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.607 Dhar Core Work-(L) (2BHK) | 1 | 4000 | 0 | 4000 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -44518.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47436 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47068.8 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23682.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.507 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -40340.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.706 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -39860.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.203 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.503 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-06-16 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -21744 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.105 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42624.9 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.205 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-202-2BHK(Near Refuse Area) Putty Work (L) | 342.6 | 1 | 0 | 342.6 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42397.7 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.208 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23061.6 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.103 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.702 Dhar Core work-(L) (2BHK) Near Refuge | 0.6 | 4000 | 0 | 2400 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -40340.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.704 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -40340.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.106 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42586.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.707 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -40340.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42624.9 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-06-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23836 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41657.9 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.108 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 346.2 | 1 | 0 | 346.2 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42394.1 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-104-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42624.9 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42377.9 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42469.7 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -22694.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.708 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -40340.3 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-202-2BHK(Near Refuse Area) Putty Work (L) | 1168 | 1 | 0 | 1168 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41572.3 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42624.9 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-06-16 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23528 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.204 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.701 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -39860.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.705 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -39860.3 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.107 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41940.3 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42377.9 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42469.7 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41657.9 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.206 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-01-10 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -41780.3 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42377.9 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 0 | 2023-01-10 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97726 | 2023-01-10 | 42740.3 | 2023-01-23 18:37 | -42469.7 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-06-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 95122 | 2022-06-17 | 24144 | 2022-06-27 18:28 | -23913.2 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27430.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28264 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.105 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.203 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28264 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.406 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-12-12 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -26000 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.505 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-12-12 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -26000 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27430.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.006 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.302 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.106 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.007 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.208 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.005 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-907-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-908-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1104-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-808-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-906-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-906-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54032.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-706-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1107-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-15 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-03-15 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54225.6 | TEJASHREE ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.706 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-12-09 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103802 | 2023-12-11 | 31240 | 2023-12-25 15:41 | -23040 | A K INTERIOR CONTRACTOR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-202-2BHK(Near Refuse Area) Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-09 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -20046.5 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 269 | 0.5 | 0 | 134.5 | 24.22 | 2024-05-09 | Labour Charges for- Wall touch up work. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21724 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21088.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21743.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 362 | 1 | 0 | 362 | 65.16 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21496.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-902-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21088.5 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1102 Dhar Core Work-(L) (3BHK) | 1 | 4800 | 0 | 4800 | 864 | 2023-12-08 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103804 | 2023-12-11 | 21600 | 1900-01-01 | -16800 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.407 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 288 | 2023-12-08 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 103804 | 2023-12-11 | 21600 | 1900-01-01 | -20000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.407 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-12-08 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 103804 | 2023-12-11 | 21600 | 1900-01-01 | -14600 | SHREE RAM INTERIOR & DECORATORS
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1004-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18499.8 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1102-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18040.8 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19737.4 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19082.8 | RUSHIYOGI ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 172.8 | 2023-10-02 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -29260 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-10-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -22020 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.104 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -23220 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.104 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 144 | 2023-10-02 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -29420 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1308 Dhar Core Work-(L) (2BHK) | 0.78 | 7000 | 0 | 5460 | 982.8 | 2023-10-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -24760 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.207 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-02 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -23220 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.207 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 144 | 2023-10-02 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102190 | 2023-10-03 | 30220 | 2023-11-07 13:59 | -29420 | SHREE RAM INTERIOR & DECORATORS
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.206 Dhar Core Work-(L) (3BHK) | 0.2 | 4800 | 0 | 960 | 0 | 2023-10-14 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 102652 | 2023-10-16 | 16960 | 2023-11-03 15:40 | -16000 | MOHD SHAFIQUE ABDUL RAUF MALIK
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.206 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 0 | 2023-10-14 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 102652 | 2023-10-16 | 16960 | 2023-11-03 15:40 | -8760 | MOHD SHAFIQUE ABDUL RAUF MALIK
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.204 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 0 | 2023-10-14 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102652 | 2023-10-16 | 16960 | 2023-11-03 15:40 | -9960 | MOHD SHAFIQUE ABDUL RAUF MALIK
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1107-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1206-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-203-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1102-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1103-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1102-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-207-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-203-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1505-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12140 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1505-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -11098 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1505-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -11098 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1505-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12140 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1002-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-703-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1004-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-704-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-906-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18894.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58921.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1807-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -8297 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1807-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-14 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -9073 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1807-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108382 | 2024-06-17 | 9650 | 1900-01-01 | -9073 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-10-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29323.1 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-10-31 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -27873.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-10-31 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -28915.5 | RUSHIYOGI ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.305 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-10-31 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -21485.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-808-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-902-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-03-16 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -54032.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-701-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-905-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-03-15 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -52990.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1104-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1107-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-03-16 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106961 | 2024-04-19 | 54802.6 | 2024-04-25 11:28 | -53449.6 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12874.2 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12990.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12782.4 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -11791.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12874.2 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-708-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -13029.4 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1507-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-21 | Labour Charges for- Ceiling Touch up work | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20641.5 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1503-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-21 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19577 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1506-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-21 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19118 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1503-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-21 | Labour Charges for- Wall touch up work. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20253.5 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1507-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-21 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20353 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1507-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-21 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19577 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1503-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-21 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20353 | SHUBHAM SURENDRA BAHADUR SINGH
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1504-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-21 | Labour Charges for- Ceiling Touch up work | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20641.5 | SHUBHAM SURENDRA BAHADUR SINGH
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1506-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-21 | Labour Charges for- Ceiling Touch up work | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20545 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1504-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-21 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19577 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1506-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-21 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20160 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1507-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-21 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19577 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1504-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-21 | Labour Charges for- Wall touch up work. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20253.5 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1503-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-21 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19577 | SHUBHAM SURENDRA BAHADUR SINGH
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.505 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-12-30 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 104261 | 2024-01-01 | 10120 | 2024-01-16 14:57 | -8200 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.503 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 288 | 2023-10-31 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -28085.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-10-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29414.9 | RUSHIYOGI ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.503 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-31 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -22685.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-10-31 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29570.1 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-10-31 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29414.9 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-10-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -29414.9 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-10-31 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103118 | 2023-10-31 | 29685.5 | 2023-11-08 16:34 | -28915.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 270.6 | 0.5 | 0 | 135.3 | 0 | 2023-09-18 | Labour Charges for- Wall touch up work. | 100 |  | 101946 | 2023-09-20 | 644.2 | 1900-01-01 | -508.9 | PATHAN HABIB MEHATAB
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 115.4 | 0.5 | 0 | 57.7 | 0 | 2023-09-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 101946 | 2023-09-20 | 644.2 | 1900-01-01 | -586.5 | PATHAN HABIB MEHATAB
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 270.6 | 0.5 | 0 | 135.3 | 0 | 2023-09-18 | Labour Charges for- Wall touch up work. | 100 |  | 101946 | 2023-09-20 | 644.2 | 1900-01-01 | -508.9 | PATHAN HABIB MEHATAB
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.001 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28418.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27797.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27430.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28418.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -27797.6 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.301 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76320 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28264 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.207 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-03-04 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 93717 | 2022-03-04 | 79200 | 2022-03-07 15:12 | -76800 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-12-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -28264 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.508 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-12-12 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -26480 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.501 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2022-12-12 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 97359 | 2022-12-13 | 28880 | 2022-12-28 12:18 | -26000 | YUGESH KUMAR
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.303 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-18 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -35920 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.301 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-10-18 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -41000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.208 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-18 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -35920 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.304 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 288 | 2023-10-18 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -41320 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.208 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 144 | 2023-10-18 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -42120 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.304 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-18 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -35920 | SHREE RAM INTERIOR & DECORATORS
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18894.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18894.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-905-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-707-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-906-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-907-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58400.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1804-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2003-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.407 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -46118.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47902.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -48056.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -48056.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47436 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.608 Dhar Core Work-(L) (2BHK) | 0.6 | 4000 | 0 | 2400 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -46118.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.602 Dhar Core Work-(L) (3BHK) | 1 | 4800 | 0 | 4800 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -43718.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47902.4 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1008-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -19171 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1006-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-02-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105554 | 2024-02-26 | 19748 | 2024-03-01 12:15 | -17936 | BHARAT KASHINATH KARCHE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1402-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30860 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1001-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-01-25 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -16989 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18031 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-01-25 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104859 | 2024-01-29 | 18801 | 2024-02-19 15:19 | -18031 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1304-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42813.5 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1601-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-04-18 | Labour Charges for- Wall touch up work. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42584 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1407-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1602-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-04-18 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42720 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1601-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42720 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1607-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1608-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1304-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-04-18 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42913 | SHAHI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-04-18 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106991 | 2024-04-22 | 43490 | 1900-01-01 | -42137 | SHAHI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1403-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30568.5 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1403-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30956.5 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1406-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30860 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1404-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30956.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1408-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1406-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30475 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1408-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.507 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-12-30 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 107241 | 2024-04-30 | 8600 | 2024-05-03 13:17 | -1600 | AAKRUTI ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.507 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 288 | 2023-12-30 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 107241 | 2024-04-30 | 8600 | 2024-05-03 13:17 | -7000 | AAKRUTI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1105-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-20 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27655 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1101-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -26613 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1103-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-20 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27848 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1003-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-20 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27848 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1207-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1107-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1101-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1103-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1104-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1201-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1203-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2107-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1405-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46007.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1405-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1703-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1708-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 83.08 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45931.2 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1501-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -11098 | SHUBHAM SURENDRA BAHADUR SINGH
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1707-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1401-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1501-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-06-07 | Labour Charges for- Ceiling Touch up work | 100 |  | 108633 | 2024-06-28 | 12910 | 2024-06-28 20:04 | -12525 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1205-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1902-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66883.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-203-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2022-05-31 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -65977.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1108-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13676.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1106-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2023-05-18 | Labour Charges for- Wall touch up work. | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13493.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1206-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1208-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13987.2 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-203-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67426.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1106-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67248 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-102-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67404.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1101-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2023-05-18 | Labour Charges for- Ceiling Touch up work | 100 |  | 99711 | 2023-05-19 | 14218 | 2023-06-10 10:32 | -13910 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1005-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-808-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-905-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1002-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28348.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 947.1 | 1 | 0 | 947.1 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18563.5 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 947.1 | 1 | 0 | 947.1 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18563.5 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-806-3BHK Putty Work (L) | 1268.4 | 1 | 0 | 1268.4 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -18242.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-903-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-804-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28425.6 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.806 Dhar Core Work-(L) (3BHK) | 0.6 | 4800 | 0 | 2880 | 0 | 2023-02-17 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -16630.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2023-02-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 98246 | 2023-02-18 | 19510.6 | 2023-02-24 11:36 | -19049 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-904-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28115.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1001-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-11-09 | Labour Charges for- Wall touch up work. | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -27931.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-702-2BHK(Near Refuse Area) Flat Putty Work (L) | 456.8 | 0.5 | 0 | 228.4 | 0 | 2022-11-09 | Labour Charges for- Ceiling Touch up work | 100 |  | 97001 | 2022-11-10 | 28656.4 | 2022-11-17 12:58 | -28428 | YUGESH KUMAR
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12374.8 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -13029.4 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 115.4 | 1 | 0 | 115.4 | 20.78 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -13029.4 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12567.8 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -11791.8 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-408-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -11791.8 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-502-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-203-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-205-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.606 Dhar Core Work-(L) (3BHK) | 1 | 4800 | 0 | 4800 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -43718.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66339.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-207-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-103-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67327.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-105-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67173.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-107-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67558.4 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-201-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-05-31 | Labour Charges for- Ceiling Touch up work | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67481.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-106-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-05-31 | Labour Charges for- Wall touch up work. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -67064.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-108-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-05-31 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 94933 | 2022-05-31 | 67789.2 | 2022-06-18 16:02 | -66706.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-12-30 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -12782.4 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -11332.8 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104259 | 2024-01-01 | 13144.8 | 2024-03-20 15:28 | -11332.8 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 1 | 4000 | 0 | 4000 | 720 | 2023-12-09 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 103802 | 2023-12-11 | 31240 | 2023-12-25 15:41 | -27240 | A K INTERIOR CONTRACTOR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-207-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-504-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-101-3BHK Putty Work (L) | 44 | 0.5 | 0 | 22 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7650 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-207-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-206-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-204-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 270 | 0.5 | 0 | 135 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7537 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-503-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24544.8 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.603 Dhar Core Work-(L) (2BHK) | 1 | 4000 | 0 | 4000 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -44518.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.604 Dhar Core Work-(L) (2BHK) | 1 | 4000 | 0 | 4000 | 0 | 2022-09-13 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -44518.4 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47902.4 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47068.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 461.6 | 1 | 0 | 461.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -48056.8 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 0 | 2022-09-13 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 96248 | 2022-09-14 | 48518.4 | 2022-10-03 11:03 | -47068.8 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-507-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-406-3BHK Putty Work (L) | 362 | 0.5 | 0 | 181 | 0 | 2024-05-16 18:34 | Labour Charges for- Wall touch up work. | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7491 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24281.6 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-407-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 0 | 2022-08-17 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -23924 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:32 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-208-2BHK Putty Work (L) | 110 | 0.5 | 0 | 55 | 0 | 2024-05-16 18:17 | Labour Charges for- Ceiling Touch up work | 100 |  | 107653 | 2024-05-20 | 7672 | 2024-07-26 12:29 | -7617 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-508-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24775.6 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 1082.4 | 0.5 | 0 | 541.2 | 0 | 2022-08-17 | Labour Charges for- Wall touch up work. | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24465.2 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 616 | 0.5 | 0 | 308 | 0 | 2022-08-17 | Labour Charges for- Ceiling Touch up work | 100 |  | 95898 | 2022-08-17 | 25006.4 | 2022-08-27 12:54 | -24698.4 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.706 Dhar Core Work-(L) (3BHK) | 0.4 | 4800 | 0 | 1920 | 345.6 | 2023-12-09 | Gypsum Dhar Core work for all 3 BHK Flats | 100 |  | 103802 | 2023-12-11 | 31240 | 2023-12-25 15:41 | -29320 | A K INTERIOR CONTRACTOR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-401-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-07-22 | Labour Charges for- Wall touch up work. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24276 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 0 | 2022-07-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24384.8 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-07-22 | Labour Charges for- Wall touch up work. | 100 |  | 95621 | 2022-07-23 | 25000.8 | 2022-08-10 11:44 | -24276 | YUGESH KUMAR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.303 Dhar Core Work-(L) (2BHK) | 0.4 | 4000 | 0 | 1600 | 288 | 2023-10-18 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -41320 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.103 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2023-10-18 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -35920 | SHREE RAM INTERIOR & DECORATORS
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.301 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2023-10-18 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 3 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -34720 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.103 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 144 | 2023-10-18 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102792 | 2023-10-19 | 42920 | 2023-11-07 13:58 | -42120 | SHREE RAM INTERIOR & DECORATORS
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1206-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1203-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -59018 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58400.5 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58630 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1902-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1904-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 0 | 2024-04-12 | Labour Charges for- Ceiling Touch up work | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43748.5 | BHARAT KASHINATH KARCHE
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1401-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2024-04-12 | Labour Charges for- Wall touch up work. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43131 | BHARAT KASHINATH KARCHE
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1902-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 0 | 2024-04-12 | Labour Charges for- Wall touch up work. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43131 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-302-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18040.8 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2023-12-30 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19698.8 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-403-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-30 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -19275.8 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1904-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42684 | BHARAT KASHINATH KARCHE
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1201-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-04-12 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -42225 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-404-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18499.8 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-405-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-30 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 104262 | 2024-01-01 | 19852.8 | 2024-01-16 14:59 | -18040.8 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1902-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-04-12 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 106777 | 2024-04-15 | 44037 | 2024-04-30 15:25 | -43267 | BHARAT KASHINATH KARCHE
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57494.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58729.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14113 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14696 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14696 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14113 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14113 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -13654 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14889 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-601-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -13654 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-603-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14889 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-604-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14113 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-608-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14889 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-605-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14696 | BHARAT KASHINATH KARCHE
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-607-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -14889 | BHARAT KASHINATH KARCHE
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-602-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-03-17 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107230 | 2024-04-30 | 15466 | 2024-05-06 12:39 | -13654 | BHARAT KASHINATH KARCHE
Dhar Core (L) (Rate Diff.) | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1508 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 0 | 2023-12-30 | Labour charges for (Rate Diff.) of Gypsum Dhar core work for 2 BHK Flats. | 100 |  | 104263 | 2024-01-01 | 11000 | 1900-01-01 | -4000 | SANTOSHI POP CONTRACTOR
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.1508 Dhar Core Work-(L) (2BHK) | 1 | 4000 | 0 | 4000 | 0 | 2023-12-30 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 104263 | 2024-01-01 | 11000 | 1900-01-01 | -7000 | SANTOSHI POP CONTRACTOR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1803-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -59018 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2303-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -59018 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2103-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2302-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58921.5 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2301-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-07-29 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58536.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2207-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2208-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-07-29 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -57953.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2104-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -59018 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2304-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -59018 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 230.8 | 1 | 0 | 230.8 | 41.54 | 2023-12-08 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16633.8 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2023-12-08 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -15052.6 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-08 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16287.6 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-08 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -15511.6 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 362.4 | 1 | 0 | 362.4 | 65.24 | 2023-12-08 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16502.2 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-305-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2023-12-08 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16710.6 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 724.8 | 1 | 0 | 724.8 | 130.46 | 2023-12-08 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16139.8 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 230.8 | 1 | 0 | 230.8 | 41.54 | 2023-12-08 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16633.8 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2023-12-08 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16094.6 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 541.2 | 1 | 0 | 541.2 | 97.42 | 2023-12-08 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16323.4 | RUSHIYOGI ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-304-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2023-12-08 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -15511.6 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-308-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2023-12-08 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16287.6 | RUSHIYOGI ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 308 | 1 | 0 | 308 | 55.44 | 2023-12-08 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16556.6 | RUSHIYOGI ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-303-2BHK Putty Work (L) | 270.6 | 1 | 0 | 270.6 | 48.7 | 2023-12-08 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 103803 | 2023-12-11 | 16864.6 | 2023-12-22 11:35 | -16594 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-901-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-906-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-506-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-606-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-501-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-908-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-901-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-904-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45703 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-02-23 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -45510 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-505-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-02-23 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 105553 | 2024-02-26 | 46280 | 2024-03-18 12:13 | -44468 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1704-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45716.3 | TEJASHREE ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1908-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-22 | Labour Charges for- Ceiling Touch up work | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -46104.3 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1701-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1705-3BHK Putty Work (L) | 616 | 1 | 0 | 616 | 110.88 | 2024-06-22 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45776.8 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1405-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-22 | Labour Charges for- Wall touch up work. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45486.8 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1901-3BHK Putty Work (L) | 1449.6 | 1 | 0 | 1449.6 | 260.92 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -44943.2 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1907-2BHK Putty Work (L) | 1082.4 | 1 | 0 | 1082.4 | 194.84 | 2024-06-22 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108510 | 2024-06-24 | 46392.8 | 2024-08-05 13:55 | -45310.4 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1707-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1707-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1403-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1404-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1408-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30568.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1404-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1406-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29433 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1707-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1402-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29433 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1404-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30568.5 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1403-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1406-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29433 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1406-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30475 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1707-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1406-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30339 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1402-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-07 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29433 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1402-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30339 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1403-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -30668 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1404-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1408-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-07 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 108198 | 2024-06-10 | 31245 | 1900-01-01 | -29892 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-802-3BHK Putty Work (L) | 543 | 1 | 0 | 543 | 97.74 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21315.5 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-803-2BHK Putty Work (L) | 405 | 1 | 0 | 405 | 72.9 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21453.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-402-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21704.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-705-3BHK Putty Work (L) | 154 | 1 | 0 | 154 | 27.72 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21704.5 | TEJASHREE ENTERPRISES
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1508-2BHK Putty Work (L) | 115 | 1 | 0 | 115 | 20.7 | 2024-05-09 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21743.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1107-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1204-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-05-09 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21281.5 | TEJASHREE ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1804-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-05-09 | Labour Charges for- Wall touch up work. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21182 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-805-3BHK Putty Work (L) | 543 | 1 | 0 | 543 | 97.74 | 2024-05-09 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107493 | 2024-05-13 | 21858.5 | 2024-06-03 12:36 | -21315.5 | TEJASHREE ENTERPRISES
Dhar Core | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-Flat.No.204 Dhar Core Work-(L) (2BHK) | 0.2 | 4000 | 0 | 800 | 0 | 2023-10-14 | Gypsum Dhar Core work for all 2 BHK Flats. | 100 |  | 102652 | 2023-10-16 | 16960 | 2023-11-03 15:40 | -16160 | MOHD SHAFIQUE ABDUL RAUF MALIK
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1306-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1307-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-07 | Labour Charges for- Wall touch up work. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -46073.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1306-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-07 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108228 | 2024-06-10 | 46750 | 2024-06-15 11:50 | -45980 | RUSHIYOGI ENTERPRISES
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 1449.6 | 0.5 | 0 | 724.8 | 0 | 2022-07-14 | Labour Charges for- Wall touch up work. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13099.2 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-306-3BHK Putty Work (L) | 462 | 1 | 0 | 462 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13362 | YUGESH KUMAR
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 1087.2 | 1 | 0 | 1087.2 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -12736.8 | YUGESH KUMAR
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-301-3BHK Putty Work (L) | 462 | 1 | 0 | 462 | 0 | 2022-07-14 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13362 | YUGESH KUMAR
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-307-2BHK Putty Work (L) | 461.6 | 0.5 | 0 | 230.8 | 0 | 2022-07-14 | Labour Charges for- Ceiling Touch up work | 100 |  | 95507 | 2022-07-14 | 13824 | 2022-07-23 16:23 | -13593.2 | YUGESH KUMAR
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1506-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-06-21 | Labour Charges for- Wall touch up work. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20024 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1507-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-21 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20353 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1504-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-21 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20353 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1504-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-06-21 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19577 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1506-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-06-21 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20160 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1506-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 326.16 | 2024-06-21 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -19118 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1503-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-21 | Labour Charges for- 1st Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20353 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1507-2BHK Putty Work (L) | 1353 | 0.5 | 0 | 676.5 | 121.78 | 2024-06-21 | Labour Charges for- Wall touch up work. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20253.5 | SHUBHAM SURENDRA BAHADUR SINGH
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1503-2BHK Putty Work (L) | 577 | 0.5 | 0 | 288.5 | 51.94 | 2024-06-21 | Labour Charges for- Ceiling Touch up work | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20641.5 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1504-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 103.86 | 2024-06-21 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 108514 | 2024-06-24 | 20930 | 2024-06-28 20:04 | -20353 | SHUBHAM SURENDRA BAHADUR SINGH
Wall Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2101-3BHK Putty Work (L) | 1812 | 0.5 | 0 | 906 | 163.08 | 2024-07-29 | Labour Charges for- Wall touch up work. | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58400.5 | RUSHIYOGI ENTERPRISES
Ceiling Touch up | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-2105-3BHK Putty Work (L) | 770 | 0.5 | 0 | 385 | 69.3 | 2024-07-29 | Labour Charges for- Ceiling Touch up work | 100 |  | 109523 | 2024-08-05 | 59306.5 | 1900-01-01 | -58921.5 | RUSHIYOGI ENTERPRISES
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1101-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 138.6 | 2024-05-20 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27655 | TEJASHREE ENTERPRISES
1st Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-1103-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 1st Coat Putty for Wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-703-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 243.54 | 2024-05-20 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 107718 | 2024-05-20 | 28425 | 2024-07-11 10:30 | -27072 | TEJASHREE ENTERPRISES
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 36.5 | 4 | 0 | 146 | 0 | 2023-02-08 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 98107 | 2023-02-09 | 640 | 1900-01-01 | -494 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 621 | 9.5 | 0 | 5899.5 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -48173.1 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 676.8 | 9.5 | 0 | 6429.6 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -47643 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 244 | 4 | 0 | 976 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53096.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 244 | 4 | 0 | 976 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53096.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 192 | 4 | 0 | 768 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53304.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 239 | 4 | 0 | 956 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53116.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 244 | 4 | 0 | 976 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53096.6 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 629 | 9.5 | 0 | 5975.5 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -48097.1 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 448 | 9.5 | 0 | 4256 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -49816.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 243 | 4 | 0 | 972 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53100.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 380 | 4 | 0 | 1520 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -52552.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 228 | 4 | 0 | 912 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53160.6 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 626 | 9.5 | 0 | 5947 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -48125.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 45.75 | 4 | 0 | 183 | 0 | 2023-02-08 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 98107 | 2023-02-09 | 640 | 1900-01-01 | -457 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 30.5 | 4 | 0 | 122 | 0 | 2023-02-08 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 98107 | 2023-02-09 | 640 | 1900-01-01 | -518 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 47.25 | 4 | 0 | 189 | 0 | 2023-02-08 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 98107 | 2023-02-09 | 640 | 1900-01-01 | -451 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 238 | 4 | 0 | 952 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53120.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 193 | 4 | 0 | 772 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53300.6 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 436 | 9.5 | 0 | 4142 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -49930.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 219 | 4 | 0 | 876 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53196.6 | SHAHID RAJA KHAN
Tikki Dhada (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 786 | 9.5 | 0 | 7467 | 0 | 2022-03-08 18:23 | Labour Charges for-Gypsum on Wall (Tikki Dhada) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -46605.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 174 | 4 | 0 | 696 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53376.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 252 | 4 | 0 | 1008 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -53064.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 399 | 4 | 0 | 1596 | 0 | 2022-03-08 18:23 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 93760 | 2022-03-08 | 54072.6 | 2022-03-11 12:46 | -52476.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 41.1 | 4 | 0 | 164.4 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2693.2 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 57.2 | 4 | 0 | 228.8 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2628.8 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 12.75 | 4 | 0 | 51 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2806.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 59.8 | 4 | 0 | 239.2 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2618.4 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 36.15 | 4 | 0 | 144.6 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2713 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 30.5 | 4 | 0 | 122 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2735.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 24.4 | 4 | 0 | 97.6 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2760 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 61 | 4 | 0 | 244 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2613.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 11 | 4 | 0 | 44 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2813.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 13.75 | 4 | 0 | 55 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2802.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 36.3 | 4 | 0 | 145.2 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2712.4 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 32.7 | 4 | 0 | 130.8 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2726.8 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 15.75 | 4 | 0 | 63 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2794.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 15.2 | 4 | 0 | 60.8 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2796.8 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 95.2 | 4 | 0 | 380.8 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2476.8 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 100 | 4 | 0 | 400 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2457.6 | SHAHID RAJA KHAN
Gypsum on Wall (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 12 | 4 | 0 | 48 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Wall (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2809.6 | SHAHID RAJA KHAN
Gypsum on Ceiling (L) | N/C | N/C | SHAHID RAJA KHAN | 388 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 59.6 | 4 | 0 | 238.4 | 0 | 2022-10-01 | Labour Charges for- Gypsum on Ceiling (Patra Finish) | 100 |  | 96478 | 2022-10-03 | 2857.6 | 2022-10-17 11:09 | -2619.2 | SHAHID RAJA KHAN
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 305 | 4 | 0 | 1220 | 219.6 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64779.5 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 846 | 9.5 | 0 | 8037 | 1446.66 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -57962.5 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 375.5 | 4 | 0 | 1502 | 270.36 | 2022-03-15 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 |  | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64497.5 | NKV HOME DEPOT
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 299 | 4 | 0 | 1196 | 215.28 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64803.5 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 242 | 4 | 0 | 968 | 174.24 | 2022-03-15 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -65031.5 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 286 | 4 | 0 | 1144 | 205.92 | 2022-03-17 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no MUM2706, Date 14/10/21 | 93930 | 2022-03-17 | 1144 | 2022-03-31 18:05 | 0 | NKV HOME DEPOT
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 304 | 4 | 0 | 1216 | 218.88 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64783.5 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 783 | 9.5 | 0 | 7438.5 | 1338.94 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 |  | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -58561 | NKV HOME DEPOT
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 315 | 4 | 0 | 1260 | 226.8 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64739.5 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 123 | 4 | 0 | 492 | 88.56 | 2022-03-17 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no -202122PUN7441 | 93936 | 2022-03-18 | 492 | 2022-03-30 13:55 | 0 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 787 | 9.5 | 0 | 7476.5 | 1345.78 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 |  | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -58523 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-26 | 218 | 4 | 0 | 872 | 156.96 | 2022-03-15 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -65127.5 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 274 | 4 | 0 | 1096 | 197.28 | 2022-03-15 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64903.5 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-29 | 561 | 9.5 | 0 | 5329.5 | 959.32 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 |  | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -60670 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 476 | 4 | 0 | 1904 | 342.72 | 2022-03-15 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64095.5 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-25 | 983 | 9.5 | 0 | 9338.5 | 1680.94 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 |  | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -56661 | NKV HOME DEPOT
Gypsum on Wall (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 241 | 4 | 0 | 964 | 173.52 | 2022-03-15 | Material Supply for- Gypsum on Wall (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -65035.5 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 544 | 9.5 | 0 | 5168 | 930.24 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -60831.5 | NKV HOME DEPOT
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-27 | 305 | 4 | 0 | 1220 | 219.6 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64779.5 | NKV HOME DEPOT
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-23 | 298 | 4 | 0 | 1192 | 214.56 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no - MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64807.5 | NKV HOME DEPOT
Tikki Dhada (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-24 | 777 | 9.5 | 0 | 7381.5 | 1328.68 | 2022-03-15 | Material Supply for- Gypsum on Wall (Tikki Dhada) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -58618 | NKV HOME DEPOT
Gypsum on Ceiling (M) | N/C | N/C | SHAHID RAJA KHAN | 389 | 2022-02-23 | F-Bldg Gypsum Work Shop No-28 | 305 | 4 | 0 | 1220 | 219.6 | 2022-03-15 | Material Supply for- Gypsum on Ceiling (Patra Finish) | 100 | Invoice no -MUM/2714 | 93886 | 2022-03-16 | 65999.5 | 2022-03-30 13:52 | -64779.5 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.303 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.307 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1804 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2003 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1007 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.108 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1102 Dhar Core Work-(L) (3BHK) | 1.5382 | 273.7 | -0.01 | 421.0053 | 75.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17236.9947 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.001 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.005 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.102 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.105 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.106 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1002 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1003 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1107 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1305 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1307 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1108 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1202 Dhar Core work-(L) (2BHK) Near Refuge | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1204 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1304 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1505 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.401 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.801 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.806 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1302 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1501 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1503 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1602 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1302 Dhar Core Work-(L) (3BHK) | 8.71 | 285 | 0 | 2482.35 | 124.12 | 2024-03-08 14:10 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -134662.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1205 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1306 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1405 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1106 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.006 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2005 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.202 Dhar Core work-(L) (2BHK) Near Refuge | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.207 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.304 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.404 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.501 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1601 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1306 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1501 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1505 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1103 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.207 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.704 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.708 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1107 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.804 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1203 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2301 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2305 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1302 Dhar Core Work-(L) (3BHK) | 0.79 | 285 | 0 | 225.15 | 11.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319768.4 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.807 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2006 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.506 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1005 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1006 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1301 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1601 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1604 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.405 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.606 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.003 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.004 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1008 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1001 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1006 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1005 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.006 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.008 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.104 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.103 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.002 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.403 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1903 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1201 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1608 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1201 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1205 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1206 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1402 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1207 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1401 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1403 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1502 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1101 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1105 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.402 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.802 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.406 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.905 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.805 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1301 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.505 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1001 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.501 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.906 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.502 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.706 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.901 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1102 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2101 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.503 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.402 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.504 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.301 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.403 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.405 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.407 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.204 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.306 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.408 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.203 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.205 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1303 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1504 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1603 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.601 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.701 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2308 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2208 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2307 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2304 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2404 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 14:06 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2207 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2303 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -24866.25 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2403 Dhar Core Work-(L) (2BHK) | 9.25 | 285 | 0 | 2636.25 | 131.82 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/213/2024-25 DT 05/06/2024 | 108444 | 2024-06-18 | 28571.25 | 2024-06-26 17:22 | -25935 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.205 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.106 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.305 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.002 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1506 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.602 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1406 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1507 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1605 Dhar Core Work-(L) (3BHK) | 1.3884 | 273.7 | -0.01 | 380.0051 | 19 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28191.0949 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1203 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1404 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1206 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1208 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1508 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1103 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:40 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No - LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1106 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1105 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -27750 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1408 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.705 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1104 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF /1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1308 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1407 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-02-05 15:16 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No- LSF/1165/2023-24 | 105083 | 2024-02-05 | 28571.1 | 2024-02-28 11:09 | -28023.7 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2008 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2203 Dhar Core Work-(L) (2BHK) | 8.538 | 285 | 0 | 2433.33 | 121.66 | 2024-05-25 15:04 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -26137.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2202 Dhar Core work-(L) (2BHK) Near Refuge | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.605 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1002 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2204 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2101 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1807 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2306 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.004 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2304 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2305 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2302 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2004 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2207 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1705 Dhar Core Work-(L) (3BHK) | 0.06 | 285 | 0 | 17.1 | 0.86 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319976.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1104 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1507 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.202 Dhar Core work-(L) (2BHK) Near Refuge | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1806 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1808 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2104 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1603 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1803 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2003 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.108 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1902 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1407 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1908 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2002 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2203 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.003 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1003 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1207 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1408 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1907 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2205 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2102 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2005 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2107 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2208 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2401 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2405 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.104 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2201 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.306 Dhar Core Work-(L) (3BHK) | 0.09 | 285 | 0 | 25.65 | 1.28 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319967.9 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.808 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1806 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2001 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2001 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2206 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2105 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1804 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1903 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2006 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2205 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1901 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2007 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2008 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2105 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2303 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1805 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1905 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2108 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2202 Dhar Core work-(L) (2BHK) Near Refuge | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2301 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2402 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.008 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.103 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.803 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1008 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1202 Dhar Core work-(L) (2BHK) Near Refuge | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1403 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1805 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2106 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.107 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1007 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1404 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1802 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2204 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 0 | 2024-06-16 13:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108393 | 2024-06-17 | 3705 | 1900-01-01 | 0 | YUGESH KUMAR
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.408 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.702 Dhar Core work-(L) (2BHK) Near Refuge | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1707 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.504 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1708 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1702 Dhar Core work-(L) (2BHK) Near Refuge | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1701 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133291.65 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.508 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.507 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2004 Dhar Core Work-(L) (2BHK) | 12.69 | 285 | 0 | 3616.65 | 180.84 | 2024-05-25 13:48 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/580/2023-24 | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133522.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2203 Dhar Core Work-(L) (2BHK) | 0.711 | 285 | 0 | 202.635 | 10.14 | 2024-05-25 14:52 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -28368.335 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2103 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2104 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2108 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.201 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.306 Dhar Core Work-(L) (3BHK) | 11.51 | 285 | 0 | 3280.35 | 164.02 | 2024-03-08 09:39 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53865 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.005 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1605 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1602 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1606 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1907 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1604 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2107 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2007 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 14:39 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF-140 | 107763 | 2024-05-25 | 28570.97 | 2024-06-26 17:22 | -24865.97 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2103 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1502 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1405 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.007 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.107 Dhar Core Work-(L) (2BHK) | 1.9985 | 273.7 | 0.01 | 546.9895 | 98.46 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -17111.0105 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1101 Dhar Core Work-(L) (3BHK) | 2.9996 | 273.7 | 0.01 | 820.9905 | 147.78 | 2022-03-29 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 94060 | 2022-03-29 | 17658 | 2022-03-30 13:53 | -16837.0095 | NKV HOME DEPOT
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1208 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.007 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1906 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2201 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2302 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319172.45 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2102 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.505 Dhar Core Work-(L) (3BHK) | 1.8743 | 273.7 | 0 | 512.9959 | 25.66 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21074.9041 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.401 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.305 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.308 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.307 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.406 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.206 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.208 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.303 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -21040.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.302 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.502 Dhar Core Work-(L) (3BHK) | 3 | 273.7 | 0 | 821.1 | 41.06 | 2023-10-17 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 | Invoice No-LSF/826/2023-24 | 102742 | 2023-10-18 | 21587.9 | 2024-01-31 17:43 | -20766.8 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.102 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.105 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.001 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.301 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.302 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.206 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 09:13 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-LSF/1293/2023-24 | 105831 | 2024-03-08 | 57145.35 | 2024-03-26 17:00 | -53297.85 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.908 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1303 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1308 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1906 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.707 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1503 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1504 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1706 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.203 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1108 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1508 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.204 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1904 Dhar Core Work-(L) (2BHK) | 2 | 273.7 | 0 | 547.4 | 27.38 | 2024-05-14 09:39 | Material Supply for- Dhar Core Gypsum Work for internal flat (2 Bgas for 2 BHK & 3 Bags for 3 BHK flat) | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -319446.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2206 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.907 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1901 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1406 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1705 Dhar Core Work-(L) (3BHK) | 12.84 | 285 | 0 | 3659.4 | 182.98 | 2024-03-08 17:35 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53865 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1305 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1506 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1402 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 15:48 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1808 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.304 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.703 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1908 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.308 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.604 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1807 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.607 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1904 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.407 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.603 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1304 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1307 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1902 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.208 Dhar Core Work-(L) (2BHK) | 12.73 | 285 | 0 | 3628.05 | 181.4 | 2024-05-20 12:34 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316365.5 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1204 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1801 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2002 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2106 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.2406 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-14 10:40 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.903 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.904 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-18 18:46 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316288.55 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1905 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-05-20 12:12 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107714 | 2024-05-20 | 319993.55 | 2024-07-06 11:10 | -316146.05 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.902 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-08 12:54 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/1167/2023-24 | 105838 | 2024-03-08 | 137144.85 | 2024-03-26 17:00 | -133297.35 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1704 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.404 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1703 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.608 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1607 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1803 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.503 Dhar Core Work-(L) (2BHK) | 13 | 285 | 0 | 3705 | 185.26 | 2024-05-25 12:54 | Material supply charges of Gypsum for Internal Flat 2BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 107764 | 2024-05-25 | 137139.15 | 2024-07-06 11:10 | -133434.15 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 397 | 2022-03-26 | D-Flat.No.1401 Dhar Core Work-(L) (3BHK) | 13.5 | 285 | 0 | 3847.5 | 192.38 | 2024-03-11 11:41 | Material supply charges of Gypsum for Internal Flat 3BHK Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | Invoice No-1552 | 106024 | 2024-03-12 | 57524.4 | 2024-03-30 18:36 | -53676.9 | SHRIRAM TRADERS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 398 | 2022-03-29 | F-Bldg Electrical Work (L) Shop No-25 | 0.8 | 3784 | 0 | 3027.2 | 544.9 | 2022-06-17 | Charges for Electrical work for shops (Ceiling light point (full)-4 nos, Ceiling light point(Half)- 4 nos,AC- 1no, 5 Amp (Half)-3nos,Fan point- 3 nos,SD-2 nos, Wall light-1 no,For toilet Wall light-1 no. & Exhuast fan-1 no.) | 100 |  | 95142 | 2022-06-18 | 78883.4 | 2022-06-27 19:34 | -75856.2 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 398 | 2022-03-29 | F-Bldg Electrical Work (L) Shop No-27 | 0.8 | 3784 | 0 | 3027.2 | 544.9 | 2022-06-17 | Charges for Electrical work for shops (Ceiling light point (full)-4 nos, Ceiling light point(Half)- 4 nos,AC- 1no, 5 Amp (Half)-3nos,Fan point- 3 nos,SD-2 nos, Wall light-1 no,For toilet Wall light-1 no. & Exhuast fan-1 no.) | 100 |  | 95142 | 2022-06-18 | 78883.4 | 2022-06-27 19:34 | -75856.2 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 398 | 2022-03-29 | F-Bldg Electrical Work (L) Shop No-24 | 0.8 | 3784 | 0 | 3027.2 | 544.9 | 2022-06-17 | Charges for Electrical work for shops (Ceiling light point (full)-4 nos, Ceiling light point(Half)- 4 nos,AC- 1no, 5 Amp (Half)-3nos,Fan point- 3 nos,SD-2 nos, Wall light-1 no,For toilet Wall light-1 no. & Exhuast fan-1 no.) | 100 |  | 95142 | 2022-06-18 | 78883.4 | 2022-06-27 19:34 | -75856.2 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 398 | 2022-03-29 | F-Bldg Electrical Work (L) Shop No-29 | 0.8 | 3784 | 0 | 3027.2 | 544.9 | 2022-06-17 | Charges for Electrical work for shops (Ceiling light point (full)-4 nos, Ceiling light point(Half)- 4 nos,AC- 1no, 5 Amp (Half)-3nos,Fan point- 3 nos,SD-2 nos, Wall light-1 no,For toilet Wall light-1 no. & Exhuast fan-1 no.) | 100 |  | 95142 | 2022-06-18 | 78883.4 | 2022-06-27 19:34 | -75856.2 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 398 | 2022-03-29 | F-Bldg Electrical Work (L) Shop No-23 | 0.8 | 3784 | 0 | 3027.2 | 544.9 | 2022-06-17 | Charges for Electrical work for shops (Ceiling light point (full)-4 nos, Ceiling light point(Half)- 4 nos,AC- 1no, 5 Amp (Half)-3nos,Fan point- 3 nos,SD-2 nos, Wall light-1 no,For toilet Wall light-1 no. & Exhuast fan-1 no.) | 100 |  | 95142 | 2022-06-18 | 78883.4 | 2022-06-27 19:34 | -75856.2 | HARISH CHANDRA JADHAV ELECTRICALS
Electrical Work (Labour) | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 398 | 2022-03-29 | F-Bldg Electrical Work (L) Shop No-28 | 0.8 | 3784 | 0 | 3027.2 | 544.9 | 2022-06-17 | Charges for Electrical work for shops (Ceiling light point (full)-4 nos, Ceiling light point(Half)- 4 nos,AC- 1no, 5 Amp (Half)-3nos,Fan point- 3 nos,SD-2 nos, Wall light-1 no,For toilet Wall light-1 no. & Exhuast fan-1 no.) | 100 |  | 95142 | 2022-06-18 | 78883.4 | 2022-06-27 19:34 | -75856.2 | HARISH CHANDRA JADHAV ELECTRICALS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-908-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1001-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1205-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1108-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1101-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-207-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-307-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-508-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-502-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-503-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-207-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-003-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-807-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1104-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1303-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-704-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2206-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1904-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1904-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-908-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-707-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-804-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-807-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-904-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-806-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1003-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1308-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1302-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1306-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1402-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1306-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1507-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1403-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1506-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1404-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1405-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1504-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1505-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1405-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1103-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1104-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1207-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1204-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1101-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1208-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-003-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-101-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-108-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-406-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-507-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-608-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-405-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-607-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-404-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-503-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-708-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-802-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-102-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-201-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-204-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-304-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-306-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-504-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1004-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-203-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-107-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-903-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1806-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-107-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-104-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-105-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1606-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1706-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1605-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-106-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-008-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1503-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1508-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-003-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1708-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1701-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1704-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1304-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1301-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1505-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1506-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1307-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1304-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1305-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1301-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1408-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1401-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1308-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1508-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-408-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-205-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-305-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-308-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-405-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1703-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1802-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-006-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-004-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-101-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1801-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-007-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-005-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1405-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1003-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2108-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1901-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1902-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2107-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2208-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-102-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1607-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1608-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1704-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1805-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1806-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1608-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1705-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1601-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1601-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1602-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1701-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1703-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1603-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1607-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1706-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1708-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1805-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1605-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1606-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1707-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1807-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1803-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2007-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-803-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-902-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-903-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1008-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2101-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-003-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1302-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-007-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1903-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2102-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2104-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2204-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-704-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-808-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1206-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2005-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-606-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1905-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2003-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2208-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-008-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1201-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-905-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1307-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1208-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2008-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2106-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2206-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2207-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2006-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2103-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1905-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1908-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-908-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1201-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1308-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-805-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1008-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-706-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1205-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-103-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-505-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-105-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-402-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-601-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1408-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1501-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1302-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1502-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1503-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1303-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1305-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1404-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1504-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1407-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1403-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1406-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1407-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1502-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-108-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-002-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-103-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1602-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1707-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1604-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-302-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-305-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-208-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-208-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-508-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-302-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1102-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1206-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1108-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1105-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1203-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1201-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1107-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1106-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1205-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-03-16 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 98751 | 2023-03-16 | 24516 | 2023-03-30 12:50 | -22881.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-807-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-907-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-704-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-805-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-902-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1002-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-701-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-803-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-905-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1004-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-306-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-507-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-507-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-401-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-406-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-407-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-403-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-708-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1002-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-804-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-501-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-701-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1203-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-602-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-604-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-902-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-205-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-207-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-502-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-208-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-408-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-705-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-707-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-206-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-407-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1204-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1207-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-106-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-308-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-104-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-005-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-108-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-104-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-106-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-002-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-101-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-007-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-104-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-108-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-208-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-307-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-406-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-603-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-201-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-203-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-303-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-404-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-504-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-504-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-505-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-801-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-204-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-303-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-402-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-403-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-406-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-407-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-401-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-801-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-801-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1005-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1006-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-802-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-901-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-808-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-907-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-707-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-903-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1203-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-204-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-306-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-502-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-608-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-103-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-104-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-306-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-503-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-102-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-203-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-405-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-606-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-606-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-607-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-106-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-206-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-501-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-601-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-407-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-604-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-402-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-707-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-903-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1203-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1207-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-105-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-408-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1004-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1101-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-508-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-607-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2304-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-808-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1001-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1207-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-708-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-801-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1205-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-701-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-701-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-804-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-706-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1001-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1002-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-201-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-204-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-308-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-402-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-403-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-208-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-604-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-207-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-207-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-804-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1101-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-205-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-502-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-901-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-301-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-305-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-305-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-405-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1204-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-103-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-107-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-301-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-503-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-506-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-508-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-602-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-603-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-107-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1604-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1104-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-506-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-605-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1002-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-708-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-904-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1205-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-802-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-902-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1204-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-901-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-307-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-401-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-603-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-904-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1001-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-303-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-301-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-403-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-801-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-305-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-606-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1101-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-506-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-508-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-605-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1107-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2023-12-26 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 104216 | 2024-01-01 | 24334.4 | 2024-01-16 15:01 | -23971.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-008-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-006-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-10 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-402-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-503-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-504-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-206-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-703-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1007-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1008-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-904-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-908-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1002-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1004-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-905-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-906-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1005-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-205-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-206-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-301-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-506-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-301-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-404-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-501-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-505-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-506-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-201-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-203-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-001-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-105-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-107-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-103-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-004-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-05-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 94744 | 2022-05-10 | 83707.2 | 2022-07-26 12:09 | -78475.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2106-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-704-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1005-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1108-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1208-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1301-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-806-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1008-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1907-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2208-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2306-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2303-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-905-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1006-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2003-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1006-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1301-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1303-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2003-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2007-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2201-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2304-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-805-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-907-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1201-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1206-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1308-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-907-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1904-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2003-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1007-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1302-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1901-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2002-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-907-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-908-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1802-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-905-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-706-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1006-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-706-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-707-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-804-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-705-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-805-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-806-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-906-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-708-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-802-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-001-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-701-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-808-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-903-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1007-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1001-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-703-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-901-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1003-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-01-27 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -211214.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-704-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-705-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-01-27 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97943 | 2023-01-28 | 212849.1 | 2023-02-08 12:50 | -207617.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1501-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1401-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1507-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1303-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1307-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1402-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-06-28 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -159554.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1406-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-06-28 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 100338 | 2023-06-29 | 164786.4 | 2023-07-11 13:07 | -163152 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1803-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1804-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1801-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1802-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1804-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-102-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-20 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96308 | 2022-09-21 | 26150.4 | 2022-10-06 11:15 | -24516 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1603-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1705-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1807-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1808-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-12-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -152688.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1808-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2023-12-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 103812 | 2023-12-11 | 157920.3 | 2023-12-22 11:36 | -156285.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1201-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1203-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1106-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1208-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1107-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1103-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1105-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1207-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1206-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1102-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1104-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1204-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2023-03-15 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 98744 | 2023-03-16 | 78475.5 | 2023-03-29 11:18 | -73243.8 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2105-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2108-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2301-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-004-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-807-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2205-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2305-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2308-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2306-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-805-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-807-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1005-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1007-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1208-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1307-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1902-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2006-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2203-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2302-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2302-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-906-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1008-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1102-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-906-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1308-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1802-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2002-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2003-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2203-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-008-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-008-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-806-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1102-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1802-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2005-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2007-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2008-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2107-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2107-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-302-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1107-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1302-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1102-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1108-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1903-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1908-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2104-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2201-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2204-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2307-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1901-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2303-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-302-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1006-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1007-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1108-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -746148.2 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-302-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1902-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2001-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1307-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2101-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2103-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2308-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1104-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1206-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1303-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-003-2BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1906-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1906-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1907-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2207-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2307-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1301-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2024-02-09 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -755341.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-608-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-901-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-601-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-507-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-705-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-705-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-803-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-101-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-101-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-201-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-304-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-304-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-602-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-102-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-108-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-205-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-105-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-206-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-706-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-902-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1107-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-507-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-802-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1004-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -386027.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-404-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-605-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-403-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-505-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:41 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-904-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-12-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 104022 | 2023-12-18 | 399397.3 | 2024-01-02 11:44 | -395220.5 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-106-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:23 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-307-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-308-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-308-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-401-3BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-408-2BHK MS Folding Door work | 18.16 | 230 | 0 | 4176.8 | 751.82 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Dry Balcony. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -785424.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-501-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2023-09-01 18:33 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 101552 | 2023-09-02 | 789601.5 | 2023-09-20 11:58 | -776231.6 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2001-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2105-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2108-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2024-02-09 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -754286.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2205-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2301-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2305-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2024-02-09 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -757883.7 | SAI ENGINEERING WORKS
Galv. Folding Door-Shutter Rate Diff.(M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1005-3BHK MS Folding Door work | 18.16 | 20 | 0 | 363.2 | 65.38 | 2024-02-09 | Rate Diff. for Providing & Fixing of Galvanized Folding Door Shutter for D-Bldg Internal Flat Dry Balcony. | 100 |  | 105229 | 2024-02-12 | 759518.1 | 2024-03-02 12:04 | -759154.9 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-602-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-602-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-607-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-604-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-603-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-601-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-601-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1703-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1903-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1103-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1608-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-2101-3BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Shutter (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-1603-2BHK MS Folding Door work | 58.13 | 230 | 0 | 13369.9 | 2406.58 | 2024-06-14 | Providing and Fixing of Galvanized Folding Door Shutter for D-Bldg Int. Flat Living Room Attached Terrace. | 100 |  | 108378 | 2024-06-17 | 187178.6 | 1900-01-01 | -173808.7 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-303-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-504-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-401-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-404-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-405-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-501-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-502-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-505-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-203-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-204-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-303-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-304-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-09-26 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -205983 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-304-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-306-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-307-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-406-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-407-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-09-26 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 96375 | 2022-09-27 | 211214.7 | 2022-10-06 11:22 | -209580.3 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-606-3BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-607-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-608-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-608-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-408-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-603-2BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-604-2BHK MS Folding Door work | 18.16 | 90 | 0 | 1634.4 | 294.2 | 2022-12-14 | Providing and Fixing of MS Folding Door Frame at Dry Balcony in D-Building. | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -53294.4 | SAI ENGINEERING WORKS
Galv. Folding Door - Door Frame (M) | N/C | N/C | SAI ENGINEERING WORKS (MATERIAL) | 399 | 2022-04-01 | D-605-3BHK MS Folding Door work | 58.13 | 90 | 0 | 5231.7 | 941.7 | 2022-12-14 | Matrial Supply for- MS Folding door frame for internal flat | 100 |  | 97392 | 2022-12-15 | 54928.8 | 2023-01-07 11:04 | -49697.1 | SAI ENGINEERING WORKS
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-24 | 63.1075 | 5 | 0 | 315.5375 | 0 | 2023-10-04 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 102272 | 2023-10-05 | 13933.87 | 2023-10-20 11:00 | -13618.3325 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-23 | 148.165 | 5 | 0 | 740.825 | 0 | 2023-10-04 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 102272 | 2023-10-05 | 13933.87 | 2023-10-20 11:00 | -13193.045 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-23 | 148.165 | 5 | 0 | 740.825 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4856.545 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-27 | 176.15 | 5 | 0 | 880.75 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4716.62 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No- 29 | 156.005 | 5 | 0 | 780.025 | 0 | 2023-04-07 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 99057 | 2023-04-08 | 3828.22 | 2023-05-04 14:11 | -3048.195 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-25 | 164.6 | 5 | 0 | 823 | 0 | 2023-05-02 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 99390 | 2023-05-03 | 823 | 2023-05-16 12:30 | 0 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No- 26 | 175.605 | 5 | 0 | 878.025 | 158.04 | 2024-05-04 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 107374 | 2024-05-07 | 878.03 | 2024-07-11 10:30 | -0.005 | TEJASHREE ENTERPRISES
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-28 | 172.7 | 5 | 0 | 863.5 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4733.87 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No- 26 | 175.605 | 5 | 0 | 878.025 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4719.345 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No- 29 | 156.005 | 5 | 0 | 780.025 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4817.345 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-25 | 164.63 | 5 | 0 | 823.15 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4774.22 | YUGESH KUMAR
Rolling Shutter Painting | N/C | N/C | YUGESH KUMAR | 400 | 2022-04-04 | Rolling Shutter Painting Work Shop No-24 | 126.215 | 5 | 0 | 631.075 | 0 | 2022-12-12 | Labour Charges for- 2 Coat of Oil Paint for Rolling shutter of shops.Tools,Equipments and raw material transportation from store to required working place to be in contractors scope. | 100 |  | 97358 | 2022-12-13 | 5597.37 | 2022-12-31 11:29 | -4966.295 | YUGESH KUMAR
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1206 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -37920.642 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.906 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.801 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1101 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2105 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1702 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -36989.642 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2004 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2104 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2106 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1405 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1703 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37278.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.808 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.907 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1003 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2002 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1306 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -36989.642 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.705 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1906 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17076.232 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1902 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-05 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17570.8 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1908 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17364.664 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1804 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17364.664 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1901 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17076.232 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1902 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-01-05 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17165.752 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1804 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-05 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17609.56 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1304 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2108 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2101 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1304 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37278.074 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2308 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2408 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.001 Brickbat Waterproofing | 133.56 | 18 | 0 | 2404.08 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13420.08 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1903 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17364.664 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2106 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1105 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1305 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -36989.642 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1405 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -36989.642 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1005 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.908 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2107 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.803 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2008 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2005 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2101 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1705 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -36989.642 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2003 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37278.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.805 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2006 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1707 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37278.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.802 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.106 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-06-29 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16916.689 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.002 Brickbat Waterproofing | 133.56 | 18 | 0 | 2404.08 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13420.08 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1302 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1301 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-08-03 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30442.362 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1403 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1503 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1505 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.104 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-06-29 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16977.09 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.107 IPS Waterproofing | 58.735 | 15 | 0 | 881.025 | 0 | 2022-06-29 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17388.235 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.107 Brickbat Waterproofing | 63.4015 | 18 | 0 | 1141.227 | 0 | 2022-06-29 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17128.033 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.105 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-06-29 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16916.689 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.108 IPS Waterproofing | 58.735 | 15 | 0 | 881.025 | 0 | 2022-06-29 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17388.235 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.104 IPS Waterproofing | 58.735 | 15 | 0 | 881.025 | 0 | 2022-06-29 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17388.235 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.106 IPS Waterproofing | 61.4805 | 15 | 0 | 922.2075 | 0 | 2022-06-29 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17347.0525 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2306 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5881.92 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.907 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.108 Brickbat Waterproofing | 63.4015 | 18 | 0 | 1141.227 | 0 | 2022-06-29 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17128.033 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1006 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38010.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1201 Brickbat Waterproofing | 47.31 | 18 | 0 | 851.58 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38431.59 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1006 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -37920.642 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1201 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38010.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1008 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38209.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1203 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.802 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.908 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1004 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.903 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1104 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.808 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.705 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.706 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1001 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.708 Brickbat Waterproofing | 37.295 | 18 | 0 | 671.31 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38611.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1006 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38415.21 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1007 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1206 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38415.21 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1606 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1706 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.206 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26231.96 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.207 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25883.76 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.304 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.305 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.505 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.401 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100169.812 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.603 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.602 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.403 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.404 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.604 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.506 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2002 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.505 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.408 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.601 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.606 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.603 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.605 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.307 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100226.66 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.502 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.508 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2005 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.706 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1704 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37278.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2106 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2103 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2104 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2001 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2003 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2105 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1806 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1805 IPS Waterproofing | 72.33 | 15 | 0 | 1084.95 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36170.53 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1905 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36387.52 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1906 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36387.52 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1802 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1904 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1805 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-11-07 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35892.952 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1806 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-11-07 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35892.952 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1808 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-07 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36181.384 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2108 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2004 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1701 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -36989.642 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2103 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1901 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1802 IPS Waterproofing | 72.33 | 15 | 0 | 1084.95 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36170.53 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1803 IPS Waterproofing | 69.1 | 15 | 0 | 1036.5 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36218.98 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1806 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36387.52 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.801 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.901 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.902 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.701 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.701 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.804 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.905 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1101 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.805 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.906 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2003 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2105 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2107 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2008 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1306 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2001 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37079.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2006 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2108 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2207 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -23015.85 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2107 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-12-15 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37136.01 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2201 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22977.09 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2104 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2101 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2103 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2208 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -23015.85 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2002 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2001 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2202 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22977.09 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2203 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -23015.85 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2005 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22482.522 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2205 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22977.09 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2204 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -23015.85 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2206 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-01-31 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22977.09 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2004 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.405 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.406 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.407 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.408 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.501 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.305 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.404 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.606 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.505 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.508 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.601 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.605 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.301 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.504 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.602 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.303 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.308 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.406 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.502 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.304 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.004 Brickbat Waterproofing | 80 | 18 | 0 | 1440 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -16998.76 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1904 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17364.664 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.205 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26231.96 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1802 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17076.232 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1907 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17364.664 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1008 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1205 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38415.21 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1107 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1208 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38209.074 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1207 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1208 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1205 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38010.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1007 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38209.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.203 Chemical Waterproofing | 69.1 | 22 | 0 | 1520.2 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25579.72 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.201 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26231.96 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.204 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26025.824 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.203 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26270.72 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.207 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26025.824 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.206 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25826.912 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.208 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26025.824 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.202 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26231.96 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.202 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25826.912 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.203 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26025.824 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.004 Brickbat Waterproofing | 34.96 | 18 | 0 | 629.28 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17809.48 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1905 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17076.232 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1804 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-01-05 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17222.6 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.202 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25737.392 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.206 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25737.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.204 Chemical Waterproofing | 69.1 | 22 | 0 | 1520.2 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25579.72 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.208 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26270.72 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.205 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25737.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.201 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25826.912 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.205 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25826.912 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.201 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-08-24 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25737.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.208 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2022-08-24 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -25883.76 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.607 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.401 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.402 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.404 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.402 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.503 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.307 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.403 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.401 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.306 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.407 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.608 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.301 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.608 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.402 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.407 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.501 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.601 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.403 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.408 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.405 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.501 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.503 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.504 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.807 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.507 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1406 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1508 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1701 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1102 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1003 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1607 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1601 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1502 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1605 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1602 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1308 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1703 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1704 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1103 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.704 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1102 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1508 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1302 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1504 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1608 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.302 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.302 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.003 Brickbat Waterproofing | 114.96 | 18 | 0 | 2069.28 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13754.88 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.102 Chemical Waterproofing | 72.33 | 22 | 0 | 1591.26 | 0 | 2022-08-04 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95808 | 2022-08-05 | 7242.19 | 2022-10-03 11:21 | -5650.93 | LAXMAN CHAVAN
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.103 Chemical Waterproofing | 69.1 | 22 | 0 | 1520.2 | 0 | 2022-08-04 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95808 | 2022-08-05 | 7242.19 | 2022-10-03 11:21 | -5721.99 | LAXMAN CHAVAN
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.101 IPS Waterproofing | 72.33 | 15 | 0 | 1084.95 | 195.3 | 2022-08-04 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95809 | 2022-08-05 | 4379.37 | 2023-01-07 11:19 | -3294.42 | CHALUKYA INFRA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.101 Chemical Waterproofing | 72.33 | 22 | 0 | 1591.26 | 286.42 | 2022-08-04 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95809 | 2022-08-05 | 4379.37 | 2023-01-07 11:19 | -2788.11 | CHALUKYA INFRA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.101 Brickbat Waterproofing | 94.62 | 18 | 0 | 1703.16 | 306.56 | 2022-08-04 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95809 | 2022-08-05 | 4379.37 | 2023-01-07 11:19 | -2676.21 | CHALUKYA INFRA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.103 Brickbat Waterproofing | 74.59 | 18 | 0 | 1342.62 | 0 | 2022-08-04 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95808 | 2022-08-05 | 7242.19 | 2022-10-03 11:21 | -5899.57 | LAXMAN CHAVAN
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.102 IPS Waterproofing | 72.33 | 15 | 0 | 1084.95 | 0 | 2022-08-04 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95808 | 2022-08-05 | 7242.19 | 2022-10-03 11:21 | -6157.24 | LAXMAN CHAVAN
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.102 Brickbat Waterproofing | 94.62 | 18 | 0 | 1703.16 | 0 | 2022-08-04 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95808 | 2022-08-05 | 7242.19 | 2022-10-03 11:21 | -5539.03 | LAXMAN CHAVAN
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.604 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.406 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.605 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.606 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.504 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.308 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.807 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.801 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.807 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.904 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1108 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.707 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62401.93 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1001 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62345.082 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.906 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.708 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62401.93 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.207 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26270.72 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.204 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-08-24 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95978 | 2022-08-25 | 27099.92 | 2022-10-05 10:44 | -26270.72 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1708 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-12-15 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104042 | 2023-12-18 | 38352.17 | 2024-01-16 14:59 | -37278.074 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2006 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13114.37 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1202 Brickbat Waterproofing | 34 | 18 | 0 | 612 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95233.49 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1103 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1103 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1502 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1604 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1603 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1605 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1501 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1608 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1703 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1506 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1106 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1504 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1403 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1106 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1408 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1501 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1605 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1407 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1408 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1406 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1602 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.703 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1505 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1607 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1307 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1507 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1003 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1005 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1407 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.703 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1701 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1603 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1708 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1601 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1506 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1601 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.902 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.702 Brickbat Waterproofing | 34 | 18 | 0 | 612 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95233.49 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1307 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1401 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1604 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1607 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1702 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.904 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.905 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2007 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-12-23 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -13153.13 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1305 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-12-23 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 104107 | 2023-12-25 | 13982.33 | 2024-01-16 15:06 | -12709.322 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.901 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.804 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.806 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.701 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23732.392 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.903 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-02-17 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98257 | 2023-02-18 | 25005.4 | 2023-03-29 11:33 | -23789.24 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2301 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1304 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35397.99 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1306 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2201 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.704 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35397.99 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1905 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1807 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1907 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1808 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36426.28 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1908 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36426.28 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1803 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1908 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2308 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2204 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2302 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2303 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1606 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1706 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2307 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1305 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2304 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35397.99 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1606 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-08 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34954.182 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1105 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2305 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.703 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35397.99 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.006 Brickbat Waterproofing | 133.56 | 18 | 0 | 2404.08 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13420.08 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.008 Brickbat Waterproofing | 114.96 | 18 | 0 | 2069.28 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13754.88 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1603 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1708 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.507 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1707 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1404 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1707 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1705 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1505 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1608 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94771.394 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.608 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.502 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100574.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.503 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.506 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.508 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.607 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.602 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.303 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.405 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.607 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100150.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.301 Chemical Waterproofing | 61.4805 | 22 | 0 | 1352.571 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100090.249 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.306 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2022-12-26 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100169.812 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2206 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2305 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2207 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1202 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38010.162 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1108 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1202 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38415.21 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1107 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2407 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1402 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-08-03 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30442.362 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1303 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1308 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.604 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.304 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.305 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.506 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1405 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2208 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2302 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2203 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2304 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35153.094 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2306 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2303 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35397.99 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2007 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2024-01-31 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 105025 | 2024-02-05 | 23845.05 | 2024-02-19 15:15 | -22770.954 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.308 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.306 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100080.292 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.307 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.603 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2022-12-26 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100368.724 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.303 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2022-12-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 97519 | 2022-12-27 | 101442.82 | 2023-01-23 18:40 | -100613.62 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.104 Brickbat Waterproofing | 63.4015 | 18 | 0 | 1141.227 | 0 | 2022-06-29 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17128.033 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1301 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-08-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30847.41 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.107 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-06-29 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16977.09 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.103 IPS Waterproofing | 58.735 | 15 | 0 | 881.025 | 0 | 2022-06-29 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17388.235 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1106 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-04-08 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -35359.23 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2205 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2301 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-04-08 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34864.662 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1303 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1702 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1005 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94977.53 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1507 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1102 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1705 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.704 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1602 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-10-16 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94482.962 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1308 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1503 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1604 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1704 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-10-16 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -95016.29 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1503 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94629.33 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1401 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-10-16 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 102686 | 2023-10-17 | 95845.49 | 2023-11-06 16:12 | -94572.482 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1805 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1801 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36387.52 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.106 Brickbat Waterproofing | 80.427 | 18 | 0 | 1447.686 | 0 | 2022-06-29 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16821.574 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.105 Brickbat Waterproofing | 80.427 | 18 | 0 | 1447.686 | 0 | 2022-06-29 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16821.574 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.108 Chemical Waterproofing | 58.735 | 22 | 0 | 1292.17 | 0 | 2022-06-29 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -16977.09 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.105 IPS Waterproofing | 61.4805 | 15 | 0 | 922.2075 | 0 | 2022-06-29 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 95306 | 2022-06-30 | 18269.26 | 2022-10-05 10:40 | -17347.0525 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2403 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2406 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5881.92 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2307 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5920.68 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2302 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2303 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2305 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2205 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2207 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2201 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1207 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1208 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1501 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2401 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2024-07-26 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 109403 | 2024-07-29 | 6749.88 | 1900-01-01 | -5881.92 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1108 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1205 Brickbat Waterproofing | 47.31 | 18 | 0 | 851.58 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38431.59 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1207 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38209.074 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1201 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38415.21 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1203 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1204 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1307 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1508 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1401 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1404 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-08-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30886.17 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1402 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1404 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1302 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-08-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30847.41 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1502 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1403 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-08-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30886.17 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1301 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1406 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1507 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1506 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30352.842 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1504 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1303 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-08-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30886.17 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1408 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1903 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36426.28 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1808 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1901 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36387.52 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1904 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36426.28 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1907 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36426.28 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1402 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-08-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30847.41 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1407 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-08-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 100994 | 2023-08-04 | 31715.37 | 2023-09-04 11:39 | -30641.274 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1706 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-08 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 106711 | 2024-04-08 | 36227.19 | 2024-05-21 12:29 | -34954.182 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.806 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.806 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.805 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.905 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.901 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.902 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1002 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1002 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62345.082 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1004 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62401.93 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.802 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1001 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.903 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1104 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62401.93 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.803 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1101 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62255.562 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.702 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-03-02 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62345.082 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.707 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.708 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.907 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.702 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1104 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.804 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.808 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1902 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2024-01-05 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 104365 | 2024-01-08 | 18438.76 | 2024-01-23 14:24 | -17076.232 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1803 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-07 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36181.384 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2306 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2307 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1801 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1903 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36039.32 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1807 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-11-07 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36181.384 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1906 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-11-07 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35982.472 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2206 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1807 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-11-07 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -36426.28 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1801 Brickbat Waterproofing | 75.696 | 18 | 0 | 1362.528 | 0 | 2023-11-07 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 103383 | 2023-11-08 | 37255.48 | 2023-12-02 12:19 | -35892.952 | PRABHURAM VERMA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.706 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.908 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1002 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.803 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.904 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1004 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62788.89 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1107 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-03-02 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62543.994 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.705 IPS Waterproofing | 57.864 | 15 | 0 | 867.96 | 0 | 2023-03-02 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 98459 | 2023-03-03 | 63618.09 | 2023-03-30 12:44 | -62750.13 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.707 Brickbat Waterproofing | 37.295 | 18 | 0 | 671.31 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38611.86 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1204 IPS Waterproofing | 55.28 | 15 | 0 | 829.2 | 0 | 2023-05-11 | Labour charges for IPS/Screeding Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38453.97 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1203 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38209.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1008 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1206 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38010.162 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1204 Brickbat Waterproofing | 59.672 | 18 | 0 | 1074.096 | 0 | 2023-05-11 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38209.074 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1007 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2023-05-11 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 99601 | 2023-05-12 | 39283.17 | 2023-05-29 13:10 | -38067.01 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.1001 Chemical Waterproofing | 13.6364 | 22 | 0 | 300.0008 | 0 | 2023-08-12 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 101241 | 2023-08-14 | 300 | 1900-01-01 | 0.0008 | PAWAR SHIVAPPA TARANAIK
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2204 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2304 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.005 Brickbat Waterproofing | 133.56 | 18 | 0 | 2404.08 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13420.08 | PRABHURAM VERMA
Brickbat W/P | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.007 Brickbat Waterproofing | 114.96 | 18 | 0 | 2069.28 | 0 | 2023-09-23 | Labour charges for 200 mm and 150 mm Brickbat Waterproofing work for Toilet sunk and Balcony sunk for Internal Flats D-building. | 100 |  | 102062 | 2023-09-25 | 15824.16 | 2023-11-01 14:26 | -13754.88 | PRABHURAM VERMA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2203 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2208 Chemical Waterproofing | 55.28 | 22 | 0 | 1216.16 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16208.03 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 401 | 2022-04-04 | D-Flat.No.2301 Chemical Waterproofing | 57.864 | 22 | 0 | 1273.008 | 0 | 2024-04-27 | Labour charges for Chemical Waterproofing work for Toilet and Balcony area for Internal Flats D-building. | 100 |  | 107140 | 2024-04-29 | 17424.19 | 2024-06-03 12:40 | -16151.182 | AJAY KUMAR GUPTA
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1002 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1204 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1902 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1302 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1702 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1803 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.703 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.904 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1701 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1703 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.903 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1002 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1003 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1004 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.102 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.603 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.702 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.402 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.503 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1101 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1704 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1003 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102594 | 2023-10-13 | 20400 | 2023-10-28 11:35 | -16320 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1103 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102594 | 2023-10-13 | 20400 | 2023-10-28 11:35 | -16320 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.803 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1001 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.103 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1301 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1503 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1802 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1601 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.904 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1001 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.403 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.802 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.304 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.804 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.401 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.402 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.704 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.801 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1103 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1603 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1904 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.102 Internal Plumbing Work(L) | 0.6 | 5100 | 0 | 3060 | 0 | 2022-08-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95810 | 2022-08-05 | 6120 | 2022-08-11 11:42 | -3060 | ANANTA YASHWANT CHORGE
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.103 Internal Plumbing Work(L) | 0.6 | 5100 | 0 | 3060 | 0 | 2022-08-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95810 | 2022-08-05 | 6120 | 2022-08-11 11:42 | -3060 | ANANTA YASHWANT CHORGE
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2204 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104247 | 2024-01-01 | 12240 | 2024-01-16 15:03 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.002 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102273 | 2023-10-05 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.001 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102273 | 2023-10-05 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1201 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1704 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102397 | 2023-10-07 | 16320 | 2023-10-28 11:34 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1703 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102397 | 2023-10-07 | 16320 | 2023-10-28 11:34 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2203 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104247 | 2024-01-01 | 12240 | 2024-01-16 15:03 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2201 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104247 | 2024-01-01 | 12240 | 2024-01-16 15:03 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1004 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1104 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.502 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.602 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1204 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1702 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102397 | 2023-10-07 | 16320 | 2023-10-28 11:34 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1701 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102397 | 2023-10-07 | 16320 | 2023-10-28 11:34 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2002 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.004 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1901 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1802 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2404 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 108512 | 2024-06-24 | 12240 | 2024-07-05 11:43 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2401 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 108512 | 2024-06-24 | 12240 | 2024-07-05 11:43 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2403 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 108512 | 2024-06-24 | 12240 | 2024-07-05 11:43 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.204 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101225 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.203 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101225 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.104 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101225 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.202 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101225 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.101 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-10-10 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 96647 | 2022-10-10 | 4080 | 2022-10-17 11:05 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.201 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101225 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2101 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2103 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2104 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2302 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 106783 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2301 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 106783 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2304 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 106783 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.703 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102594 | 2023-10-13 | 20400 | 2023-10-28 11:35 | -16320 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.401 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.801 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1401 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.003 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.101 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1801 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.701 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1202 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.404 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.502 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.304 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.601 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.704 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.802 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.004 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1804 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1903 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.302 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1401 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1403 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1502 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1504 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1601 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.303 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.602 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.001 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1104 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1404 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1901 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1303 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1402 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1304 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.301 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.604 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.804 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2003 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2001 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2004 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104023 | 2023-12-18 | 32640 | 2023-12-25 15:33 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.003 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102273 | 2023-10-05 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.604 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.501 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1202 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.104 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1101 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.202 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.504 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.201 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.204 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.504 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2303 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 106783 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.203 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.503 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.601 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.603 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 95985 | 2022-08-25 | 53040 | 2022-08-27 13:00 | -48960 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1203 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.002 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1102 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1501 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1602 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1604 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.902 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1201 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1203 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.403 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.501 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.901 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-21 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 107779 | 2024-05-27 | 38760 | 2024-07-05 11:51 | -38250 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.302 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102594 | 2023-10-13 | 20400 | 2023-10-28 11:35 | -16320 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1102 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 102594 | 2023-10-13 | 20400 | 2023-10-28 11:35 | -16320 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.903 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 99678 | 2023-05-17 | 44880 | 2023-05-29 12:52 | -40800 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1303 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1301 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1302 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1401 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1903 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1804 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-01-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104556 | 2024-01-15 | 12240 | 2024-02-02 14:28 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1902 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-01-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104556 | 2024-01-15 | 12240 | 2024-02-02 14:28 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1602 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1502 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1501 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1504 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1503 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1402 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1603 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1604 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1403 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1404 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 101414 | 2023-08-24 | 61200 | 2023-09-04 11:46 | -57120 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1801 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1904 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1304 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.1803 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 103289 | 2023-11-06 | 28560 | 2023-11-22 11:31 | -24480 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.2202 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-01-13 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 104556 | 2024-01-15 | 12240 | 2024-02-02 14:28 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.301 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.303 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.701 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.803 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.901 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.702 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.404 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | SAI PLUMBING WORKS | 413 | 2022-04-16 | D-Flat.No.902 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-12-15 | Labour Charges for- Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 |  | 97413 | 2022-12-16 | 65280 | 2022-12-24 11:05 | -61200 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2208 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104248 | 2024-01-01 | 16320 | 2024-01-16 15:04 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1808 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.808 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.707 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.907 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.705 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.706 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.908 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.807 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.708 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1905 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1907 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1805 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1705 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102398 | 2023-10-07 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1708 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102398 | 2023-10-07 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1707 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-06 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102398 | 2023-10-07 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1007 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1107 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1008 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1206 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1205 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1208 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1108 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1207 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1006 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-05-16 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99674 | 2023-05-17 | 36720 | 2023-05-29 13:12 | -32640 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1506 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1406 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1607 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1307 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.306 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.308 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.105 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-08-24 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 95987 | 2022-08-25 | 4080 | 2022-12-24 11:04 | 0 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1807 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.507 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-07 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103379 | 2023-11-08 | 4080 | 2023-12-19 10:48 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2105 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1908 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1708 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1406 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1408 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1606 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1607 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1705 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1806 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.106 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-10-10 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96645 | 2022-10-10 | 12240 | 2022-10-17 11:07 | -8160 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.107 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-10-10 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96645 | 2022-10-10 | 12240 | 2022-10-17 11:07 | -8160 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.108 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-10-10 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96645 | 2022-10-10 | 12240 | 2022-10-17 11:07 | -8160 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.406 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.405 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.407 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.408 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.305 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1706 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-01-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104555 | 2024-01-15 | 4080 | 2024-02-02 14:27 | 0 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1307 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1507 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1906 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2406 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 108517 | 2024-06-24 | 4080 | 1900-01-01 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1606 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2006 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2007 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2008 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1305 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2308 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 106784 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2306 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 106784 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2307 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 106784 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2305 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-04-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 106784 | 2024-04-15 | 16320 | 2024-05-06 12:00 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.006 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102274 | 2023-10-05 | 16320 | 2023-10-28 11:33 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1306 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102591 | 2023-10-13 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1106 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102591 | 2023-10-13 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1005 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102591 | 2023-10-13 | 12240 | 2023-10-28 11:34 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2108 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2106 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2005 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2107 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1105 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1407 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1308 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1707 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.007 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-10-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102555 | 2023-10-12 | 2520 | 2023-11-24 10:34 | -1519.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.008 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-10-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102555 | 2023-10-12 | 2520 | 2023-11-24 10:34 | -1519.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.006 Internal Plumbing Work(L) | 0.102 | 5100 | -0.2 | 520.2 | 0 | 2023-10-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102555 | 2023-10-12 | 2520 | 2023-11-24 10:34 | -1999.8 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2407 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 108515 | 2024-06-24 | 12240 | 2024-07-05 11:52 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1405 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 0 | 2023-12-15 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104024 | 2023-12-18 | 48960 | 2023-12-25 15:36 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1906 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1806 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1807 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1908 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-11-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 103293 | 2023-11-06 | 32640 | 2023-11-22 11:30 | -28560 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.605 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.207 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.208 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-22 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.606 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.205 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.608 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1407 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1508 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1508 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.205 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101224 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.206 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101224 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.106 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101224 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.107 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101224 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.108 Internal Plumbing Work(L) | 0.1961 | 5100 | -0.11 | 1000.11 | 0 | 2023-08-12 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101224 | 2023-08-12 | 5000 | 2023-08-12 14:25 | -3999.89 | PAWAR SHIVAPPA TARANAIK
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1608 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1706 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.905 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.906 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.805 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.806 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-04-11 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 99124 | 2023-04-12 | 48960 | 2023-04-24 10:48 | -44880 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2405 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 108515 | 2024-06-24 | 12240 | 2024-07-05 11:52 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2408 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2024-06-21 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 108515 | 2024-06-24 | 12240 | 2024-07-05 11:52 | -8160 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1405 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1905 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1907 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1306 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1805 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1808 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.508 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.505 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.506 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.307 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-01-03 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 97615 | 2023-01-04 | 44880 | 2023-01-23 18:42 | -40800 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2206 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104248 | 2024-01-01 | 16320 | 2024-01-16 15:04 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2207 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104248 | 2024-01-01 | 16320 | 2024-01-16 15:04 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.2205 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-12-30 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 104248 | 2024-01-01 | 16320 | 2024-01-16 15:04 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.607 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.206 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2022-09-13 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 96339 | 2022-09-23 | 32640 | 2022-10-03 11:00 | -28560 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1408 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1505 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1507 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1608 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1605 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1308 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-08-23 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 101415 | 2023-08-24 | 48960 | 2023-09-04 11:46 | -44880 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.005 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102274 | 2023-10-05 | 16320 | 2023-10-28 11:33 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.007 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102274 | 2023-10-05 | 16320 | 2023-10-28 11:33 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1505 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.008 Internal Plumbing Work(L) | 0.8 | 5100 | 0 | 4080 | 734.4 | 2023-10-04 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 102274 | 2023-10-05 | 16320 | 2023-10-28 11:33 | -12240 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1605 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Int Plumbing PPRC Work | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 414 | 2022-04-16 | D-Flat.No.1506 Internal Plumbing Work(L) | 0.1 | 5100 | 0 | 510 | 91.8 | 2024-05-25 | Labour Charges for- Internal Plumbing work. PPRC,PVC & ASTM Pipe work (For Flat series 5,6,7 & 8) | 100 |  | 107784 | 2024-05-27 | 13770 | 2024-07-05 11:47 | -13260 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 6 | 1700 | 0 | 10200 | 1836 | 2024-06-21 | Labour Charges for- External Plumbing Duct line work. (For Flat series 1,2,3 & 4) | 100 |  | 108524 | 2024-06-24 | 10200 | 2024-07-05 11:46 | 0 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 10 | 1700 | 0 | 17000 | 3060 | 2024-02-24 | Labour Charges for- External Plumbing Duct line work. (For Flat series 1,2,3 & 4) | 100 |  | 105561 | 2024-02-26 | 17000 | 2024-03-18 12:02 | 0 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 7 | 1700 | 0 | 11900 | 2142 | 2024-01-27 | Labour Charges for- External Plumbing Duct line work. (For Flat series 1,2,3 & 4) | 100 |  | 104865 | 2024-01-29 | 54400 | 2024-02-21 11:35 | -42500 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 15 | 1700 | 0 | 25500 | 4590 | 2023-12-30 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 104222 | 2024-01-01 | 64600 | 2024-01-16 15:07 | -39100 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 23 | 1700 | 0 | 39100 | 7038 | 2023-12-28 18:07 | Labour Charges for- External Plumbing Duct line work. (For Flat series 1,2,3 & 4) | 100 |  | 104222 | 2024-01-01 | 64600 | 2024-01-16 15:07 | -25500 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 20 | 1700 | 0 | 34000 | 6120 | 2024-04-13 | Labour Charges for- External Plumbing Duct line work. (For Flat series 1,2,3 & 4) | 100 |  | 106785 | 2024-04-15 | 34000 | 2024-05-07 12:48 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 8 | 1700 | 0 | 13600 | 2448 | 2023-10-04 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 102275 | 2023-10-05 | 13600 | 2023-10-28 11:37 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 2 | 1700 | 0 | 3400 | 612 | 2023-12-15 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 104026 | 2023-12-18 | 3400 | 2023-12-25 15:38 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 4 | 1700 | 0 | 6800 | 1224 | 2023-11-04 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 103295 | 2023-11-06 | 6800 | 2023-11-22 11:31 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 10 | 1700 | 0 | 17000 | 3060 | 2024-05-12 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 107502 | 2024-05-13 | 17000 | 2024-06-04 15:20 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 5 | 1700 | 0 | 8500 | 1530 | 2024-01-27 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 104865 | 2024-01-29 | 54400 | 2024-02-21 11:35 | -45900 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 20 | 1700 | 0 | 34000 | 6120 | 2024-01-27 | Labour Charges for- External Plumbing Duct line work. (For Flat series 1,2,3 & 4) | 100 |  | 104865 | 2024-01-29 | 54400 | 2024-02-21 11:35 | -20400 | SAI PLUMBING WORKS
Rising Main Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 92 | 1700 | 0 | 156400 | 28152 | 2024-06-17 | Labour Charges for- External Plumbing Rising main line work. (For Flat series 1,2,3 & 4) | 100 |  | 108428 | 2024-06-17 | 156400 | 2024-07-05 11:46 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 17 | 1700 | 0 | 28900 | 5202 | 2022-12-15 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 97414 | 2022-12-16 | 28900 | 2022-12-28 12:22 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 8 | 1700 | 0 | 13600 | 2448 | 2023-08-23 17:54 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 101416 | 2023-08-24 | 13600 | 2023-09-04 11:48 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | SAI PLUMBING WORKS | 415 | 2022-04-18 | D-External Plumbing Work(L) | 6 | 1700 | 0 | 10200 | 1836 | 2023-05-16 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 1,2,3 & 4) | 100 |  | 99677 | 2023-05-17 | 10200 | 2023-05-29 12:52 | 0 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-Bldg Plumbing Groove in Toilet & Kitchen | 400 | 30 | 0 | 12000 | 0 | 2022-12-12 | Labour charges for Making Plumbing Grooves on Concrete wall in Toilet and Kitchen for D-Bldg. | 100 |  | 97360 | 2022-12-13 | 12000 | 2022-12-23 11:18 | 0 | YUGESH KUMAR
Plumbing Groove. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-Bldg Plumbing Groove in Toilet & Kitchen | 1066.4244 | 30 | 0 | 31992.732 | 0 | 2022-09-13 | Labour charges for Making Plumbing Grooves on Concrete wall in Toilet and Kitchen for D-Bldg. | 100 |  | 96251 | 2022-09-14 | 31992.73 | 2022-09-24 11:17 | 0.002 | YUGESH KUMAR
Plumbing Groove. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-Bldg Plumbing Groove in Toilet & Kitchen | 503.18 | 30 | 0 | 15095.4 | 2717.18 | 2023-09-13 18:58 | Labour charges for Making Plumbing Grooves on Concrete wall in Toilet and Kitchen for D-Bldg. | 100 |  | 101864 | 2023-09-15 | 15095.4 | 2023-09-30 12:06 | 0 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 20 | 1700 | 0 | 34000 | 6120 | 2024-02-24 | Labour Charges for- External Plumbing Duct line work. (For Flat series 5,6,7 & 8) | 100 |  | 105565 | 2024-02-26 | 51000 | 2024-03-18 12:02 | -17000 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 10 | 1700 | 0 | 17000 | 3060 | 2024-05-12 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 107504 | 2024-05-13 | 17000 | 2024-06-04 15:22 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 2 | 1700 | 0 | 3400 | 0 | 2023-12-15 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 104027 | 2023-12-18 | 3400 | 2023-12-29 10:55 | 0 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-Bldg Plumbing Groove in Toilet & Kitchen | 1133.2675 | 30 | 0 | 33998.025 | 6119.64 | 2022-09-13 | Labour charges for Making Plumbing Grooves on Concrete wall in Toilet and Kitchen for D-Bldg. | 100 |  | 96252 | 2022-09-14 | 33998.03 | 2022-10-03 10:59 | -0.005 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Plumbing Groove. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-Bldg Plumbing Groove in Toilet & Kitchen | 1466.6667 | 30 | 0 | 44000.001 | 7920 | 2022-10-10 | Labour charges for Making Plumbing Grooves on Concrete wall in Toilet and Kitchen for D-Bldg. | 100 |  | 96644 | 2022-10-10 | 44000 | 2022-10-17 11:07 | 0.001 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 5 | 1700 | 0 | 8500 | 1530 | 2024-01-27 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 104866 | 2024-01-29 | 22100 | 2024-02-19 15:19 | -13600 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 8 | 1700 | 0 | 13600 | 2448 | 2024-01-27 | Labour Charges for- External Plumbing Duct line work. (For Flat series 5,6,7 & 8) | 100 |  | 104866 | 2024-01-29 | 22100 | 2024-02-19 15:19 | -8500 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 22 | 1700 | 0 | 37400 | 6732 | 2023-12-28 18:14 | Labour Charges for- External Plumbing Duct line work. (For Flat series 5,6,7 & 8) | 100 |  | 104223 | 2024-01-01 | 62900 | 2024-01-16 15:03 | -25500 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 6 | 1700 | 0 | 10200 | 1836 | 2023-04-11 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 99126 | 2023-04-12 | 10200 | 2023-04-24 10:48 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 6 | 1700 | 0 | 10200 | 1836 | 2023-05-16 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 99676 | 2023-05-17 | 10200 | 2023-05-29 12:53 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 15 | 1700 | 0 | 25500 | 4590 | 2023-12-30 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 104223 | 2024-01-01 | 62900 | 2024-01-16 15:03 | -37400 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 8 | 1700 | 0 | 13600 | 2448 | 2023-08-23 17:55 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 101417 | 2023-08-24 | 13600 | 2023-09-04 11:48 | 0 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 10 | 1700 | 0 | 17000 | 3060 | 2024-02-24 | Labour Charges for- External Plumbing Duct line work. (For Flat series 5,6,7 & 8) | 100 |  | 105565 | 2024-02-26 | 51000 | 2024-03-18 12:02 | -34000 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 20 | 1700 | 0 | 34000 | 6120 | 2024-04-13 | Labour Charges for- External Plumbing Duct line work. (For Flat series 5,6,7 & 8) | 100 |  | 106786 | 2024-04-15 | 34000 | 2024-05-07 12:48 | 0 | SAI PLUMBING WORKS
Plumbing Groove. | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-Bldg Plumbing Groove in Toilet & Kitchen | 1506.7333 | 30 | 0 | 45201.999 | 8136.36 | 2023-01-03 | Labour charges for Making Plumbing Grooves on Concrete wall in Toilet and Kitchen for D-Bldg. | 100 |  | 97616 | 2023-01-04 | 65602 | 2023-01-24 12:21 | -20400.001 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 12 | 1700 | 0 | 20400 | 3672 | 2023-01-03 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 97616 | 2023-01-04 | 65602 | 2023-01-24 12:21 | -45202 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Rising Main Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 92 | 1700 | 0 | 156400 | 0 | 2024-06-17 | Labour Charges for- External Plumbing Rising main line work. (For Flat series 5,6,7 & 8) | 100 |  | 108427 | 2024-06-17 | 156400 | 2024-07-05 11:46 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 8 | 1700 | 0 | 13600 | 2448 | 2023-10-04 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 102277 | 2023-10-05 | 13600 | 2023-10-28 11:37 | 0 | SAI PLUMBING WORKS
Rainwater Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 4 | 1700 | 0 | 6800 | 1224 | 2023-11-04 | Labour Charges for- External Plumbing Rainwater line work. (For Flat series 5,6,7 & 8) | 100 |  | 103291 | 2023-11-06 | 6800 | 2023-11-22 11:31 | 0 | SAI PLUMBING WORKS
Duct Line | N/C | N/C | OM SAI ENTERPRISES (PROP. UMED SHITOLE) | 416 | 2022-04-18 | D-External Plumbing Work(L) | 6 | 1700 | 0 | 10200 | 1836 | 2024-06-21 | Labour Charges for- External Plumbing Duct line work. (For Flat series 5,6,7 & 8) | 100 |  | 108526 | 2024-06-24 | 10200 | 2024-07-05 11:46 | 0 | SAI PLUMBING WORKS
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-9th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104372 | 2024-01-08 | 4059.6 | 2024-01-23 14:23 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-9th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 104372 | 2024-01-08 | 4059.6 | 2024-01-23 14:23 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-16th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-20th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-7th Fl-Lobby Common Lobby+Staircase chemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-7th Fl-Lobby Common Lobby+Staircase chemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-11th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-12th Fl-Lobby Common Lobby +Staircasechemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-13th Fl-Lobby Common Lobby +Staircasechemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-1st Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-15th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-3rd Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-14th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-16th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-14th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-17th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-12th Fl-Lobby Common Lobby +Staircasechemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-11th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-3rd Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-18th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108673 | 2024-07-01 | 8119.2 | 2024-07-26 12:47 | -6089.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-19th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-06-27 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 108673 | 2024-07-01 | 8119.2 | 2024-07-26 12:47 | -6089.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-Stilt Fl Lobby Common Lobby+Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-03-07 | Labour charges for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105875 | 2024-03-11 | 4059.6 | 2024-03-26 14:52 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-18th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-03-07 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105875 | 2024-03-11 | 4059.6 | 2024-03-26 14:52 | -2029.8 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-21st Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108673 | 2024-07-01 | 8119.2 | 2024-07-26 12:47 | -6089.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-21st Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-06-27 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 108673 | 2024-07-01 | 8119.2 | 2024-07-26 12:47 | -6089.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-10th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-17th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-10th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-8th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-4th Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-13th Fl-Lobby Common Lobby +Staircasechemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-15th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-5th Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-2nd Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-5th Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-2nd Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-4th Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-6th Fl-Lobby Common Lobby +Staircase chemical grouting wor | 811.92 | 2 | 0 | 1623.84 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64953.6 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-1st Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Labour charges for Chemical Grouting work for Common lobby and Staircase. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-6th Fl-Lobby Common Lobby +Staircase chemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 425 | 2022-05-13 | D-8th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-02-01 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105026 | 2024-02-05 | 66577.44 | 2024-02-20 12:21 | -64547.64 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-19th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-06-27 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 108675 | 2024-07-01 | 4059.6 | 1900-01-01 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-Stilt Fl Lobby Common Lobby+Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-03-07 | Supply of Material for chemical Grouting work for common Lobby and Staircase. | 100 |  | 105905 | 2024-03-11 | 4059.6 | 2024-03-26 14:52 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-2nd Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 104035 | 2023-12-18 | 8119.2 | 2024-01-16 14:58 | -6089.4 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-4th Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 104035 | 2023-12-18 | 8119.2 | 2024-01-16 14:58 | -6089.4 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-3rd Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 104035 | 2023-12-18 | 8119.2 | 2024-01-16 14:58 | -6089.4 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-5th Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 104035 | 2023-12-18 | 8119.2 | 2024-01-16 14:58 | -6089.4 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-21st Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-06-27 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 108675 | 2024-07-01 | 4059.6 | 1900-01-01 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-11th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-12th Fl-Lobby Common Lobby +Staircasechemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-20th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-7th Fl-Lobby Common Lobby+Staircase chemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-1st Fl-Lobby Common Lobby+Staircase chemical grouting work | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-6th Fl-Lobby Common Lobby +Staircase chemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-13th Fl-Lobby Common Lobby +Staircasechemical grouting wor | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-10th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-9th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 104373 | 2024-01-08 | 2029.8 | 2024-01-23 14:24 | 0 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-8th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-15th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-16th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-18th Fl-Lobby Common Lobby +Staircase chemical grouting wo | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-03-07 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105905 | 2024-03-11 | 4059.6 | 2024-03-26 14:52 | -2029.8 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-17th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 426 | 2022-05-13 | D-14th Fl-Lobby Common Lobby +Staircase chemical grouting w | 1014.9 | 2 | 0 | 2029.8 | 0 | 2024-01-31 | Supply of Material for Chemical Grouting work for Common Lobby and Staircase. | 100 |  | 105027 | 2024-02-05 | 26387.4 | 2024-02-20 12:22 | -24357.6 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1502 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1208 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1205-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-705-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-707-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-907-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1207-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-707-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1108-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-804-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1001-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1004-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1204-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-801-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1208-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-704-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-706-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1003-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1005-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1205-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-604-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1105-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1107-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1204-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1707 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1903 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.704 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1202 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79648.12 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1106 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.907 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1804 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42981.48 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1902 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2024-01-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43256.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1905 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1908 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1804 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.007 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.008 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1907 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.105 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-06-29 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8093.24 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-06-29 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8093.24 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.103 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2022-08-04 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95811 | 2022-08-05 | 1650 | 2022-10-03 11:21 | -1375 | LAXMAN CHAVAN
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1303 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1501 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1207 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1302 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.706 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 100996 | 2023-08-04 | 5303.66 | 2023-09-04 11:39 | -3964.74 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1301-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1607-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1608-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1701-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1808-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.502 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.504 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.603 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.402 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.705 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 100996 | 2023-08-04 | 5303.66 | 2023-09-04 11:39 | -3964.74 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1905 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14037.16 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1902 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1806 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1908 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14356.96 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1804 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1802 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1802 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.003 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1808 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.003 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.905 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.906 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 100996 | 2023-08-04 | 5303.66 | 2023-09-04 11:39 | -4284.54 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1906 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-27 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10152.36 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1002 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.806 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.401 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.906 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.908 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.708 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.802 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.506 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.808 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.904 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.807 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1906 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-06-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10451.28 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1103 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10472.16 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1906 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10152.36 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1907 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10472.16 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.101 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 198 | 2022-08-04 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95812 | 2022-08-05 | 1375 | 2022-12-24 16:32 | -275 | CHALUKYA INFRA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.101 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 49.5 | 2022-08-04 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95812 | 2022-08-05 | 1375 | 2022-12-24 16:32 | -1100 | CHALUKYA INFRA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.003 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.004 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.005 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36906.28 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1802 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1804 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.003 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1906 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-706-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-805-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1007-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-905-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1004-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-806-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1006-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1008-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-702-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-803-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-704-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-002-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-006-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-007-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-001-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-004-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-003-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-005-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2023-09-27 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102117 | 2023-09-29 | 1225 | 1900-01-01 | -1050 | VIRAJ CONSTRUCTION AND SERVICES
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.908 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1202 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79648.12 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1405 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.703 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.905 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1005 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2003 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1605 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1002 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1705 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1306 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1801 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1901 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36906.28 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36906.28 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1803 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1905 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-11-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36586.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-11-07 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36586.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.008 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-11-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36586.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36906.28 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1807 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1901 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.808 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.902 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.403 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.404 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.202 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90337.96 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.806 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.906 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.407 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.904 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1104 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1505 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1107 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1202-2BHK(Near Refuse Area) Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-904-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-607-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-608-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-701-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-807-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1101-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1208-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-701-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-902-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1104-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-902-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-903-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1102-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1105-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-605-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-906-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1007-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1106-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1207-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-706-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-708-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-908-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-708-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-907-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-801-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-804-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1004-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1203-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1206-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-602-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-804-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-707-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1106-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1207-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1201-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-801-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-802-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-908-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1001-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1002-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1203-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-803-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1005-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1201-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-802-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-803-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1001-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1002-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1003-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-901-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1102-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1408 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1504 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1504 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1507 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1503 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1406 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1704 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1102 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1703 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1108 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1607 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1507 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1502 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2102 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2303-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1103 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1303 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1305 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1503 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2104 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2304-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1502 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.507 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1407 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2001 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2308-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1503 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1702 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.703 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1205 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2004 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2305-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174075 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2308-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174250 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1606 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2304-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174250 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2306-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174075 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1907 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14356.96 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1902 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-07 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14037.16 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1702 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.304 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.305 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.308 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.702 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.303 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.406 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.803 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.902 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1004 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1104 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.803 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91432.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.208 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-306-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-504-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-608-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.706 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.801 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2401-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2403-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1607 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1608 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1605 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1608 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1108 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1701 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1308 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1401 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1602 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1503 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1603 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1505 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1508 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.606 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.608 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.503 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.401 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1302-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1402-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1404-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1903 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.507 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1707 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.507 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1506 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.807 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1708 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1705 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.302 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1305 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1306 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1806 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1801 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1803 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2103 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.302 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.702 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79648.12 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.702 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79648.12 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1705 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.808 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1306 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1305 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.907 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.703 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1801 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1801 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1901 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1903 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.908 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1901 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1708 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1901 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1305-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1405-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1507-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1507-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1308-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1607-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1804-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1404-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.604 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.501 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1701-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1504-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1603-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1705-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1405-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1501-3BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1303-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1402-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1303-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1602-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.906 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1405 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.805 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1904 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1801 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1904 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1807 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1805 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1808 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.006 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1807 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.006 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1808 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.004 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2024-01-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42981.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.004 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-105-3BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4725 | ANANTA YASHWANT CHORGE
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1401 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1701 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1508 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.004 IPS Seal Pack at Toilet & Terrace Door | 1 | 1300 | 0 | 1300 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14076.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1807 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1808 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1905 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1907 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1805 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1403 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1404 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1703 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.801 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1502 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.704 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.707 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1207 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1403 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1406 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1603 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1301 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1101 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1204 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1501 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1601 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.302 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.706 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.906 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1608 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1202 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1401 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1108 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1201 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1607 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2101 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2103 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1303 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1505 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1508 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1205 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1308 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1602 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1604 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.903 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1304 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1605 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1708 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1201 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1203 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1402 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1501 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1403 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2003 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2004 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1102 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1705 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1706 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2307-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1208 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.305 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.307 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.807 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.808 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.902 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1603 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1206 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1307 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.501 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.708 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.208 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.208 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.508 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.304 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.804 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.903 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.408 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.801 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.805 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.402 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.502 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.705 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.804 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.903 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1101 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.303 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.305 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.705 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1001 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.307 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.404 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.306 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-101-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2022-10-10 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2100 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.307 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.508 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.208 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.405 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.407 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.408 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.105 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.108 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.607 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.203 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.406 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.606 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.704 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1506 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.005 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.005 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.006 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.007 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1906 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1904 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1904 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.001 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1806 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.006 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.008 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.608 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.201 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.301 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.501 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.304 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.603 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.204 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.604 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.104 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.106 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.107 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.305 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.306 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-108-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2022-10-10 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2625 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-107-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2022-10-10 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2625 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-201-3BHK Core Cutting Work | 2 | 175 | 0 | 350 | 63 | 2022-10-10 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2450 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-201-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 126 | 2022-10-10 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2100 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.705 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 100996 | 2023-08-04 | 5303.66 | 2023-09-04 11:39 | -3964.74 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-106-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2022-10-10 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2625 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-101-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2022-10-10 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2625 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-201-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2022-10-10 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2625 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1204-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-703-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-806-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-903-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1006-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1206-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-705-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-907-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1007-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-606-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-808-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-902-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1103-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1103-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-701-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-703-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1108-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1006-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1107-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.001 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1803 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-001-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1307-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1504-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-001-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1801-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2005-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2105-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1902-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-06-29 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8413.04 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.007 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.001 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.007 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1803 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1308 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1407 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1304 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1904-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1801-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2201-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.204 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.207 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.404 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.407 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.605 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.607 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.106 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.107 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.201 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.105 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.307 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.506 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.401 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1303 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1006 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1403 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1403 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1404 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-406-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-501-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-502-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-505-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-506-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-408-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-508-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-104-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-208-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-303-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-502-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-504-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-608-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1208 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1301 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1402 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1404 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1402 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1501 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1502 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1902 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10152.36 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.904 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1305 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1606 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2008 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1106 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1301 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1302 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1507 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1402 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1601 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2002 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1407 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.304 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1303 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1307 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1404 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1406 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1505 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1705 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1006 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1107 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1201 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1307 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1703 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2308-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1107 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.802 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1704 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.708 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1205 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1404 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1604 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2005 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2006 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2007 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1104 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1203 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1704 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.707 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.907 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1501 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1701 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1703 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1203 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1204 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1405 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1605 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2307-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1102 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1207 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1304 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1408 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.705 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.804 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1504 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1006 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1707 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1003 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1206 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2408-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2405-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2408-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8750 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2406-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2406-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2404-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8750 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2406-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8575 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2401-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2408-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2301-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2302-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2303-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174250 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-102-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4900 | ANANTA YASHWANT CHORGE
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-103-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4200 | ANANTA YASHWANT CHORGE
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-102-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4550 | ANANTA YASHWANT CHORGE
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-103-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4900 | ANANTA YASHWANT CHORGE
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1601 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2301-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2302-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1408 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1507 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1608 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2008 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1007 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1407 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1508 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1602 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1708 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2405-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8575 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2403-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2405-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2401-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8575 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2403-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8750 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1603-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1708-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1605-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1304-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1603-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1501-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1502-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1503-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1604-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1501-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1805-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1807-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1408-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1507-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1704-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1705-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1406-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1601-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1706-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1304-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1706-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1308-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1401-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1506-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1508-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1307-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.403 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.601 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.503 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1308-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1401-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1407-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1302-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1504-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1601-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1607-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1403-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1405-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1803-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1502-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1408-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1608-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1707-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1802-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1402-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1503-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1506-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1702-2BHK(Near Refuse Area) Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1703-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1306-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1307-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1404-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1506-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1508-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1703-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1704-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1305-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1306-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1601-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1608-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1502-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1801-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1302-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1403-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1606-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1701-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1705-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1307-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1707-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1708-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1306-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1401-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1606-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1407-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1606-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1702-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1707-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1301-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1602-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1704-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1605-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1708-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-104-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4725 | ANANTA YASHWANT CHORGE
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-101-3BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4725 | ANANTA YASHWANT CHORGE
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2108-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2201-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1805-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1807-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2006-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2008-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1703-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1902-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2003-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2005-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-003-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1803-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1107 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1605 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1304 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1603 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1604 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1307 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1604 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1307 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1406 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1704 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-905-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-806-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-808-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-905-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-805-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1105-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-807-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-908-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1008-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1106-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-903-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1101-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-702-2BHK(Near Refuse Area) Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-704-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-901-3BHK Core Cutting Work | 0.09 | 175 | 0 | 15.75 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67550 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1103-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1104-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.802 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14380.22 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-705-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-808-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1008-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-702-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-703-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-603-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-805-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-904-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-708-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1706 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2005 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.901 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1208 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1106 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1108 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1207 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1701 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1406 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.908 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1408 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1002 Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14648.004 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1401 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1603 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.701 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.805 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.803 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1507 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2006 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1005 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1007 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1208 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2003 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2302-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1402 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1701 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.708 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1301 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1302 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1204 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1206 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1202 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.403 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.408 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.504 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.501 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.102 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.104 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.603 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.601 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.402 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.406 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.101 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.103 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.202 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.606 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1205 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.304 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.306 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.205 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.206 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.605 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.305 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.601 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.202 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.503 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.602 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.506 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.707 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.505 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.507 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.505 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.206 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.303 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.308 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.608 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.604 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.403 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.607 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1302 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1207 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1006 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.102 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.103 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.208 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.603 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.303 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.504 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.302 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.401 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.502 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.205 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.602 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.404 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.502 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.608 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.207 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.601 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.402 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.503 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.301 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.405 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.605 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1908 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-03-07 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 105877 | 2024-03-11 | 15376.08 | 2024-03-26 14:53 | -14336.08 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1607 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1606 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-06-29 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8093.24 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-06-29 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8413.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1301 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.108 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-06-29 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8413.04 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1206 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2002-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2106-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-002-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-004-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1802-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1901-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2103-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2202-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2005-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2207-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2108-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1806-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-203-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-403-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-207-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-508-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.204 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-504-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-505-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-104-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-107-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-505-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-507-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-402-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-403-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-605-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-606-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.206 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91432.48 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-008-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-407-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-106-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92071.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-301-3BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-402-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-406-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-408-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-502-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-503-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-108-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-105-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-306-3BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-506-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-202-2BHK(Near Refuse Area) Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-403-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-206-3BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-604-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.206 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91432.48 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.108 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.201 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-401-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-202-2BHK(Near Refuse Area) Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-503-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-507-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-506-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-304-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-407-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.206 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-503-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.205 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91432.48 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1908 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1806 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1907 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-303-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-601-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-401-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-606-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-205-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-405-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-603-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.105 Bore Packing + Perma Eazee Coat | 4.8 | 275 | 0 | 1320 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91451.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.107 Bore Packing + Perma Eazee Coat | 4.8 | 275 | 0 | 1320 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91451.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-508-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-106-3BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-204-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-307-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-604-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.202 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91607.56 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.104 Bore Packing + Perma Eazee Coat | 4.8 | 275 | 0 | 1320 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91451.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-402-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-406-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-002-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-408-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-302-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-303-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91432.48 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-108-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92071.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-006-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-008-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1607-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1907-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1805-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2006-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1408-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1807-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1901-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2201-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2001-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1904-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2008-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2208-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-105-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-08-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4375 | ANANTA YASHWANT CHORGE
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2306-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.306 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.308 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1401 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2001 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1105 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1008 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1102 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1105 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1505 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1704 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2106 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1707 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2107 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2108 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2306-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1604 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1008 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1504 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2105 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2305-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-12-26 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174425 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2305-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2307-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174250 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2304-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-102-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4550 | ANANTA YASHWANT CHORGE
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1506 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2007 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1306 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1308 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2002 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2303-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-12-26 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173900 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2301-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-12-26 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174075 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1602 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1103 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1302 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1304 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173500 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1506 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36906.28 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1806 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1808 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.005 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.006 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1805 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 Bore Packing + Perma Eazee Coat | 3.76 | 275 | 0 | 1034 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36891.4 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-11-07 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36586.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1904 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1905 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1805 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1807 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1601 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1602 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1601 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1001 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1707 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1708 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1703 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1407 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1408 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -55053.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1102 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104106 | 2023-12-25 | 56072.8 | 2024-01-16 15:07 | -54733.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.901 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14380.22 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.902 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14380.22 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.903 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14700.02 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1608 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1007 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1105 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.802 Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14648.004 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.901 Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14648.004 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.105 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-06-29 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8093.24 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.108 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-06-29 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95307 | 2022-06-30 | 9432.16 | 2022-10-05 10:39 | -8413.04 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1903-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2204-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2002-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1905-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1802-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1804-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2006-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2204-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1905-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1804-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2007-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2205-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.102 Bore Packing + Perma Eazee Coat | 5 | 275 | 0 | 1375 | 0 | 2022-08-04 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95811 | 2022-08-05 | 1650 | 2022-10-03 11:21 | -275 | LAXMAN CHAVAN
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.903 Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14903.844 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14380.22 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-004-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1503-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.403 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.601 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.401 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.205 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.602 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.504 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.402 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1706-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1504-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1505-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1505-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.501 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.608 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1505-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1703-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1303-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1305-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1501-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1602-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.605 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.603 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.502 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2106-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1403-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2007-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2101-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2203-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2004-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1603-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1806-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2007-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2101-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1905-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1906-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-007-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1604-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1906-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1102-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2001-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1807-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1808-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1907-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2105-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1507-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1303-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1707-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2103-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2107-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1902-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2205-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1808-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1407-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1808-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2008-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-007-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1604-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1907-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1908-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2206-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2208-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1708-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1903-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2205-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2207-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1901-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1908-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2204-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1404-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1804-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2108-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2203-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-006-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-008-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1906-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2107-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-005-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1608-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1908-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2107-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1508-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1803-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2105-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2206-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2003-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2207-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1803-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2001-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2003-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2102-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-003-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1904-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2208-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57494.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-005-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2103-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2104-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2203-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-002-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1304-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1308-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1704-2BHK Core Cutting Work | 0.06 | 175 | 0 | 10.5 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58184 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2104-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2002-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2004-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2104-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57844.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2106-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2206-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-10-12 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57669.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2101-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2004-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2023-10-12 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -57319.5 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1903-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-10-12 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 102588 | 2023-10-13 | 58194.5 | 2023-11-06 16:11 | -58019.5 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1902 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1801 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36906.28 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.002 Bore Packing + Perma Eazee Coat | 0.24 | 275 | 0 | 66 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37859.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1904 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.308 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.804 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.106 Bore Packing + Perma Eazee Coat | 6 | 275 | 0 | 1650 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91121.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.301 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.405 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.407 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.905 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1101 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.307 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.706 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.707 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-602-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-208-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.701 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.907 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.504 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.505 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-405-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.407 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.506 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.805 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.901 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.801 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.801 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.803 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.803 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-103-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-404-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-607-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1004 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1105 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79473.04 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1407-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1508-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57225 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2103 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 106675 | 2024-04-08 | 80811.96 | 2024-04-25 11:35 | -79792.84 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.103 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-09-21 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 96314 | 2022-09-21 | 1100 | 2022-10-03 11:21 | 0 | LAXMAN CHAVAN
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10472.16 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1907 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.405 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.404 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.702 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.905 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.503 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.301 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.408 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.505 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.406 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.701 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.802 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.408 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.508 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1107 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1108 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.505 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.807 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.405 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.406 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.804 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90482.68 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1908 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.001 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.006 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1808 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1005-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-906-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1007-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1107-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1206-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-906-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1101-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1108-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1208-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67215.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-101-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 31.5 | 2022-10-10 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 96643 | 2022-10-10 | 2800 | 2022-10-17 10:51 | -2625 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1001 Int Flat Chemical Grouting Work | 133.892 | 2 | 0 | 267.784 | 0 | 2023-08-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 100996 | 2023-08-04 | 5303.66 | 2023-09-04 11:39 | -5035.876 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.908 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90401.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.508 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10472.16 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1908 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10472.16 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1905 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-27 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 108674 | 2024-07-01 | 11491.28 | 2024-07-26 12:46 | -10152.36 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.701 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1002 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-03-02 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90676.8 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.506 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-03-02 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90461.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.306 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -90162.88 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.701 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.907 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1001 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-03-02 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 98462 | 2023-03-03 | 91501.8 | 2023-03-30 12:43 | -91281.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1903 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1906 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2023-11-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37705.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1802 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -37100.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1903 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.008 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2023-11-07 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 103384 | 2023-11-08 | 37925.4 | 2023-12-02 12:20 | -36825.4 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1202 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1106 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2008 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2007 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.904 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14700.02 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1004 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2001 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.904 Int Flat Chemical Grouting Work | 407.648 | 2 | 0 | 815.296 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14903.844 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1506 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2104 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1006 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2002 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.301 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.303 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.806 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.905 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1306 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1005 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2023-12-26 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173775 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14380.22 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1503 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1001 Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14648.004 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1504 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1508 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.901 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2023-12-26 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -173560 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1308 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1405 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1607 Bore Packing + Perma Eazee Coat | 1 | 275 | 0 | 275 | 0 | 2023-12-26 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104215 | 2024-01-01 | 174600 | 2024-01-16 15:06 | -174325 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1205 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.806 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2407-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1103 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.108 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.706 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.707 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.508 Bore Packing + Perma Eazee Coat | 0.8 | 275 | 0 | 220 | 0 | 2022-12-27 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63955 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.308 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-302-3BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-304-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-607-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-605-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-206-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-305-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.205 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.207 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.203 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.202 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-08-24 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91671.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-008-2BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-407-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2407-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2404-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2024-06-14 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2404-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2024-06-14 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8925 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-308-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-601-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92071.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-107-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-601-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-602-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-203-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-308-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-501-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-507-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-001-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-107-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-003-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92596.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-101-3BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-204-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-205-3BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-207-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-405-3BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-603-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91896.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-301-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.207 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-307-2BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-305-3BHK Core Cutting Work | 6 | 175 | 0 | 1050 | 0 | 2022-08-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91721.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-401-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92246.4 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-404-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -92421.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.207 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95979 | 2022-08-25 | 92771.4 | 2022-10-05 10:51 | -91752.28 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34671.28 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1206 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102687 | 2023-10-17 | 35690.4 | 2023-11-06 16:12 | -34351.48 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.902 Int Flat Chemical Grouting Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2023-05-11 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99602 | 2023-05-12 | 15719.14 | 2023-05-29 13:11 | -14648.004 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2101 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2103 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2004 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.605 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.602 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.604 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1605-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1406-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1408-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1806-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.607 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1702-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1503-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1604-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1301-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2023-05-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57050 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1403-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1406-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2023-05-04 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -57400 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1304-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2023-05-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 99424 | 2023-05-05 | 57575 | 2023-05-29 13:10 | -56875 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.606 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -35690.4 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.607 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 97520 | 2022-12-27 | 37029.32 | 2023-01-23 18:41 | -36010.2 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-2407-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2024-06-14 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 108376 | 2024-06-17 | 9100 | 2024-07-05 11:34 | -8750 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.2005 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1008 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-04-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 107141 | 2024-04-29 | 30160 | 1900-01-01 | -29120 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.806 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -22940.8 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.602 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.604 Bore Packing + Perma Eazee Coat | 4 | 275 | 0 | 1100 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63075 | AJAY KUMAR GUPTA
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.606 Bore Packing + Perma Eazee Coat | 3 | 275 | 0 | 825 | 0 | 2022-12-27 | Labour charges for 5" Bore Packing with perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63350 | AJAY KUMAR GUPTA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.203 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2022-12-27 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 97530 | 2022-12-28 | 64175 | 2023-01-23 18:42 | -63135 | AJAY KUMAR GUPTA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.708 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101242 | 2023-08-14 | 24279.72 | 2023-09-04 11:39 | -23260.6 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-901-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-904-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1102-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1202-2BHK(Near Refuse Area) Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1203-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1205-3BHK Core Cutting Work | 3 | 175 | 0 | 525 | 0 | 2022-12-24 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67040.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1201-3BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-802-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1002-3BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1003-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1202-2BHK(Near Refuse Area) Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66865.75 | AJAY KUMAR GUPTA
Core Cutting 6" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-1104-2BHK Core Cutting Work | 1 | 175 | 0 | 175 | 0 | 2022-12-24 | Labour charges for 6 inch Core cutting work for D-Bldg Internal Flat | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -67390.75 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-807-2BHK Core Cutting Work | 5 | 175 | 0 | 875 | 0 | 2022-12-24 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 97511 | 2022-12-26 | 67565.75 | 2023-01-23 18:40 | -66690.75 | AJAY KUMAR GUPTA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1804 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
IPS Seal Pack | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1802 IPS Seal Pack at Toilet & Terrace Door | 0.8 | 1300 | 0 | 1040 | 0 | 2024-01-05 | Labour charges for IPS Seal pack work for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43041.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1803 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1902 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1803 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Labour charges for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -43062.36 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1804 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1807 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1805 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1806 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
6"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1805 Bore Packing + Perma Eazee Coat | 0.2 | 275 | 0 | 55 | 0 | 2024-01-07 | Labour charges for 6" Bore packing with Perma Eazee coat for D-Bldg Internal Flats. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -44026.48 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-Flat.No.1802 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Ghadi work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface, including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 104369 | 2024-01-08 | 44081.48 | 2024-01-23 14:24 | -42742.56 | PRABHURAM VERMA
Core Cutting Work 2" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-103-2BHK Core Cutting Work | 2 | 175 | 0 | 350 | 0 | 2022-08-04 | Labour charges for 2 inch Dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4725 | ANANTA YASHWANT CHORGE
Core Cutting Work 5" BCE | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 427 | 2022-05-17 | D-104-2BHK Core Cutting Work | 4 | 175 | 0 | 700 | 0 | 2022-08-04 | Labour charges for 5 inch dia Core Cutting work for D-Bldg Internal Flat. | 100 |  | 95813 | 2022-08-05 | 5075 | 2022-08-11 11:43 | -4375 | ANANTA YASHWANT CHORGE
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.902 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7393.92 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7393.92 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.903 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7713.72 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7393.92 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.108 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-06-29 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95308 | 2022-06-30 | 4716.08 | 2022-10-06 11:03 | -3696.96 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8413.04 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1504 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1605 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15546.88 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1405 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1604 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1607 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1105 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1106 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.904 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7713.72 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.806 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8413.04 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1907 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105874 | 2024-03-11 | 4716.08 | 2024-03-26 14:51 | -3696.96 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1902 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105874 | 2024-03-11 | 4716.08 | 2024-03-26 14:51 | -3377.16 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1205 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8413.04 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.506 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1804 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -13129.12 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1806 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -12809.32 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103385 | 2023-11-08 | 5735.2 | 2023-12-02 12:19 | -4716.08 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103385 | 2023-11-08 | 5735.2 | 2023-12-02 12:19 | -4716.08 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1301 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1302 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.603 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.402 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.504 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.607 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.501 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.608 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8732.84 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8732.84 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1303 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1403 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1208 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1402 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1102 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -9811.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1108 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1406 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -9811.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1501 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 108676 | 2024-07-01 | 3377.16 | 1900-01-01 | -2358.04 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1707 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1506 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2008 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1602 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15546.88 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1508 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1901 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1608 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1305 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1306 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.605 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.604 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.602 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.503 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.401 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.601 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1307 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1807 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -13129.12 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.005 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -12809.32 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -13129.12 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1801 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -12809.32 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.006 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -12809.32 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8732.84 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1703 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1507 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1601 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15546.88 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1202 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28616.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1505 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15546.88 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1903 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1705 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1708 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.301 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.303 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.804 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.305 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.405 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.407 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.408 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.308 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.801 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.306 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.105 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-06-29 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95308 | 2022-06-30 | 4716.08 | 2022-10-06 11:03 | -3377.16 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.706 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8413.04 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1704 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1701 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15546.88 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2103 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28441.2 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1503 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1603 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-23 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104104 | 2023-12-25 | 16885.8 | 2024-01-16 14:58 | -15866.68 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.2007 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-04-08 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 106676 | 2024-04-08 | 29780.12 | 2024-04-25 11:32 | -28761 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-06-29 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95308 | 2022-06-30 | 4716.08 | 2022-10-06 11:03 | -3377.16 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1107 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1304 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.003 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-11-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103385 | 2023-11-08 | 5735.2 | 2023-12-02 12:19 | -4716.08 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.403 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1006 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1207 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1404 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16826.08 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1502 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.502 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1206 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-10-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 102688 | 2023-10-17 | 17845.2 | 2023-11-03 15:42 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.001 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-11-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103385 | 2023-11-08 | 5735.2 | 2023-12-02 12:19 | -4396.28 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.002 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-11-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 103385 | 2023-11-08 | 5735.2 | 2023-12-02 12:19 | -4396.28 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1407 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.606 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-12-26 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 97521 | 2022-12-27 | 17845.2 | 2023-01-23 18:41 | -16506.28 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1408 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1308 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -10131.48 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.204 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -8237.96 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.201 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -7918.16 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.208 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -8237.96 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.203 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -8237.96 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.205 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -7918.16 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.104 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-06-29 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95308 | 2022-06-30 | 4716.08 | 2022-10-06 11:03 | -3696.96 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.802 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7393.92 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.901 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-05-11 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 99604 | 2023-05-12 | 8732.84 | 2023-05-29 13:08 | -7393.92 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1808 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -13129.12 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1904 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -13129.12 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1802 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -12809.32 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1905 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105874 | 2024-03-11 | 4716.08 | 2024-03-26 14:51 | -3377.16 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1908 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-07 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105874 | 2024-03-11 | 4716.08 | 2024-03-26 14:51 | -3696.96 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1004 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-08-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 100998 | 2023-08-04 | 2358.04 | 1900-01-01 | -1338.92 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1103 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-06-27 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 108676 | 2024-07-01 | 3377.16 | 1900-01-01 | -2358.04 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.705 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 100998 | 2023-08-04 | 2358.04 | 1900-01-01 | -1019.12 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.202 Int Flat Chemical Grouting Work | 581.92 | 2 | 0 | 1163.84 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -8093.24 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.207 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -8237.96 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.701 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.505 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.304 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.406 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -20902.56 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.803 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.508 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.404 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.307 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2023-03-02 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 98463 | 2023-03-03 | 22241.48 | 2023-03-30 12:44 | -21222.36 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1101 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-08-12 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 101243 | 2023-08-14 | 9751.96 | 1900-01-01 | -8413.04 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1906 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-27 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 108676 | 2024-07-01 | 3377.16 | 1900-01-01 | -2038.24 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.206 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2022-08-24 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 95980 | 2022-08-25 | 9257.08 | 2022-09-26 10:44 | -7918.16 | AJAY KUMAR GUPTA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1805 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -12809.32 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1803 Int Flat Chemical Grouting Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-01-05 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 105175 | 2024-02-10 | 14148.24 | 2024-02-10 11:26 | -13129.12 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | S. K ENTERPRISES (LAXMI SHINDE) | 428 | 2022-05-17 | D-Flat.No.1401 Int Flat Chemical Grouting Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2023-12-16 | Supply of Material for Chemical Grouting work for Internal Flat D-Bldg. | 100 |  | 104632 | 2024-01-17 | 11150.6 | 2024-01-31 17:40 | -9811.68 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 13th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 8th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 11th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 17th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 10th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 12th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 9th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 15th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 16th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 19th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 22nd Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 14th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 7th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2023-05-04 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 99427 | 2023-05-05 | 11660 | 2023-07-13 15:49 | -10600 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 20th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 18th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 23rd Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 5th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2022-08-24 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 95983 | 2022-08-25 | 5300 | 2022-09-10 16:45 | -4240 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 6th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2022-08-24 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 95983 | 2022-08-25 | 5300 | 2022-09-10 16:45 | -4240 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 3rd Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2022-08-24 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 95983 | 2022-08-25 | 5300 | 2022-09-10 16:45 | -4240 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 4th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2022-08-24 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 95983 | 2022-08-25 | 5300 | 2022-09-10 16:45 | -4240 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 2nd Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2022-08-24 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 95983 | 2022-08-25 | 5300 | 2022-09-10 16:45 | -4240 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 24th Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 2" BCE | N/C | N/C | AJAY KUMAR GUPTA | 432 | 2022-05-25 | 21st Fl-Lobby Core Cutting Work | 4 | 265 | 0 | 1060 | 0 | 2024-06-14 | Labour charges for 2 inch Core Cutting work for D-Bldg Common Lobby. | 100 |  | 108377 | 2024-06-17 | 7420 | 2024-07-05 11:33 | -6360 | AJAY KUMAR GUPTA
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-26 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 4" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-25 | 1 | 175 | 0 | 175 | 0 | 2022-10-08 | Labour charges for 4 inch core cutting work for Nanhi trap for F-shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12235 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-27 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 4" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-28 | 1 | 175 | 0 | 175 | 0 | 2022-10-08 | Labour charges for 4 inch core cutting work for Nanhi trap for F-shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12235 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-25 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 4" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-29 | 1 | 175 | 0 | 175 | 0 | 2022-10-08 | Labour charges for 4 inch core cutting work for Nanhi trap for F-shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12235 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-29 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 4" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-27 | 1 | 175 | 0 | 175 | 0 | 2022-10-08 | Labour charges for 4 inch core cutting work for Nanhi trap for F-shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12235 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 4" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-24 | 1 | 175 | 0 | 175 | 0 | 2022-10-08 | Labour charges for 4 inch core cutting work for Nanhi trap for F-shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12235 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-24 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-23 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 5" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-28 | 1 | 265 | 0 | 265 | 0 | 2022-10-08 | Labour charges for 5 inch Core cutting work for Commode for F-Shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12145 | SHINDE PLUMBING CONTRACTOR
Core Cutting Work 4" BCE | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 436 | 2022-06-02 | Core Cutting Work Shop No-23 | 1 | 175 | 0 | 175 | 0 | 2022-10-08 | Labour charges for 4 inch core cutting work for Nanhi trap for F-shops. | 100 |  | 96628 | 2022-10-10 | 12410 | 2022-10-17 10:47 | -12235 | SHINDE PLUMBING CONTRACTOR
4"Bore Packing with Perma Eazee Coat (L) - No. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 23 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 4 inch Bore Packing + Perma Eazee for Nanhi Trap for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 25 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 28 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 24 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
4"Bore Packing with Perma Eazee Coat (L) - No. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 27 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 4 inch Bore Packing + Perma Eazee for Nanhi Trap for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
4"Bore Packing with Perma Eazee Coat (L) - No. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 24 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 4 inch Bore Packing + Perma Eazee for Nanhi Trap for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
4"Bore Packing with Perma Eazee Coat (L) - No. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 29 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 4 inch Bore Packing + Perma Eazee for Nanhi Trap for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 23 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
4"Bore Packing with Perma Eazee Coat (L) - No. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 28 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 4 inch Bore Packing + Perma Eazee for Nanhi Trap for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 26 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
4"Bore Packing with Perma Eazee Coat (L) - No. | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 25 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 4 inch Bore Packing + Perma Eazee for Nanhi Trap for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 27 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
5"Bore Packing with Perma Eazee Coat (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 437 | 2022-06-02 | Bore Packing + Perma Eazee Work Shop No- 29 | 1 | 275 | 0 | 275 | 0 | 2022-10-13 | Labour charges for 5 inch Bore Packing + Perma Eazee for Commode for F-shops. | 100 |  | 96738 | 2022-10-13 | 15400 | 2022-10-17 10:51 | -15125 | SHINDE PLUMBING CONTRACTOR
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 10th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 15th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 12th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Plaster Work BCE | N/C | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Toilet ledge wall plaster work | 7.1429 | 700 | -0.03 | 5000.03 | 0 | 2023-08-12 | Labour charges for Toilet Ledge wall Plaster work (Single coat tar plaster) for D-Building. | 100 |  | 101222 | 2023-08-12 | 5000 | 2023-08-12 14:26 | 0.03 | PAWAR SHIVAPPA TARANAIK
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 11th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 3rd Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 24th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 7th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 9th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 22nd Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Stilt Fl Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 13th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 8th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P2 Floor AAC Blockwork (L) | 110.4 | 18 | 0 | 1987.2 | 357.7 | 2023-12-28 15:35 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 104221 | 2024-01-01 | 12810.53 | 2024-01-16 14:56 | -10823.33 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking Ground Floor AAC Blockwork (L) | 135.824 | 18 | 0 | 2444.832 | 440.06 | 2023-12-28 15:35 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 104221 | 2024-01-01 | 12810.53 | 2024-01-16 14:56 | -10365.698 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P1 Floor AAC Blockwork (L) | 124.96 | 18 | 0 | 2249.28 | 404.88 | 2023-12-28 15:35 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 104221 | 2024-01-01 | 12810.53 | 2024-01-16 14:56 | -10561.25 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P5 Floor AAC Blockwork (L) | 100 | 18 | 0 | 1800 | 324 | 2023-12-28 15:35 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 104221 | 2024-01-01 | 12810.53 | 2024-01-16 14:56 | -11010.53 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P1 Floor AAC Blockwork (L) | 269.75 | 18 | 0 | 4855.5 | 0 | 2024-06-11 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 108296 | 2024-06-11 | 13717.26 | 2024-06-24 12:20 | -8861.76 | JAY GANESH ENTERPRISES
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P2 Floor AAC Blockwork (L) | 138.11 | 18 | 0 | 2485.98 | 0 | 2024-06-11 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 108296 | 2024-06-11 | 13717.26 | 2024-06-24 12:20 | -11231.28 | JAY GANESH ENTERPRISES
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 2nd Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 23rd Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 18th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 14th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Plaster Work BCE | N/C | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Toilet ledge wall plaster work | 18 | 700 | 0 | 12600 | 0 | 2022-12-12 | Labour charges for Toilet Ledge wall Plaster work (Single coat tar plaster) for D-Building. | 100 |  | 97357 | 2022-12-13 | 12600 | 2022-12-23 11:28 | 0 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 5th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 19th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P3 Floor AAC Blockwork (L) | 187.21 | 18 | 0 | 3369.78 | 0 | 2024-06-11 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 108296 | 2024-06-11 | 13717.26 | 2024-06-24 12:20 | -10347.48 | JAY GANESH ENTERPRISES
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking P3 Floor AAC Blockwork (L) | 240.512 | 18 | 0 | 4329.216 | 779.26 | 2023-12-28 15:35 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 104221 | 2024-01-01 | 12810.53 | 2024-01-16 14:56 | -8481.314 | JAI SEVALAL CONSTRUCTION
Plaster Work BCE | N/C | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Toilet ledge wall plaster work | 19 | 700 | 0 | 13300 | 0 | 2022-06-24 | Labour charges for Toilet Ledge wall Plaster work (Single coat tar plaster) for D-Building. | 100 |  | 95214 | 2022-06-24 | 13300 | 2022-07-26 11:56 | 0 | K RAMU RATHOD
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Parking Ground Floor AAC Blockwork (L) | 167 | 18 | 0 | 3006 | 0 | 2024-06-11 | Charges for Construction of 5 Inch Blockwork at D Build parking area in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 108296 | 2024-06-11 | 13717.26 | 2024-06-24 12:20 | -10711.26 | JAY GANESH ENTERPRISES
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 21st Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 4th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 6th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 17th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 20th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Blockwork 5" - BC - | GLAZING SERVICES | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg 16th Fl-Lobby AAC Blockwork | 77 | 18 | 0 | 1386 | 249.48 | 2024-05-05 | Charges for Construction of 5 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 107383 | 2024-05-07 | 33264 | 2024-05-28 19:05 | -31878 | JAI SEVALAL CONSTRUCTION
Plaster Work BCE | N/C | N/C | K RAMU RATHOD | 440 | 2022-06-04 | D-Bldg Toilet ledge wall plaster work | 11 | 700 | 0 | 7700 | 0 | 2022-12-09 | Labour charges for Toilet Ledge wall Plaster work (Single coat tar plaster) for D-Building. | 100 |  | 97323 | 2022-12-10 | 7700 | 2023-03-29 11:18 | 0 | K RAMU RATHOD
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-805-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-906-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-003-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-004-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-303-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-403-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-507-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-208-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-503-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-806-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1003-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-206-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-405-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-406-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-408-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-606-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1005-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-204-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-205-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-501-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1006-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1007-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-302-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-007-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-108-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-308-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-702-2BHK(Near Refuse Area) Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-706-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-803-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1008-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-301-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-603-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-002-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-103-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-104-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-107-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-601-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-707-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-008-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-101-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-006-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-201-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-602-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-604-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-703-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-804-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-903-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-904-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-502-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-504-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-102-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-304-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-307-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-907-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-908-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-106-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-306-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-506-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1002-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-207-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-407-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-607-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-608-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-807-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-808-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-005-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1004-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-708-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-305-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-508-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-801-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-802-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-905-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1001-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-202-2BHK(Near Refuse Area) Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-605-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-704-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-401-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-705-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-701-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-901-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-902-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-001-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-203-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-404-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-505-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-105-3BHK Door Frame Fixing Work | 1.2727 | 1980 | 0.05 | 2519.946 | 0 | 2023-10-11 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102554 | 2023-10-12 | 2520 | 2023-11-24 10:34 | -0.054 | PAWAR SHIVAPPA TARANAIK
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1403-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1702-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1908-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2306-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1701-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1907-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2001-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2106-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 30 | 15 | 0 | 450 | 0 | 2024-01-15 16:12 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -20741.94 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-11-08 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 103398 | 2023-11-09 | 5280.48 | 2023-12-02 12:18 | -4413.72 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-304-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-11-08 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 103398 | 2023-11-09 | 5280.48 | 2023-12-02 12:18 | -4413.72 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2023-11-08 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 103398 | 2023-11-09 | 5280.48 | 2023-12-02 12:18 | -4373.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2023-11-08 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 103398 | 2023-11-09 | 5280.48 | 2023-12-02 12:18 | -4373.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-801-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1506-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-708-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-807-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1001-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1008-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1507-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1306-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17004.81 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1508-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-502-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1602-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
False Ceiling (L)- SOS | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 105.0667 | 15 | 0 | 1576.0005 | 0 | 2024-01-30 | Labour Charges for Shop No.29 False Ceiling work | 100 |  | 105007 | 2024-02-05 | 2180.65 | 2024-03-02 12:03 | -604.6495 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-106-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5280.48 | RADHEYSHYAM YADAV
Gypsum Board Partition (L) | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 40.31 | 15 | 0 | 604.65 | 0 | 2024-01-30 | Labour Charges for Shop No.29 Gypsum board partition | 100 |  | 105007 | 2024-02-05 | 2180.65 | 2024-03-02 12:03 | -1576 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-105-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5280.48 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-101-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5280.48 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-104-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5320.44 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-108-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5320.44 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-608-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1003-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1005-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1502-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-806-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1004-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1003-2BHK Toilet False ceiling work | 43.338 | 15 | 0 | 650.07 | 0 | 2024-06-17 18:47 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -14187.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1501-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1503-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-306-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-404-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2236.83 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-402-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-407-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2236.83 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-607-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1008-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1104-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-801-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-601-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-902-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-904-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-505-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-605-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-606-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-403-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-405-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-705-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-406-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-502-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1006-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1101-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-804-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-508-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-701-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-407-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1004-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-708-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 195 | 15 | 0 | 2925 | 0 | 2024-01-15 16:12 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -18266.94 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-403-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2236.83 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-406-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-401-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-302-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
False Ceiling (l) -BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 15 | 0 | 17366.94 | 0 | 2024-01-15 16:08 | Labour Charges for- Internal False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -3825 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 88 | 15 | 0 | 1320 | 0 | 2024-04-07 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106645 | 2024-04-08 | 2385 | 2024-04-30 15:26 | -1065 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1001-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-503-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-508-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-803-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-804-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-805-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1102-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-703-2BHK Toilet False ceiling work | 72.23 | 15 | 0 | 1083.45 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -16828.08 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-705-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1302-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17004.81 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1304-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17044.77 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1102-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-505-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-507-2BHK Toilet False ceiling work | 72.23 | 15 | 0 | 1083.45 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -16828.08 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-606-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-908-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-604-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-707-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-901-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-906-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-706-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-802-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-707-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1107-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-807-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-908-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-602-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-906-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-907-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1002-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6227.16 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6187.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-501-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-405-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2226.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1604-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1606-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-702-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 15 | 0 | 1133.4 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -16778.13 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-902-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-905-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1204-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17044.77 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1601-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1603-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
False Ceiling (l) -BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 15 | 0 | 17366.94 | 0 | 2023-12-21 16:03 | Labour Charges for- Internal False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104097 | 2023-12-25 | 17366.94 | 2024-01-02 11:46 | 0 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-308-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-11-08 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 103398 | 2023-11-09 | 5280.48 | 2023-12-02 12:18 | -4413.72 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-307-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-11-08 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 103398 | 2023-11-09 | 5280.48 | 2023-12-02 12:18 | -4413.72 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 64 | 15 | 0 | 960 | 0 | 2024-04-07 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106645 | 2024-04-08 | 2385 | 2024-04-30 15:26 | -1425 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2101-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6187.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6187.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6187.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6227.16 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-204-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6227.16 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2023-10-04 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 102268 | 2023-10-05 | 7093.92 | 2023-11-03 15:38 | -6227.16 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-408-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 14:57 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108429 | 2024-06-17 | 2453.52 | 2024-07-05 11:39 | -2236.83 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1006-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1104-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1901-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-603-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1108-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-805-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-503-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-803-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1005-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-408-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-404-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-506-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-306-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-905-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-401-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-302-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-808-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-704-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 30 | 15 | 0 | 450 | 0 | 2024-01-15 16:12 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 104672 | 2024-01-22 | 21191.94 | 2024-02-02 14:24 | -20741.94 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 7 | 15 | 0 | 105 | 0 | 2024-04-07 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106645 | 2024-04-08 | 2385 | 2024-04-30 15:26 | -2280 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-603-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1607-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-506-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-605-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1505-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-704-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-903-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17044.77 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-904-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
False Ceiling (l) -BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1543.7 | 15 | 0 | 23155.5 | 0 | 2024-04-15 | Labour Charges for- Internal False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 106827 | 2024-04-15 | 23155.5 | 2024-04-30 15:26 | 0 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1703-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1808-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2103-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2005-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-806-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-402-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-604-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-504-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49777.32 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-901-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-501-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-03-02 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 105726 | 2024-03-04 | 50644.08 | 2024-03-16 10:56 | -49737.36 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1002-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-601-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-602-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-802-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-504-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-907-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-808-2BHK Toilet False ceiling work | 14.446 | 15 | 0 | 216.69 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17694.84 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1007-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:13 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17044.77 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1605-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13931.19 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1504-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1805-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2006-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2304-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2107-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1706-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2105-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1803-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2007-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2308-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1704-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1801-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2104-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2302-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2204-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2002-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1905-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2004-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1402-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1906-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2108-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2307-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-107-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5320.44 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-103-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2022-12-23 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 97494 | 2022-12-23 | 6187.2 | 2022-12-31 11:23 | -5320.44 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1903-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1806-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1807-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2008-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-701-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-706-3BHK Toilet False ceiling work | 15.112 | 15 | 0 | 226.68 | 0 | 2024-06-17 17:54 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108435 | 2024-06-17 | 17911.53 | 2024-07-05 11:40 | -17684.85 | RADHEYSHYAM YADAV
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1608-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 0 | 2024-06-17 18:48 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 108502 | 2024-06-24 | 14837.91 | 2024-07-05 11:39 | -13971.15 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26402.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-105-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26402.4 | RADHEYSHYAM YADAV
Gypsum Board Partition (M) | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 40.31 | 60 | 0 | 2418.6 | 0 | 2024-01-30 | Material Charges for Shop No.29 Gypsum Board Partition Work. | 100 |  | 105006 | 2024-02-05 | 8721.6 | 2024-03-02 11:57 | -6303 | RADHEYSHYAM YADAV
False Ceiling (M)- SOS | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | Altus-Shop-29-Grid Ceiling &Partition Work | 105.05 | 60 | 0 | 6303 | 0 | 2024-01-30 | Material Charges for Shop No.29 False ceiling work. | 100 |  | 105006 | 2024-02-05 | 8721.6 | 2024-03-02 11:57 | -2418.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-305-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -21868.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-308-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-303-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-801-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1403-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:38 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1008-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-704-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-902-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1704-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-204-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1606-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1003-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1005-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-601-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-606-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1002-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-603-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-605-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-806-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-807-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-808-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-404-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-501-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1006-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-508-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-701-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-903-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-306-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-406-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1004-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1102-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-906-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-301-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -21868.8 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1543 | 60 | 0 | 92580 | 0 | 2024-04-15 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106828 | 2024-04-15 | 92580 | 2024-04-30 15:26 | 0 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1104-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1407-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1703-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2006-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1806-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2004-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2005-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2002-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 7 | 60 | 0 | 420 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -9120 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-304-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 60 | 0 | 69467.76 | 0 | 2023-12-21 16:07 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104098 | 2023-12-25 | 69467.76 | 2024-01-08 16:12 | 0 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-401-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1505-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1604-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1502-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1001-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-507-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-608-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-803-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-403-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-408-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-604-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-405-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-505-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-705-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1603-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1508-2BHK Toilet False ceiling work | 21.669 | 60 | 0 | 1300.14 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88300.56 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1503-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1601-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1306-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1501-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1506-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1607-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1507-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1302-3BHK Toilet False ceiling work | 22.668 | 60 | 0 | 1360.08 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88240.62 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1608-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-502-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-503-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-706-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-905-3BHK Toilet False ceiling work | 22.6 | 60 | 0 | 1356 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182064 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2007-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1805-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1807-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1303-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-704-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1302-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-804-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1004-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1304-2BHK Toilet False ceiling work | 21.669 | 60 | 0 | 1300.14 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88300.56 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1504-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1605-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1602-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-506-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-802-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-402-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 22.668 | 60 | 0 | 1360.08 | 244.82 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -235285.8 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1903-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-708-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-805-3BHK Toilet False ceiling work | 22.6 | 60 | 0 | 1356 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182064 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-804-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-504-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-707-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-908-2BHK Toilet False ceiling work | 21.66 | 60 | 0 | 1299.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182120.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-908-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2003-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-307-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-11-08 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 103399 | 2023-11-09 | 26402.4 | 2023-12-02 12:17 | -22068.6 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-501-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-903-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-807-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-506-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1804-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-505-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-605-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-606-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1905-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2104-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1907-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2001-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1901-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 195 | 60 | 0 | 11700 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -73067.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg LG Floor Toilet False Ceiling Work | 30 | 60 | 0 | 1800 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -82967.76 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 30 | 60 | 0 | 1800 | 0 | 2024-01-15 16:21 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -82967.76 | RADHEYSHYAM YADAV
False Ceiling (m) -BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Int Part False Ceiling Work | 1157.796 | 60 | 0 | 69467.76 | 0 | 2024-01-15 16:04 | Material Supply Charges for- Internal Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 104671 | 2024-01-22 | 84767.76 | 2024-02-02 14:23 | -15300 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 1st Floor Toilet False Ceiling Work | 88 | 60 | 0 | 5280 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -4260 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1204-2BHK Toilet False ceiling work | 21.669 | 60 | 0 | 1300.14 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -88300.56 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-702-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85067.1 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-703-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-06-18 18:14 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 108508 | 2024-06-24 | 89600.7 | 2024-07-05 11:38 | -85266.9 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | F-Bldg 2nd Floor Toilet False Ceiling Work | 64 | 60 | 0 | 3840 | 0 | 2024-04-07 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation,Loading/Unloading of material to be done by Contractor. | 100 |  | 106647 | 2024-04-08 | 9540 | 2024-04-30 15:26 | -5700 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-507-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1204-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1401-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-408-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1001-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1102-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-905-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -31135.8 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-708-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1304-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-805-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-801-3BHK Toilet False ceiling work | 52.892 | 60 | 0 | 3173.52 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -95861.64 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1508-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1904-2BHK Toilet False ceiling work | 50.561 | 60 | 0 | 3033.66 | 0 | 2023-12-30 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 104250 | 2024-01-01 | 99035.16 | 2024-01-16 15:07 | -96001.5 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2103-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2105-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-904-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-401-3BHK Toilet False ceiling work | 22.66 | 60 | 0 | 1359.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182060.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1402-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:38 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1906-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1702-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1808-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2008-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1803-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1908-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1706-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-104-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-103-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26602.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2023-10-04 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 102270 | 2023-10-05 | 35469.6 | 2023-11-03 15:38 | -30936 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2204-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1801-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1301-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-106-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2022-12-23 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 97495 | 2022-12-23 | 30936 | 2022-12-31 11:10 | -26402.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1701-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1305-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-907-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-302-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-607-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-901-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1104-2BHK Toilet False ceiling work | 21.6 | 60 | 0 | 1296 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -182124 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-602-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -178886.4 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-407-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 0 | 2024-03-06 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 105857 | 2024-03-11 | 183420 | 2024-03-16 10:53 | -179086.2 | RADHEYSHYAM YADAV
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2106-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Labour Lumpsum - BC | N/C | N/C | RADHEYSHYAM YADAV | 453 | 2022-06-30 | D-102-3BHK Toilet False ceiling work | 1 | 17000 | 0 | 17000 | 0 | 2022-07-20 | Providing and Fixing of Toilet false ceiling in sample flat 102 D-Building including Cement sheet, Acrylic material. | 100 |  | 95593 | 2022-07-22 | 17000 | 2022-08-27 12:56 | 0 | RADHEYSHYAM YADAV
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88744.852 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144842.938 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144778.7908 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2024-01-15 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142867.434 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144617.1796 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176510.836 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176510.836 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172346.9 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176473.828 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -19475.636 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61250.936 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -20724.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -17244.18 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -19475.636 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -19475.636 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -20724.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -20724.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61862.08 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2304-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Window sill -granite work | 16.136 | 52.2 | 0 | 842.2992 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26404.5008 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90341.228 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88744.852 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90341.228 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90468.164 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88744.852 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90468.164 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90468.164 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2404-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-06-07 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14294.8808 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2403-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -12100.8104 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2401-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-06-07 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14294.8808 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45541.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2303-2BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14419.7432 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26650.8848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2301-3BHK Window sill -granite work | 16.136 | 52.2 | 0 | 842.2992 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26404.5008 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2401-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-06-07 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14133.2696 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2403-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-06-07 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14294.8808 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-04-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -25329.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2403-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-06-07 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14133.2696 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2404-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -12100.8104 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2301-3BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14419.7432 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-04-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -25329.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29143.708 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29359.316 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -27509.908 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29143.708 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Toilet door frame -granite wor | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61217.848 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61814.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61862.08 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61814.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -17244.18 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Window sill -granite work | 16.136 | 52.2 | 0 | 842.2992 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61133.9408 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232618.47 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Ledge wall top -granite work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Ledge wall top -granite work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232618.47 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1003-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76162.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -74313.348 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176510.836 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-704-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1202-2BHK(Near Refuse Area) Window sill -granite work | 21.384 | 10 | 0 | 213.84 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42194.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41794.892 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 0 | 2024-02-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -40342.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42272.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41939.292 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41871.508 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1003-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76026.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75888.42 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61217.848 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102394 | 2023-10-07 | 21541.62 | 2023-10-30 15:44 | -17244.18 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61396.448 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61814.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29365.548 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29365.548 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29223.092 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76544.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -74313.348 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76026.532 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76162.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76026.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76026.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -74313.348 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29084.98 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29434.732 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-02-26 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29778.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29787.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29434.732 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-702-2BHK(Near Refuse Area) Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29269.388 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29084.98 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61862.08 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2204-2BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-04-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -25329.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-04-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -25329.8 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88581.748 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88581.748 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2304-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26650.8848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2302-3BHK Window sill -granite work | 16.136 | 52.2 | 0 | 842.2992 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26404.5008 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2303-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2303-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26650.8848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26650.8848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2204-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2204-2BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-04-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26727.7232 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1003-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -74313.348 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1702-2BHK(Near Refuse Area) Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29434.732 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29096.5496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-703-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29396.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76162.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76162.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76268.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1702-2BHK(Near Refuse Area) Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29143.708 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-02-26 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29778.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29747.78 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76125.748 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29365.548 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-703-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29269.388 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-02-26 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29778.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75130.54 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-12-05 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75980.236 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3412.194 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3529.842 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3412.194 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3529.842 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3875.25 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-003-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3844.29 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3529.842 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3412.194 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3844.29 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2302-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2304-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2204-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-04-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26727.7232 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2301-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26441.2496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2302-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41821.644 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 0 | 2024-02-02 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42030.188 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41974.252 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42253.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-704-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41775.348 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-704-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 0 | 2024-02-02 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42000.356 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41794.892 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41794.892 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41974.252 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41974.252 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41871.508 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41649.668 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176616.084 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176510.836 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176328.316 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176473.828 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1003-2BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88744.852 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90468.164 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144842.938 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144617.1796 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2304-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142867.434 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144617.1796 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2302-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2303-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144697.426 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144697.426 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Ledge wall top -granite work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Ledge wall top -granite work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232618.47 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-703-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29434.044 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29740.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29740.74 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29143.708 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29258.1608 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29740.74 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29434.732 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-703-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -27673.012 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2401-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -12100.8104 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2404-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-06-07 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14133.2696 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2302-3BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14419.7432 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2304-2BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-06-07 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 108207 | 2024-06-10 | 14938.82 | 1900-01-01 | -14419.7432 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41794.892 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41649.668 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-02-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42284.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-704-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2024-02-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -40178.972 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176510.836 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176510.836 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172346.9 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172346.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-704-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41902.284 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3875.25 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-08-16 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -85678.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88581.748 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144778.7908 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2304-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142867.434 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Toilet door frame -granite wor | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2303-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144697.426 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1204-2BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90341.228 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29434.732 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29096.5496 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-702-2BHK(Near Refuse Area) Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29396.324 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-702-2BHK(Near Refuse Area) Window sill -granite work | 21.384 | 41 | 0 | 876.744 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29025.356 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29740.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-02-26 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29778.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1603-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29787.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29365.548 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29365.548 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29747.78 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29787.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-001-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3844.29 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-002-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103248 | 2023-11-04 | 3998.61 | 2023-11-23 11:39 | -3875.25 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144842.938 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144617.1796 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144697.426 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144778.7908 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2203-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -88581.748 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1001-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140613.69 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Toilet -ventilator frame | 15.432 | 52.2 | 0 | 805.5504 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144617.1796 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29747.78 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29766.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2023-12-05 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -75018.04 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2023-12-05 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76238.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-02-26 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29258.1608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-702-2BHK(Near Refuse Area) Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -27673.012 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29747.78 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29787.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29740.74 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29787.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29084.98 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2024-03-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -59420.944 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Window sill -granite work | 16.136 | 47 | 0 | 758.392 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61217.848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61380.3248 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61814.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90431.156 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90294.932 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90838.58 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2302-3BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142867.434 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2301-3BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140613.69 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Ledge wall top -granite work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144778.7908 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144778.7908 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2204-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2301-3BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236563.53 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237253.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-401-3BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-604-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235589.298 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-804-2BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-902-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -236451.03 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237454.863 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Toilet -ventilator frame | 17.361 | 41 | 0 | 711.801 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237201.729 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Toilet door frame -granite work | 61.164 | 41 | 0 | 2507.724 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -235405.806 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Ledge wall top -grainte work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -233078.91 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-701-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-301-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-403-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237386.166 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-404-2BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237488.424 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-603-2BHK Ledge wall top -granite work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Ledge wall top -granite work | 13.878 | 41 | 0 | 568.998 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -237344.532 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Kitchen otta making | 11.511 | 440 | 0 | 5064.84 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98825 | 2023-03-20 | 237913.53 | 2023-03-29 11:34 | -232848.69 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2202-2BHK(Near Refuse Area) Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45553.18 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Kitchen otta making | 11.511 | 460 | 0 | 5295.06 | 0 | 2023-05-03 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -40381.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -45522.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-402-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99413 | 2023-05-04 | 45676.54 | 2023-05-16 12:29 | -44859.42 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60401.24 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2003-2BHK Umbra Patti -granite work | 9.944 | 52.2 | 0 | 519.0768 | 0 | 2024-03-06 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61457.1632 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61840.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Umbra Patti -granite work | 9.944 | 47 | 0 | 467.368 | 0 | 2024-03-06 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61508.872 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61439.688 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1902-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1702-2BHK(Near Refuse Area) Toilet door frame -granite wor | 54.368 | 47 | 0 | 2555.296 | 0 | 2024-03-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -59420.944 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61159.12 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1901-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1304-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 0 | 2024-02-26 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29464.564 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1103-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29084.98 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1804-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-26 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105586 | 2024-02-26 | 29902.1 | 2024-03-18 12:05 | -29787.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-12-09 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76582.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76570.18 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1701-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-12-09 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103796 | 2023-12-11 | 76705.54 | 2023-12-22 11:32 | -76551.22 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1702-2BHK(Near Refuse Area) Window sill -granite work | 21.384 | 47 | 0 | 1005.048 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60971.192 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Window sill -granite work | 11.416 | 47 | 0 | 536.552 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61439.688 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61862.08 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1903-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140613.69 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1904-2BHK Ledge wall top -granite work | 12.336 | 47 | 0 | 579.792 | 0 | 2024-01-10 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -144842.938 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Counter Basin Work | 0.9 | 1625 | 0 | 1462.5 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89511.44 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Counter Basin Work | 0.9 | 1750 | 0 | 1575 | 0 | 2023-08-16 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -89398.94 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-802-3BHK Umbra Patti -granite work | 11.187 | 41 | 0 | 458.667 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90515.273 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Umbra Patti -granite work | 11.187 | 44 | 0 | 492.228 | 0 | 2023-08-16 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90481.712 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2023-08-16 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90341.228 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-803-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-903-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Toilet door frame -granite work | 54.368 | 52.2 | 0 | 2838.0096 | 0 | 2024-01-10 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -142584.7204 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2103-2BHK Kitchen otta making | 10.232 | 494.2 | 0 | 5056.6544 | 0 | 2024-01-10 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104649 | 2024-01-20 | 145422.73 | 2024-02-02 14:26 | -140366.0756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-704-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-302-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41590.94 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-303-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-502-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-304-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41974.252 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-501-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41746.484 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1401-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-801-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90156.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-901-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1002-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-08-16 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90819.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-08-16 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101307 | 2023-08-18 | 90973.94 | 2023-09-04 11:30 | -90850.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-504-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41940.004 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1104-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1102-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1201-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41698.076 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1203-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -41905.756 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-601-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-602-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42246.7 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-904-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105045 | 2024-02-05 | 42408.06 | 2024-03-12 14:20 | -42293.9 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Window sill -granite work | 16.136 | 52.2 | 0 | 842.2992 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61133.9408 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-503-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1803-2BHK Counter Basin Work | 0.9 | 1875 | 0 | 1687.5 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60288.74 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2004-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61380.3248 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2001-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2002-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61821.92 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2104-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -61852.88 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176328.316 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1301-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1801-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1703-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1402-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1504-2BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1802-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2101-3BHK Counter Basin Work | 0.9 | 2130 | 0 | 1917 | 0 | 2024-03-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 105869 | 2024-03-11 | 61976.24 | 2024-03-18 12:08 | -60059.24 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Ledge wall top -grainte work | 12.336 | 47 | 0 | 579.792 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176473.828 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1704-2BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1602-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1004-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176374.612 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1302-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1604-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1404-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172346.9 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176236.5 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1503-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Kitchen otta making | 10.232 | 470 | 0 | 4809.04 | 0 | 2023-10-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -172244.58 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1101-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174661.428 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1501-3BHK Toilet -ventilator frame | 15.432 | 47 | 0 | 725.304 | 0 | 2023-10-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176328.316 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1601-3BHK Toilet door frame -granite work | 54.368 | 47 | 0 | 2555.296 | 0 | 2023-10-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -174498.324 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1303-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-10-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176930.26 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1403-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-1502-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-10-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102617 | 2023-10-14 | 177053.62 | 2023-10-28 11:59 | -176899.3 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2303-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26650.8848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2201-3BHK Window sill -granite work | 16.136 | 52.2 | 0 | 842.2992 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26404.5008 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2204-2BHK Window sill -granite work | 11.416 | 52.2 | 0 | 595.9152 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26650.8848 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | PAPPU BAGELA | 454 | 2022-06-30 | D-2301-3BHK Ledge wall top -grainte work | 12.336 | 52.2 | 0 | 643.9392 | 0 | 2024-04-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 106776 | 2024-04-15 | 27246.8 | 2024-05-03 13:25 | -26602.8608 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Ledge wall top -grainte work | 7.71 | 38 | 0 | 292.98 | 52.74 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318505.37 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Umbra Patti -granite work | 6.215 | 38 | 0 | 236.17 | 42.52 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318562.18 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317478.35 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5177.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33345.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1705-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Window sill -granite work | 11.416 | 49 | 0 | 559.384 | 100.69 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207319.996 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -29755.506 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -29755.506 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -39809.038 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Window sill -granite work | 12.843 | 38 | 0 | 488.034 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46361.286 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Ledge wall top -grainte work | 15.42 | 38 | 0 | 585.96 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46263.36 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46424.214 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Window sill -granite work | 18.153 | 38 | 0 | 689.814 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46159.506 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -42014.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-09-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41658.446 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-09-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41522.222 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42046.91 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -44525.088 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -27524.05 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31004.37 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 119.08 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207217.804 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 127.8 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207169.396 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 84.25 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207411.324 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Umbra Patti -granite work | 11.187 | 38 | 0 | 425.106 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46424.214 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Toilet door frame -granite work | 13.1579 | 38 | 0 | 500.0002 | 0 | 2023-08-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101221 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4499.9998 | PAWAR SHIVAPPA TARANAIK
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34527.484 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34459.244 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 84.25 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207411.324 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1705-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Ledge wall top -grainte work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 119.08 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207217.804 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Ledge wall top -grainte work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105872 | 2024-03-11 | 2622.03 | 2024-03-20 15:36 | -2116.254 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6015.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5996.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5333.68 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6027.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5333.68 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317478.35 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 127.8 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207169.396 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Umbra Patti -granite work | 9.944 | 49 | 0 | 487.256 | 87.71 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207392.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Umbra Patti -granite work | 9.944 | 49 | 0 | 487.256 | 87.71 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207392.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1705-3BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206259.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.21 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -203172.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6027.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5333.68 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.21 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -203172.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.21 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -203172.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Counter Basin Work | 0.9 | 1950 | 0 | 1755 | 315.9 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206124.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6027.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5333.68 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6015.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6015.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6027.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5996.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6015.44 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5996.48 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206259.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 84.25 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207411.324 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 119.08 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207217.804 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Window sill -granite work | 11.416 | 49 | 0 | 559.384 | 100.69 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207319.996 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 84.25 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207411.324 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Window sill -granite work | 16.136 | 49 | 0 | 790.664 | 142.32 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207088.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1705-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Window sill -granite work | 11.416 | 49 | 0 | 559.384 | 100.69 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207319.996 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Counter Basin Work | 0.1 | 1800 | 0 | 180 | 32.4 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207699.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Counter Basin Work | 0.1 | 1800 | 0 | 180 | 32.4 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207699.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Counter Basin Work | 0.9 | 1950 | 0 | 1755 | 315.9 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206124.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Window sill -granite work | 16.136 | 44 | 0 | 709.984 | 127.8 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207169.396 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Window sill -granite work | 16.136 | 49 | 0 | 790.664 | 142.32 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207088.716 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Counter Basin Work | 0.8 | 1800 | 0 | 1440 | 259.2 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206439.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Counter Basin Work | 0.9 | 1950 | 0 | 1755 | 315.9 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206124.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5177.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5208.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4862.712 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4862.712 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5177.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34286.012 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34332.308 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34557.316 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -32572.828 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33345.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Counter Basin Work | 0.9 | 1650 | 0 | 1485 | 267.3 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33480.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-27 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34147.9 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34527.484 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34527.484 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34557.316 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33345.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Counter Basin Work | 0.9 | 1650 | 0 | 1485 | 267.3 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33480.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34422.236 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33345.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-27 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34147.9 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Counter Basin Work | 0.9 | 1650 | 0 | 1485 | 267.3 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33480.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34422.236 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34332.308 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34459.244 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34422.236 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34527.484 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34286.012 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34557.316 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Counter Basin Work | 0.8 | 1800 | 0 | 1440 | 259.2 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206439.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4745.064 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5208.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5208.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4862.712 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4745.064 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4745.064 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Counter Basin Work | 0.9 | 1650 | 0 | 1485 | 267.3 | 2023-10-27 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -33480.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -27524.05 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31004.37 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31004.37 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -29755.506 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -29755.506 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-10-06 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31278.706 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -27524.05 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-10-06 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31383.954 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-09-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41658.446 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-09-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41384.11 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Counter Basin Work | 0.9 | 1500 | 0 | 1350 | 0 | 2023-03-18 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -45499.32 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5333.68 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5996.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6027.44 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34459.244 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1005-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 84.25 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207411.324 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 84.25 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207411.324 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206259.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206259.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Umbra Patti -granite work | 9.944 | 49 | 0 | 487.256 | 87.71 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207392.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317478.35 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317478.35 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.21 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -203172.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1806-3BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1808-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1508-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Umbra Patti -granite work | 9.944 | 49 | 0 | 487.256 | 87.71 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207392.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1705-3BHK Ledge wall top -grainte work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Counter Basin Work | 0.9 | 1950 | 0 | 1755 | 315.9 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206124.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Counter Basin Work | 0.9 | 1950 | 0 | 1755 | 315.9 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206124.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1607-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Counter Basin Work | 0.9 | 1800 | 0 | 1620 | 291.6 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206259.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 119.08 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207217.804 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 119.08 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207217.804 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1707-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2024-01-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207062.26 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-01-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207725.06 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.21 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -203172.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207441.844 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1505-3BHK Ledge wall top -grainte work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1705-3BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Ledge wall top -granite work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1807-2BHK Toilet door frame -granite work | 54.368 | 49 | 0 | 2664.032 | 479.53 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -205215.348 | S S ENTERISES (PROP. SOBRAN SINGH)
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1805-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -202968.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Umbra Patti -granite work | 9.944 | 49 | 0 | 487.256 | 87.71 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207392.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Umbra Patti -granite work | 9.944 | 49 | 0 | 487.256 | 87.71 | 2024-01-12 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207392.124 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1708-2BHK Toilet -ventilator frame | 15.432 | 49 | 0 | 756.168 | 136.11 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207123.212 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 119.08 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207217.804 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Window sill -granite work | 11.416 | 44 | 0 | 502.304 | 90.41 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207377.076 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Window sill -granite work | 11.416 | 49 | 0 | 559.384 | 100.69 | 2024-01-13 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207319.996 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 29.04 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207718.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-01-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207744.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34286.012 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34459.244 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -32572.828 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1006-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34332.308 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-10-27 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34810.7 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34422.236 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34286.012 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-10-27 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34332.308 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-907-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-10-27 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34557.316 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1007-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-906-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1008-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-10-27 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34829.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-905-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-10-27 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103064 | 2023-10-30 | 34965.02 | 2023-11-18 14:35 | -34841.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Toilet door frame -granite work | 33.98 | 38 | 0 | 1291.24 | 232.42 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317507.11 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Toilet door frame -granite work | 33.98 | 38 | 0 | 1291.24 | 232.42 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317507.11 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Umbra Patti -granite work | 6.215 | 38 | 0 | 236.17 | 42.52 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318562.18 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42065.87 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41763.694 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -39809.038 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Counter Basin Work | 0.8 | 1800 | 0 | 1440 | 259.2 | 2023-09-13 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -40761.23 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42046.91 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-09-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41522.222 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Counter Basin Work | 0.8 | 1800 | 0 | 1440 | 259.2 | 2023-09-13 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -40761.23 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -39809.038 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Counter Basin Work | 0.8 | 1800 | 0 | 1440 | 259.2 | 2023-09-13 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -40761.23 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -39809.038 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41763.694 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42077.87 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-09-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -37494.51 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42065.87 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Ledge wall top -granite work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32418.676 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 0 | 2024-03-06 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 105872 | 2024-03-11 | 2622.03 | 2024-03-20 15:36 | -1989.318 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 0 | 2024-03-06 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 105872 | 2024-03-11 | 2622.03 | 2024-03-20 15:36 | -2214.326 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14636.404 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14829.924 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317478.35 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14636.404 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14829.924 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 0 | 2023-05-04 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -5996.48 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2023-05-04 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 99425 | 2023-05-05 | 6150.8 | 2023-05-16 12:30 | -6015.44 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Toilet door frame -granite work | 33.98 | 38 | 0 | 1291.24 | 232.42 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317507.11 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Counter Basin Work | 0.8 | 1500 | 0 | 1200 | 216 | 2023-06-23 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317598.35 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-104-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Toilet door frame -granite work | 51.07 | 10 | 0 | 510.7 | 91.92 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318287.65 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318165.638 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Counter Basin Work | 0.8 | 1800 | 0 | 1440 | 259.2 | 2023-10-06 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -30381.49 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-10-06 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31142.482 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-10-06 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -27524.05 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-007-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-10-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 102395 | 2023-10-07 | 31821.49 | 2023-10-30 15:45 | -31004.37 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.21 | 2024-01-12 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -203172.66 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1605-3BHK Ledge wall top -grainte work | 12.336 | 49 | 0 | 604.464 | 108.8 | 2024-01-12 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207274.916 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1608-2BHK Counter Basin Work | 0.9 | 1950 | 0 | 1755 | 315.9 | 2024-01-12 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -206124.38 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-008-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4862.712 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-908-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 20.55 | 2024-01-13 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207765.22 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1507-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-01-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 104550 | 2024-01-15 | 207879.38 | 2024-02-05 11:42 | -207756.02 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5208.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-005-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -4745.064 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-006-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103249 | 2023-11-04 | 5331.48 | 2023-11-23 11:39 | -5177.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Umbra Patti -granite work | 6.215 | 38 | 0 | 236.17 | 42.52 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318562.18 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-107-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-204-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314500.91 | R.M.Marbles
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-11 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26098.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-805-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-11 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26079.52 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1107-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1108-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1408-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1307-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.59 | 2023-11-02 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -30569.268 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1406-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-02 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32144.34 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1308-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-11-02 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32807.14 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-11-02 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32838.1 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1407-2BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-11-02 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 103203 | 2023-11-02 | 32961.46 | 2023-11-22 11:30 | -32282.452 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14636.404 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-201-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-202-2BHK(Near Refuse Area) Window sill -granite work | 21.384 | 38 | 0 | 812.592 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14485.388 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-408-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14829.924 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-207-2BHK Window sill -granite work | 11.416 | 38 | 0 | 433.808 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14864.172 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-205-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Window sill -granite work | 16.136 | 41 | 0 | 661.576 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14636.404 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-305-3BHK Window sill -granite work | 16.136 | 38 | 0 | 613.168 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14684.812 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-607-2BHK Window sill -granite work | 11.416 | 41 | 0 | 468.056 | 0 | 2024-02-02 | Labour charges for Granite Cutting and Fixing for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -14829.924 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Window sill -granite work | 16.136 | 10 | 0 | 161.36 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15136.62 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Window sill -granite work | 11.416 | 10 | 0 | 114.16 | 0 | 2024-02-02 | Labour charges for Granite Edge Polish for Window Sill work for D-Bldg Internal Flats. | 100 |  | 105044 | 2024-02-05 | 15297.98 | 2024-03-12 14:20 | -15183.82 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-09-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -37494.51 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-09-13 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42065.87 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-09-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41384.11 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42077.87 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1207-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-09-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41384.11 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Toilet door frame -granite work | 61.164 | 38 | 0 | 2324.232 | 0 | 2023-03-18 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -44525.088 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-203-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Kitchen otta making | 11.511 | 420 | 0 | 4834.62 | 0 | 2023-03-18 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -42014.7 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Ledge wall top -granite work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1206-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-09-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -37494.51 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1208-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-09-13 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -37494.51 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-09-13 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42046.91 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-13 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -42077.87 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-102-3BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Umbra Patti -granite work | 9.944 | 44 | 0 | 437.536 | 78.76 | 2023-09-13 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41763.694 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-103-2BHK Toilet -ventilator frame | 17.361 | 38 | 0 | 659.718 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46189.602 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-106-3BHK Ledge wall top -grainte work | 13.878 | 38 | 0 | 527.364 | 0 | 2023-03-18 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 98824 | 2023-03-20 | 46849.32 | 2023-03-29 11:35 | -46321.956 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 105872 | 2024-03-11 | 2622.03 | 2024-03-20 15:36 | -2486.67 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 0 | 2024-03-06 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 105872 | 2024-03-11 | 2622.03 | 2024-03-20 15:36 | -1804.91 | PAPPU BAGELA
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Counter (L) | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Counter Basin Work | 0.8 | 1650 | 0 | 1320 | 237.6 | 2023-09-11 | Labour charges for fixing Granite Counter Basin for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -24913.84 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25728.064 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.89 | 2023-09-11 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25601.128 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-707-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.39 | 2023-09-11 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -25826.136 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-09-11 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101812 | 2023-09-12 | 26233.84 | 2023-09-30 11:37 | -26110.48 | S S ENTERISES (PROP. SOBRAN SINGH)
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Toilet door frame -granite work | 51.07 | 10 | 0 | 510.7 | 91.92 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318287.65 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Toilet door frame -granite work | 51.07 | 10 | 0 | 510.7 | 91.92 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318287.65 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Ledge wall top -grainte work | 7.71 | 10 | 0 | 77.1 | 13.88 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318721.25 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-706-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-708-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Ledge wall top -grainte work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-606-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-06-23 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -317981.23 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-806-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-808-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-307-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-705-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316569.262 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-108-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318420.478 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-105-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Kitchen Otta (L)- BC | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-807-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-06-23 | Labour charges for Kitchen Otta Making for Cooking Platform and Service Platform for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -314296.27 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-208-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -316732.366 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318211.934 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-506-3BHK Umbra Patti -granite work | 9.944 | 41 | 0 | 407.704 | 73.38 | 2023-06-23 | Labour charges for Granite cutting and Fixing for Umbra Patti work for Main Door and Toilet Door. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318390.646 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-206-3BHK Ledge wall top -grainte work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-508-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-605-3BHK Ledge wall top -grainte work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-507-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 0 | 2024-03-06 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 105872 | 2024-03-11 | 2622.03 | 2024-03-20 15:36 | -2498.67 | PAPPU BAGELA
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-406-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-505-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-101-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-407-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318329.582 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-608-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2023-06-23 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318292.574 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-306-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2023-06-23 | Labour charges for Granite Edge Polish work for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318644.03 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-308-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2023-06-23 | Labour charges for Granite Edge polish for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318674.99 | R.M.Marbles
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-405-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2023-06-23 | Labour charges for Granite Edge polish for Umbra Patti work for Main Door and Toilet Door D-Bldg. | 100 |  | 100277 | 2023-06-24 | 318798.35 | 2023-07-29 10:56 | -318662.99 | R.M.Marbles
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Ledge wall top -grainte work | 12.336 | 44 | 0 | 542.784 | 97.7 | 2023-09-13 | Labour charges for Granite Cutting and Fixing for Ledge Wall Top work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41658.446 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Toilet -ventilator frame | 15.432 | 44 | 0 | 679.008 | 122.22 | 2023-09-13 | Labour charges for Granite Cutting and Fixing for Toilet Ventilator work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41522.222 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | R.M.Marbles | 455 | 2022-06-30 | D-1205-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-09-13 | Labour charges for Granite Edge Polish for Toilet Door Frame work for D-Bldg Internal Flats. | 100 |  | 101851 | 2023-09-15 | 42201.23 | 2023-09-20 12:26 | -41384.11 | SUNIL CONSTRUCTION AND CONTRACTORS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 458 | 2022-07-01 | D-1st Fl-Lobby S.S. Railing Work | 69.76 | 85 | 0 | 5929.6 | 1067.32 | 2022-12-22 | Labour charges for Fixing of SS Railing for Common Lobby D-Building. | 100 |  | 97488 | 2022-12-23 | 5929.6 | 2023-01-14 11:08 | 0 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 459 | 2022-07-01 | D-1st Fl-Lobby S.S. Railing Work | 87.2 | 215 | 0 | 18748 | 3374.64 | 2022-12-22 | Material supply of SS Railing 304 Grade for Common Lobby D-Building. | 100 |  | 97489 | 2022-12-23 | 18748 | 2023-01-14 11:09 | 0 | HELIOS
Excavation - Mkt | N/C | N/C | PRAKASH CONTRACTOR | 46 | 2020-07-20 | Tower D Corner Points Grouting | 144 | 6.5 | 0 | 936 | 0 | 2020-12-04 | Excavation for Building Corner Point | 100 |  | 88301 | 2020-12-05 | 47338.45 | 2020-12-10 14:41 | -46402.45 | PRAKASH CONTRACTOR
Concrete Work - BCP | N/C | N/C | PRAKASH CONTRACTOR | 46 | 2020-07-20 | Tower D Corner Points Grouting | 4.08 | 299.88 | 0 | 1223.5104 | 0 | 2020-12-04 | Concreting work for Building Corner Point | 100 |  | 88301 | 2020-12-05 | 47338.45 | 2020-12-10 14:41 | -46114.9396 | PRAKASH CONTRACTOR
Concrete Work - BCP | N/C | N/C | PRAKASH CONTRACTOR | 46 | 2020-07-20 | Tower E Corner Points Grouting | 4.08 | 299.88 | 0 | 1223.5104 | 0 | 2020-12-04 | Concreting work for Building Corner Point | 100 |  | 88301 | 2020-12-05 | 47338.45 | 2020-12-10 14:41 | -46114.9396 | PRAKASH CONTRACTOR
Excavation - Mkt | N/C | N/C | PRAKASH CONTRACTOR | 46 | 2020-07-20 | Tower E Corner Points Grouting | 144 | 6.5 | 0 | 936 | 0 | 2020-12-04 | Excavation for Building Corner Point | 100 |  | 88301 | 2020-12-05 | 47338.45 | 2020-12-10 14:41 | -46402.45 | PRAKASH CONTRACTOR
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-005-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-001-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-002-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1306-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1308-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1302-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1303-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-008-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1402-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-004-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1301-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-006-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-007-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-504-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-501-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-203-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-405-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-003-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 11:45 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1304-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1305-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1307-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33796 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1401-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-09-02 15:27 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 101579 | 2023-09-04 | 35764 | 2023-12-25 15:33 | -33762 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-105-3BHK Terrace+Dry Balcony- Railing Work | 7.216 | 85 | 0 | 613.36 | 110.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17691.44 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-103-2BHK Terrace+Dry Balcony- Railing Work | 7.608 | 85 | 0 | 646.68 | 116.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17658.12 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-105-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16302.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-101-3BHK Terrace+Dry Balcony- Railing Work | 7.216 | 85 | 0 | 613.36 | 110.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17691.44 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1004-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-307-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1005-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1408-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1108-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-406-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1006-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1105-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-205-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1405-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-407-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-506-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-606-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-706-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-807-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1206-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-903-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-206-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-102-3BHK Terrace+Dry Balcony- Railing Work | 9.02 | 85 | 0 | 766.7 | 138 | 2022-11-10 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97014 | 2022-11-11 | 3269.2 | 1900-01-01 | -2502.5 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-107-2BHK Terrace+Dry Balcony- Railing Work | 7.608 | 85 | 0 | 646.68 | 116.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17658.12 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-108-2BHK Terrace+Dry Balcony- Railing Work | 7.608 | 85 | 0 | 646.68 | 116.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17658.12 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-104-2BHK Terrace+Dry Balcony- Railing Work | 7.608 | 85 | 0 | 646.68 | 116.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17658.12 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-104-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16336.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-303-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-607-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-403-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-508-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-601-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-604-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-304-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-306-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-802-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-302-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-308-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-204-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-305-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1208-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1403-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-608-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-701-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-704-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-207-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-301-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-904-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1003-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-605-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-901-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1204-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1407-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-505-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-808-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1203-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1205-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-201-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-401-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-602-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-906-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-907-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1008-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1101-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-603-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-805-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-806-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-905-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-908-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1102-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1104-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-402-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-803-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-804-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1103-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-208-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-408-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-703-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1001-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1107-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-404-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-507-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-705-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-801-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-902-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1007-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1406-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1106-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-106-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16302.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-502-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-503-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1002-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172610 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1207-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-1404-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2023-04-06 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 99018 | 2023-04-07 | 174612 | 2023-08-09 12:21 | -172644 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-102-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 250 | 0 | 2502.5 | 450.46 | 2022-11-10 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97014 | 2022-11-11 | 3269.2 | 1900-01-01 | -766.7 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-107-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16336.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-103-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16336.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-108-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16336.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-101-3BHK Terrace+Dry Balcony- Railing Work | 8.008 | 250 | 0 | 2002 | 360.36 | 2022-12-22 | Labour charges for Fixing of SS Railing for Living Terrace for D-Building. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -16302.8 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 460 | 2022-07-01 | D-106-3BHK Terrace+Dry Balcony- Railing Work | 7.216 | 85 | 0 | 613.36 | 110.4 | 2022-12-22 | Labour charges for Fixing of SS Railing for Dry Balcony for D-Bldg. | 100 |  | 97490 | 2022-12-23 | 18304.8 | 2023-01-23 18:37 | -17691.44 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1503-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1704-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1801-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1902-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2201-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-307-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-401-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1001-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-807-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1006-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-903-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-908-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1204-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1405-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1206-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1207-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-603-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-804-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1301-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1407-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1408-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1306-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1402-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-208-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-608-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-803-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1201-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-406-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-408-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-502-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-708-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-801-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-808-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1102-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1303-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1305-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-106-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100097.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-101-3BHK Terrace+Dry Balcony- Railing Work | 9.02 | 215 | 0 | 1939.3 | 349.08 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112672.7 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-106-3BHK Terrace+Dry Balcony- Railing Work | 9.02 | 215 | 0 | 1939.3 | 349.08 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112672.7 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-104-2BHK Terrace+Dry Balcony- Railing Work | 9.51 | 215 | 0 | 2044.65 | 368.04 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112567.35 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-107-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100344 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-103-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100344 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-108-2BHK Terrace+Dry Balcony- Railing Work | 9.51 | 215 | 0 | 2044.65 | 368.04 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112567.35 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-105-3BHK Terrace+Dry Balcony- Railing Work | 9.02 | 215 | 0 | 1939.3 | 349.08 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112672.7 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-101-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100097.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-104-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100344 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-108-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100344 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-103-2BHK Terrace+Dry Balcony- Railing Work | 9.51 | 215 | 0 | 2044.65 | 368.04 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112567.35 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-107-2BHK Terrace+Dry Balcony- Railing Work | 9.51 | 215 | 0 | 2044.65 | 368.04 | 2022-12-22 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -112567.35 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1103-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1203-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1403-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1404-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1108-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1307-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1308-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2206-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2407-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-402-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-604-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-805-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-806-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1004-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1007-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1208-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1205-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-405-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-605-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-105-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2022-12-22 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97491 | 2022-12-23 | 114612 | 2023-01-23 18:37 | -100097.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-002-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100615.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-003-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100862 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-005-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100615.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-006-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100615.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-008-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100862 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-001-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100615.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-007-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100862 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-004-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-09-02 15:30 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 101580 | 2023-09-04 | 115130 | 2023-12-25 15:33 | -100862 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-204-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-403-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1502-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-201-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-203-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-304-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-305-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-503-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-504-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-704-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-706-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-904-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-505-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-506-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-906-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-907-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1807-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1901-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2002-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2205-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-507-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1003-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-601-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-703-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-902-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1104-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1406-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-905-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1105-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1106-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1601-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1707-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2102-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-207-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-306-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-508-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1302-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-205-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-404-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-606-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1005-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1008-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-802-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-901-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1002-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1504-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1905-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2106-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2307-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2401-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1505-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1907-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1507-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2003-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2303-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2305-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2402-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-501-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-607-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-701-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1101-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-301-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-308-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-407-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-602-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1304-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1604-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1605-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1803-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2207-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2208-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2104-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2108-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2308-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-302-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-705-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1107-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1401-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1600 | 0 | 16016 | 2882.88 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553227.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1501-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1506-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2101-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2203-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2304-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1602-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1701-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2302-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2403-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-206-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554729 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1508-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1607-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1908-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1603-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1806-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2006-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2007-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1708-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1802-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1608-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2008-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1903-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2103-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2405-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2004-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2406-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-102-3BHK Terrace+Dry Balcony- Railing Work | 9.02 | 215 | 0 | 1939.3 | 349.08 | 2022-11-10 | Material Supply of SS Railing 304 Grade for Dry Balcony D-Building. | 100 |  | 97015 | 2022-11-11 | 20217.56 | 1900-01-01 | -18278.26 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-102-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1826 | 0 | 18278.26 | 3290.08 | 2022-11-10 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 97015 | 2022-11-11 | 20217.56 | 1900-01-01 | -1939.3 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1805-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2005-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-303-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1554975.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-707-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1600 | 0 | 15744 | 2833.92 | 2023-04-06 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 99019 | 2023-04-07 | 1569243.5 | 2023-08-09 17:04 | -1553499.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1706-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2107-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2306-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1705-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1904-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1906-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2105-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1606-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1804-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2301-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2408-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1703-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-1808-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2001-3BHK Terrace+Dry Balcony- Railing Work | 10.01 | 1750 | 0 | 17517.5 | 3153.16 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1336947.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2204-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 461 | 2022-07-01 | D-2404-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1750 | 0 | 17220 | 3099.6 | 2023-12-09 | Material supply of SS Railing 304 Grade for Living Terrace D-Bldg. | 100 |  | 103813 | 2023-12-11 | 1354465 | 2024-01-16 15:01 | -1337245 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1706-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1708-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1908-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2008-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1306-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1607-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1301-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1303-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1402-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1702-2BHK(Near Refuse Area) Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1902-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2006-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1001-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-304-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1201-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1304-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1503-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1701-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1901-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1903-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2005-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1203-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1302-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1905-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2103-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1601-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1603-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2004-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2106-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1205-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1207-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1406-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1707-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1102-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-303-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-305-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-604-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-605-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-805-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1208-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1408-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1305-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1808-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1105-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-606-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1004-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1104-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-607-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-806-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1502-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1507-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2101-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-307-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-401-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-507-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-601-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-702-2BHK(Near Refuse Area) Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-901-3BHK Int Flat MS Window Grill | 113.34 | 27.5 | 0 | 3116.85 | 561.04 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193244.7 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-903-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1008-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-002-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-105-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-503-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1704-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1803-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1904-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2104-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1605-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2108-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-005-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-007-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-006-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1801-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-008-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1005-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-402-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1007-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-501-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-703-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-602-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-701-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-708-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-801-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-803-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-902-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-407-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1604-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1806-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1807-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-308-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-808-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-907-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1401-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1508-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1703-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2105-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1006-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-108-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-908-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1307-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1308-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1606-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1608-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1805-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-004-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1101-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-201-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-301-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-302-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-608-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-802-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1504-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1505-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1506-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1705-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1907-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2102-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-001-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1407-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1501-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1106-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1108-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-206-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1202-2BHK(Near Refuse Area) Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1404-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-103-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-202-2BHK(Near Refuse Area) Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-506-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-704-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-705-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-603-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-804-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-807-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2002-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2003-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-203-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-205-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-403-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-505-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-707-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-003-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-101-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-204-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-404-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-405-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-706-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-904-2BHK Int Flat MS Window Grill | 75.56 | 27.5 | 0 | 2077.9 | 374.02 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194283.65 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1107-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-408-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1002-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1003-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1103-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-306-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1802-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2007-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1403-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1602-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1804-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-106-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-207-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-502-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-906-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-104-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-406-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-504-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-905-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -193868.07 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-107-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-508-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-10-10 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 102493 | 2023-10-11 | 196361.55 | 2023-12-25 18:25 | -194699.23 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1204-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2107-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1206-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1405-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-1906-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-2001-3BHK Int Flat MS Window Grill | 90.672 | 27.5 | 0 | 2493.48 | 448.82 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -165400.84 | HELIOS
Window Grill (L) | N/C | N/C | FURNITURE ZONE | 462 | 2022-07-01 | D-208-2BHK Int Flat MS Window Grill | 60.448 | 27.5 | 0 | 1662.32 | 299.22 | 2023-12-15 | Labour Charges for- Fixing of Internal Flat window MS Grill including all tools & equipments.Work to be done with proper Line, Level & Alignment as per drawing.Transporatation of raw materail from store to required working place to be done by contractor. | 100 |  | 104032 | 2023-12-18 | 167894.32 | 2024-01-16 15:05 | -166232 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-502-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1105-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-006-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-805-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-307-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-505-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-302-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-708-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-901-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-605-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-606-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-806-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-807-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-503-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-705-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-706-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1404-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1603-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1504-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1706-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2105-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1304-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1704-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1602-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1402-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1405-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1604-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2005-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1202-2BHK(Near Refuse Area) Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1204-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1002-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1102-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1104-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-306-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-506-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-703-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-904-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-905-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-001-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-407-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-603-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-804-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-008-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1107-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-402-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-601-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-608-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-201-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1003-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-305-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-504-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-704-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-906-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-907-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-108-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-301-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-303-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-103-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-005-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1001-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-401-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-508-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-607-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-205-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-801-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-207-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-208-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-203-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-204-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1004-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1005-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-107-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1108-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-304-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-701-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-802-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-903-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-106-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-404-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-507-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-202-2BHK(Near Refuse Area) Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-501-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-702-2BHK(Near Refuse Area) Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-808-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-902-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-908-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-206-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-11 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-007-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1006-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1101-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-104-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1206-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1307-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1406-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1303-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1403-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2004-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2006-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1701-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104031 | 2023-12-18 | 9350.55 | 1900-01-01 | 0 | FURNITURE ZONE
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1007-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-707-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-002-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-003-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-101-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1008-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1106-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-403-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-602-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1703-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1705-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2106-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1904-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1905-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2104-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2107-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2108-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1608-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2102-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1808-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2008-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1408-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1507-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1801-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1804-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1207-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1301-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1506-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1508-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2002-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2103-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1902-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2003-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1208-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1401-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1601-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1702-2BHK(Near Refuse Area) Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1707-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2001-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1205-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1306-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1308-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1802-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1807-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1903-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1201-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1606-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1803-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1805-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1806-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2007-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1407-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1501-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1607-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1708-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1901-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1302-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1305-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1502-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1503-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1505-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1906-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1907-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1908-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-2101-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1203-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -607785.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1605-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-12-15 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 104030 | 2023-12-18 | 614019.45 | 2024-01-16 15:05 | -604668.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-105-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-604-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-1103-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-308-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-406-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-004-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-405-3BHK Int Flat MS Window Grill | 113.34 | 82.5 | 0 | 9350.55 | 1683.1 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -729342.9 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-408-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Window Grill (M) | N/C | N/C | FURNITURE ZONE | 463 | 2022-07-01 | D-803-2BHK Int Flat MS Window Grill | 75.56 | 82.5 | 0 | 6233.7 | 1122.06 | 2023-10-10 | Material Supply Charges for- Internal Flat MS Window Grill work.Material Should Free From Bends,Cracks & Other Defects.Thickness and weight material as per requirement of GGG.Transportation,Loading & Unloading of raw material to be done by contractor. | 100 |  | 102538 | 2023-10-12 | 738693.45 | 2023-12-25 15:39 | -732459.75 | HELIOS
Labour Lumpsum | N/C | N/C | FURNITURE ZONE | 464 | 2022-07-01 | D-102-3BHK Int Sample - Flat Work | 1 | 2200 | 0 | 2200 | 396 | 2022-09-19 | Charges for- Providing and Fixing of MS Clit Angle for kitchen otta of Sample Flat no 102.Thickness and Weight of Angle as per requirement of GGG. | 100 |  | 96299 | 2022-09-20 | 17200 | 2022-12-31 12:00 | -15000 | FURNITURE ZONE
Labour Lumpsum | N/C | N/C | FURNITURE ZONE | 464 | 2022-07-01 | D-102-3BHK Int Sample - Flat Work | 1 | 15000 | 0 | 15000 | 2700 | 2022-09-19 | Charges for- Providing, Making & Fixing of MS Window Grill for Sample Flat 102. Including Transporatation, Powder Coating, Bullet Fastner+PVC Boost etc.Material Should be free from bends,Cracks & other Defects. | 100 |  | 96299 | 2022-09-20 | 17200 | 2022-12-31 12:00 | -2200 | FURNITURE ZONE
Aluminium work lumpsum-AIE | N/C | N/C | M.S. ENTERPRISES | 470 | 2022-07-09 | D-102-3BHK Alu. Sliding Window | 1 | 25000 | 0 | 25000 | 4500 | 2022-09-19 | Labour & Material Supply charges of Sample Flat D-102 for All Aluminium Window Work Including transportation,loading/unloading,mathadi.Material Should be free from any defect and damage.Fixing of Window as per Drawing in proper line,level & plumb. | 100 |  | 103410 | 2023-11-09 | 25000 | 2023-11-09 11:33 | 0 | M.S. ENTERPRISES
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2002-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2003-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1903-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1002-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1101-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1401-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-804-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1601-3BHK 3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-802-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-803-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-801-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-101-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99387 | 2023-05-03 | 1000 | 1900-01-01 | 0 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2204-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-303-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-502-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-401-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-402-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-403-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-503-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-601-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2004-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2103-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2304-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1902-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2104-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2302-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2101-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1904-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2001-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2201-3BHK 3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-002-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102405 | 2023-10-07 | 3000 | 2023-10-30 15:44 | -2000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-003-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102405 | 2023-10-07 | 3000 | 2023-10-30 15:44 | -2000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-001-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102405 | 2023-10-07 | 3000 | 2023-10-30 15:44 | -2000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-902-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1503-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1703-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1901-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2303-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1303-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-901-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1501-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1204-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1801-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1203-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1301-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-903-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-904-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1502-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1004-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1402-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1804-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1602-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1302-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1802-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1404-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2203-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-2301-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2024-01-10 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104545 | 2024-01-15 | 18000 | 2024-01-23 14:18 | -17000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-204-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100407 | 2023-07-01 | 3000 | 2023-07-26 12:45 | -2000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-201-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-06-30 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100407 | 2023-07-01 | 3000 | 2023-07-26 12:45 | -2000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-203-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100407 | 2023-07-01 | 3000 | 2023-07-26 12:45 | -2000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1701-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1704-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1403-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1504-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1803-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-404-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-602-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-603-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1104-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1603-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-301-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-504-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-304-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-501-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-604-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2022-10-14 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 96768 | 2022-10-15 | 15000 | 2022-10-17 19:38 | -14000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-701-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | PAPPU BAGELA | 473 | 2022-07-10 | D-1001-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 0 | 2023-05-03 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 99414 | 2023-05-04 | 37000 | 2023-05-16 12:31 | -36000 | PAPPU BAGELA
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2008-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2106-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-205-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-406-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-407-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-707-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-807-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-207-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-308-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-505-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-608-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1208-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-09-13 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 101850 | 2023-09-15 | 4000 | 2023-09-20 12:27 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1505-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1907-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1606-3BHK 3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2305-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2307-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1306-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2006-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2007-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-805-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-408-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-708-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-806-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-208-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-706-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-508-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1407-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-605-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-606-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-206-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-307-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-305-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-306-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-506-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1406-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1408-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1607-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1806-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1805-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1605-3BHK 3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-005-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102406 | 2023-10-07 | 4000 | 1900-01-01 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-006-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102406 | 2023-10-07 | 4000 | 1900-01-01 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1705-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1708-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-008-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102406 | 2023-10-07 | 4000 | 1900-01-01 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1807-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-007-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-10-06 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 102406 | 2023-10-07 | 4000 | 1900-01-01 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1107-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1108-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1307-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1308-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-02 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 103205 | 2023-11-02 | 7000 | 2023-11-18 14:36 | -6000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1405-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1905-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2306-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2108-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1908-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2207-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1106-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2107-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2206-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-607-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-808-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-405-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-705-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-07-01 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 100406 | 2023-07-01 | 27000 | 2023-07-26 12:45 | -26000 | R.M.Marbles
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1507-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1808-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1508-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1707-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1608-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-01-12 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 104552 | 2024-01-15 | 13000 | 2024-02-02 14:26 | -12000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2005-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1105-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1706-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1906-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2208-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2105-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2205-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-2308-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1305-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2024-02-20 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 107598 | 2024-05-15 | 27000 | 2024-05-15 17:10 | -26000 | S S ENTERISES (PROP. SOBRAN SINGH)
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1206-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-09-13 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 101850 | 2023-09-15 | 4000 | 2023-09-20 12:27 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1207-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-09-13 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 101850 | 2023-09-15 | 4000 | 2023-09-20 12:27 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | RAJESH MEHTA | 474 | 2022-07-10 | D-1205-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-09-13 | Labour and Material Supply Charges for- MS Angle Support for Kitchen otta work.FIxing of Angle as per Drawing in Plumb & Line.Transporatation of material,Loading/Unloading,Mathadi in Contractor Scope.Material Should be free from any Defect & Damage. | 100 |  | 101850 | 2023-09-15 | 4000 | 2023-09-20 12:27 | -3000 | SUNIL CONSTRUCTION AND CONTRACTORS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 22nd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | P2 Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 2nd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | Ground Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | P1 Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 10th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 5th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 7th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 9th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 14th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | P3 Floor Lift Duct Cement Paint | 131 | 2 | 0 | 262 | 47.16 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6702 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 12th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 21st Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 23rd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 1st Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 20th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | P5 Floor Lift Duct Cement Paint | 117 | 2 | 0 | 234 | 42.12 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6730 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 13th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 24th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 6th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 8th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | LG Floor Lift Duct Cement Paint | 172 | 2 | 0 | 344 | 61.92 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6620 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 11th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 3rd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 4th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 16th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | Stilt Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 18th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 19th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | Terrace Floor Lift Duct Cement Paint | 65 | 2 | 0 | 130 | 23.4 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6834 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 475 | 2022-07-10 | 17th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Labour charges for 2 Coat Cement Paint for D-Building Lift Duct. | 100 |  | 104244 | 2024-01-01 | 6964 | 2024-03-18 12:10 | -6742 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 14th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 7th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 8th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 11th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | Stilt Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 22nd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | P2 Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 17th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | P5 Floor Lift Duct Cement Paint | 117 | 2 | 0 | 234 | 42.12 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6952 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 16th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 1st Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | P1 Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 18th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 5th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 6th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 10th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 9th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 24th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 3rd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | Ground Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 20th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 21st Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 23rd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | P3 Floor Lift Duct Cement Paint | 131 | 2 | 0 | 262 | 47.16 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6924 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | Terrace Floor Lift Duct Cement Paint | 65 | 2 | 0 | 130 | 23.4 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -7056 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | LG Floor Lift Duct Cement Paint | 172 | 2 | 0 | 344 | 61.92 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6842 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 12th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 13th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 15th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 19th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 2nd Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 476 | 2022-07-10 | 4th Floor Lift Duct Cement Paint | 111 | 2 | 0 | 222 | 39.96 | 2023-12-30 | Material Supply for 2 Coat Cement Paint work for D-Building Lift Duct. | 100 |  | 104245 | 2024-01-01 | 7186 | 2024-03-18 12:11 | -6964 | TEJASHREE ENTERPRISES
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P2-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-01 | Labour Charges for- Ghadai Work with hammer,Chisel,Breaker etc. to prepare plain floor surface,including cleaning,shifting debris at one place including all tools & equipments required. | 100 |  | 107913 | 2024-06-03 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P1-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-01 | Labour Charges for- Ghadai Work with hammer,Chisel,Breaker etc. to prepare plain floor surface,including cleaning,shifting debris at one place including all tools & equipments required. | 100 |  | 107913 | 2024-06-03 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P5 Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-01 | Labour Charges for- Ghadai Work with hammer,Chisel,Breaker etc. to prepare plain floor surface,including cleaning,shifting debris at one place including all tools & equipments required. | 100 |  | 107913 | 2024-06-03 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | F-Bldg 2nd Floor Chemical Grouting Work | 2000 | 2 | 0 | 4000 | 0 | 2024-02-12 | Labour Charges for Chemical Grouting work for F Building internal area. | 100 |  | 105289 | 2024-02-12 | 4000 | 2024-03-18 12:03 | 0 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | F-Bldg 1st Floor Chemical Grouting Work | 1498.14 | 2 | 0 | 2996.28 | 0 | 2023-08-17 14:53 | Labour Charges for Chemical Grouting work for F Building internal area. | 100 |  | 101312 | 2023-08-18 | 5992.56 | 2023-09-04 11:45 | -2996.28 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | Ground Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-01 | Labour Charges for- Ghadai Work with hammer,Chisel,Breaker etc. to prepare plain floor surface,including cleaning,shifting debris at one place including all tools & equipments required. | 100 |  | 107913 | 2024-06-03 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | F-Bldg 1st Floor Chemical Grouting Work | 1498.14 | 2 | 0 | 2996.28 | 0 | 2023-08-17 14:53 | Ghadai work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface,including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 101312 | 2023-08-18 | 5992.56 | 2023-09-04 11:45 | -2996.28 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | F-Bldg 1st Floor Chemical Grouting Work | 2563.8984 | 2 | 0 | 5127.7968 | 0 | 2023-10-06 09:52 | Labour Charges for Chemical Grouting work for F Building internal area. | 100 |  | 102352 | 2023-10-06 | 10255.6 | 2023-10-28 11:57 | -5127.8032 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P1-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Labour Charges for- Chemical Grouting work of D building Parking Area. | 100 |  | 108195 | 2024-06-10 | 2860 | 2024-08-05 14:02 | -2288 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P5 Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Labour Charges for- Chemical Grouting work of D building Parking Area. | 100 |  | 108195 | 2024-06-10 | 2860 | 2024-08-05 14:02 | -2288 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | Ground Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Labour Charges for- Chemical Grouting work of D building Parking Area. | 100 |  | 108195 | 2024-06-10 | 2860 | 2024-08-05 14:02 | -2288 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | F-Bldg 2nd Floor Chemical Grouting Work | 2000 | 2 | 0 | 4000 | 0 | 2024-02-02 | Ghadai work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface,including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 105041 | 2024-02-05 | 4000 | 2024-03-18 12:03 | 0 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P3-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-01 | Labour Charges for- Ghadai Work with hammer,Chisel,Breaker etc. to prepare plain floor surface,including cleaning,shifting debris at one place including all tools & equipments required. | 100 |  | 107913 | 2024-06-03 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P3-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Labour Charges for- Chemical Grouting work of D building Parking Area. | 100 |  | 108195 | 2024-06-10 | 2860 | 2024-08-05 14:02 | -2288 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | F-Bldg 1st Floor Chemical Grouting Work | 2563.8984 | 2 | 0 | 5127.7968 | 0 | 2023-10-06 09:52 | Ghadai work with Hammer, Chisel, Breaker, etc. to Prepare Plain Floor Surface,including cleaning, shifting debris at one place includingall lead & lift. with all tools & equipments required. | 100 |  | 102352 | 2023-10-06 | 10255.6 | 2023-10-28 11:57 | -5127.8032 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | AJAY KUMAR GUPTA | 477 | 2022-07-10 | P2-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Labour Charges for- Chemical Grouting work of D building Parking Area. | 100 |  | 108195 | 2024-06-10 | 2860 | 2024-08-05 14:02 | -2288 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | F-Bldg 2nd Floor Chemical Grouting Work | 2000.5 | 2 | 0 | 4001 | 0 | 2024-03-22 | Material Supply Charges for Chemical Grouting work of internal area of F Building. | 100 |  | 106364 | 2024-03-22 | 4001 | 2024-03-26 14:53 | 0 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | P5 Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Material Supply charges for- Chemical Grouting work for D Building Parking area.Tansporatation of Material loading/Unloading and mathadi in contractor scope. | 100 |  | 108193 | 2024-06-10 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | P1-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Material Supply charges for- Chemical Grouting work for D Building Parking area.Tansporatation of Material loading/Unloading and mathadi in contractor scope. | 100 |  | 108193 | 2024-06-10 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | Ground Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Material Supply charges for- Chemical Grouting work for D Building Parking area.Tansporatation of Material loading/Unloading and mathadi in contractor scope. | 100 |  | 108193 | 2024-06-10 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | P3-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Material Supply charges for- Chemical Grouting work for D Building Parking area.Tansporatation of Material loading/Unloading and mathadi in contractor scope. | 100 |  | 108193 | 2024-06-10 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | F-Bldg 1st Floor Chemical Grouting Work | 1498.14 | 2 | 0 | 2996.28 | 0 | 2023-08-17 15:01 | Material Supply Charges for Chemical Grouting work of internal area of F Building. | 100 |  | 101314 | 2023-08-18 | 2996.28 | 2023-09-04 11:44 | 0 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | P2-Floor Common Lobby Chemical Grouting Work | 286 | 2 | 0 | 572 | 0 | 2024-06-06 | Material Supply charges for- Chemical Grouting work for D Building Parking area.Tansporatation of Material loading/Unloading and mathadi in contractor scope. | 100 |  | 108193 | 2024-06-10 | 2860 | 2024-08-05 14:03 | -2288 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | AJAY KUMAR GUPTA | 478 | 2022-07-11 | F-Bldg 1st Floor Chemical Grouting Work | 2563.8984 | 2 | 0 | 5127.7968 | 0 | 2023-10-06 10:02 | Material Supply Charges for Chemical Grouting work of internal area of F Building. | 100 |  | 102353 | 2023-10-06 | 5127.8 | 2023-10-28 11:58 | -0.0032 | PRABHURAM VERMA
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2306-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1908-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2001-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2106-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-108-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-105-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-305-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-506-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1107-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1108-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1004-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1902-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2003-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1506-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1607-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1602-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1306-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14637.52 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1801-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2008-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1507-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1407-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1408-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1404-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107240 | 2024-04-30 | 1964.16 | 2024-05-03 13:23 | -1636.8 | BHARAT KASHINATH KARCHE
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-502-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-601-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-805-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-503-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-604-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-804-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-905-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1608-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1904-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1504-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1907-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2004-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2201-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1503-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1505-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1508-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1501-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1502-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1601-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1603-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107410 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-607-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1101-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1104-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1008-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1201-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-308-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-603-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-704-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-803-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1302-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1402-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-303-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-504-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-508-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1006-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2202-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1903-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1803-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1901-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2005-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2006-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2102-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2203-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2303-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1706-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2204-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1303-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-403-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-605-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-808-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-304-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-306-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-801-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-802-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-904-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-402-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-706-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1203-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1205-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-707-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-708-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1207-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-405-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-407-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-702-2BHK(Near Refuse Area) Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-901-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-902-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-102-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2103-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1905-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2101-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1806-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1807-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1808-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2007-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2206-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2208-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2301-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-401-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-806-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1202-2BHK(Near Refuse Area) Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1403-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-307-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-301-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1007-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1204-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-606-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-807-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-501-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-705-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-505-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-507-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1005-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1301-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-404-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-903-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2302-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2002-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2105-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1805-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-2207-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14478.92 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1906-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-07-31 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109505 | 2024-08-05 | 14806.28 | 2024-08-08 11:15 | -14468.76 | G M ENTERPRISES
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1208-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-602-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-703-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-907-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-908-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1001-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-1206-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-408-2BHK Toilet Cement Paint | 147.312 | 2 | 0 | 294.624 | 53.04 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22131.276 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-906-3BHK Toilet Cement Paint | 151.884 | 2 | 0 | 303.768 | 54.68 | 2023-12-02 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103607 | 2023-12-04 | 22425.9 | 2023-12-16 17:33 | -22122.132 | CITY PAINTS
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-103-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-104-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-106-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-101-3BHK Toilet Cement Paint | 135.008 | 2 | 0 | 270.016 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1857.624 | YUGESH KUMAR
Cement Paint (L)- BC | N/C | N/C | YUGESH KUMAR | 479 | 2022-07-11 | D-107-2BHK Toilet Cement Paint | 130.944 | 2 | 0 | 261.888 | 0 | 2023-05-18 | Labour charges for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99712 | 2023-05-19 | 2127.64 | 2023-06-10 10:34 | -1865.752 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-306-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-505-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-808-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-605-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-807-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-906-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-707-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1001-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1403-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-507-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-802-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-804-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1007-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-301-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-303-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-508-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-803-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-405-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-806-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1205-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1207-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-408-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-502-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-705-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-903-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2002-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2008-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2304-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1803-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2107-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2108-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1801-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2208-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1905-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2206-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2203-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2104-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2201-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2305-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2207-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1903-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1504-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1505-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1607-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1603-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1902-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1502-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1506-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-106-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-108-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-101-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-105-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-102-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2322 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-308-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-604-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-907-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1302-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1303-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1104-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-905-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1202-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1204-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1005-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1006-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1301-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-402-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-506-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-607-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1004-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1107-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1402-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1501-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2003-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2101-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1808-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2103-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2306-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1908-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1305-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:41 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1906-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1807-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2006-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2106-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2307-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2308-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1706-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1901-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2303-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1805-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1601-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1507-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1904-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1503-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1508-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1602-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4971.36 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-708-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1101-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1404-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1304-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1408-2BHK Toilet Cement Paint | 163.5 | 2 | 0 | 327 | 0 | 2024-03-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.44 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1407-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2024-03-17 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.08 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1308-2BHK Toilet Cement Paint | 163.5 | 2 | 0 | 327 | 0 | 2024-03-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107228 | 2024-04-30 | 1963.44 | 2024-05-03 13:23 | -1636.44 | BHARAT KASHINATH KARCHE
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2202-2BHK(Near Refuse Area) Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1907-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2001-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:31 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-307-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-706-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-901-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1206-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1208-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-305-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-401-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-601-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-602-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-805-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-501-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-702-2BHK(Near Refuse Area) Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-902-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-904-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1008-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-404-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-504-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-603-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-908-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1608-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2024-05-06 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 107412 | 2024-05-07 | 5308.88 | 2024-06-03 12:35 | -4981.52 | TEJASHREE ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-403-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-503-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-407-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-703-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-704-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1201-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-1203-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 58.92 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24590.4 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-103-2BHK Toilet Cement Paint | 163.68 | 2 | 0 | 327.36 | 0 | 2023-05-18 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 99713 | 2023-05-19 | 2659.52 | 2023-06-10 10:34 | -2332.16 | YUGESH KUMAR
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2204-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2105-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2005-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2301-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2302-3BHK Toilet Cement Paint | 84.38 | 2 | 0 | 168.76 | 30.38 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6812.48 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2007-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-606-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-801-3BHK Toilet Cement Paint | 168.76 | 2 | 0 | 337.52 | 60.76 | 2023-12-02 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 103606 | 2023-12-04 | 24917.76 | 2023-12-16 17:33 | -24580.24 | CITY PAINTS
Cement Paint (M)- BC | N/C | N/C | YUGESH KUMAR | 480 | 2022-07-11 | D-2004-2BHK Toilet Cement Paint | 81.84 | 2 | 0 | 163.68 | 29.46 | 2024-07-31 17:23 | Material supply for 2 coat Cement Paint work for D-Building Internal Flat Toilets. | 100 |  | 109506 | 2024-08-05 | 6981.24 | 2024-08-08 11:17 | -6817.56 | G M ENTERPRISES
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 2nd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour Charges for Ghadai work for 2nd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F- Bldg Common Lobby Stilt Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for Stilt Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common LobbyTerrace Floor Chemical Grouting Work | 90.89 | 2 | 0 | 181.78 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for Terrace Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14947.18 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 1st Floor Chemical Grouting Work | 2261.21 | 2 | 0 | 4522.42 | 0 | 2023-08-17 14:44 | Labour Charges for Ghadai work for 1st Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -10606.54 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 2nd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for 2nd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 3rd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour Charges for Ghadai work for 3rd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F- Bldg Common Lobby Stilt Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 14:27 | Labour Charges for Ghadai work for Stilt Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Ghadai work- BCP | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common LobbyTerrace Floor Chemical Grouting Work | 90.89 | 2 | 0 | 181.78 | 0 | 2023-08-17 17:34 | Labour Charges for Ghadai work for Terrace Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14947.18 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 1st Floor Chemical Grouting Work | 2266.21 | 2 | 0 | 4532.42 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for 1st Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -10596.54 | PRABHURAM VERMA
Chemical Grouting (L) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 484 | 2022-07-11 | F-Bldg Common Lobby 3rd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:34 | Labour charges for Chemical Grouting work for 3rd Floor F-Bldg Common Lobby. | 100 |  | 101309 | 2023-08-18 | 15128.96 | 2023-09-04 11:45 | -14177.2 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common Lobby 3rd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:45 | Material supply for Chemical Grouting work for 3rd Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -6617.72 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common Lobby 1st Floor Chemical Grouting Work | 2266.21 | 2 | 0 | 4532.42 | 0 | 2023-08-17 14:49 | Material supply for Chemical Grouting work for 1st Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -3037.06 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common Lobby 2nd Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 17:45 | Material supply for Chemical Grouting work for 2nd Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -6617.72 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F- Bldg Common Lobby Stilt Floor Chemical Grouting Work | 475.88 | 2 | 0 | 951.76 | 0 | 2023-08-17 14:49 | Material supply for Chemical Grouting work for Stilt Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -6617.72 | PRABHURAM VERMA
Chemical Grouting (M) | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 485 | 2022-07-11 | F-Bldg Common LobbyTerrace Floor Chemical Grouting Work | 90.89 | 2 | 0 | 181.78 | 0 | 2023-08-17 17:45 | Material supply for Chemical Grouting work for Terrace Floor F-Bldg Common Lobby. | 100 |  | 101311 | 2023-08-18 | 7569.48 | 2023-09-04 11:44 | -7387.7 | PRABHURAM VERMA
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 11th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 9th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 19th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 12th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 14th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 24th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 23rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 22nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-29 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 109437 | 2024-07-29 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 10th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 18th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 17th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 21st Floor | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-27 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104862 | 2024-01-29 | 13000 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - Stilt Floor | 1 | 13000 | 0 | 13000 | 2340 | 2022-09-27 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 96393 | 2022-09-28 | 13000 | 1900-01-01 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 8th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 1st Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 20th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 13th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 15th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 16th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-12-23 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 104110 | 2023-12-25 | 169000 | 1900-01-01 | -156000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 3rd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 2nd Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 4th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-03-18 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 98823 | 2023-03-20 | 52000 | 1900-01-01 | -39000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 6th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-22 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 99749 | 2023-05-23 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 5th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-22 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 99749 | 2023-05-23 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Sleeve Fixing Work | No category | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 486 | 2022-07-14 | Sleeve Fixing Work - 7th Floor | 1 | 13000 | 0 | 13000 | 2340 | 2023-05-22 | Labour charges for Sleeve Fixing work for AC, Plumbing and Fire Fighting work for E-Building. | 100 |  | 99749 | 2023-05-23 | 39000 | 1900-01-01 | -26000 | HARISH CHANDRA JADHAV ELECTRICALS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37864.818 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -103112.504 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13560.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Vitrified Flooring Work | 101 | 2 | 0 | 202 | 0 | 2024-03-22 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14377.8 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 33.368 | 2 | 0 | 66.736 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.784 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14292.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114059.564 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -113600.14 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -34300.418 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -38572.834 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -38572.834 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 210.56 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37864.818 | SUNIL CONSTRUCTION AND CONTRACTORS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388417.316 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388417.316 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390460.572 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110339.118 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108518.662 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-05-17 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -98918.734 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -103112.504 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Flooring Work | 70 | 18 | 0 | 1260 | 0 | 2023-10-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102548 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260 | PAWAR SHIVAPPA TARANAIK
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1003-2BHK Vitrified Flooring Work | 70 | 18 | 0 | 1260 | 0 | 2023-10-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102548 | 2023-10-12 | 2520 | 2023-11-24 10:35 | -1260 | PAWAR SHIVAPPA TARANAIK
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -100298.264 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -103112.504 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108093.112 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108910.84 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2024-03-06 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -110357.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108910.84 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61364.524 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Skirting | 76.2 | 20 | 0 | 1524 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60139.66 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-202-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -56929.468 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-202-2BHK(Near Refuse Area) Flooring & Tiling Work | 57.864 | 13 | 0 | 752.232 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60911.428 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -55141.292 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -95910.69 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -107760.808 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -107760.808 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -165075.296 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169730.72 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172276.248 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -108093.112 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170218.4 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170218.4 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172206.824 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99603.922 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101532.29 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99870.866 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101732.154 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100187.066 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96409.026 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -95910.69 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101532.29 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-10-10 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -92499.666 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100664.394 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96409.026 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99870.866 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -90551.906 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92039.17 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100723.826 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99870.866 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101809.266 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-09-26 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -62724.33 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Toilet Dado Work | 62.1053 | 19 | 0 | 1180.0007 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3819.9993 | PAWAR SHIVAPPA TARANAIK
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-202-2BHK(Near Refuse Area) Vitrified Skirting | 148.744 | 18 | 0 | 2677.392 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109403.368 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186023.366 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187733.398 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190992.13 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -189863.65 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -381046.116 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390127.348 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384955.476 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-702-2BHK(Near Refuse Area) Vitrified Flooring Work | 465.536 | 16 | 0 | 7448.576 | 0 | 2024-03-06 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -104632.184 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100664.394 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96495.322 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101580.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100664.394 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100600.69 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101809.266 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-10-10 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -92499.666 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101809.266 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11581.92 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10576.68 | MARSH HOUSEKEEPING SOLUTIONS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100187.066 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96495.322 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101732.154 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -99603.922 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-10-10 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -101732.154 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100723.826 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96495.322 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-10-10 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100187.066 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -96409.026 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100723.826 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-10-10 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 102497 | 2023-10-11 | 102139.89 | 2023-10-28 11:58 | -100600.69 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -222406.654 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234040.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-703-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233983.014 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234040.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232585.35 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233581.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1202-2BHK(Near Refuse Area) Vitrified Flooring Work | 465.536 | 18 | 0 | 8379.648 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225809.502 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233581.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233963.382 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232585.35 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389270.276 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2301-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-05-17 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -98918.734 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108165.262 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-11-02 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -31536.658 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 852.16 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -34300.418 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-002-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-11-02 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37299.474 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 83.12 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -38572.834 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 839.32 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -34371.706 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Comm Passage wash basin-Dado Work | 5.944 | 27 | 0 | 160.488 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234028.662 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -229035.414 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233727.374 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228053.75 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383188.388 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388004.1 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1003-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389210.844 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384955.476 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2022-08-17 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114301.364 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-08-17 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -112803.964 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234040.55 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233678.766 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233019.358 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Comm Passage wash basin-Dado Work | 5.944 | 27 | 0 | 160.488 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234028.662 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Toilet Dado Work | 245.416 | 27 | 0 | 6626.232 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227562.918 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -234052.438 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233963.382 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227959.95 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1702-2BHK(Near Refuse Area) Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59940.58 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60316.468 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -186664.322 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190748.29 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -63749.098 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-09-26 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -57420.938 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -185688.738 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -185688.738 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187479.618 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -184617.602 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -182561.526 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -189863.65 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -178652.166 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191451.554 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -178652.166 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -184617.602 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-01-04 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -186664.322 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190195.954 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1202-2BHK(Near Refuse Area) Vitrified Skirting | 148.744 | 22 | 0 | 3272.368 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107428.862 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2023-11-02 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -31536.658 | SUNIL CONSTRUCTION AND CONTRACTORS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16240.6 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -16560.4 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14292.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114575.812 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115464.628 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -108296.748 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2022-08-17 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -114624.908 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2022-08-17 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -115527.052 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 0 | 2022-08-17 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 96030 | 2022-08-27 | 115794.7 | 2022-08-27 13:36 | -110087.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191451.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192856.618 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192856.618 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191893.762 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191893.762 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191463.61 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192016.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186023.366 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191451.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2022-09-26 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64588.818 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108518.662 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2023-12-01 | Labour Charges for- Vitrified Flooring work with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103604 | 2023-12-04 | 5707.07 | 2023-12-11 14:13 | 0.002 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92854.466 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2024-02-26 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -98456.994 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2024-02-26 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -98239.306 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111750.136 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111718.648 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109398.52 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2024-03-06 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -109154.68 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2024-03-06 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 105868 | 2024-03-11 | 112080.76 | 2024-03-20 15:38 | -111634.192 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -162772.736 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Vitrified Skirting | 166.152 | 20 | 0 | 3323.04 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169089.92 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92039.17 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -92039.17 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -89480.77 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -89480.77 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -91223.874 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383348.676 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1303-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388004.1 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387695.604 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388004.1 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1802-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1103-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388733.516 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Flooring & Tiling Work | 133.472 | 19 | 0 | 2535.968 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388150.372 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1302-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390278.604 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390278.604 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Vitrified Skirting | 166.152 | 24 | 0 | 3987.648 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -386698.692 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390239.772 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390356.268 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59940.58 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61294.756 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61294.756 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2022-12-12 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -61364.524 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60370.732 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1404-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383348.676 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Vitrified Flooring Work | 407.648 | 20 | 0 | 8152.96 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -382533.38 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390549.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59661.58 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Vitrified Skirting | 76.2 | 20 | 0 | 1524 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60139.66 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1803-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59661.58 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -55141.292 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2023-12-05 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390324.228 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384550.94 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389147.14 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387030.996 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 0 | 2022-12-12 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59928.524 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -53094.572 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1601-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390549.628 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1401-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389270.276 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Vitrified Skirting | 121.92 | 24 | 0 | 2926.08 | 0 | 2023-12-05 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -387760.26 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2023-12-05 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -388503.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Kitchen Dado Work | 24.304 | 25 | 0 | 607.6 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390078.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191839.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186876.326 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172113.824 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -168757.616 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166768.392 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170460.136 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Flooring & Tiling Work | 114.872 | 17 | 0 | 1952.824 | 0 | 2023-08-13 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170460.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Comm Passage wash basin-Dado Work | 5.944 | 19 | 0 | 112.936 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172300.024 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Skirting | 45.72 | 20 | 0 | 914.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171498.56 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Vitrified Skirting | 121.92 | 22 | 0 | 2682.24 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169730.72 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172187.192 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170996.896 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107045.886 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Living Terrace Skirting | 19.416 | 25 | 0 | 485.4 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110215.83 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Living Terrace Skirting | 15.744 | 25 | 0 | 393.6 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110307.63 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Flooring & Tiling Work | 133.472 | 21 | 0 | 2802.912 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107898.318 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Comm Passage wash basin-Dado Work | 5.944 | 21 | 0 | 124.824 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172288.136 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170218.4 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1001-3BHK Vitrified Skirting | 166.152 | 22 | 0 | 3655.344 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling.Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -168757.616 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Comm Passage wash basin-Dado Work | 5.944 | 23 | 0 | 136.712 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172276.248 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1101-3BHK Toilet Dado Work | 249.168 | 23 | 0 | 5730.864 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -166682.096 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Living Terrace Skirting | 15.744 | 21 | 0 | 330.624 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172082.336 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Vitrified Skirting | 62.307 | 20 | 0 | 1246.14 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171166.82 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Comm Passage wash basin-Dado Work | 9.816 | 19 | 0 | 186.504 | 0 | 2023-08-13 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172226.456 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1203-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -171853.968 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172044.056 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1201-3BHK Living Terrace Skirting | 19.416 | 21 | 0 | 407.736 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172005.224 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-08-13 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -165075.296 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-08-13 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -169974.56 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2023-08-13 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -170937.464 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-08-13 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 101245 | 2023-08-14 | 172412.96 | 2023-08-23 18:29 | -172113.824 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Vitrified Skirting | 121.92 | 26 | 0 | 3169.92 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -107531.31 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Living Terrace Skirting | 19.416 | 23 | 0 | 446.568 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110254.662 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Living Terrace Skirting | 15.744 | 23 | 0 | 362.112 | 0 | 2024-05-18 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -110339.118 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Vitrified Skirting | 166.152 | 26 | 0 | 4319.952 | 0 | 2024-05-18 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -106381.278 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2203-2BHK Flooring & Tiling Work | 114.872 | 21 | 0 | 2412.312 | 0 | 2024-05-18 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 107655 | 2024-05-20 | 110701.23 | 2024-06-15 11:47 | -108288.918 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 0 | 2022-09-26 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -62724.33 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60184.698 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -64457.114 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2022-09-26 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 96385 | 2022-09-27 | 64918.89 | 2022-10-17 11:22 | -60255.986 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -89480.77 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Flooring & Tiling Work | 114.872 | 19 | 0 | 2182.568 | 0 | 2024-02-26 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -98009.562 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2001-3BHK Vitrified Flooring Work | 535.568 | 22 | 0 | 11782.496 | 0 | 2024-02-26 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 105585 | 2024-02-26 | 100192.13 | 2024-03-18 12:05 | -88409.634 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5558.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-603-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -187954.162 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192016.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2022-12-12 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -53094.572 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60316.468 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Vitrified Skirting | 103.845 | 20 | 0 | 2076.9 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59586.76 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-602-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2022-12-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -60370.732 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -58672.924 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Skirting | 103.845 | 20 | 0 | 2076.9 | 0 | 2022-12-12 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97361 | 2022-12-13 | 61663.66 | 2022-12-31 11:27 | -59586.76 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191184.61 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192856.618 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192919.042 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-502-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192817.786 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192887.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Flooring & Tiling Work | 61.568 | 19 | 0 | 1169.792 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192016.898 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188032.954 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-903-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Skirting | 166.152 | 18 | 0 | 2990.736 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190195.954 | PAPPU BAGELA
Vitrified Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 0 | 2023-01-04 | Labour Charges for- Vitrified Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -190748.29 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191184.61 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186945.198 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Flooring & Tiling Work | 61.568 | 23 | 0 | 1416.064 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186876.326 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186569.31 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-06-02 12:57 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -10896.48 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1604-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1204-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-06-02 15:35 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 107942 | 2024-06-03 | 11915.6 | 2024-06-26 11:42 | -11628.42 | MARSH HOUSEKEEPING SOLUTIONS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2304-2BHK Vitrified Flooring Work | 407.648 | 22 | 0 | 8968.256 | 0 | 2024-04-11 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -225220.894 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Toilet Dado Work | 62.1053 | 19 | 0 | 1180.0007 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3819.9993 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Toilet Dado Work | 61.0526 | 19 | 0 | 1159.9994 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3840.0006 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2201-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1903-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233943.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Comm Passage wash basin-Dado Work | 9.816 | 21 | 0 | 206.136 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233983.014 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -229454.958 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1904-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228053.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Flooring & Tiling Work | 64.152 | 23 | 0 | 1475.496 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232713.654 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Kitchen Dado Work | 24.304 | 23 | 0 | 558.992 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233630.158 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1304-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228544.582 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2003-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2004-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Kitchen Dado Work | 24.304 | 27 | 0 | 656.208 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233532.942 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2002-3BHK Toilet Dado Work | 249.168 | 27 | 0 | 6727.536 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -227461.614 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2103-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1804-2BHK Toilet Dado Work | 245.416 | 25 | 0 | 6135.4 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -228053.75 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1901-3BHK Flooring & Tiling Work | 61.568 | 25 | 0 | 1539.2 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232649.95 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2104-2BHK Comm Passage wash basin-Dado Work | 9.816 | 27 | 0 | 265.032 | 0 | 2024-04-12 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -233924.118 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232841.958 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2101-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2302-3BHK Flooring & Tiling Work | 61.568 | 27 | 0 | 1662.336 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232526.814 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2303-2BHK Flooring & Tiling Work | 64.152 | 27 | 0 | 1732.104 | 0 | 2024-04-12 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 106775 | 2024-04-15 | 234189.15 | 2024-05-03 13:25 | -232457.046 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-402-3BHK Toilet Dado Work | 249.168 | 19 | 0 | 4734.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188452.498 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-801-3BHK Vitrified Flooring Work | 535.568 | 16 | 0 | 8569.088 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -179723.302 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-901-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-902-3BHK Toilet Dado Work | 249.168 | 21 | 0 | 5232.528 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183059.862 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Flooring & Tiling Work | 114.872 | 15 | 0 | 1723.08 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191463.61 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192817.786 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191967.802 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Flooring & Tiling Work | 64.152 | 21 | 0 | 1347.192 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191839.498 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192676.306 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 0 | 2023-01-04 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -191693.354 | PAPPU BAGELA
Ceramic Skirting BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 0 | 2023-01-04 | Labour Charges for- Skirting work with cutting & fixing in line,level,right angle & proper joint filling. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192887.554 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Kitchen Dado Work | 24.304 | 19 | 0 | 461.776 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -192724.914 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Toilet Dado Work | 245.416 | 19 | 0 | 4662.904 | 0 | 2023-01-04 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 97634 | 2023-01-05 | 193186.69 | 2023-01-24 19:44 | -188523.786 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Kitchen Dado Work | 24.304 | 21 | 0 | 510.384 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Kitchen (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -187782.006 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-904-2BHK Toilet Dado Work | 245.416 | 21 | 0 | 5153.736 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -183138.654 | PAPPU BAGELA
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-104-2BHK Flooring & Tiling Work | 114.872 | 2 | 0 | 229.744 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18249.136 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-203-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Vitrified Flooring Work | 535.568 | 2 | 0 | 1071.136 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17407.744 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Flooring Work | 407.648 | 2 | 0 | 815.296 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -17663.584 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 133.472 | 2 | 0 | 266.944 | 0 | 2024-01-15 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 104619 | 2024-01-15 | 18478.88 | 2024-02-05 11:47 | -18211.936 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1603-2BHK Flooring & Tiling Work | 64.152 | 25 | 0 | 1603.8 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -389082.54 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1801-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1402-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -381046.116 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Vitrified Flooring Work | 407.648 | 18 | 0 | 7337.664 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -383348.676 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Vitrified Flooring Work | 535.568 | 18 | 0 | 9640.224 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -381046.116 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1003-2BHK Toilet Dado Work | 245.416 | 23 | 0 | 5644.568 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -385041.772 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1502-3BHK Comm Passage wash basin-Dado Work | 5.944 | 25 | 0 | 148.6 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390537.74 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1602-3BHK Toilet Dado Work | 249.168 | 25 | 0 | 6229.2 | 0 | 2023-12-05 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -384457.14 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Vitrified Flooring Work | 535.568 | 20 | 0 | 10711.36 | 0 | 2023-12-05 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -379974.98 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Comm Passage wash basin-Dado Work | 9.816 | 23 | 0 | 225.768 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390460.572 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Comm Passage wash basin-Dado Work | 9.816 | 25 | 0 | 245.4 | 0 | 2023-12-05 | Labour charges for Dado Fixing work (300 x 600 mm) for D-Building Common Passage Wash Basin Dado work. | 100 |  | 103795 | 2023-12-11 | 390686.34 | 2023-12-22 11:35 | -390440.94 | PAPPU BAGELA
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 0 | 2023-05-29 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186290.31 | PAPPU BAGELA
Vitrified Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-803-2BHK Vitrified Flooring Work | 407.648 | 16 | 0 | 6522.368 | 0 | 2023-05-29 | Labour Charges for- Vitrified Flooring work (600 x 600mm) with floor guard laying . Including Proper Fixing with line,level,right angle & joint filling. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -181770.022 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-802-3BHK Flooring & Tiling Work | 61.568 | 21 | 0 | 1292.928 | 0 | 2023-05-29 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 99835 | 2023-05-30 | 188292.39 | 2023-06-15 13:02 | -186999.462 | PAPPU BAGELA
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-103-2BHK Toilet Dado Work | 61.0526 | 19 | 0 | 1159.9994 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -3840.0006 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-106-3BHK Toilet Dado Work | 16.8421 | 19 | 0 | 319.9999 | 0 | 2023-08-12 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101220 | 2023-08-12 | 5000 | 2023-08-12 14:26 | -4680.0001 | PAWAR SHIVAPPA TARANAIK
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -5878.68 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-804-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-19 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105460 | 2024-02-23 | 6897.8 | 2024-03-02 12:05 | -6610.62 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -3011.52 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -3011.52 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-301-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -2006.28 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1102-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-06-14 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 108398 | 2024-06-17 | 3345.2 | 1900-01-01 | -2006.28 | MAULI ENTERPRISES
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-504-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-701-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-503-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-02-05 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-401-3BHK Flooring & Tiling Work | 33.35 | 2 | 0 | 66.7 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17512.82 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-501-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-302-3BHK Vitrified Flooring Work | 133.892 | 2 | 0 | 267.784 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.736 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-601-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13240.88 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-107-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-403-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-04 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-204-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-303-2BHK Vitrified Flooring Work | 101.9 | 2 | 0 | 203.8 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17375.72 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-604-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -13560.68 | A R CLEANING SERVICS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-001-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2023-11-02 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37299.474 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Flooring & Tiling Work | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2023-11-02 | Labour Charges for- Ceramic Flooring work. Including Proper Fixing with line,level,right angle & joint filling.transportation of raw material from store to required working place to be done by contractor. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37541.274 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-003-2BHK Flooring & Tiling Work | 64.152 | 19 | 0 | 1218.888 | 219.4 | 2023-11-02 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 103246 | 2023-11-04 | 39034.61 | 2023-11-23 11:40 | -37815.722 | SUNIL CONSTRUCTION AND CONTRACTORS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1002-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-03-18 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14246.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1104-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-201-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17245.84 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-704-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17292.34 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-102-3BHK Vitrified Flooring Work | 133.88 | 2 | 0 | 267.76 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17311.76 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-304-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-404-2BHK Flooring & Tiling Work | 28.5 | 2 | 0 | 57 | 0 | 2024-03-22 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 106370 | 2024-03-22 | 14579.8 | 2024-03-28 12:41 | -14522.8 | A R CLEANING SERVICS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-108-2BHK Flooring & Tiling Work | 28.7 | 2 | 0 | 57.4 | 0 | 2024-02-03 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 105085 | 2024-02-05 | 17579.52 | 2024-02-20 12:26 | -17522.12 | A R CLEANING SERVICS
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1004-2BHK Toilet Dado Work | 60.8696 | 23 | 0 | 1400.0008 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -1500.9992 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-101-3BHK Toilet Dado Work | 57.8947 | 19 | 0 | 1099.9993 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work in Toilets (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -1801.0007 | PAWAR SHIVAPPA TARANAIK
Dado BC | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-105-3BHK Flooring & Tiling Work | 5.7895 | 19 | 0 | 110.0005 | 0 | 2023-08-31 | Labour Charges for- Fixing of Ceramic Dado work (300 x 600mm) with proper joint filling,line level & right angle. | 100 |  | 101543 | 2023-09-01 | 2901 | 2023-09-01 13:01 | -2790.9995 | PAWAR SHIVAPPA TARANAIK