Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-105-3BHK Toilet Dado Work | 249.168 | 20 | 0 | 4983.36 | 897 | 2024-01-12 18:28 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -49698.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-407-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54195.35 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-905-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-107-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2024-01-12 18:22 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -53398.39 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-006-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2024-01-12 19:01 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -52946.294 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-007-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2024-01-12 19:01 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -53188.094 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-307-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54195.35 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-508-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-707-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-207-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2024-01-12 19:01 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -53188.094 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-408-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54195.35 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-808-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-507-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-408-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2024-01-12 18:22 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -53398.39 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-008-2BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2024-01-12 17:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54195.35 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-607-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-608-2BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-1007-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54098.134 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-406-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -60852.8 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-607-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -61405.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-206-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -60852.8 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-208-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -61649.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-706-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -60520.48 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-707-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -61405.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-805-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -60520.48 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-207-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -61649.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-505-3BHK Vitrified Skirting | 166.16 | 20 | 0 | 3323.2 | 598.18 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -60520.48 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-408-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -61649.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-808-2BHK Vitrified Skirting | 121.92 | 20 | 0 | 2438.4 | 438.92 | 2024-06-03 12:26 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 107949 | 2024-06-03 | 63843.68 | 2024-06-15 11:46 | -61405.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-705-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-04-07 21:43 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96342.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-305-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-04-07 21:51 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -98833.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-405-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-706-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101693.392 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-505-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101693.392 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-807-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101608.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-707-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-04-07 21:46 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -100101.08 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-007-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-206-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-407-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-608-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101608.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-207-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-305-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-805-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-04-07 21:43 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96342.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-705-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-04-07 21:46 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -99822.08 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-306-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2024-04-07 21:49 | Labour Charges for Vitrified Flooring work with Floor Guard Sheet Laying including proper fixing, Line, Level, Right Angle & Joint Filling. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -94326.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-005-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-208-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-007-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2024-01-07 20:52 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -90585.53 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-208-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2024-01-07 21:09 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -91600.922 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-105-3BHK Vitrified Skirting | 166.16 | 18 | 0 | 2990.88 | 538.36 | 2024-01-07 20:48 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -88877.69 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-406-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2024-01-07 21:09 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -91538.498 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-005-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2024-01-07 21:09 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -91538.498 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-205-3BHK Flooring & Tiling Work | 61.568 | 20 | 0 | 1231.36 | 221.64 | 2024-01-07 20:52 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -90637.21 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-208-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 20 | 0 | 1283.04 | 230.94 | 2024-01-07 20:52 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -90585.53 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-407-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2024-01-07 21:09 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -91600.922 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-207-2BHK Living Terrace Skirting | 15.744 | 17 | 0 | 267.648 | 48.18 | 2024-01-07 21:09 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -91600.922 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-306-3BHK Living Terrace Skirting | 19.416 | 17 | 0 | 330.072 | 59.42 | 2024-01-07 21:09 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104390 | 2024-01-08 | 91868.57 | 2024-02-02 14:29 | -91538.498 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-806-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101693.392 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-806-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-04-07 21:46 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -99822.08 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-107-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-205-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-605-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101693.392 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-508-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85409.4 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-506-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85130.4 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-507-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85409.4 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-1107-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-25 16:57 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -86549.184 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-1206-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-25 17:12 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -86549.184 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-508-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-25 16:53 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -81733.328 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-507-2BHK Flooring & Tiling Work-(Flat) | 64.152 | 22 | 0 | 1411.344 | 254.04 | 2024-02-25 17:04 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85721.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-506-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-25 17:04 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85777.984 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-606-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85130.4 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-1108-2BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-25 16:57 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -86549.184 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-1205-3BHK Kitchen Dado Work | 24.304 | 24 | 0 | 583.296 | 105 | 2024-02-25 16:57 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -86549.184 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-608-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85409.4 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-506-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-02-25 16:53 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -81650.784 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-607-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-02-25 16:53 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -81733.328 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-606-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-02-25 16:53 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -81650.784 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-406-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85397.344 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-405-3BHK Flooring & Tiling Work | 133.472 | 13 | 0 | 1735.136 | 312.32 | 2024-02-25 16:50 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85397.344 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-606-3BHK Flooring & Tiling Work | 61.568 | 22 | 0 | 1354.496 | 243.82 | 2024-02-25 17:04 | Labour charges for Ceramic Dado Fixing work (300x600mm) including proper line, level, right angle for Dry Balcony at E-Bldg. | 100 |  | 105573 | 2024-02-26 | 87132.48 | 2024-03-16 10:57 | -85777.984 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-307-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-04-07 21:51 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -99629.6 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-306-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-308-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-707-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101608.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-708-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101608.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-707-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-04-07 21:43 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96425.008 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-706-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-04-07 21:46 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -99822.08 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-805-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-04-07 21:46 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -99822.08 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-305-3BHK Vitrified Flooring Work | 535.568 | 14 | 0 | 7497.952 | 1349.64 | 2024-04-07 21:49 | Labour Charges for Vitrified Flooring work with Floor Guard Sheet Laying including proper fixing, Line, Level, Right Angle & Joint Filling. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -94326.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-307-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2024-04-07 21:49 | Labour Charges for Vitrified Flooring work with Floor Guard Sheet Laying including proper fixing, Line, Level, Right Angle & Joint Filling. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96117.088 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-905-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-06-03 16:13 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -64624.004 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-905-3BHK Flooring & Tiling Work | 133.472 | 15 | 0 | 2002.08 | 360.38 | 2024-06-03 16:49 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -68103.62 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-1006-3BHK Flooring & Tiling Work | 133.472 | 17 | 0 | 2269.024 | 408.42 | 2024-06-03 17:04 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -67836.676 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-808-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-03 17:08 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -69806.564 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-907-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 15 | 0 | 1723.08 | 310.16 | 2024-06-03 16:49 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -68382.62 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-607-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-03 17:08 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -69806.564 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-705-3BHK Living Terrace Skirting | 19.416 | 19 | 0 | 368.904 | 66.4 | 2024-06-03 17:08 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -69736.796 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-908-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-06-03 16:13 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -64706.548 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-508-2BHK Living Terrace Skirting | 15.744 | 19 | 0 | 299.136 | 53.84 | 2024-06-03 17:08 | Labour Charges for fixing of Ceramic Skirting work for Dry Balcony area including proper fixing, line, level, right angle for E-Bldg. | 100 |  | 108009 | 2024-06-03 | 70105.7 | 2024-06-15 11:46 | -69806.564 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-308-2BHK Vitrified Flooring Work | 407.648 | 14 | 0 | 5707.072 | 1027.28 | 2024-04-07 21:49 | Labour Charges for Vitrified Flooring work with Floor Guard Sheet Laying including proper fixing, Line, Level, Right Angle & Joint Filling. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96117.088 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-905-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101693.392 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-708-2BHK Toilet Dado Work | 245.416 | 22 | 0 | 5399.152 | 971.84 | 2024-04-07 21:43 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96425.008 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-806-3BHK Toilet Dado Work | 249.168 | 22 | 0 | 5481.696 | 986.7 | 2024-04-07 21:43 | Labour Charges for Dado fixing work (300x600mm) including in proper line, level, Right angle & Proper Joint Filling for Master Toilet & Common Toilet area E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -96342.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-108-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 20 | 0 | 196.32 | 35.34 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101627.84 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-506-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 22 | 0 | 130.768 | 23.54 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101693.392 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-507-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101608.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Vitrified Skirting BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-308-2BHK Vitrified Skirting | 121.92 | 18 | 0 | 2194.56 | 395.02 | 2024-04-07 21:51 | Labour Charges for Vitrified Skirting work including cutting & fixing in line level, Right angle & Proper Joint Filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -99629.6 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-106-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-508-2BHK Comm Passage Wash Basin Dado Work | 9.816 | 22 | 0 | 215.952 | 38.88 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101608.208 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-005-3BHK Kitchen Dado Work | 24.304 | 20 | 0 | 486.08 | 87.5 | 2024-01-12 17:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54195.35 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-805-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Ceramic Flooring & Floor Guard Laying | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-008-2BHK Flooring & Tiling Work-(Flat) | 114.872 | 13 | 0 | 1493.336 | 268.8 | 2024-01-12 19:01 | Labour Charges for Fixing of Ceramic Flooring for Dry Balcony area with proper fixing, line, level, right angle for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -53188.094 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-706-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-906-3BHK Kitchen Dado Work | 24.304 | 22 | 0 | 534.688 | 96.24 | 2024-01-12 18:15 | Labour charges for Dado fixing work (600x300mm) for Kitchen area including proper line, level, right angle, joint filling for E-Bldg. | 100 |  | 104553 | 2024-01-15 | 54681.43 | 2024-02-02 14:29 | -54146.742 | SUNIL CONSTRUCTION AND CONTRACTORS
Dado Work - BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 765 | 2023-09-05 | E-105-3BHK Comm. Passage Wash Basin Dado Work | 5.944 | 20 | 0 | 118.88 | 21.4 | 2024-04-07 21:56 | Labour Charges for Dado fixing work (300x600mm) for Basin area including proper fixing in line, level, Right angle & joint filling for E-Bldg. | 100 |  | 106669 | 2024-04-08 | 101824.16 | 2024-05-03 13:21 | -101705.28 | SUNIL CONSTRUCTION AND CONTRACTORS
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 2068 | 205 | 0 | 423940 | 76309.2 | 2024-02-02 17:52 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Bldg | 100 |  | 105093 | 2024-02-05 | 423940 | 2024-02-27 10:40 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 77.4357 | 155 | 0 | 12002.5335 | 0 | 2024-03-17 15:30 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Bldg | 100 | slab chipping work P3,P5 | 106115 | 2024-03-18 | 12002.53 | 2024-03-27 10:40 | 0.0035 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 2068 | 155 | 0 | 320540 | 57697.2 | 2023-11-25 18:59 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Bldg | 100 |  | 103500 | 2023-11-27 | 320540 | 2023-12-16 17:30 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 311.9024 | 205 | 0.01 | 63939.992 | 11509.2 | 2024-02-03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Bldg | 100 | Debit for Rebaring (Challan No-43,44 ) | 105097 | 2024-02-05 | 63940 | 1900-01-01 | -0.008 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 1769.3176 | 205 | 0 | 362710.108 | 0 | 2024-02-19 14:10 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Bldg | 100 | P1,P2 d bldg driveway slab chipping | 105417 | 2024-02-19 | 362710.11 | 1900-01-01 | -0.002 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 2068 | 155 | 0 | 320540 | 57697.2 | 2023-11-02 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Bldg | 100 |  | 103201 | 2023-11-02 | 320540 | 2023-11-23 11:39 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 2025.776 | 145 | 0 | 293737.52 | 52872.76 | 2023-09-13 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Building. | 100 |  | 101828 | 2023-09-13 | 293737.52 | 2023-09-20 12:00 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 768 | 2023-09-08 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 2068.976 | 145 | 0 | 300001.52 | 54000.28 | 2023-10-02 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc.Area Between D & E Building. | 100 |  | 102188 | 2023-10-03 | 300001.52 | 2023-10-20 11:01 | 0 | RITU ENTERPRISES
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking G.Fl RCC Wall-Sand Face Plaster 1.1m Ht - 1 | 984.76 | 25 | 0 | 24619 | 0 | 2024-05-07 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 107428 | 2024-05-07 | 32720.75 | 2024-05-21 12:30 | -8101.75 | JAY GANESH ENTERPRISES
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P5 Floor RCC Wall-Sand Face Plaster 1.1m Ht-( | 1913.193 | 25 | 0 | 47829.825 | 8609.36 | 2023-09-23 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 102059 | 2023-09-25 | 126034.85 | 2023-10-11 11:09 | -78205.025 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P1-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 69.5 | 25 | 0 | 1737.5 | 0 | 2024-05-07 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 107428 | 2024-05-07 | 32720.75 | 2024-05-21 12:30 | -30983.25 | JAY GANESH ENTERPRISES
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P2-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 1948.9665 | 25 | 0 | 48724.1625 | 8770.34 | 2023-09-23 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 102059 | 2023-09-25 | 126034.85 | 2023-10-11 11:09 | -77310.6875 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P1-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 1179.2342 | 25 | 0 | 29480.855 | 5306.56 | 2023-09-23 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 102059 | 2023-09-25 | 126034.85 | 2023-10-11 11:09 | -96553.995 | JAI SEVALAL CONSTRUCTION
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P5 Floor RCC Wall-Sand Face Plaster 1.1m Ht-( | 44.76 | 25 | 0 | 1119 | 0 | 2024-05-07 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 107428 | 2024-05-07 | 32720.75 | 2024-05-21 12:30 | -31601.75 | JAY GANESH ENTERPRISES
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P3 Floor RCC Wall-Sand Face Plaster 1.1m Ht | 140.31 | 25 | 0 | 3507.75 | 0 | 2024-05-07 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 107428 | 2024-05-07 | 32720.75 | 2024-05-21 12:30 | -29213 | JAY GANESH ENTERPRISES
Sand face Plaster- BC | GLAZING SERVICES | N/C | JAI SEVALAL CONSTRUCTION | 769 | 2023-09-08 | D-Bldg parking P2-Fl RCC Wall-Sand Face Plaster 1.1m Ht - | 69.5 | 25 | 0 | 1737.5 | 0 | 2024-05-07 | Labour Charges for single coat sand face plaster (Qty diff.) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparaton between RCC (column beam) & Block- work using Chicken mesh, nails, drill machine etc | 100 |  | 107428 | 2024-05-07 | 32720.75 | 2024-05-21 12:30 | -30983.25 | JAY GANESH ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1081.9951 | 155 | 0 | 167709.2405 | 29053.66 | 2024-07-23 09:01 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 |  | 109315 | 2024-07-26 | 167709.24 | 2024-08-05 13:58 | 0.0005 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2740.528 | 140 | 0 | 383673.92 | 69061.3 | 2023-10-02 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 |  | 102189 | 2023-10-03 | 383673.92 | 2023-10-17 12:47 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1083.875 | 155 | 0 | 168000.625 | 30240.12 | 2024-05-14 12:54 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 |  | 107644 | 2024-05-20 | 168000.63 | 2024-06-03 12:36 | -0.005 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2084.9419 | 140 | 0 | 291891.866 | 52540.54 | 2024-04-18 16:26 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 |  | 106994 | 2024-04-22 | 291891.87 | 2024-05-03 13:23 | -0.004 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2101.05 | 155 | 0 | 325662.75 | 58619.3 | 2024-06-16 12:17 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 |  | 108390 | 2024-06-17 | 325662.75 | 2024-06-26 11:42 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 440.2786 | 140 | 0 | 61639.004 | 11095.02 | 2023-10-03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 | 268 nos x 230 = 61640 ( Ch. date -30/9/23) | 102217 | 2023-10-04 | 61639 | 2023-11-06 16:14 | 0.004 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 67.45 | 140 | 0 | 9443 | 0 | 2024-07-02 15:21 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 | Debit for Safety net Removing | 108761 | 2024-07-02 | 9443 | 2024-08-05 14:00 | 0 | FAIJANA KHATUN
RCC Superstructure (B-up area) | N/C | N/C | RITU ENTERPRISES | 770 | 2023-09-08 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1083.875 | 140 | 0 | 151742.5 | 27313.66 | 2024-03-18 17:13 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc. | 100 | E bldg 2nd ramp slab 25.2m*5m | 106217 | 2024-03-18 | 151742.5 | 2024-03-28 12:34 | 0 | RITU ENTERPRISES
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 4 | 3500 | 0 | 14000 | 0 | 2023-11-21 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 103474 | 2023-11-23 | 88000 | 2023-12-11 14:16 | -74000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 5 | 6000 | 0 | 30000 | 0 | 2023-11-21 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 103474 | 2023-11-23 | 88000 | 2023-12-11 14:16 | -58000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 5 | 7000 | 0 | 35000 | 0 | 2023-11-21 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 103474 | 2023-11-23 | 88000 | 2023-12-11 14:16 | -53000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 3 | 3000 | 0 | 9000 | 0 | 2023-11-21 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 103474 | 2023-11-23 | 88000 | 2023-12-11 14:16 | -79000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 19 | 7000 | 0 | 133000 | 0 | 2023-09-18 17:15 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 101951 | 2023-09-20 | 276500 | 2023-09-30 12:06 | -143500 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 18 | 6000 | 0 | 108000 | 0 | 2023-09-18 17:15 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 101951 | 2023-09-20 | 276500 | 2023-09-30 12:06 | -168500 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 5 | 3500 | 0 | 17500 | 0 | 2023-09-18 17:15 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 101951 | 2023-09-20 | 276500 | 2023-09-30 12:06 | -259000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 4 | 3000 | 0 | 12000 | 0 | 2023-10-13 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 102618 | 2023-10-14 | 148000 | 2023-10-28 11:57 | -136000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 8 | 7000 | 0 | 56000 | 0 | 2023-10-13 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 102618 | 2023-10-14 | 148000 | 2023-10-28 11:57 | -92000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 4 | 3500 | 0 | 14000 | 0 | 2023-10-13 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 102618 | 2023-10-14 | 148000 | 2023-10-28 11:57 | -134000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 11 | 6000 | 0 | 66000 | 0 | 2023-10-13 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 102618 | 2023-10-14 | 148000 | 2023-10-28 11:57 | -82000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Building Gypsum Removing for Kutch-Per Flat | 6 | 3000 | 0 | 18000 | 0 | 2023-09-18 17:15 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for D-Bldg. | 100 |  | 101951 | 2023-09-20 | 276500 | 2023-09-30 12:06 | -258500 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Stilt Floor-Grinding Work-3BHK Flats | 4 | 7000 | 0 | 28000 | 0 | 2024-01-05 | Labour charges for Internal Flat (3 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for Stilt Floor | 100 |  | 104363 | 2024-01-08 | 52000 | 2024-01-23 14:19 | -24000 | GUFRAN GULZAR SHAIKH
Chipping & Grinding | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | D-Stilt Floor-Grinding Work-2BHK Flats | 4 | 6000 | 0 | 24000 | 0 | 2024-01-05 | Labour charges for Internal Flat (2 BHK) Grinding work for kutch making vertical & horizontal, skirting butt finish,Dhar, Jamb in line, level work with grinder machine, blade,labour,housekeeping, cleaning etc all included for Stilt Floor | 100 |  | 104363 | 2024-01-08 | 52000 | 2024-01-23 14:19 | -28000 | GUFRAN GULZAR SHAIKH
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | 252 | 7.5 | 0 | 1890 | 340.2 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -50107.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 2nd Fl-Refuge Fl-West Acrylic Texture Paint - 1 Floor | 505 | 7.5 | 0 | 3787.5 | 681.76 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48210 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | 176 | 7.5 | 0 | 1320 | 237.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -50677.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 4th Fl-West Side Acrylic Texture Paint - 1 Floor | 505 | 7.5 | 0 | 3787.5 | 681.76 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48210 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | 352 | 7.5 | 0 | 2640 | 475.2 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -49357.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | Stilt Fl South Acrylic Texture Paint - 1 Floor | 130 | 7.5 | 0 | 975 | 175.5 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -51022.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | 505 | 7.5 | 0 | 3787.5 | 681.76 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48210 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 3rd Fl South Acrylic Texture Paint - 1 Floor | 476 | 7.5 | 0 | 3570 | 642.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48427.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | 476 | 7.5 | 0 | 3570 | 642.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48427.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 4th Fl South Acrylic Texture Paint - 1 Floor | 476 | 7.5 | 0 | 3570 | 642.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48427.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 3rd Floor North side Acrylic Texture Paint | 476 | 7.5 | 0 | 3570 | 642.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48427.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 5th Fl South Acrylic Texture Paint - 1 Floor | 476 | 7.5 | 0 | 3570 | 642.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48427.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 2nd Floor North side Acrylic Texture Paint | 476 | 7.5 | 0 | 3570 | 642.6 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48427.5 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 3rd Fl-West Side Acrylic Texture Paint - 1 Floor | 505 | 7.5 | 0 | 3787.5 | 681.76 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48210 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | 505 | 7.5 | 0 | 3787.5 | 681.76 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48210 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | 4th Floor North side Acrylic Texture Paint | 237 | 7.5 | 0 | 1777.5 | 319.96 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -50220 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 774 | 2023-09-16 | Stilt Fl West Side Acrylic Texture Paint - 1 Floor | 405 | 7.5 | 0 | 3037.5 | 546.76 | 2023-12-31 15:42 | Labour charges for Applying Texture Paint on External Surface of wall for E-Bldg External Texture Painting work. | 100 |  | 104252 | 2024-01-01 | 51997.5 | 2024-01-16 15:35 | -48960 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 3rd Fl-East side Acrylic Texture Paint - 1 Floor | 505 | 8 | 0 | 4040 | 727.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 3rd Fl South Acrylic Texture Paint - 1 Floor | 476 | 8 | 0 | 3808 | 685.44 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51888 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 4th Floor North side Acrylic Texture Paint | 237 | 8 | 0 | 1896 | 341.28 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -53800 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 5th Fl South Acrylic Texture Paint - 1 Floor | 476 | 8 | 0 | 3808 | 685.44 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51888 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 2nd Fl-East side Acrylic Texture Paint - 1 Floor | 252 | 8 | 0 | 2016 | 362.88 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -53680 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 2nd Fl-Refuge Fl-West Acrylic Texture Paint - 1 Floor | 505 | 8 | 0 | 4040 | 727.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 4th Fl-West Side Acrylic Texture Paint - 1 Floor | 505 | 8 | 0 | 4040 | 727.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 4th Fl South Acrylic Texture Paint - 1 Floor | 476 | 8 | 0 | 3808 | 685.44 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51888 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 4th Fl-East side Acrylic Texture Paint - 1 Floor | 352 | 8 | 0 | 2816 | 506.88 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -52880 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 3rd Fl-West Side Acrylic Texture Paint - 1 Floor | 505 | 8 | 0 | 4040 | 727.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 2nd Fl Refuge Fl-South Acylic Texture Paint - 1 Floor | 505 | 8 | 0 | 4040 | 727.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | Stilt Fl South Acrylic Texture Paint - 1 Floor | 130 | 8 | 0 | 1040 | 187.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -54656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | Stilt Fl East side Acrylic Texture Paint - 1 Floor | 176 | 8 | 0 | 1408 | 253.44 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -54288 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 5th Fl-East side Acrylic Texture Paint - 1 Floor | 505 | 8 | 0 | 4040 | 727.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51656 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 2nd Floor North side Acrylic Texture Paint | 476 | 8 | 0 | 3808 | 685.44 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51888 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | 3rd Floor North side Acrylic Texture Paint | 476 | 8 | 0 | 3808 | 685.44 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -51888 | VEER BHADRA ENTERPRISES (MATERIAL)
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 775 | 2023-09-16 | Stilt Fl West Side Acrylic Texture Paint - 1 Floor | 405 | 8 | 0 | 3240 | 583.2 | 2023-12-31 17:30 | Material Supply charges of Texture Paint for E-Bldg External Wall Painting work. | 100 |  | 104253 | 2024-01-01 | 55696 | 2024-01-16 15:38 | -52456 | VEER BHADRA ENTERPRISES (MATERIAL)
2nd Coat Putty (L) | N/C | N/C | YUGESH KUMAR | 780 | 2023-09-20 | F-Bldg Satin Matt Paint- On Wall Shop No-23 | 241 | 1.25 | 0 | 301.25 | 0 | 2024-05-16 | Labour Charges for F Building 2nd Coat Putty for Shop No. 23 | 100 |  | 107650 | 2024-05-20 | 1786.25 | 2024-07-26 12:29 | -1485 | YUGESH KUMAR
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1201-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1204-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1401-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1303-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1404-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1302-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Granite Work (M) | 0.005 | 1700 | 0 | 8.5 | 1.54 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28925.5 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1303-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1402-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1404-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:04 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1304-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1302-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1303-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1302-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1404-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1301-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1302-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1303-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:04 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1304-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:04 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1401-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:04 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1304-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1301-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1204-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1201-3BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1203-2BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-702-2BHK(Near Refuse Area) Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-702-2BHK(Near Refuse Area) Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1201-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1401-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1401-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1304-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1203-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1301-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1402-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:04 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1202-2BHK(Near Refuse Area) Kadappa Work (M) | 24.08 | 47.97 | 0 | 1155.1176 | 207.92 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192642.9024 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1403-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1002-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1204-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1401-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-702-2BHK(Near Refuse Area) Granite Work (M) | 17.1284 | 110.7 | 0 | 1896.1139 | 341.3 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97597.0461 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-202-2BHK(Near Refuse Area) Granite Work (M) | 17.1284 | 110.7 | 0 | 1896.1139 | 341.3 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97597.0461 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Granite Work (M) | 0.995 | 1700 | 0 | 1691.5 | 304.48 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101757.58 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1503-2BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1504-2BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1503-2BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1502-3BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1601-3BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1501-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-10 19:36 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -47221.3692 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1604-2BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1504-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1603-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1504-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1604-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1601-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Granite Work (M) | 0.995 | 1700 | 0 | 1691.5 | 304.48 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101757.58 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Granite Work (M) | 0.005 | 1700 | 0 | 8.5 | 1.54 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28925.5 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Granite Work (M) | 0.005 | 1700 | 0 | 8.5 | 1.54 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28925.5 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Granite Work (M) | 0.005 | 1700 | 0 | 8.5 | 1.54 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28925.5 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-104-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1403-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1404-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1402-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1403-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1201-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1404-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-502-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-504-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-804-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-603-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-203-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-402-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-601-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-702-2BHK(Near Refuse Area) Kadappa Work (M) | 4.5752 | 47.97 | 0 | 219.4723 | 39.5 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103229.6077 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-801-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-303-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Granite Work (M) | 0.995 | 1700 | 0 | 1691.5 | 304.48 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101757.58 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1202-2BHK(Near Refuse Area) Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1204-2BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1502-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-10 19:36 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -47221.3692 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1601-3BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1603-2BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1603-2BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1602-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1501-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1504-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-10 19:36 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -47300.409 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1602-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1604-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1503-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1501-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1502-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2024-02-10 20:45 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52674.6 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1203-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1403-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:04 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1203-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1402-3BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1304-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1003-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1201-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-404-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 17:25 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -67661.323 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:22 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102592 | 2023-10-13 | 67968.7 | 2023-10-30 15:47 | -66487.4344 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-004-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-002-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-803-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1301-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1403-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-902-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-903-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-201-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-703-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-904-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-003-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-11 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102543 | 2023-10-12 | 28934 | 2023-10-30 15:47 | -28084 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1302-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1503-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-10 19:36 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -47300.409 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1603-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1502-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1503-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1601-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-10 19:53 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -52388.7493 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1602-3BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1501-3BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1502-3BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1504-2BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1602-3BHK Kadappa Work (M) | 4.8 | 60.27 | 0 | 289.296 | 52.08 | 2024-02-10 19:49 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53745.304 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1501-3BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1604-2BHK Kadappa Work (M) | 1.2 | 60.27 | 0 | 72.324 | 13.02 | 2024-02-10 19:55 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105252 | 2024-02-12 | 54034.6 | 2024-02-27 10:43 | -53962.276 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-101-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-103-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-302-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-304-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-503-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-802-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-701-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-09 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102486 | 2023-10-11 | 204294.48 | 2023-10-30 15:47 | -199056.156 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1201-3BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1402-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1303-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1001-3BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1104-2BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-301-3BHK Granite Work (M) | 18.102 | 110.7 | 0 | 2003.8914 | 360.7 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97489.2686 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-704-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:46 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1103-2BHK Granite Work (M) | 17.892 | 110.7 | 0 | 1980.6444 | 356.52 | 2024-03-10 14:58 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -97512.5156 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1101-3BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Granite Work (M) | 0.2 | 1700 | 0 | 340 | 61.2 | 2024-03-10 15:33 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 107226 | 2024-04-30 | 99493.16 | 2024-05-03 13:14 | -99153.16 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-901-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-18 07:17 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103284.4949 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-204-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-401-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-602-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-604-2BHK Granite Work (M) | 13.6874 | 110.7 | 0 | 1515.1952 | 272.74 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101933.8848 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-102-3BHK Granite Work (M) | 0.995 | 1700 | 0 | 1691.5 | 304.48 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101757.58 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-501-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-18 07:44 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -102599.08 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-403-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-18 07:10 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -103394.837 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-001-3BHK Granite Work (M) | 13.848 | 110.7 | 0 | 1532.9736 | 275.94 | 2023-10-18 07:34 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 102746 | 2023-10-18 | 103449.08 | 2023-10-30 15:48 | -101916.1064 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1203-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1004-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -187063.829 | SHIVAM CONSTRUCTION
Granite work (M) | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-16 19:18 | Material Supply charges of Granite with Polish including transportation, loading & unloading of Material for E-Bldg. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -186984.7892 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1203-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1204-2BHK Kadappa Work (M) | 6.862 | 47.97 | 0 | 329.1701 | 59.26 | 2023-12-11 19:09 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193468.8499 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1102-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-16 19:25 | Material supply charges of Araldite for E-Bldg including transportation, loading & unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192438.02 | SHIVAM CONSTRUCTION
Kadappa Single Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1204-2BHK Kadappa Work (M) | 27.448 | 47.97 | 0 | 1316.6806 | 237 | 2023-12-11 18:50 | Material supply charges of Kadappa single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -192481.3394 | SHIVAM CONSTRUCTION
Kadappa Double Polish | N/C | N/C | SHIVAM CONSTRUCTION | 781 | 2023-09-23 | E-1301-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-11 19:03 | Material Supply charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 103987 | 2023-12-18 | 193798.02 | 2023-12-25 15:37 | -193436.4 | SHIVAM CONSTRUCTION
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1108-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1106-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-907-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1105-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1007-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-805-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1307-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90248.469 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1506-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90169.4292 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1405-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1407-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90248.469 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1308-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90248.469 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1406-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1405-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90169.4292 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1306-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90169.4292 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1507-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90248.469 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1408-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-805-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1208-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-805-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-806-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1007-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-807-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-808-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1107-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1205-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1207-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-906-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1606-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-04-07 22:05 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 106670 | 2024-04-08 | 27094.84 | 2024-05-03 13:21 | -20281.6092 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 16:16 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 16:16 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 16:16 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 16:16 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1306-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1308-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1508-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90248.469 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1106-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1006-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1205-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-807-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1005-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1006-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1007-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1008-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-808-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1208-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56577.877 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56577.877 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1207-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-908-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-906-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1205-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1005-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1108-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-808-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1107-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1008-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-807-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1006-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56577.877 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1007-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-806-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-806-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1608-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-04-07 22:05 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 106670 | 2024-04-08 | 27094.84 | 2024-05-03 13:21 | -20360.649 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1607-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-04-07 22:05 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 106670 | 2024-04-08 | 27094.84 | 2024-05-03 13:21 | -20360.649 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1605-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-04-07 22:05 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 106670 | 2024-04-08 | 27094.84 | 2024-05-03 13:21 | -20281.6092 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1005-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1108-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1206-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-907-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-806-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-905-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1008-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1105-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1106-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-807-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1206-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1205-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1008-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1105-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1208-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1107-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-706-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1306-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1305-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1406-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1407-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1308-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1307-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1407-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1405-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2024-02-25 17:32 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -95336.8093 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1307-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1408-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2024-02-25 17:29 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -96621.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1408-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90248.469 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1305-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90169.4292 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1406-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90169.4292 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1505-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2024-02-25 15:47 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 105571 | 2024-02-26 | 96982.66 | 2024-03-16 10:57 | -90169.4292 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-906-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1005-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1106-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1108-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1207-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1107-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1206-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1207-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-805-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-908-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-905-3BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:54 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-308-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-305-3BHK Kadappa Work (M) | 5.1465 | 47.97 | 0 | 246.8776 | 44.44 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53241.3524 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-106-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-107-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-208-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-708-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-205-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-108-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-008-2BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-207-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-406-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-707-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-507-2BHK Granite Work (M) | 13.5085 | 110.7 | 0 | 1495.3909 | 269.18 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51992.8391 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-408-2BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-605-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Kadappa Work (M) | 3.431 | 47.97 | 0 | 164.5851 | 29.62 | 2023-10-20 11:19 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53323.6449 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Granite Work (M) | 13.667 | 110.7 | 0 | 1512.9369 | 272.32 | 2023-10-20 11:09 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -51975.2931 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Kadappa Work (M) | 0.9 | 60.27 | 0 | 54.243 | 9.76 | 2023-10-20 11:13 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102839 | 2023-10-20 | 53488.23 | 2023-11-07 13:57 | -53433.987 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1105-3BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-31 18:37 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -55272.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-905-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-907-2BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:48 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1208-2BHK Kadappa Work (M) | 6 | 60.27 | 0 | 361.62 | 65.1 | 2023-12-31 18:45 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -56270.5 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1206-3BHK Kadappa Work (M) | 34.31 | 47.97 | 0 | 1645.8507 | 296.26 | 2023-12-31 18:51 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104256 | 2024-01-01 | 56632.12 | 2024-01-16 15:09 | -54986.2693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-005-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-206-3BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Granite Work (M) | 1 | 1700 | 0 | 1700 | 306 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -35700 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-22 13:18 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102918 | 2023-10-23 | 37400 | 2023-11-07 13:57 | -36550 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-306-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-608-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-606-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-505-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-508-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-006-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-407-2BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-506-3BHK Granite Work (M) | 47.32 | 110.7 | 0 | 5238.324 | 942.9 | 2023-10-12 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -227897.746 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-405-3BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-007-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-607-2BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-705-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Single Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Kadappa Work (M) | 30.879 | 47.97 | 0 | 1481.2656 | 266.62 | 2023-10-12 17:16 | Material Supply Charges of Kadappa Single Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -231654.8044 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-307-2BHK Granite Work (M) | 0.5 | 1700 | 0 | 850 | 153 | 2023-10-12 16:26 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232286.07 | SUNIL CONSTRUCTION AND CONTRACTORS
Kadappa Double Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-105-3BHK Kadappa Work (M) | 5.1 | 60.27 | 0 | 307.377 | 55.32 | 2023-10-12 16:37 | Material Supply Charges of Kadappa Double Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 102589 | 2023-10-13 | 233136.07 | 2023-10-30 15:43 | -232828.693 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-907-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-808-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-905-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-906-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-908-2BHK Granite Work (M) | 60.8328 | 110.7 | 0 | 6734.191 | 1212.16 | 2023-12-22 15:57 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139620.009 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite work (M) | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-1006-3BHK Granite Work (M) | 61.5468 | 110.7 | 0 | 6813.2308 | 1226.38 | 2023-12-22 16:00 | Material Supply Charges of Granite with Polish for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -139540.9692 | SUNIL CONSTRUCTION AND CONTRACTORS
Araldite | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 782 | 2023-09-23 | E-908-2BHK Granite Work (M) | 0.8 | 1700 | 0 | 1360 | 244.8 | 2023-12-22 16:04 | Material Supply Charges of Araldite for E-Bldg including Transportation, Loading & Unloading of Material. | 100 |  | 104103 | 2023-12-25 | 146354.2 | 2024-02-02 14:29 | -144994.2 | SUNIL CONSTRUCTION AND CONTRACTORS
Fire Door Installation (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 783 | 2023-09-26 | Wing F - Second Floor Staircase Fire Door | 1 | 1200 | 0 | 1200 | 216 | 2023-10-16 | Labour Charges for Fire Door installation work for F Building. | 100 |  | 102689 | 2023-10-17 | 10800 | 2023-11-03 15:42 | -9600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Door Installation (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 783 | 2023-09-26 | Wing F . L.G. Floor Fire Door | 4 | 1200 | 0 | 4800 | 864 | 2023-10-16 | Labour Charges for Fire Door installation work for F Building. | 100 |  | 102689 | 2023-10-17 | 10800 | 2023-11-03 15:42 | -6000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Door Installation (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 783 | 2023-09-26 | Wing F - First Floor Staircase Fire Door | 1 | 1200 | 0 | 1200 | 216 | 2023-10-16 | Labour Charges for Fire Door installation work for F Building. | 100 |  | 102689 | 2023-10-17 | 10800 | 2023-11-03 15:42 | -9600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Door Installation (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 783 | 2023-09-26 | Wing F - Third Floor Staircase Fire Door | 1 | 1200 | 0 | 1200 | 216 | 2023-10-16 | Labour Charges for Fire Door installation work for F Building. | 100 |  | 102689 | 2023-10-17 | 10800 | 2023-11-03 15:42 | -9600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Door Installation (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 783 | 2023-09-26 | Wing F - Ground Floor Staircase Fire Door | 1 | 1200 | 0 | 1200 | 216 | 2023-10-16 | Labour Charges for Fire Door installation work for F Building. | 100 |  | 102689 | 2023-10-17 | 10800 | 2023-11-03 15:42 | -9600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Door Installation (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 783 | 2023-09-26 | Wing F - Stilt Floor Staircase Fire Door | 1 | 1200 | 0 | 1200 | 216 | 2023-10-16 | Labour Charges for Fire Door installation work for F Building. | 100 |  | 102689 | 2023-10-17 | 10800 | 2023-11-03 15:42 | -9600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Wall OBD Paint Work | 506.9 | 1.25 | 0 | 633.625 | 114.06 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20835.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Wall OBD Paint Work | 544.39 | 1.25 | 0 | 680.4875 | 122.48 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20788.1525 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1.25 | 0 | 633.625 | 114.06 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20835.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1.25 | 0 | 1004.5375 | 180.82 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20464.1025 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Ceiling OBD Painting Work | 333.71 | 1.25 | 0 | 417.1375 | 75.08 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21051.5025 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 67.5 | 2024-04-13 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21093.6525 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Ceiling OBD Painting Work | 203.12 | 1.25 | 0 | 253.9 | 45.7 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21214.74 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Wall OBD Paint Work | 1056.41 | 1.25 | 0 | 1320.5125 | 237.7 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20148.1275 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1.25 | 0 | 1004.5375 | 180.82 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20464.1025 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Ceiling OBD Painting Work | 320.66 | 1.25 | 0 | 400.825 | 72.14 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21067.815 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 36.52 | 2024-04-13 12:34 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21265.7275 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1.25 | 0 | 203.625 | 36.66 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21265.015 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Ceiling OBD Painting Work | 163.01 | 1.25 | 0 | 203.7625 | 36.68 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21264.8775 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1.25 | 0 | 633.625 | 114.06 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20835.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1.25 | 0 | 1004.5375 | 180.82 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20464.1025 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Ceiling OBD Painting Work | 169.75 | 1.25 | 0 | 212.1875 | 38.2 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21256.4525 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Wall OBD Paint Work | 528.21 | 1.25 | 0 | 660.2625 | 118.84 | 2024-04-13 12:34 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20808.3775 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 67.5 | 2024-04-13 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21093.6525 | SHAHI ENTERPRISES
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1 | 0 | 803.63 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39009.54 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39438.1825 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39610.2575 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1 | 0 | 162.9 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39650.27 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Ceiling OBD Painting Work | 320.66 | 1 | 0 | 320.66 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39492.51 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Ceiling OBD Painting Work | 203.12 | 0.5 | 0 | 101.56 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39711.61 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Ceiling OBD Paint | 299.99 | 1 | 0 | 299.99 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39513.18 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Ceiling OBD Painting Work | 333.6 | 0.5 | 0 | 166.8 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39646.37 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 0.5 | 0 | 81.45 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39731.72 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Parking+Meter R,Oxygen Piping R-Ceiling OBD | 5057.98 | 0.5 | 0 | 2528.99 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -37284.18 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Ceiling OBD Painting Work | 203.12 | 1 | 0 | 203.12 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39610.05 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Wall OBD Paint Work | 528.21 | 1 | 0 | 528.21 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39284.96 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Ceiling OBD Paint | 299.99 | 0.5 | 0 | 149.995 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39663.175 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Ceiling OBD Paint | 285.14 | 0.5 | 0 | 142.57 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39670.6 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Ceiling OBD Painting Work | 203.12 | 1 | 0 | 203.12 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8780.29 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Ceiling OBD Painting Work | 253 | 1 | 0 | 253 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8730.41 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1 | 0 | 506.9 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8476.51 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Wall OBD Paint Work | 751.57 | 1 | 0 | 751.57 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8231.84 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1 | 0 | 803.63 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8179.78 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1 | 0 | 506.9 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8476.51 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8821.08 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Meter R,Oxygen Piping R-Wall OBD Paint Work | 1322 | 1 | 0 | 1322 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 | for oxygen room walls | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -7661.41 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Wall OBD Paint Work | 506.9 | 1 | 0 | 506.9 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8476.51 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Wall OBD Paint Work | 544.39 | 1 | 0 | 544.39 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8439.02 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Wall OBD Paint Work | 751.57 | 1 | 0 | 751.57 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39061.6 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Wall OBD Paint Work | 506.9 | 0.5 | 0 | 253.45 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39559.72 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Meter R,Oxygen Piping R-Wall OBD Paint Work | 2710.85 | 1.25 | 0 | 3388.5625 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -36424.6075 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Wall OBD Paint Work | 751.57 | 1.25 | 0 | 939.4625 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -4798.0375 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Ceiling OBD Painting Work | 76.21 | 1.25 | 0 | 95.2625 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5642.2375 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Wall OBD Paint Work | 1056.41 | 1.25 | 0 | 1320.5125 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -4416.9875 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Ceiling OBD Painting Work | 169.75 | 1.25 | 0 | 212.1875 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5525.3125 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39650.84 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Wall OBD Paint Work | 751.57 | 0.5 | 0 | 375.785 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39437.385 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1 | 0 | 162.9 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39650.27 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Ceiling OBD Painting Work | 345.09 | 1 | 0 | 345.09 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39468.08 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Ceiling OBD Paint | 299.99 | 1 | 0 | 299.99 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39513.18 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Meter R,Oxygen Piping R-Wall OBD Paint Work | 2710.85 | 1 | 0 | 2710.85 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -37102.32 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Wall OBD Paint Work | 1056.41 | 0.5 | 0 | 528.205 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39284.965 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Ceiling OBD Painting Work | 163.01 | 0.5 | 0 | 81.505 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39731.665 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 0.5 | 0 | 81.45 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39731.72 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Ceiling OBD Paint | 100 | 1 | 0 | 100 | 0 | 2024-02-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 105233 | 2024-02-12 | 1549 | 1900-01-01 | -1449 | BHARAT KASHINATH KARCHE
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Ceiling OBD Paint | 200 | 1 | 0 | 200 | 0 | 2024-02-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 105233 | 2024-02-12 | 1549 | 1900-01-01 | -1349 | BHARAT KASHINATH KARCHE
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Meter R,Oxygen Piping R-Wall OBD Paint Work | 450 | 1 | 0 | 450 | 0 | 2024-02-10 | Labour Charges for 1st Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 105233 | 2024-02-12 | 1549 | 1900-01-01 | -1099 | BHARAT KASHINATH KARCHE
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Wall OBD Paint Work | 500 | 1 | 0 | 500 | 0 | 2024-02-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 105233 | 2024-02-12 | 1549 | 1900-01-01 | -1049 | BHARAT KASHINATH KARCHE
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Ceiling OBD Paint | 299 | 1 | 0 | 299 | 0 | 2024-02-10 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 105233 | 2024-02-12 | 1549 | 1900-01-01 | -1250 | BHARAT KASHINATH KARCHE
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Ceiling OBD Paint | 285.14 | 1.25 | 0 | 356.425 | 0 | 2023-10-20 11:33 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5381.075 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Ceiling OBD Painting Work | 203.12 | 1.25 | 0 | 253.9 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5483.6 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Ceiling OBD Painting Work | 345.09 | 1.25 | 0 | 431.3625 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5306.1375 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Ceiling OBD Painting Work | 344.23 | 1.25 | 0 | 430.2875 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5307.2125 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Wall OBD Paint Work | 544.39 | 1.25 | 0 | 680.4875 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -5057.0125 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Wall OBD Paint Work | 814.09 | 1.25 | 0 | 1017.6125 | 0 | 2023-10-20 11:33 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102840 | 2023-10-20 | 5737.5 | 2023-11-01 14:26 | -4719.8875 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Ceiling OBD Painting Work | 333.6 | 1 | 0 | 333.6 | 60.04 | 2023-10-27 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4284.42 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Ceiling OBD Paint | 299.99 | 1 | 0 | 299.99 | 54 | 2023-10-27 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4318.03 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Ceiling OBD Paint | 21 | 1 | 0 | 21 | 3.78 | 2023-10-27 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4597.02 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Wall OBD Paint Work | 1056.41 | 1 | 0 | 1056.41 | 190.16 | 2023-10-27 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -3561.61 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Ceiling OBD Paint | 299.99 | 1 | 0 | 299.99 | 54 | 2023-10-27 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4318.03 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Wall OBD Paint Work | 814.09 | 1 | 0 | 814.09 | 146.54 | 2023-10-27 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -3803.93 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Ceiling OBD Paint | 299.99 | 1 | 0 | 299.99 | 54 | 2023-10-27 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4318.03 | ANIL MAHTO ENTERPRISES
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Wall OBD Paint Work | 506.9 | 1 | 0 | 506.9 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39306.27 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Wall OBD Paint Work | 866.46 | 1 | 0 | 866.46 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -38946.71 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Wall OBD Paint Work | 544.39 | 0.5 | 0 | 272.195 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39540.975 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Ceiling OBD Paint | 299.99 | 0.5 | 0 | 149.995 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39663.175 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1 | 0 | 803.63 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39009.54 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Ceiling OBD Painting Work | 333.71 | 0.5 | 0 | 166.855 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39646.315 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Ceiling OBD Painting Work | 320.66 | 0.5 | 0 | 160.33 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39652.84 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39610.2575 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39610.2575 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Wall OBD Paint Work | 506.9 | 0.5 | 0 | 253.45 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39559.72 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Wall OBD Paint Work | 866.46 | 0.5 | 0 | 433.23 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39379.94 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Ceiling OBD Paint | 299.99 | 0.5 | 0 | 149.995 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39663.175 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1 | 0 | 506.9 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39306.27 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Wall OBD Paint Work | 506.9 | 0.5 | 0 | 253.45 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39559.72 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Wall OBD Paint Work | 803.63 | 0.5 | 0 | 401.815 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39411.355 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Ceiling OBD Painting Work | 345.09 | 0.5 | 0 | 172.545 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39640.625 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Parking+Meter R,Oxygen Piping R-Ceiling OBD | 5057.98 | 1 | 0 | 5057.98 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -34755.19 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Ceiling OBD Paint | 299.99 | 1 | 0 | 299.99 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39513.18 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39438.1825 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Wall OBD Paint Work | 544.39 | 1 | 0 | 544.39 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39268.78 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Parking+Meter R,Oxygen Piping R-Ceiling OBD | 5057.98 | 1.25 | 0 | 6322.475 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -33490.695 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Ceiling OBD Painting Work | 163.01 | 1 | 0 | 163.01 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39650.16 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1 | 0 | 506.9 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39306.27 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39650.84 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Ceiling OBD Painting Work | 344.23 | 0.5 | 0 | 172.115 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39641.055 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8821.08 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1 | 0 | 162.9 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8820.51 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1 | 0 | 162.9 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8820.51 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Wall OBD Paint Work | 866.46 | 1 | 0 | 866.46 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8116.95 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Parking+Meter R,Oxygen Piping R-Ceiling OBD | 162 | 1 | 0 | 162 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 | for Oxygen room ceiling | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8821.41 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Ceiling OBD Painting Work | 320.66 | 1 | 0 | 320.66 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8662.75 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8821.08 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Ceiling OBD Painting Work | 163.01 | 1 | 0 | 163.01 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8820.4 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Parking+Meter R,Oxygen Piping R-Ceiling OBD | 198 | 1 | 0 | 198 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 | for LG floor Meter room ceiling | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8785.41 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Ceiling OBD Painting Work | 169.75 | 1 | 0 | 169.75 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8813.66 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8821.08 | PATHAN HABIB MEHATAB
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Floor-Meter R,Oxygen Piping R-Wall OBD Paint Work | 730 | 1 | 0 | 730 | 0 | 2023-10-10 | Labour Charges for 1st Coat Putty for OBD Paint of Labby F Building Parking area.Transportation of Raw material from store to required working place to be done by Contractor. | 100 | for meter room walls | 102494 | 2023-10-11 | 8983.41 | 2023-11-01 14:26 | -8253.41 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Wall OBD Paint Work | 1056.41 | 1 | 0 | 1056.41 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -38756.76 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Ceiling OBD Painting Work | 169.75 | 1 | 0 | 169.75 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39643.42 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Ceiling OBD Painting Work | 344.23 | 1 | 0 | 344.23 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39468.94 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Wall OBD Paint Work | 162.33 | 1 | 0 | 162.33 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39650.84 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Ceiling OBD Paint | 285.14 | 1 | 0 | 285.14 | 0 | 2023-10-06 | Labour Charges for 2nd Coat Putty for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39528.03 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39438.1825 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Wall OBD Paint Work | 814.09 | 1 | 0 | 814.09 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -38999.08 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Wall OBD Paint Work | 803.63 | 0.5 | 0 | 401.815 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39411.355 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39610.2575 | PATHAN HABIB MEHATAB
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 0 | 2023-10-06 | Labour Charges for 1st Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39438.1825 | PATHAN HABIB MEHATAB
Water Base Primer (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Wall OBD Paint Work | 814.09 | 0.5 | 0 | 407.045 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Wall OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39406.125 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Ceiling OBD Painting Work | 333.71 | 1 | 0 | 333.71 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39479.46 | PATHAN HABIB MEHATAB
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Ceiling OBD Painting Work | 345.09 | 1.25 | 0 | 431.3625 | 77.64 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21037.2775 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 67.5 | 2024-04-13 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21093.6525 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 36.52 | 2024-04-13 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21265.7275 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Wall OBD Paint Work | 814.09 | 1.25 | 0 | 1017.6125 | 183.16 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20451.0275 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Ceiling OBD Painting Work | 163.01 | 1.25 | 0 | 203.7625 | 36.68 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21264.8775 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1.25 | 0 | 633.625 | 114.06 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20835.015 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1.25 | 0 | 1004.5375 | 180.82 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20464.1025 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Wall OBD Paint Work | 506.9 | 1.25 | 0 | 633.625 | 114.06 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20835.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Ceiling OBD Painting Work | 320.66 | 1.25 | 0 | 400.825 | 72.14 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21067.815 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Wall OBD Paint Work | 866.46 | 1.25 | 0 | 1083.075 | 194.96 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20385.565 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Floor Wall OBD Paint Work | 162.33 | 1.25 | 0 | 202.9125 | 36.52 | 2024-04-13 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21265.7275 | SHAHI ENTERPRISES
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Common Staircase Ceiling OBD Painting Work | 169.75 | 0.5 | 0 | 84.875 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for Staircase Ceiling OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39728.295 | PATHAN HABIB MEHATAB
2nd Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Ceiling OBD Painting Work | 333.6 | 1 | 0 | 333.6 | 0 | 2023-10-05 | Labour Charges for 2nd Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39479.57 | PATHAN HABIB MEHATAB
Primer Water Base- Ceiling | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Floor Ceiling OBD Paint | 299.99 | 0.5 | 0 | 149.995 | 0 | 2023-10-06 | Labour Charges for Water Base Primer for OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 102417 | 2023-10-07 | 39813.17 | 2023-11-01 14:26 | -39663.175 | PATHAN HABIB MEHATAB
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Wall OBD Paint Work | 506.9 | 1.25 | 0 | 633.625 | 114.06 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20835.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1.25 | 0 | 203.625 | 36.66 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21265.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Floor Ceiling OBD Paint | 299.99 | 1.25 | 0 | 374.9875 | 67.5 | 2024-04-13 12:34 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21093.6525 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Terrace Floor Ceiling OBD Paint | 285.14 | 1.25 | 0 | 356.425 | 64.16 | 2024-04-13 12:34 | Labour Charges for 2nd Coat OBD Paint for Lobby of F Building.Transportation of Raw material from store to required working place to be done by contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21112.215 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Ceiling OBD Painting Work | 333.6 | 1.25 | 0 | 417 | 75.06 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21051.64 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Ceiling OBD Painting Work | 344.23 | 1.25 | 0 | 430.2875 | 77.46 | 2024-04-13 12:34 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21038.3525 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Fire Staircase Wall OBD Paint Work | 866.46 | 1.25 | 0 | 1083.075 | 194.96 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20385.565 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 2nd Fl Fire Staircase Ceiling OBD Painting Work | 333.71 | 1.25 | 0 | 417.1375 | 75.08 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21051.5025 | SHAHI ENTERPRISES
1st Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 3rd Fl Common Staircase Ceiling OBD Painting Work | 162.9 | 1.25 | 0 | 203.625 | 36.66 | 2024-04-13 12:46 | Labour Charges for 1st OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -21265.015 | SHAHI ENTERPRISES
2nd Coat OBD (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Common Staircase Wall OBD Paint Work | 751.57 | 1.25 | 0 | 939.4625 | 169.1 | 2024-04-13 | Labour Charges for 2nd OBD Paint for staircase.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 106782 | 2024-04-15 | 21468.64 | 2024-05-06 13:32 | -20529.1775 | SHAHI ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg LG Fl Fire Staircase Ceiling OBD Painting Work | 345.09 | 1 | 0 | 345.09 | 62.12 | 2023-10-27 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4272.93 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg 1st Fl Fire Staircase Wall OBD Paint Work | 803.63 | 1 | 0 | 803.63 | 144.66 | 2023-10-27 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -3814.39 | ANIL MAHTO ENTERPRISES
1st Coat Putty (L) | N/C | N/C | PATHAN HABIB MEHATAB | 786 | 2023-09-30 | F-Bldg Stilt Fl Fire Staircase Ceiling OBD Painting Work | 344.23 | 1 | 0 | 344.23 | 61.96 | 2023-10-27 | Labour Charges for 1st Coat Putty for Staircase OBD Paint.Transportation of Raw material from store to required working place to be done by Contractor. | 100 |  | 103043 | 2023-10-27 | 4618.02 | 2023-11-07 13:57 | -4273.79 | ANIL MAHTO ENTERPRISES
6" R.C.C. Pipe laying | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 123 | 19 | 0 | 2337 | 0 | 2024-01-30 13:51 | Labour charges for 6 inch RCC pipe (Hume Pipe) Laying work for F-Bldg External Road side. | 100 |  | 104895 | 2024-01-30 | 20641 | 2024-02-09 11:07 | -18304 | JAISAN
Chamber Making -USL | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 5 | 1200 | 0 | 6000 | 0 | 2024-01-30 13:51 | Labour Charges for Chamber Making work (1ft 6inch x 3ft x 2ft 3inch) including Brickwork, Plaster, Internal Cement Ghotai, External Plaster, PCC Work, Chamber Cover Fixing work for F-Bldg External Road side. | 100 |  | 104895 | 2024-01-30 | 20641 | 2024-02-09 11:07 | -14641 | JAISAN
Chamber Making -USL | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 4 | 1200 | 0 | 4800 | 0 | 2024-01-30 13:51 | Labour Charges for Chamber Making work (2ft x 2ft x 2ft 6inch) including Brickwork, Plaster, Internal Cement Ghotai, External Plaster, PCC Work, Chamber Cover Fixing work for F-Bldg External Road side. | 100 |  | 104895 | 2024-01-30 | 20641 | 2024-02-09 11:07 | -15841 | JAISAN
Chamber Making -USL | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 1 | 1600 | 0 | 1600 | 0 | 2024-01-30 13:51 | Labour Charges for Chamber Making work (4ft x 4ft x 3ft) including Brickwork, Plaster, Internal Cement Ghotai, External Plaster, PCC Work, Chamber Cover Fixing work for F-Bldg External Road side. | 100 |  | 104895 | 2024-01-30 | 20641 | 2024-02-09 11:07 | -19041 | JAISAN
12" RCC Pipe Laying-USL | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 236.16 | 25 | 0 | 5904 | 0 | 2024-01-30 13:51 | Labour charges for 12 inch RCC pipe (Hume Pipe) Laying & Fixing work for F-Bldg External Road side. | 100 |  | 104895 | 2024-01-30 | 20641 | 2024-02-09 11:07 | -14737 | JAISAN
Chamber Rate Diff. - UDR | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 5 | 600 | 0 | 3000 | 0 | 2024-02-02 12:05 | Rate Difference for-Labour Charges for Chamber making work including Brickwork, Plaster, internal Cement Ghotai, External Plaster, PCC Work, Chamber Cover Fixing work for F-Bldg External Road side.-(1feet 6 inches x 3 feet x 2 feet 3 inches) | 100 |  | 105048 | 2024-02-05 | 7800 | 2024-02-19 15:28 | -4800 | JAISAN
Chamber Rate Diff. - UDR | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 4 | 600 | 0 | 2400 | 0 | 2024-02-02 12:05 | Rate Difference for-Labour Charges for Chamber making work including Brickwork, Plaster, internal Cement Ghotai, External Plaster, PCC Work, Chamber Cover Fixing work for F-Bldg External Road side.-(2 feet x 2 feet x 2 feet 6 inches) | 100 |  | 105048 | 2024-02-05 | 7800 | 2024-02-19 15:28 | -5400 | JAISAN
Chamber Rate Diff. - UDR | N/C | N/C | JAISAN | 788 | 2023-10-09 | F Bldg-Chamber- Bricks,Ghotai& Pipe Work | 1 | 2400 | 0 | 2400 | 0 | 2024-02-02 12:05 | Rate Difference for-Labour Charges for Chamber making work including Brickwork, Plaster, internal Cement Ghotai, External Plaster, PCC Work, Chamber Cover Fixing work for F-Bldg External Road side.-(4 feet x 4 feet x 3 feet ) | 100 |  | 105048 | 2024-02-05 | 7800 | 2024-02-19 15:28 | -5400 | JAISAN
12mm Toughned Glass work (L) | N/C | N/C | NAMOH GLASSES | 791 | 2023-10-24 | OPD-1 to 13 Door -Toughened Glass work | 39.771 | 55 | 0 | 2187.405 | 393.74 | 2023-11-07 14:08 | Labour charges for fixing of 12mm Toughned Glass including Twin pro section, H section, L section, Silicone sealant and rubber bedding for F-Bldg OPD. | 100 |  | 103387 | 2023-11-08 | 39695.81 | 2023-12-02 13:06 | -37508.405 | NAMOH GLASSES
12mm Toughned Glass Door (L). | N/C | N/C | NAMOH GLASSES | 791 | 2023-10-24 | OPD-1 to 13 Door -Toughened Glass work | 312.57 | 120 | 0 | 37508.4 | 6751.52 | 2023-11-07 14:08 | Labour charges for fixing of 12mm Toughned Glass Door including Doorset with lock 9400 enox,D-Handle H to H600mm Enox, Silicone sealant for F-Bldg OPD. | 100 |  | 103387 | 2023-11-08 | 39695.81 | 2023-12-02 13:06 | -2187.41 | NAMOH GLASSES
12mm Toughned Glass Door (M). | N/C | N/C | NAMOH GLASSES | 792 | 2023-10-24 | OPD-1 to 13 Door -Toughened Glass work | 347.305 | 480 | 0 | 166706.4 | 30007.16 | 2023-11-07 14:07 | Material supply charges for fixing of 12mm Toughned Glass Door including Doorset with lock 9400 enox,D-Handle H to H600mm Enox, Silicone sealant,Holes, Cutouts for F-Bldg OPD. | 100 |  | 103388 | 2023-11-08 | 176428.42 | 2023-12-02 13:06 | -9722.02 | NAMOH GLASSES
12mm Toughned Glass work (M) | N/C | N/C | NAMOH GLASSES | 792 | 2023-10-24 | OPD-1 to 13 Door -Toughened Glass work | 44.191 | 220 | 0 | 9722.02 | 1749.96 | 2023-11-07 14:07 | Material supply charges for fixing of 12mm Toughned Glass with Twin pro section, H section, L section, Silicone sealant and rubber bedding for F-Bldg OPD. | 100 |  | 103388 | 2023-11-08 | 176428.42 | 2023-12-02 13:06 | -166706.4 | NAMOH GLASSES
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 54 | 644 | 0 | 34776 | 6259.68 | 2024-02-02 | Material supply and Labour charges for fixing of Wall Panel-04. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -726364.75 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 186.552 | 644 | 0 | 120139.488 | 21625.1 | 2024-05-13 | Material supply and Labour charges for fixing of Wall Panel-07. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -886436.082 | ANAND FURNITURE AND INTERIOR
4 Seater Bench (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 1.8 | 12220 | 0 | 21996 | 3959.28 | 2024-05-13 | Material supply and Labour charges for fixing of 4 seater waiting Bench-SS. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -984579.57 | ANAND FURNITURE AND INTERIOR
Column Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 50.2425 | 799 | 0 | 40143.7575 | 7225.88 | 2024-05-13 | Material supply and Labour charges for fixing of Column Panel- Louvers. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -966431.8125 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 124.74 | 644 | 0 | 80332.56 | 14459.86 | 2024-05-13 | Material supply and Labour charges for fixing of Wall Panel-04. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -926243.01 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 174.24 | 644 | 0 | 112210.56 | 20197.9 | 2024-05-13 | Material supply and Labour charges for fixing of Wall Panel-05. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -894365.01 | ANAND FURNITURE AND INTERIOR
3 Seater Bench (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 5.4 | 10340 | 0 | 55836 | 10050.48 | 2024-05-13 | Material supply and Labour charges for fixing of 3 seater waiting Bench-SS. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -950739.57 | ANAND FURNITURE AND INTERIOR
Reception Chairs (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 5.4 | 8075 | 0 | 43605 | 7848.9 | 2024-05-13 | Material supply and Labour charges for fixing of Reception chairs- High Neck. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -962970.57 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 21.78 | 644 | 0 | 14026.32 | 2524.74 | 2024-05-13 | Material supply and Labour charges for fixing of Wall Panel-06. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -992549.25 | ANAND FURNITURE AND INTERIOR
Full Cushion round sofa (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 90 | 3431 | 0 | 308790 | 55582.2 | 2024-05-13 | Material supply and Labour charges for fixing of Full Cushion Round Sofa. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -697785.57 | ANAND FURNITURE AND INTERIOR
Storage Cabinet (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 28.44 | 1269 | 0 | 36090.36 | 6496.26 | 2024-05-13 | Material supply and Labour charges for fixing of Storage Cabinet at Wall Panel-01-A. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -970485.21 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 46.7796 | 644 | 0 | 30126.0624 | 5422.7 | 2024-05-13 | Material supply and Labour charges for fixing of Wall Panel-02. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -976449.5076 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 116.0768 | 644 | 0 | 74753.4592 | 13455.62 | 2024-05-13 | Material supply and Labour charges for fixing of Wall Panel-03. | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -931822.1108 | ANAND FURNITURE AND INTERIOR
Reception Table (M+L). | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 48.6 | 1410 | 0 | 68526 | 12334.68 | 2024-05-13 | Material supply and Labour charges for fixing of Reception Table (Size- 10ft x 4.5ft) | 100 |  | 108123 | 2024-06-08 | 1006575.57 | 2024-06-29 12:48 | -938049.57 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 72 | 644 | 0 | 46368 | 8346.24 | 2024-02-02 | Material supply and Labour charges for fixing of Wall Panel-03. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -714772.75 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 72 | 644 | 0 | 46368 | 8346.24 | 2024-02-02 | Material supply and Labour charges for fixing of Wall Panel-05. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -714772.75 | ANAND FURNITURE AND INTERIOR
Storage Cabinet (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 111.38 | 1282.5 | 0 | 142844.85 | 25712.08 | 2024-02-02 | Material supply and Labour charges for fixing of Storage Cabinet behind Reception table. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -618295.9 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 54 | 644 | 0 | 34776 | 6259.68 | 2024-02-02 | Material supply and Labour charges for fixing of Wall Panel-02. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -726364.75 | ANAND FURNITURE AND INTERIOR
Partition Work | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 111.38 | 705 | 0 | 78522.9 | 14134.12 | 2024-02-02 | Material supply and Labour charges for fixing of Partition work at Panel-2. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -682617.85 | ANAND FURNITURE AND INTERIOR
Reception Table (M+L). | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 135 | 1410 | 0 | 190350 | 34263 | 2024-02-02 | Material supply and Labour charges for fixing of Reception Table (Size- 10ft x 4.5ft) | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -570790.75 | ANAND FURNITURE AND INTERIOR
Wall Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 158.4006 | 644 | 0.01 | 102009.9864 | 18361.8 | 2024-02-02 | Material supply and Labour charges for fixing of Wall Panel-06. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -659130.7636 | ANAND FURNITURE AND INTERIOR
Column Panel (M+L) | N/C | N/C | ANAND FURNITURE AND INTERIOR | 793 | 2023-10-27 | F Bldg.-OPD Furniture Work | 106.5394 | 799 | 0.02 | 85124.9806 | 15322.5 | 2024-02-02 | Material supply and Labour charges for fixing of Column Panel- Louvers. | 100 |  | 104920 | 2024-02-02 | 761140.75 | 2024-02-05 11:38 | -676015.7694 | ANAND FURNITURE AND INTERIOR
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1207-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1208-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1306-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1106-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1405-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1408-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1105-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1407-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1205-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1306-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1307-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-708-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-906-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1206-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-908-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1105-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1107-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-806-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1008-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-805-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1207-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-808-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1205-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1208-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1208-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-807-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-808-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-706-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-708-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-907-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1007-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1008-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1106-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1105-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-705-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-905-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-907-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1207-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1108-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-906-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-908-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1006-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1205-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-705-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-707-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1506-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1508-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1308-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1405-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1007-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1406-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-705-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-11-07 18:22 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -238884.032 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1307-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1107-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1608-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-706-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-707-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:42 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236611.04 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-708-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1007-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1006-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1005-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1206-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-905-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-706-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Kitchen otta making | 10.232 | 420 | 0 | 4297.44 | 773.54 | 2023-11-07 16:14 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -236815.68 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-706-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Toilet door frame -granite work | 54.368 | 38 | 0 | 2065.984 | 371.88 | 2023-11-07 18:08 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -239047.136 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-705-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-707-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-11-07 16:20 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240113.12 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-11-07 18:33 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 103389 | 2023-11-08 | 241113.12 | 2023-11-23 11:38 | -240296 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1605-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1408-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1505-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1407-2BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1606-3BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-905-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-905-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-808-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-907-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-908-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-906-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1005-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2023-12-31 18:43 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -100328.44 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-707-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1008-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-605-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1308-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1005-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1108-2BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1106-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1107-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1108-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-31 18:40 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104035.16 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-806-3BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-807-2BHK Toilet door frame -granite work | 54.368 | 41 | 0 | 2229.088 | 401.24 | 2023-12-31 19:05 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -102806.072 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-708-2BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-805-3BHK Toilet door frame -granite work | 81.712 | 10 | 0 | 817.12 | 147.08 | 2023-12-31 19:11 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 104257 | 2024-01-01 | 105035.16 | 2024-02-02 14:30 | -104218.04 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-205-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1305-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-507-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-108-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-408-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1006-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-607-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-608-2BHK Toilet -ventilator frame | 15.432 | 41 | 0 | 632.712 | 113.88 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95023.528 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-406-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-505-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-007-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-407-2BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-106-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-508-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-206-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-207-2BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-005-3BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-306-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Toilet -ventilator frame | 15.432 | 10 | 0 | 154.32 | 27.78 | 2024-02-25 16:39 | Labour charges for Granite Edge Polish Work for Granite Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95501.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-308-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-405-3BHK Ledge wall top -granite work | 12.336 | 10 | 0 | 123.36 | 22.2 | 2024-02-25 16:47 | Labour charges for Granite Edge Polish Work for Granite Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95532.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Umbra Patti -granite work | 9.944 | 38 | 0 | 377.872 | 68.02 | 2024-02-25 15:50 | Labour charges for Granite Cutting & Fixing work for Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95278.368 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1206-3BHK Toilet door frame -granite work | 54.368 | 44 | 0 | 2392.192 | 430.6 | 2024-02-25 15:57 | Labour charges for Granite Cutting & Fixing work for Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -93264.048 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-006-3BHK Toilet -ventilator frame | 15.432 | 38 | 0 | 586.416 | 105.56 | 2024-02-25 16:10 | Labour charges for Granite Cutting & Fixing work for Toilet Ventilator for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95069.824 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-107-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-606-3BHK Ledge wall top -granite work | 12.336 | 41 | 0 | 505.776 | 91.04 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95150.464 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-506-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:34 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Cutting & fixing | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-307-2BHK Ledge wall top -granite work | 12.336 | 38 | 0 | 468.768 | 84.38 | 2024-02-25 16:17 | Labour charges for Granite Cutting & Fixing work for Ledge wall Top for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95187.472 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-008-2BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-105-3BHK Umbra Patti -granite work | 13.536 | 10 | 0 | 135.36 | 24.36 | 2024-02-25 16:24 | Labour charges for Granite Edge Polish Work for Granite Umbra Patti for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95520.88 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-208-2BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
Granite Edge Polish | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-305-3BHK Toilet door frame -granite work | 20.428 | 10 | 0 | 204.28 | 36.78 | 2024-02-25 16:30 | Labour charges for Granite Edge Polish Work for Granite Toilet Door Frame for E-Bldg Internal Flats. | 100 |  | 105572 | 2024-02-26 | 95656.24 | 2024-03-16 10:56 | -95451.96 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-808-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-805-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-806-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-806-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-807-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-805-3BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-807-2BHK Kitchen otta making | 10.232 | 440 | 0 | 4502.08 | 810.38 | 2023-12-24 22:56 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -39514.56 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-906-3BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-907-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
MS Angle (M+L). | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-908-2BHK MS angle support for kitchen otta work | 5 | 200 | 0 | 1000 | 180 | 2023-12-24 22:48 | Charges for Fixing of MS Angle below Granite Kitchen Otta for E-Bldg Internal Flats. | 100 |  | 104115 | 2023-12-25 | 44016.64 | 2024-01-23 14:25 | -43016.64 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1305-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1406-3BHK Kitchen otta making | 10.232 | 460 | 0 | 4706.72 | 847.2 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72237.92 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1507-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Kitchen Otta (L)- BC | N/C | N/C | SUNIL CONSTRUCTION AND CONTRACTORS | 797 | 2023-11-01 | E-1607-2BHK Kitchen otta making | 10.232 | 480 | 0 | 4911.36 | 884.04 | 2024-04-05 18:55 | Labour charges for Fixing of Granite Kitchen Otta work for E-Bldg Internal Flats | 100 |  | 106639 | 2024-04-08 | 76944.64 | 2024-05-03 13:21 | -72033.28 | SUNIL CONSTRUCTION AND CONTRACTORS
Texture Paint (L) | N/C | N/C | K RAMESH KUMAR | 807 | 2023-11-09 | P5 Floor D-Parking Wall Above 1.1m Ht Painting Work | 6779.114 | 7.5 | 0 | 50843.355 | 0 | 2024-01-05 | Labour Charges for Applying Texture Paint for D-Bldg Parking area Above 1.1m Height. | 100 |  | 104361 | 2024-01-08 | 244338.58 | 2024-03-23 12:24 | -193495.225 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | K RAMESH KUMAR | 807 | 2023-11-09 | P3 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8689.76 | 7.5 | 0 | 65173.2 | 0 | 2024-01-05 | Labour Charges for Applying Texture Paint for D-Bldg Parking area Above 1.1m Height. | 100 |  | 104361 | 2024-01-08 | 244338.58 | 2024-03-23 12:24 | -179165.38 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | K RAMESH KUMAR | 807 | 2023-11-09 | Ground Floor D-Parking Wall Above 1.1m Ht Painting Work | 3111.029 | 7.5 | 0 | 23332.7175 | 0 | 2024-01-05 | Labour Charges for Applying Texture Paint for D-Bldg Parking area Above 1.1m Height. | 100 |  | 104361 | 2024-01-08 | 244338.58 | 2024-03-23 12:24 | -221005.8625 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | K RAMESH KUMAR | 807 | 2023-11-09 | P1 Floor D-Parking Wall Above 1.1m Ht Painting Work | 6842.787 | 7.5 | 0 | 51320.9025 | 0 | 2024-01-05 | Labour Charges for Applying Texture Paint for D-Bldg Parking area Above 1.1m Height. | 100 |  | 104361 | 2024-01-08 | 244338.58 | 2024-03-23 12:24 | -193017.6775 | K RAMESH KUMAR
Texture Paint (L) | N/C | N/C | K RAMESH KUMAR | 807 | 2023-11-09 | P2 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7155.786 | 7.5 | 0 | 53668.395 | 0 | 2024-01-05 | Labour Charges for Applying Texture Paint for D-Bldg Parking area Above 1.1m Height. | 100 |  | 104361 | 2024-01-08 | 244338.58 | 2024-03-23 12:24 | -190670.185 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | K RAMESH KUMAR | 808 | 2023-11-09 | Ground Floor D-Parking Wall Above 1.1m Ht Painting Work | 3111.029 | 8 | 0 | 24888.232 | 0 | 2024-01-05 | Material supply charges of Texture Paint for D-Bldg Parking area above 1.1 meter height. | 100 |  | 104362 | 2024-01-08 | 260627.34 | 2024-03-23 12:23 | -235739.108 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | K RAMESH KUMAR | 808 | 2023-11-09 | P1 Floor D-Parking Wall Above 1.1m Ht Painting Work | 6842.787 | 8 | 0 | 54742.296 | 0 | 2024-01-05 | Material supply charges of Texture Paint for D-Bldg Parking area above 1.1 meter height. | 100 |  | 104362 | 2024-01-08 | 260627.34 | 2024-03-23 12:23 | -205885.044 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | K RAMESH KUMAR | 808 | 2023-11-09 | P2 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7155.786 | 8 | 0 | 57246.288 | 0 | 2024-01-05 | Material supply charges of Texture Paint for D-Bldg Parking area above 1.1 meter height. | 100 |  | 104362 | 2024-01-08 | 260627.34 | 2024-03-23 12:23 | -203381.052 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | K RAMESH KUMAR | 808 | 2023-11-09 | P3 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8689.675 | 8 | 0 | 69517.4 | 0 | 2024-01-05 | Material supply charges of Texture Paint for D-Bldg Parking area above 1.1 meter height. | 100 |  | 104362 | 2024-01-08 | 260627.34 | 2024-03-23 12:23 | -191109.94 | K RAMESH KUMAR
Texture Paint (M) | N/C | N/C | K RAMESH KUMAR | 808 | 2023-11-09 | P5 Floor D-Parking Wall Above 1.1m Ht Painting Work | 6779.14 | 8 | 0 | 54233.12 | 0 | 2024-01-05 | Material supply charges of Texture Paint for D-Bldg Parking area above 1.1 meter height. | 100 |  | 104362 | 2024-01-08 | 260627.34 | 2024-03-23 12:23 | -206394.22 | K RAMESH KUMAR
Lift Scaffolding Work BC | N/C | N/C | ADLER | 814 | 2023-11-22 | D-Bldg Lift Scaffolding Work | 0.3 | 65000 | 0 | 19500 | 3510 | 2024-04-27 | Material & Labour Charges for Lift Scaffolding work including all required accessories MS Pipe, Coupler,Joint pipe, Loading, Unloading, Fixing & Removing work. | 100 |  | 107138 | 2024-04-29 | 19500 | 2024-05-28 19:02 | 0 | ADLER
Lift Scaffolding Work BC | N/C | N/C | ADLER | 814 | 2023-11-22 | D-Bldg Lift Scaffolding Work | 1 | 65000 | 0 | 65000 | 11700 | 2024-04-03 | Material & Labour Charges for Lift Scaffolding work including all required accessories MS Pipe, Coupler,Joint pipe, Loading, Unloading, Fixing & Removing work. | 100 |  | 106635 | 2024-04-08 | 65000 | 2024-05-28 19:02 | 0 | ADLER
Lift Scaffolding Work BC | N/C | N/C | ADLER | 814 | 2023-11-22 | D-Bldg Lift Scaffolding Work | 0.69 | 65000 | 0 | 44850 | 8073 | 2023-12-20 | Material & Labour Charges for Lift Scaffolding work including all required accessories MS Pipe, Coupler,Joint pipe, Loading, Unloading, Fixing & Removing work. | 100 |  | 104095 | 2023-12-25 | 44850 | 2024-01-16 15:33 | 0 | ADLER
Lift Pit Cleaning Work - BC | N/C | N/C | PRAKASH SAHU | 819 | 2023-11-24 | D Building Lift Pit Cleaning | 1 | 4500 | 0 | 4500 | 0 | 2024-07-17 | Labour charges for D-Bldg Lift pit cleaning work including Sludge and debris,breaking work including breaker for further civil work & Erection of lift | 100 |  | 109234 | 2024-07-22 | 4500 | 1900-01-01 | 0 | PRAKASH SAHU
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 820 | 2023-11-24 | D Bldg.-Lift Door Barrication Work | 6 | 500 | 0 | 3000 | 0 | 2023-12-25 | Labour charges for lift Door Barrication work for D-Bldg including Horizontal & Vertical Pipe fixing. | 100 |  | 104189 | 2023-12-25 | 3000 | 2024-01-16 15:08 | 0 | SURESH RANGNATH SHITOLE
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 820 | 2023-11-24 | D Bldg.-Lift Door Barrication Work | 12 | 500 | 0 | 6000 | 0 | 2024-01-25 | Labour charges for lift Door Barrication work for D-Bldg including Horizontal & Vertical Pipe fixing. | 100 |  | 104858 | 2024-01-29 | 6000 | 2024-03-12 14:35 | 0 | SURESH RANGNATH SHITOLE
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 820 | 2023-11-24 | D Bldg.-Lift Door Barrication Work | 4 | 500 | 0 | 2000 | 0 | 2024-06-24 | Labour charges for lift Door Barrication work for D-Bldg including Horizontal & Vertical Pipe fixing. | 100 |  | 108553 | 2024-06-24 | 2000 | 2024-08-05 13:52 | 0 | SURESH RANGNATH SHITOLE
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 820 | 2023-11-24 | D Bldg.-Lift Door Barrication Work | 6 | 500 | 0 | 3000 | 0 | 2024-02-03 | Labour charges for lift Door Barrication work for D-Bldg including Horizontal & Vertical Pipe fixing. | 100 |  | 105065 | 2024-02-05 | 3000 | 2024-03-02 12:02 | 0 | SURESH RANGNATH SHITOLE
Tapping Screw- Den | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 600 | 2.5 | 0 | 1500 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-3 2 inchesTappimg Screws Fixing | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -22646.82 | GURUDATTA KRUPA ENTERPRISES
MS Pipe Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 614.4 | 12 | 0 | 7372.8 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-03 (40 x40x 16 Guage)MS Pipe Fixing | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -16774.02 | GURUDATTA KRUPA ENTERPRISES
GI Sheet Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 1085 | 5 | 0 | 5425 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-3 GI Sheet Fixing. | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -18721.82 | GURUDATTA KRUPA ENTERPRISES
MS Pipe Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 614.4 | 6 | 0 | 3686.4 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-02 (40 x40x 16 Guage) MS Pipe Removing | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -20460.42 | GURUDATTA KRUPA ENTERPRISES
MS Pipe Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 254.16 | 12 | 0 | 3049.92 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-03 (40 x40x 16 Guage)MS Pipe Fixing | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -21096.9 | GURUDATTA KRUPA ENTERPRISES
GI Sheet Removing - DCW | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 1085 | 2.5 | 0 | 2712.5 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-2 GI Sheet removing | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -21434.32 | GURUDATTA KRUPA ENTERPRISES
MS Pipe Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 66.7 | 6 | 0 | 400.2 | 0 | 2024-02-01 | Labour Charges for D-Bldg Lift-02 (40 x40x 16 Guage) MS Pipe Removing | 100 |  | 106361 | 2024-03-21 | 24146.82 | 2024-03-27 10:41 | -23746.62 | GURUDATTA KRUPA ENTERPRISES
Fabrication Work | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-MS Jali fabrication work at Lift Shaft door for safety | 634.49 | 10 | 0 | 6344.9 | 0 | 2024-07-15 | Labour charges for Fixing of MS Jali Fabrication work in old steel 18mm & 12mm Bar for Safety purpose for D-Bldg Lift shaft door. | 100 |  | 109116 | 2024-07-15 | 6344.9 | 2024-08-05 13:52 | 0 | SURESH RANGNATH SHITOLE
GI Sheet Removing - DCW | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 434 | 2.5 | 0 | 1085 | 0 | 2024-05-19 16:54 | Labour Charges for D-Bldg Lift-2 GI Sheet removing | 100 |  | 107681 | 2024-05-20 | 20385 | 2024-07-15 14:59 | -19300 | SURESH RANGNATH SHITOLE
MS Pipe Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 179 | 6 | 0 | 1074 | 0 | 2024-01-30 | Labour Charges for D-Bldg Lift-02 (40 x40x 16 Guage) MS Pipe Removing | 100 |  | 105008 | 2024-02-05 | 2277.42 | 1900-01-01 | -1203.42 | SURESH RANGNATH SHITOLE
GI Sheet Removing - DCW | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 162.6 | 2.5 | 0 | 406.5 | 0 | 2024-01-27 | Labour Charges for D-Bldg Lift-2 GI Sheet removing | 100 |  | 105334 | 2024-02-17 | 2388.74 | 2024-02-19 15:15 | -1982.24 | SURESH RANGNATH SHITOLE
GI Sheet Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 108.4 | 5 | 0 | 542 | 0 | 2024-01-27 | Labour Charges for D-Bldg Lift-3 GI Sheet Fixing. | 100 |  | 105334 | 2024-02-17 | 2388.74 | 2024-02-19 15:15 | -1846.74 | SURESH RANGNATH SHITOLE
MS Pipe Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 61.44 | 12 | 0 | 737.28 | 0 | 2024-01-27 | Labour Charges for D-Bldg Lift-03 (40 x40x 16 Guage)MS Pipe Fixing | 100 |  | 105334 | 2024-02-17 | 2388.74 | 2024-02-19 15:15 | -1651.46 | SURESH RANGNATH SHITOLE
Tapping Screw- Den | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift3-Fixing of G.I Sheet & MS Pipe | 60 | 2.5 | 0 | 150 | 0 | 2024-01-27 | Labour Charges for D-Bldg Lift-3 2 inchesTappimg Screws Fixing | 100 |  | 105334 | 2024-02-17 | 2388.74 | 2024-02-19 15:15 | -2238.74 | SURESH RANGNATH SHITOLE
MS Pipe Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | D-Lift2-Removing of G.I Sheet & MS Pipe | 92.16 | 6 | 0 | 552.96 | 0 | 2024-01-27 | Labour Charges for D-Bldg Lift-02 (40 x40x 16 Guage) MS Pipe Removing | 100 |  | 105334 | 2024-02-17 | 2388.74 | 2024-02-19 15:15 | -1835.78 | SURESH RANGNATH SHITOLE
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 823 | 2023-11-24 | E Bldg.-Lift Door Barrication Work | 16 | 500 | 0 | 8000 | 0 | 2024-02-05 | Labour charges for Lift Door Barrication work for E-Bldg including Horizontal & vertical pipe fixing. | 100 |  | 105078 | 2024-02-05 | 8000 | 2024-03-07 11:22 | 0 | SURESH RANGNATH SHITOLE
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 823 | 2023-11-24 | E Bldg.-Lift Door Barrication Work | 1 | 500 | 0 | 500 | 0 | 2024-02-10 17:15 | Labour charges for Lift Door Barrication work for E-Bldg including Horizontal & vertical pipe fixing. | 100 |  | 105242 | 2024-02-12 | 1000 | 2024-03-02 12:02 | -500 | SURESH RANGNATH SHITOLE
Barrication fixing work | N/C | N/C | SURESH RANGNATH SHITOLE | 823 | 2023-11-24 | E Bldg.-Lift Door Barrication Work | 1 | 500 | 0 | 500 | 0 | 2024-02-10 17:19 | Labour charges for Lift Door Barrication work for E-Bldg including Horizontal & vertical pipe fixing. | 100 |  | 105242 | 2024-02-12 | 1000 | 2024-03-02 12:02 | -500 | SURESH RANGNATH SHITOLE
Breaking Work-BRE | N/C | N/C | PRAKASH SAHU | 824 | 2023-11-24 | Extra work F Bldg.-North Side Chajja Breaking Work | 6 | 800 | 0 | 4800 | 0 | 2023-11-30 14:43 | Labour charges for Chajja Breaking work including all required tools & Equipments, breaker,operater,etc for F-Bldg. | 100 |  | 103603 | 2023-12-04 | 4800 | 1900-01-01 | 0 | PRAKASH SAHU
Grinding work- BC | N/C | N/C | HB POLYTECH INDUSTRIES | 835 | 2023-12-05 | P2 Floor D-RCC Surface Grinding Work | 5553.02 | 6.97 | 0 | 38704.5494 | 6966.82 | 2024-03-18 | Charges for RCC Surface grinding work/Floor preparation work with mechanical grinding by (Pneumatic tools) Diamond wheel,Bushing/Brushing wheel including dry cleaning,dust removal,loose material removal before & after grinding. | 100 |  | 107871 | 2024-05-29 | 117863.33 | 2024-05-29 12:47 | -79158.7806 | HB POLYTECH INDUSTRIES
Grinding work- BC | N/C | N/C | HB POLYTECH INDUSTRIES | 835 | 2023-12-05 | P1 Floor D-RCC Surface Grinding Work | 5613.27 | 6.97 | 0 | 39124.4919 | 7042.4 | 2024-03-18 | Charges for RCC Surface grinding work/Floor preparation work with mechanical grinding by (Pneumatic tools) Diamond wheel,Bushing/Brushing wheel including dry cleaning,dust removal,loose material removal before & after grinding. | 100 |  | 107871 | 2024-05-29 | 117863.33 | 2024-05-29 12:47 | -78738.8381 | HB POLYTECH INDUSTRIES
Grinding work- BC | N/C | N/C | HB POLYTECH INDUSTRIES | 835 | 2023-12-05 | P3 Floor D-RCC Surface Grinding Work | 5743.8 | 6.97 | 0 | 40034.286 | 7206.18 | 2024-03-18 | Charges for RCC Surface grinding work/Floor preparation work with mechanical grinding by (Pneumatic tools) Diamond wheel,Bushing/Brushing wheel including dry cleaning,dust removal,loose material removal before & after grinding. | 100 |  | 107871 | 2024-05-29 | 117863.33 | 2024-05-29 12:47 | -77829.044 | HB POLYTECH INDUSTRIES
GI Strip 25 x 6mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 150 | 158 | 0 | 2370 | 426.6 | 2024-06-25 | After Completion of all work | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -401882.26 | VAHAS TECHNO SOLUTIONS
Copper Bonded steel rod (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 9 | 4700 | 0 | 4230 | 761.4 | 2024-06-25 | Advance along with Work order | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -400022.26 | VAHAS TECHNO SOLUTIONS
Vertical Air termination 1000mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 6 | 1534 | 0 | 920.4 | 165.68 | 2024-06-25 | Advance along with Work order | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -403331.86 | VAHAS TECHNO SOLUTIONS
Lighting Event Counter (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 1 | 13245.75 | 0 | 1324.575 | 238.42 | 2024-06-25 | Advance along with Work order | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -402927.685 | VAHAS TECHNO SOLUTIONS
8mm Al solid round conductor (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 1473 | 210.5 | 0 | 31006.65 | 5581.2 | 2024-06-25 | Advance along with Work order | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -373245.61 | VAHAS TECHNO SOLUTIONS
Vertical Air termination 500mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 4 | 1434 | 0 | 573.6 | 103.24 | 2024-06-25 | After Completion of all work | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -403678.66 | VAHAS TECHNO SOLUTIONS
GI Strip 25 x 6mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 150 | 158 | 0 | 18960 | 3412.8 | 2024-06-25 | After Delivery of material at Site | 80 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -385292.26 | VAHAS TECHNO SOLUTIONS
Copper Bonded steel rod (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 9 | 4700 | 0 | 33840 | 6091.2 | 2024-06-25 | After Delivery of material at Site | 80 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -370412.26 | VAHAS TECHNO SOLUTIONS
Vertical Air termination 1000mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 6 | 1534 | 0 | 920.4 | 165.68 | 2024-06-25 | After Completion of all work | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -403331.86 | VAHAS TECHNO SOLUTIONS
Lighting Event Counter (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 1 | 13245.75 | 0 | 1324.575 | 238.42 | 2024-06-25 | After Completion of all work | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -402927.685 | VAHAS TECHNO SOLUTIONS
Vertical Air termination 500mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 4 | 1434 | 0 | 4588.8 | 825.98 | 2024-06-25 | After Delivery of material at Site | 80 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -399663.46 | VAHAS TECHNO SOLUTIONS
Vertical Air termination 500mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 4 | 1434 | 0 | 573.6 | 103.24 | 2024-06-25 | Advance along with Work order | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -403678.66 | VAHAS TECHNO SOLUTIONS
Copper Bonded steel rod (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 9 | 4700 | 0 | 4230 | 761.4 | 2024-06-25 | After Completion of all work | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -400022.26 | VAHAS TECHNO SOLUTIONS
8mm Al solid round conductor (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 1473 | 210.5 | 0 | 248053.2 | 44649.58 | 2024-06-25 | After Delivery of material at Site | 80 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -156199.06 | VAHAS TECHNO SOLUTIONS
8mm Al solid round conductor (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 1473 | 210.5 | 0 | 31006.65 | 5581.2 | 2024-06-25 | After Completion of all work | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -373245.61 | VAHAS TECHNO SOLUTIONS
Vertical Air termination 1000mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 6 | 1534 | 0 | 7363.2 | 1325.38 | 2024-06-25 | After Delivery of material at Site | 80 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -396889.06 | VAHAS TECHNO SOLUTIONS
GI Strip 25 x 6mm (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 150 | 158 | 0 | 2370 | 426.6 | 2024-06-25 | Advance along with Work order | 10 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -401882.26 | VAHAS TECHNO SOLUTIONS
Lighting Event Counter (M) | N/C | N/C | VAHAS TECHNO SOLUTIONS | 842 | 2023-12-09 | D Bldg-Lighting Arrestor | 1 | 13245.75 | 0 | 10596.6 | 1907.38 | 2024-06-25 | After Delivery of material at Site | 80 |  | 108631 | 2024-06-28 | 404252.26 | 2024-08-07 11:17 | -393655.66 | VAHAS TECHNO SOLUTIONS
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 161 | 338.7 | 0 | 54530.7 | 0 | 2024-06-03 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of MAY-2024 | 100 |  | 107974 | 2024-06-03 | 100482.1 | 2024-06-27 18:36 | -45951.4 | DIAMOND SHINE CLEAN SERVICES
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 128.0012 | 338.7 | -0.01 | 43354.0064 | 0 | 2024-02-10 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of JANUARY-2024 | 100 |  | 105236 | 2024-02-12 | 43354 | 2024-03-20 15:40 | 0.00644 | DIAMOND SHINE CLEAN SERVICES
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 22 | 338.7 | 0 | 7451.4 | 0 | 2024-06-03 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of MARCH-2024 | 100 |  | 107974 | 2024-06-03 | 100482.1 | 2024-06-27 18:36 | -93030.7 | DIAMOND SHINE CLEAN SERVICES
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 110 | 350 | 0 | 38500 | 0 | 2024-06-03 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of APRIL-2024 | 100 |  | 107974 | 2024-06-03 | 100482.1 | 2024-06-27 18:36 | -61982.1 | DIAMOND SHINE CLEAN SERVICES
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 70.5 | 362.068 | 0 | 25525.794 | 0 | 2024-03-18 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of FEBRUARY-2024 | 100 |  | 106187 | 2024-03-18 | 25525.79 | 2024-03-20 15:39 | 0.004 | DIAMOND SHINE CLEAN SERVICES
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 57.0003 | 338.7 | 0 | 19306.0016 | 0 | 2024-01-15 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of DECEMBER-2023 | 100 |  | 104668 | 2024-01-22 | 19306 | 2024-02-05 15:40 | 0.00161 | DIAMOND SHINE CLEAN SERVICES
Female Coolie - SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 862 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 91.5 | 350 | 0 | 32025 | 0 | 2024-07-08 | Charges for Female Coolie (6 No/ Day) for Housekeeping & Cleaning work for the month of JUNE-2024 | 100 |  | 108934 | 2024-07-08 | 32025 | 2024-08-05 13:57 | 0 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-07-08 | Material Charges for Housekeeping & Cleaning work for the month of JUNE-2024 | 100 |  | 108942 | 2024-07-08 | 3000 | 2024-08-05 13:57 | 0 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-06-06 | Material Charges for Housekeeping & Cleaning work for the month of MARCH-2024 | 100 |  | 108192 | 2024-06-10 | 9000 | 2024-06-26 11:42 | -6000 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-06-06 | Material Charges for Housekeeping & Cleaning work for the month of APRIL-2024 | 100 |  | 108192 | 2024-06-10 | 9000 | 2024-06-26 11:42 | -6000 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-06-06 | Material Charges for Housekeeping & Cleaning work for the month of MAY-2024 | 100 |  | 108192 | 2024-06-10 | 9000 | 2024-06-26 11:42 | -6000 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-03-18 | Material Charges for Housekeeping & Cleaning work for the month of FEBRUARY-2024 | 100 |  | 106188 | 2024-03-18 | 3000 | 2024-03-20 15:40 | 0 | DIAMOND SHINE CLEAN SERVICES
Housekeeping work-SOS | N/C | N/C | DIAMOND SHINE CLEAN SERVICES | 863 | 2023-12-15 | D Bldg.-Housekeeping & Cleaning Work | 1 | 3000 | 0 | 3000 | 0 | 2024-02-10 | Material Charges Housekeeping & Cleaning for the month of JANUARY-2024 | 100 |  | 105238 | 2024-02-12 | 3000 | 2024-03-20 15:40 | 0 | DIAMOND SHINE CLEAN SERVICES
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.202 Dhar Core work-(L) (2BHK) Near Refuge | 1 | 11500 | 0 | 11500 | 2070 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108379 | 2024-06-17 | 64500 | 2024-07-15 14:58 | -53000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.602 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108379 | 2024-06-17 | 64500 | 2024-07-15 14:58 | -51000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.1401 Dhar Core Work-(L) (3BHK) | 1 | 15000 | 0 | 15000 | 2700 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108379 | 2024-06-17 | 64500 | 2024-07-15 14:58 | -49500 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.1407 Dhar Core Work-(L) (2BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108379 | 2024-06-17 | 64500 | 2024-07-15 14:58 | -51500 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.404 Dhar Core Work-(L) (2BHK) | 1 | 900 | 0 | 900 | 162 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -97600 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.407 Dhar Core Work-(L) (2BHK) | 1 | 2900 | 0 | 2900 | 522 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -95600 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.302 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -85000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.304 Dhar Core Work-(L) (2BHK) | 1 | 900 | 0 | 900 | 162 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -97600 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.603 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -87000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.303 Dhar Core Work-(L) (2BHK) | 1 | 900 | 0 | 900 | 162 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -97600 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.604 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108379 | 2024-06-17 | 64500 | 2024-07-15 14:58 | -53000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.508 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-16 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107236 | 2024-04-30 | 34500 | 2024-05-03 13:19 | -23000 | AAKRUTI ENTERPRISES
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.505 Dhar Core Work-(L) (3BHK) | 1 | 3380 | 0 | 3380 | 608.4 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -95120 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.408 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -87000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.301 Dhar Core Work-(L) (3BHK) | 1 | 1380 | 0 | 1380 | 248.4 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -97120 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.506 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -85000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.401 Dhar Core Work-(L) (3BHK) | 1 | 2340 | 0 | 2340 | 421.2 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -96160 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.502 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-01-31 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105023 | 2024-02-05 | 38500 | 2024-02-19 15:16 | -25000 | RUSHIYOGI ENTERPRISES
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.504 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-01-31 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105023 | 2024-02-05 | 38500 | 2024-02-19 15:16 | -27000 | RUSHIYOGI ENTERPRISES
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.607 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107236 | 2024-04-30 | 34500 | 2024-05-03 13:19 | -23000 | AAKRUTI ENTERPRISES
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.608 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107236 | 2024-04-30 | 34500 | 2024-05-03 13:19 | -23000 | AAKRUTI ENTERPRISES
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.1102 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -96500 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.501 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -85000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.403 Dhar Core Work-(L) (2BHK) | 1 | 1700 | 0 | 1700 | 306 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -96800 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.405 Dhar Core Work-(L) (3BHK) | 1 | 1380 | 0 | 1380 | 248.4 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -97120 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.406 Dhar Core Work-(L) (3BHK) | 1 | 1380 | 0 | 1380 | 248.4 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -97120 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.101 Dhar Core Work-(L) (3BHK) | 1 | 2340 | 0 | 2340 | 421.2 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -96160 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.402 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104844 | 2024-01-29 | 98500 | 2024-02-19 15:19 | -85000 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SHREE RAM INTERIOR & DECORATORS | 893 | 2023-12-26 | D-Flat.No.306 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-01-31 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105023 | 2024-02-05 | 38500 | 2024-02-19 15:16 | -25000 | RUSHIYOGI ENTERPRISES
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | D&EBldg.-Between Podium Driveway(1stSlab)-Rebaring Work | 128 | 230 | 0 | 29440 | 5299.2 | 2024-01-24 | Labour charges for Rebarring work of 12mm bar with 200mm depth for D & E Bldg Between Podium drive way 1st Slab S/8. | 100 | Doc No-52 ,ACK No- 122318268532696 | 104759 | 2024-01-24 | 61180 | 2024-02-28 11:09 | -31740 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 110 | 200 | 0 | 22000 | 3960 | 2024-07-21 11:55 | Labour charges for 10mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -83235 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 169 | 260 | 0 | 43940 | 7909.2 | 2024-07-21 11:55 | Labour charges for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -61295 | AVCON TECHNICS PVT LTD
Rebarring work 12mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | EBldg.-Podium,Ramp-Rebaring Work | 124 | 260 | 0 | 32240 | 5803.2 | 2024-07-21 11:55 | Labour charges for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for E-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -72995 | AVCON TECHNICS PVT LTD
Rebarring work 12mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | EBldg.-Podium,Ramp-Rebaring Work | 174 | 230 | 0 | 40020 | 7203.6 | 2024-01-24 | Labour charges for Rebarring work of 12mm Bar with 200mm depth for E-Bldg Podium Driveway slab S/8 1st Slab. | 100 | Doc-59, Ack No-122318618965055 | 104760 | 2024-01-24 | 41600 | 2024-02-28 11:09 | -1580 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 1 | 230 | 0 | 230 | 41.4 | 2024-01-24 | Labour charges for Rebarring work of 12mm Bar with 200mm Depth for D-Bldg Podium Driveway 2nd Slab. | 100 | Doc-59, Ack No-122318618965055 | 104760 | 2024-01-24 | 41600 | 2024-02-28 11:09 | -41370 | AVCON TECHNICS PVT LTD
Rebarring work 8mm dia- BPo | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 5 | 175 | 0 | 875 | 157.5 | 2024-07-21 11:55 | Labour charges for 8mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -104360 | AVCON TECHNICS PVT LTD
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 1 | 500 | 0 | 500 | 90 | 2024-07-22 11:44 | Labour charges for 16mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Podium Ramp work. | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -104735 | AVCON TECHNICS PVT LTD
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 3 | 450 | 0 | 1350 | 243 | 2024-01-24 | Labour charges for Rebarring work of 16mm Bar with 200mm depth for D-Bldg Podium Driveway 2nd slab. | 100 | Doc-59, Ack No-122318618965055 | 104760 | 2024-01-24 | 41600 | 2024-02-28 11:09 | -40250 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | DBldg.-Podium,Ramp-Rebaring Work | 138 | 230 | 0 | 31740 | 5713.2 | 2024-01-24 | Labour charges for Rebarring work of 12mm Bar with 200mm Depth for D-Bldg Podium Driveway 2nd Slab. | 100 | Doc No-52 ,ACK No- 122318268532696 | 104759 | 2024-01-24 | 61180 | 2024-02-28 11:09 | -29440 | AVCON TECHNICS PVT LTD
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1206-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1208-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1501-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-207-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-403-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-706-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1007-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-403-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-504-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-705-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1508-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-906-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1101-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1401-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1408-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1507-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1404-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1406-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1503-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-303-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1305-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-104-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1001-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1301-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-108-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1205-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1206-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1207-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1502-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1504-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-107-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-601-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-801-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1004-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-701-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1104-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-105-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-508-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1005-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1204-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1406-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1002-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1204-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-703-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-904-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1102-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1304-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-207-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-501-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-903-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-905-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1102-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-705-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1001-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1201-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1503-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1504-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:47 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-108-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-203-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-504-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-605-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-801-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-606-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1203-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1405-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1502-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-103-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-205-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-403-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1001-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1204-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1301-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-102-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-305-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-503-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-604-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-607-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-808-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1107-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1301-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-201-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-303-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-507-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-604-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-606-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1007-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1106-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-804-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1407-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-106-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-607-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-707-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1006-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1008-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1303-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1407-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-203-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1104-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-601-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1003-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1307-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-208-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-301-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-502-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-902-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1103-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1304-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-101-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-103-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-106-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1305-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1306-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1507-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:10 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-703-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-903-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1306-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1308-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1507-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:47 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-401-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-602-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-803-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-201-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-204-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-208-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-501-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-608-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-901-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1101-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1304-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-304-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-204-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-404-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-406-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-503-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-708-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-805-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1402-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-804-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1501-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-204-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-301-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1008-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1308-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-305-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-901-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1302-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1505-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-404-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-704-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-902-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-905-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1508-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:10 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-703-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-704-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1105-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-506-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-603-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-907-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1303-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1501-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-505-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1203-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-107-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1405-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-508-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-802-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-803-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1005-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1405-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1208-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-201-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-401-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1404-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1408-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-401-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-602-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-603-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1003-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-302-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-206-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-302-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-408-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-608-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-904-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1306-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1307-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-504-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-605-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1401-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-306-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1108-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1203-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1208-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1502-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-806-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-808-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1308-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-505-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-707-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1404-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-708-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-101-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-302-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-405-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-402-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-404-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-502-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-805-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-901-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-906-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1506-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-25 17:43 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-304-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-25 18:10 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -545264.88 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1006-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1402-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-102-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-104-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-706-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-807-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-908-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1108-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1403-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-608-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-903-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1103-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1105-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1106-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1505-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:10 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1506-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:10 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-407-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-701-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-807-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-908-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1101-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-101-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-103-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-304-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-907-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-104-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-105-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-106-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-306-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-507-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1006-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1007-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1205-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1407-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1403-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-502-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-506-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-704-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-705-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-706-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-905-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1104-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-601-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-603-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-406-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-408-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-904-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1508-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:47 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-107-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1105-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1401-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1506-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:47 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-607-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-701-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-808-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1003-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1201-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-604-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-804-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-805-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-806-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1005-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1408-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-206-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-301-3BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-407-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1004-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1207-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1406-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-906-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1106-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1107-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1307-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-508-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-902-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1008-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1303-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1305-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1505-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:47 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-707-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-907-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1102-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1402-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1503-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-303-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-503-2BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-802-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1302-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-307-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-308-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-402-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-806-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-708-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1302-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1403-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1504-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:10 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-203-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-205-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-405-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-506-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-605-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:20 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-507-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-24 18:41 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -550845.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-802-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-803-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1002-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1207-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1108-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-602-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-801-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 18:51 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1004-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1205-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1206-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-24 19:06 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -553170.56 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-105-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-108-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:14 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1107-2BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1201-3BHK MS Folding Door work | 14.528 | 100 | 0 | 1452.8 | 261.5 | 2024-02-24 19:24 | Providing and Fixing of Galvanized Folding Door frame for internal flat Kitchen Dry Balcony.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105567 | 2024-02-26 | 555495.76 | 2024-03-12 14:34 | -554042.96 | TATHAWADE INDUSTRIES
Galv. Folding Door - Shutter (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-505-3BHK MS Folding Door work | 46.504 | 220 | 0 | 10230.88 | 1841.56 | 2024-02-09 19:39 | Providing and Fixing of 4 fold Galvanized Folding Door Shutter for living area attched terrce of internal flat.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by Contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -391563.68 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-307-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-308-2BHK MS Folding Door work | 46.504 | 100 | 0 | 4650.4 | 837.08 | 2024-02-09 18:58 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -397144.16 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-807-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-908-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1002-3BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:36 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Galv. Folding Door - Door Frame (M) | N/C | N/C | TATHAWADE INDUSTRIES | 897 | 2023-12-30 | E-1103-2BHK MS Folding Door work | 23.252 | 100 | 0 | 2325.2 | 418.54 | 2024-02-05 19:43 | Providing and Fixing of 4 Fold Galvanized Folding Door frame for internal flat attched terrace.Transportation,Loading/Unloading and Shifting of material from store to required working place to be done by contractor. | 100 |  | 105216 | 2024-02-12 | 401794.56 | 2024-03-12 14:35 | -399469.36 | TATHAWADE INDUSTRIES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2008 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-05-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107500 | 2024-05-13 | 13000 | 2024-06-04 15:16 | -2000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2107 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-06-03 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107946 | 2024-06-03 | 22000 | 2024-06-15 11:44 | -11000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2008 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 2024-08-08 11:17 | -8000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2108 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 2024-08-08 11:17 | -8000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2007 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 2024-08-08 11:17 | -8000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1207 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -72000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1907 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108463 | 2024-06-19 | 4000 | 2024-07-05 11:34 | -2000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1206 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-05-12 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 107500 | 2024-05-13 | 13000 | 2024-06-04 15:16 | -11000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1905 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 2024-08-08 11:17 | -8000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2105 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108545 | 2024-06-24 | 40274 | 2024-08-05 13:56 | -27274 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1708 Dhar Core Work-(L) (2BHK) | 0.0364 | 11000 | 0 | 400.4 | 72.08 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108545 | 2024-06-24 | 40274 | 2024-08-05 13:56 | -39873.6 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2105 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-23 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109431 | 2024-07-29 | 10000 | 2024-08-08 11:17 | -8000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1705 Dhar Core Work-(L) (3BHK) | 0.2 | 13000 | 0 | 2600 | 468 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108178 | 2024-06-10 | 7000 | 2024-06-15 11:43 | -4400 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1708 Dhar Core Work-(L) (2BHK) | 0.2 | 11000 | 0 | 2200 | 396 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108178 | 2024-06-10 | 7000 | 2024-06-15 11:43 | -4800 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2006 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108545 | 2024-06-24 | 40274 | 2024-08-05 13:56 | -27274 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1707 Dhar Core Work-(L) (2BHK) | 0.0364 | 11000 | 0 | 400.4 | 72.08 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108545 | 2024-06-24 | 40274 | 2024-08-05 13:56 | -39873.6 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1707 Dhar Core Work-(L) (2BHK) | 0.2 | 11000 | 0 | 2200 | 396 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108178 | 2024-06-10 | 7000 | 2024-06-15 11:43 | -4800 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1907 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106765 | 2024-04-15 | 22000 | 2024-05-06 12:11 | -11000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1908 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106765 | 2024-04-15 | 22000 | 2024-05-06 12:11 | -11000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1906 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109509 | 2024-08-05 | 133000 | 2024-08-08 11:17 | -131000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2006 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109509 | 2024-08-05 | 133000 | 2024-08-08 11:17 | -131000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2107 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109509 | 2024-08-05 | 133000 | 2024-08-08 11:17 | -131000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1203 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106766 | 2024-04-15 | 8000 | 2024-05-03 13:24 | -6000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1208 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106766 | 2024-04-15 | 8000 | 2024-05-03 13:24 | -6000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2005 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-04-27 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107143 | 2024-04-29 | 37000 | 2024-06-04 15:15 | -24000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2007 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-04-27 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107143 | 2024-04-29 | 37000 | 2024-06-04 15:15 | -26000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1908 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108463 | 2024-06-19 | 4000 | 2024-07-05 11:34 | -2000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1705 Dhar Core Work-(L) (3BHK) | 0.0364 | 13000 | 0 | 473.2 | 85.18 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108545 | 2024-06-24 | 40274 | 2024-08-05 13:56 | -39800.8 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1905 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-04-27 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107143 | 2024-04-29 | 37000 | 2024-06-04 15:15 | -24000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2108 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-06-03 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107946 | 2024-06-03 | 22000 | 2024-06-15 11:44 | -11000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1204 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -72000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1206 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -70000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1208 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -72000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2005 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109509 | 2024-08-05 | 133000 | 2024-08-08 11:17 | -131000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1201 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -70000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1205 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -70000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1203 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104854 | 2024-01-29 | 83000 | 2024-02-19 15:18 | -72000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1202 Dhar Core work-(L) (2BHK) Near Refuge | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 2024-08-05 13:56 | -52000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1706 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 2024-08-05 13:56 | -50000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2306 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 2024-08-05 13:56 | -50000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2305 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 2024-08-05 13:56 | -50000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1906 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109243 | 2024-07-22 | 63000 | 2024-08-05 13:56 | -50000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1205 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106766 | 2024-04-15 | 8000 | 2024-05-03 13:24 | -6000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.1207 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106766 | 2024-04-15 | 8000 | 2024-05-03 13:24 | -6000 | G M ENTERPRISES
Dhar Core | N/C | N/C | G M ENTERPRISES | 898 | 2024-01-03 | D-Flat.No.2106 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108545 | 2024-06-24 | 40274 | 2024-08-05 13:56 | -27274 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1604 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 0 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104843 | 2024-01-29 | 37000 | 2024-02-19 15:18 | -26000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2301 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 2024-08-05 13:57 | -35000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1703 Dhar Core Work-(L) (2BHK) | 0.0364 | 11000 | 0 | 400.4 | 72.08 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109321 | 2024-07-26 | 1274 | 2024-08-05 13:57 | -873.6 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1704 Dhar Core Work-(L) (2BHK) | 0.0364 | 11000 | 0 | 400.4 | 72.08 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109321 | 2024-07-26 | 1274 | 2024-08-05 13:57 | -873.6 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1903 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106767 | 2024-04-15 | 11000 | 2024-05-06 12:09 | 0 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.008 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-03-02 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105727 | 2024-03-04 | 36500 | 2024-03-16 10:55 | -25000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2203 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-04-20 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106999 | 2024-04-22 | 22000 | 2024-05-03 13:22 | -11000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2204 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-04-20 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106999 | 2024-04-22 | 22000 | 2024-05-03 13:22 | -11000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2201 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-05-25 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107788 | 2024-05-27 | 13000 | 2024-06-03 12:35 | 0 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2002 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106768 | 2024-04-15 | 32000 | 2024-05-03 13:24 | -19000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.003 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105563 | 2024-02-26 | 38500 | 2024-03-18 12:12 | -27000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2003 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 0 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105321 | 2024-02-15 | 22000 | 2024-02-19 15:22 | -11000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1904 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105321 | 2024-02-15 | 22000 | 2024-02-19 15:22 | -11000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2304 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109510 | 2024-08-05 | 47000 | 1900-01-01 | -45000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2004 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109510 | 2024-08-05 | 47000 | 1900-01-01 | -45000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.006 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-03-02 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105727 | 2024-03-04 | 36500 | 2024-03-16 10:55 | -23000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.007 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-03-02 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105727 | 2024-03-04 | 36500 | 2024-03-16 10:55 | -25000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2002 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-05-12 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 107501 | 2024-05-13 | 15000 | 2024-06-04 15:14 | -13000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2304 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 2024-08-05 13:57 | -37000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2303 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 2024-08-05 13:57 | -37000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1601 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 0 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104843 | 2024-01-29 | 37000 | 2024-02-19 15:18 | -24000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.001 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105563 | 2024-02-26 | 38500 | 2024-03-18 12:12 | -25000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.002 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105563 | 2024-02-26 | 38500 | 2024-03-18 12:12 | -25000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1902 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-03-16 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106106 | 2024-03-18 | 26000 | 2024-03-28 12:42 | -13000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1901 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-03-16 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106106 | 2024-03-18 | 26000 | 2024-03-28 12:42 | -13000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1701 Dhar Core Work-(L) (3BHK) | 0.2 | 13000 | 0 | 2600 | 468 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108177 | 2024-06-10 | 7000 | 2024-06-15 11:43 | -4400 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1703 Dhar Core Work-(L) (2BHK) | 0.2 | 11000 | 0 | 2200 | 396 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108177 | 2024-06-10 | 7000 | 2024-06-15 11:43 | -4800 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2201 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 109510 | 2024-08-05 | 47000 | 1900-01-01 | -45000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1903 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108462 | 2024-06-19 | 2000 | 2024-07-05 11:35 | 0 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1602 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106768 | 2024-04-15 | 32000 | 2024-05-03 13:24 | -30000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2001 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-05-12 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 107501 | 2024-05-13 | 15000 | 2024-06-04 15:14 | -13000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2004 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-05-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107501 | 2024-05-13 | 15000 | 2024-06-04 15:14 | -4000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2001 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106768 | 2024-04-15 | 32000 | 2024-05-03 13:24 | -19000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1604 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106768 | 2024-04-15 | 32000 | 2024-05-03 13:24 | -30000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1601 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 106768 | 2024-04-15 | 32000 | 2024-05-03 13:24 | -30000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2204 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108639 | 2024-06-28 | 12000 | 2024-07-05 11:33 | -10000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2203 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108639 | 2024-06-28 | 12000 | 2024-07-05 11:33 | -10000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1902 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108639 | 2024-06-28 | 12000 | 2024-07-05 11:33 | -10000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2003 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108639 | 2024-06-28 | 12000 | 2024-07-05 11:33 | -10000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1904 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108639 | 2024-06-28 | 12000 | 2024-07-05 11:33 | -10000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1901 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum work in schedule for D-Bldg internal flats. | 100 |  | 108639 | 2024-06-28 | 12000 | 2024-07-05 11:33 | -10000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1602 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 0 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104843 | 2024-01-29 | 37000 | 2024-02-19 15:18 | -24000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1701 Dhar Core Work-(L) (3BHK) | 0.0364 | 13000 | 0 | 473.2 | 85.18 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109321 | 2024-07-26 | 1274 | 2024-08-05 13:57 | -800.8 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.004 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108367 | 2024-06-17 | 25000 | 2024-07-15 14:58 | -13500 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1704 Dhar Core Work-(L) (2BHK) | 0.2 | 11000 | 0 | 2200 | 396 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108177 | 2024-06-10 | 7000 | 2024-06-15 11:43 | -4800 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.1603 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-16 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107237 | 2024-04-30 | 11000 | 2024-05-03 13:18 | 0 | AAKRUTI ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.2302 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-07-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 109242 | 2024-07-22 | 48000 | 2024-08-05 13:57 | -35000 | G M ENTERPRISES
Dhar Core | N/C | N/C | SANTOSHI POP CONTRACTOR | 899 | 2024-01-03 | D-Flat.No.005 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108367 | 2024-06-17 | 25000 | 2024-07-15 14:58 | -11500 | SHREE RAM INTERIOR & DECORATORS
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.2104 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-05-25 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107780 | 2024-05-27 | 11000 | 2024-06-03 12:34 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1507 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1608 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.804 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -88000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.806 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -86000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.801 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -86000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.805 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -86000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.807 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -88000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.802 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -86000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.803 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -88000 | J K INTERIOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.808 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105034 | 2024-02-05 | 99500 | 2024-03-01 12:28 | -88500 | J K INTERIOR
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1505 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1504 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -98000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1506 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -96000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1507 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -98000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1501 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -96000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1406 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108461 | 2024-06-19 | 8000 | 2024-07-05 11:35 | -6000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1402 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108461 | 2024-06-19 | 8000 | 2024-07-05 11:35 | -6000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1403 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108461 | 2024-06-19 | 8000 | 2024-07-05 11:35 | -6000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.2103 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108461 | 2024-06-19 | 8000 | 2024-07-05 11:35 | -6000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1405 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108544 | 2024-06-24 | 26400.4 | 2024-08-05 13:56 | -13400.4 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1503 Dhar Core Work-(L) (2BHK) | 0.0364 | 11000 | 0 | 400.4 | 72.08 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108544 | 2024-06-24 | 26400.4 | 2024-08-05 13:56 | -26000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1404 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 18:20 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108272 | 2024-06-10 | 4000 | 2024-06-24 12:27 | -2000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1408 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 18:20 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108272 | 2024-06-10 | 4000 | 2024-06-24 12:27 | -2000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1606 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-06-22 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108544 | 2024-06-24 | 26400.4 | 2024-08-05 13:56 | -13400.4 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1605 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -96000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1505 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -96000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1607 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -98000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1502 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -96000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1608 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105239 | 2024-02-12 | 109000 | 2024-02-19 15:20 | -98000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1404 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104852 | 2024-01-29 | 11000 | 2024-02-19 15:22 | 0 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.2101 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-05-12 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107507 | 2024-05-13 | 24000 | 2024-06-04 15:16 | -11000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.2103 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-05-12 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107507 | 2024-05-13 | 24000 | 2024-06-04 15:16 | -13000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1503 Dhar Core Work-(L) (2BHK) | 0.2 | 11000 | 0 | 2200 | 396 | 2024-06-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 | Balance & repairing work done by GM enterprises | 108179 | 2024-06-10 | 2200 | 2024-06-15 11:43 | 0 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1605 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1503 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1504 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1607 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106771 | 2024-04-15 | 14000 | 2024-05-03 13:24 | -12000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1403 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105564 | 2024-02-26 | 37000 | 1900-01-01 | -26000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1402 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105564 | 2024-02-26 | 37000 | 1900-01-01 | -24000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1405 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109511 | 2024-08-05 | 4000 | 2024-08-08 11:15 | -2000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1606 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109511 | 2024-08-05 | 4000 | 2024-08-08 11:15 | -2000 | G M ENTERPRISES
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1408 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105032 | 2024-02-05 | 11000 | 2024-03-18 12:13 | 0 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | J K INTERIOR | 900 | 2024-01-03 | D-Flat.No.1406 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105564 | 2024-02-26 | 37000 | 1900-01-01 | -24000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.605 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105741 | 2024-03-04 | 13500 | 2024-03-18 12:20 | 0 | P R PATEL INTERIOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.606 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107235 | 2024-04-30 | 16400 | 2024-05-03 13:19 | -2900 | AAKRUTI ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1104 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1304 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.907 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.902 Dhar Core Work-(L) (3BHK) | 1 | 4800 | 0 | 4800 | 864 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -153760 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1006 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -145560 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1006 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1007 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.908 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1104 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.905 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1804 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105035 | 2024-02-05 | 35000 | 2024-03-18 12:13 | -24000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.707 Dhar Core Work-(L) (2BHK) | 1 | 11500 | 0 | 11500 | 2070 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105038 | 2024-02-05 | 25000 | 2024-03-01 12:29 | -13500 | J K INTERIOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.701 Dhar Core Work-(L) (3BHK) | 1 | 13500 | 0 | 13500 | 2430 | 2024-02-01 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105038 | 2024-02-05 | 25000 | 2024-03-01 12:29 | -11500 | J K INTERIOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.903 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1801 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106770 | 2024-04-15 | 6000 | 2024-05-03 13:24 | -4000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1805 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106770 | 2024-04-15 | 6000 | 2024-05-03 13:24 | -4000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1002 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.904 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.906 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1803 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105035 | 2024-02-05 | 35000 | 2024-03-18 12:13 | -24000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.902 Dhar Core Work-(L) (3BHK) | 1 | 8200 | 0 | 8200 | 1476 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -89480 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1108 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -86680 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.704 Dhar Core Work-(L) (2BHK) | 1 | 8600 | 0 | 8600 | 1548 | 2024-02-28 | Labour charges for internal flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -89080 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.002 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.003 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1106 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1106 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-03-16 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 106107 | 2024-03-18 | 13000 | 2024-03-28 12:41 | 0 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1008 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1002 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.904 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1802 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105562 | 2024-02-26 | 31800 | 2024-03-18 12:12 | -18800 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1305 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-05-25 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107786 | 2024-05-27 | 13000 | 2024-06-03 12:34 | 0 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1908 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.2203 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.001 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1807 Dhar Core Work-(L) (2BHK) | 0.8 | 11000 | 0 | 8800 | 1584 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105240 | 2024-02-12 | 56600 | 2024-02-19 15:17 | -47800 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.902 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.901 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1104 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1003 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -86680 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.908 Dhar Core Work-(L) (2BHK) | 0.01 | 11000 | 0 | 110 | 19.8 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -97570 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1101 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -84680 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1001 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -84680 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.708 Dhar Core Work-(L) (2BHK) | 1 | 8600 | 0 | 8600 | 1548 | 2024-02-28 | Labour charges for internal flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -89080 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1105 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -84680 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.903 Dhar Core Work-(L) (2BHK) | 0.01 | 4000 | 0 | 40 | 7.2 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -97640 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.905 Dhar Core Work-(L) (3BHK) | 0.01 | 13000 | 0 | 130 | 23.4 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -97550 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1103 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-02-28 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105671 | 2024-03-04 | 97680 | 2024-03-18 12:12 | -86680 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1005 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105562 | 2024-02-26 | 31800 | 2024-03-18 12:12 | -18800 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.704 Dhar Core Work-(L) (2BHK) | 1 | 2900 | 0 | 2900 | 522 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105562 | 2024-02-26 | 31800 | 2024-03-18 12:12 | -28900 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.708 Dhar Core Work-(L) (2BHK) | 1 | 2900 | 0 | 2900 | 522 | 2024-02-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105562 | 2024-02-26 | 31800 | 2024-03-18 12:12 | -28900 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1303 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104855 | 2024-01-29 | 35000 | 2024-02-19 15:18 | -24000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1808 Dhar Core Work-(L) (2BHK) | 0.8 | 11000 | 0 | 8800 | 1584 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105240 | 2024-02-12 | 56600 | 2024-02-19 15:17 | -47800 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1805 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105240 | 2024-02-12 | 56600 | 2024-02-19 15:17 | -43600 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1803 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108357 | 2024-06-17 | 6000 | 2024-07-05 11:36 | -4000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1904 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1903 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.2003 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.2104 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1307 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104855 | 2024-01-29 | 35000 | 2024-02-19 15:18 | -24000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.2103 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1108 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1802 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1002 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -145560 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.708 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1408 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-07-24 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 109380 | 2024-07-29 | 2000 | 1900-01-01 | -1000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1404 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-07-24 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 109380 | 2024-07-29 | 2000 | 1900-01-01 | -1000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.705 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1806 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-05-12 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 107509 | 2024-05-13 | 6000 | 2024-06-04 15:14 | -4000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1808 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-05-12 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 107509 | 2024-05-13 | 6000 | 2024-06-04 15:14 | -4000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1807 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-05-12 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 107509 | 2024-05-13 | 6000 | 2024-06-04 15:14 | -4000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1301 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105035 | 2024-02-05 | 35000 | 2024-03-18 12:13 | -22000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.901 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.901 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -145560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.706 Dhar Core Work-(L) (3BHK) | 1 | 3380 | 0 | 3380 | 608.4 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -155180 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.906 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -145560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1107 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.705 Dhar Core Work-(L) (3BHK) | 1 | 3380 | 0 | 3380 | 608.4 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -155180 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1008 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1007 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.904 Dhar Core Work-(L) (2BHK) | 1 | 11000 | 0 | 11000 | 1980 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -147560 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.903 Dhar Core Work-(L) (2BHK) | 1 | 7000 | 0 | 7000 | 1260 | 2024-01-23 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104830 | 2024-01-29 | 158560 | 2024-02-19 15:22 | -151560 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.704 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.706 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.903 Dhar Core Work-(L) (2BHK) | 0.99 | 4000 | 0 | 3960 | 712.8 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 106769 | 2024-04-15 | 27720 | 2024-05-30 11:27 | -23760 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.905 Dhar Core Work-(L) (3BHK) | 0.99 | 13000 | 0 | 12870 | 2316.6 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 106769 | 2024-04-15 | 27720 | 2024-05-30 11:27 | -14850 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1107 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.908 Dhar Core Work-(L) (2BHK) | 0.99 | 11000 | 0 | 10890 | 1960.2 | 2024-04-11 | Labour charges for Internal Flat Gypsum work Dhar core, Katch vertical & horizontal,Butt finish,Door & window jambs including all tools, equipments & accessories. | 100 |  | 106769 | 2024-04-15 | 27720 | 2024-05-30 11:27 | -16830 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1902 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1306 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-04-11 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 106770 | 2024-04-15 | 6000 | 2024-05-03 13:24 | -4000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1008 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1004 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1802 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108357 | 2024-06-17 | 6000 | 2024-07-05 11:36 | -4000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1804 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108357 | 2024-06-17 | 6000 | 2024-07-05 11:36 | -4000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1101 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1301 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1001 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.903 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1101 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.908 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.906 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1301 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1304 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.905 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.907 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1006 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1007 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-09 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108181 | 2024-06-10 | 36000 | 2024-06-24 12:27 | -34000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1303 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-03-02 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 105735 | 2024-03-04 | 2000 | 2024-03-16 10:55 | 0 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1302 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-01-24 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 104855 | 2024-01-29 | 35000 | 2024-02-19 15:18 | -22000 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1806 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105240 | 2024-02-12 | 56600 | 2024-02-19 15:17 | -43600 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1801 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-02-10 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 105240 | 2024-02-12 | 56600 | 2024-02-19 15:17 | -43600 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.507 Dhar Core Work-(L) (2BHK) | 1 | 2900 | 0 | 2900 | 522 | 2024-02-04 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107235 | 2024-04-30 | 16400 | 2024-05-03 13:19 | -13500 | AAKRUTI ENTERPRISES
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1108 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 18:20 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108273 | 2024-06-10 | 6000 | 2024-06-24 12:26 | -4000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.907 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1106 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 18:20 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108273 | 2024-06-10 | 6000 | 2024-06-24 12:26 | -4000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1005 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-10 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108273 | 2024-06-10 | 6000 | 2024-06-24 12:26 | -4000 | A K INTERIOR CONTRACTOR
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.702 Dhar Core work-(L) (2BHK) Near Refuge | 0.8 | 11500 | 0 | 9200 | 1656 | 2024-06-14 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 108359 | 2024-06-17 | 9200 | 2024-07-15 14:57 | 0 | SHREE RAM INTERIOR & DECORATORS
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.703 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109507 | 2024-08-05 | 16700 | 2024-08-08 11:14 | -14700 | G M ENTERPRISES
Dhar Core | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1306 Dhar Core Work-(L) (3BHK) | 1 | 13000 | 0 | 13000 | 2340 | 2024-04-27 | Labour charges for Internal Flat Gypsum work Dhar Core, Katch vertical & Horizontal,Butt finish, Door & window jambs all work with schedule & Quality, Safety,etc.including all tools,equipments & accessories. | 100 |  | 107142 | 2024-04-29 | 13000 | 2024-06-04 15:15 | 0 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.2101 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1907 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1304 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1804 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.2204 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1803 Dhar Core Work-(L) (2BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1901 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1005 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 13:00 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108509 | 2024-06-24 | 24000 | 2024-08-05 13:56 | -23000 | G M ENTERPRISES
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.902 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Dhar Core (L) (Rate Diff.) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1001 Dhar Core Work-(L) (3BHK) | 1 | 1000 | 0 | 1000 | 180 | 2024-06-19 12:42 | Labour Charges & Rate Diff. for D-Bldg Internal Flat Dhar Core & Katch work. | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -21000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1107 Dhar Core Work-(L) (2BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-06-18 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 108460 | 2024-06-19 | 22000 | 2024-07-05 11:35 | -20000 | A K INTERIOR CONTRACTOR
Schedule (Gypsum Work) | N/C | N/C | A K INTERIOR CONTRACTOR | 901 | 2024-01-03 | D-Flat.No.1305 Dhar Core Work-(L) (3BHK) | 1 | 2000 | 0 | 2000 | 360 | 2024-07-31 | Charges for Gypsum Dhar core,katch,Butt finish work in schedule for D-Bldg Internal Flat | 100 |  | 109507 | 2024-08-05 | 16700 | 2024-08-08 11:14 | -14700 | G M ENTERPRISES
GI Sheet Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 904 | 2024-01-10 | D-Store Room Making Work | 525.32 | 5 | 0 | 2626.6 | 0 | 2024-01-22 | Labour Charges for GI Sheet fixing for D-Bldg lift material store room making & Dismantling work | 100 |  | 104689 | 2024-01-22 | 4747.28 | 2024-02-19 15:20 | -2120.68 | SURESH RANGNATH SHITOLE
MS Pipe Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 904 | 2024-01-10 | D-Store Room Making Work | 152.14 | 12 | 0 | 1825.68 | 0 | 2024-01-22 | Labour Chrarges for MS Pipe with 16 guage 40 x 40 Fixingfor D-Bldg Lift material store room making work& Dismantling work | 100 |  | 104689 | 2024-01-22 | 4747.28 | 2024-02-19 15:20 | -2921.6 | SURESH RANGNATH SHITOLE
Tapping Screw- Den | N/C | N/C | SURESH RANGNATH SHITOLE | 904 | 2024-01-10 | D-Store Room Making Work | 78 | 2.5 | 0 | 195 | 0 | 2024-01-22 | Labour Charges for 2 inches Tapping screws for D-Bldg Lift material store room making work & Dismantling work. | 100 |  | 104689 | 2024-01-22 | 4747.28 | 2024-02-19 15:20 | -4552.28 | SURESH RANGNATH SHITOLE
Door Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 904 | 2024-01-10 | D-Store Room Making Work | 1 | 100 | 0 | 100 | 0 | 2024-01-22 | Labour Charges for Old Door Fixing only for D-Bldg Lift material store room making work & Dismantling work | 100 |  | 104689 | 2024-01-22 | 4747.28 | 2024-02-19 15:20 | -4647.28 | SURESH RANGNATH SHITOLE
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg LG Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P2 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P3 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg Ground Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P5 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P3 Floor BBM & Plaster Work | 0.75 | 2000 | 0 | 1500 | 270 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -50200 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P1 Floor BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg Ground Floor BBM & Plaster Work | 0.75 | 2000 | 0 | 1500 | 270 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -50200 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P5 Floor BBM & Plaster Work | 0.75 | 2000 | 0 | 1500 | 270 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -50200 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 18th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg Stilt Fl Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 1 | 2000 | 0 | 2000 | 360 | 2024-02-14 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 105367 | 2024-02-19 | 62000 | 2024-03-01 11:46 | -60000 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg LG Floor BBM & Plaster Work | 0.25 | 2000 | 0 | 500 | 90 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -51200 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 20th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 23rd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 21st Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P1 Floor BBM & Plaster Work | 0.75 | 2000 | 0 | 1500 | 270 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -50200 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg P2 Floor BBM & Plaster Work | 0.75 | 2000 | 0 | 1500 | 270 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -50200 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 8th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 5th Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 0.95 | 2000 | 0 | 1900 | 342 | 2024-05-04 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 107377 | 2024-05-07 | 51700 | 2024-05-28 19:05 | -49800 | JAI SEVALAL CONSTRUCTION
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 16th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 24th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 10th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 11th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 4th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 7th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 9th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 1st Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 13th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 14th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 22nd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 6th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 12th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 2nd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 3rd Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 17th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 19th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
Blockwork & Plaster Rate Diff. | N/C | N/C | JAI SEVALAL CONSTRUCTION | 905 | 2024-01-10 | D-Bldg 15th Fl-Lobby Common Lobby BBM & Plaster Work | 0.5 | 2000 | 0 | 1000 | 180 | 2024-07-01 | Labour charges and Rate Diff. for Blockwork & Applying Sand Face Plaster for Lift Wall (Lift-01, Lift-02 & Lift-03) for D-Bldg. | 100 |  | 108687 | 2024-07-01 | 25000 | 2024-08-05 13:56 | -24000 | SHUBHAM SURENDRA BAHADUR SINGH
2 Coat Oil Paint (M+L) | N/C | N/C | AAKRUTI ENTERPRISES | 908 | 2024-01-17 | F-Bldg OPD+Com Area Rolling Shutter Work | 868.2784 | 10 | 0 | 8682.784 | 1562.9 | 2024-04-07 | Material & Labour charges for Applying 2 Coat Oil paint on Red oxide for Rolling Shutter Painting work in F-Bldg for stilt,1st,2nd & 3rd Floor. | 100 |  | 106659 | 2024-04-08 | 8682.78 | 2024-07-15 11:05 | 0.004 | TEJASHREE ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 509.75 | 7.5 | 0 | 3823.125 | 688.16 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328056.955 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 382.52 | 7.5 | 0 | 2868.9 | 516.4 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329011.18 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 16.84 | 7.5 | 0 | 126.3 | 22.74 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -331753.78 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 951 | 7.5 | 0 | 7132.5 | 1283.86 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -324747.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Southside Acrylic Texture Paint | 1203 | 7.5 | 0 | 9022.5 | 1624.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322857.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 482.37 | 7.5 | 0 | 3617.775 | 651.2 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328262.305 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Southside Acrylic Texture Paint | 1203.48 | 7.5 | 0 | 9026.1 | 1624.7 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322853.98 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Southside Acrylic Texture Paint | 1203 | 7.5 | 0 | 9022.5 | 1624.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322857.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 133.87 | 7.5 | 0 | 1004.025 | 180.72 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -330876.055 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Westside Acrylic Texture Paint | 616.03 | 7.5 | 0 | 4620.225 | 831.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327259.855 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 459.52 | 7.5 | 0 | 3446.4 | 620.36 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328433.68 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 469 | 7.5 | 0 | 3517.5 | 633.16 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328362.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 500 | 7.5 | 0 | 3750 | 675 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328130.08 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 382.34 | 7.5 | 0 | 2867.55 | 516.16 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329012.53 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 369.12 | 7.5 | 0 | 2768.4 | 498.32 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329111.68 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 149.26 | 7.5 | 0 | 1119.45 | 201.5 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -330760.63 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 356.72 | 7.5 | 0 | 2675.4 | 481.58 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -55280.36 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Westside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 160.06 | 7.5 | 0 | 1200.45 | 216.08 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56755.31 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 160.06 | 7.5 | 0 | 1200.45 | 216.08 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56755.31 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 127.75 | 7.5 | 0 | 958.125 | 172.46 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56997.635 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 258.39 | 7.5 | 0 | 1937.925 | 348.82 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56017.835 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 418.45 | 7.5 | 0 | 3138.375 | 564.9 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54817.385 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Northside Acrylic Texture Paint | 446.58 | 7.5 | 0 | 3349.35 | 602.88 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -110774.19 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 157.63 | 7.5 | 0 | 1182.225 | 212.8 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112941.315 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Northside Acrylic Texture Paint | 446.58 | 7.5 | 0 | 3349.35 | 602.88 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -110774.19 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 188.19 | 7.5 | 0 | 1411.425 | 254.06 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112712.115 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 335.84 | 7.5 | 0 | 2518.8 | 453.38 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -111604.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 208.09 | 7.5 | 0 | 1560.675 | 280.92 | 2024-04-18 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112562.865 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 219.46 | 7.5 | 0 | 1645.95 | 296.28 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112477.59 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Eastside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 248.3 | 7.5 | 0 | 1862.25 | 335.2 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56093.51 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 258.39 | 7.5 | 0 | 1937.925 | 348.82 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56017.835 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Eastside Acrylic Texture Paint | 482.16 | 7.5 | 0 | 3616.2 | 650.92 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54339.56 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 516.78 | 7.5 | 0 | 3875.85 | 697.66 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54079.91 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Eastside Acrylic Texture Paint | 354.41 | 7.5 | 0 | 2658.075 | 478.46 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -55297.685 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Eastside Acrylic Texture Paint | 262.7 | 7.5 | 0 | 1970.25 | 354.64 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112153.29 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 98.41 | 7.5 | 0 | 738.075 | 132.86 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113385.465 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 98.41 | 7.5 | 0 | 738.075 | 132.86 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113385.465 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 157.63 | 7.5 | 0 | 1182.225 | 212.8 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112941.315 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 157.63 | 7.5 | 0 | 1182.225 | 212.8 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112941.315 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 317.69 | 7.5 | 0 | 2382.675 | 428.88 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -111740.865 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Northside Acrylic Texture Paint | 446.58 | 7.5 | 0 | 3349.35 | 602.88 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -110774.19 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 188.19 | 7.5 | 0 | 1411.425 | 254.06 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112712.115 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 208.09 | 7.5 | 0 | 1560.675 | 280.92 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112562.865 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 157.63 | 7.5 | 0 | 1182.225 | 212.8 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112941.315 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Eastside Acrylic Texture Paint | 219.46 | 7.5 | 0 | 1645.95 | 296.28 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112477.59 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 199.09 | 7.5 | 0 | 1493.175 | 268.78 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112630.365 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 219.46 | 7.5 | 0 | 1645.95 | 296.28 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112477.59 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 286.52 | 7.5 | 0 | 2148.9 | 386.8 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -111974.64 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 208.09 | 7.5 | 0 | 1560.675 | 280.92 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112562.865 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Northside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113653.74 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -109760.94 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | electrical duct 1st coat primer work | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Labour charges for Applying 1 coat water Base Primer on wall surface including proper cleaning,tools & Equipments for D-Bldg Hidden Duct. | 100 | Fire duct 1st coat primer | 107657 | 2024-05-20 | 10234.6 | 2024-07-15 15:19 | -10064.6 | TEJASHREE ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 516.78 | 7.5 | 0 | 3875.85 | 697.66 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -54079.91 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 361.11 | 7.5 | 0 | 2708.325 | 487.5 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -55247.435 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 356.72 | 7.5 | 0 | 2675.4 | 481.58 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -55280.36 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 258.39 | 7.5 | 0 | 1937.925 | 348.82 | 2024-02-24 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 105560 | 2024-02-26 | 57955.76 | 2024-03-12 14:24 | -56017.835 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 262.7 | 7.5 | 0 | 1970.25 | 354.64 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112153.29 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Eastside Acrylic Texture Paint | 219.46 | 7.5 | 0 | 1645.95 | 296.28 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112477.59 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Westside Acrylic Texture Paint | 616.03 | 7.5 | 0 | 4620.225 | 831.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327259.855 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 459.52 | 7.5 | 0 | 3446.4 | 620.36 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328433.68 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 459.52 | 7.5 | 0 | 3446.4 | 620.36 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328433.68 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 158.25 | 7.5 | 0 | 1186.875 | 213.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -330693.205 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Southside Acrylic Texture Paint | 990 | 7.5 | 0 | 7425 | 1336.5 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -324455.08 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 581.68 | 7.5 | 0 | 4362.6 | 785.26 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -43827 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Southside Acrylic Texture Paint | 62.64 | 7.5 | 0 | 469.8 | 84.56 | 2024-04-13 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106790 | 2024-04-15 | 48189.6 | 2024-05-06 12:55 | -47719.8 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 594 | 3.5 | 0 | 2079 | 374.22 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329801.08 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Westside Acrylic Texture Paint | 616.03 | 7.5 | 0 | 4620.225 | 831.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327259.855 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 594 | 3.5 | 0 | 2079 | 374.22 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329801.08 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Westside Acrylic Texture Paint | 616 | 7.5 | 0 | 4620 | 831.6 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327260.08 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Southside Acrylic Texture Paint | 594 | 3.5 | 0 | 2079 | 374.22 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329801.08 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Eastside Acrylic Texture Paint | 91.71 | 7.5 | 0 | 687.825 | 123.8 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113435.715 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 208.09 | 7.5 | 0 | 1560.675 | 280.92 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112562.865 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 594 | 3.5 | 0 | 2079 | 374.22 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329801.08 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Southside Acrylic Texture Paint | 1203 | 7.5 | 0 | 9022.5 | 1624.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322857.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 133.1 | 7.5 | 0 | 998.25 | 179.68 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -330881.83 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 133.87 | 7.5 | 0 | 1004.025 | 180.72 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -330876.055 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 413.75 | 7.5 | 0 | 3103.125 | 558.56 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328776.955 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 1045.74 | 7.5 | 0 | 7843.05 | 1411.74 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -324037.03 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 790.91 | 7.5 | 0 | 5931.825 | 1067.72 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -325948.255 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 382.52 | 7.5 | 0 | 2868.9 | 516.4 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329011.18 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 538.32 | 7.5 | 0 | 4037.4 | 726.74 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327842.68 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 383 | 7.5 | 0 | 2872.5 | 517.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329007.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Westside Acrylic Texture Paint | 616.03 | 7.5 | 0 | 4620.225 | 831.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327259.855 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 882.33 | 7.5 | 0 | 6617.475 | 1191.14 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -325262.605 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 487.06 | 7.5 | 0 | 3652.95 | 657.54 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328227.13 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Southside Acrylic Texture Paint | 1203 | 7.5 | 0 | 9022.5 | 1624.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322857.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Westside Acrylic Texture Paint | 616.03 | 7.5 | 0 | 4620.225 | 831.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327259.855 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 561 | 7.5 | 0 | 4207.5 | 757.36 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327672.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 317.69 | 7.5 | 0 | 2382.675 | 428.88 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -111740.865 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 446.58 | 7.5 | 0 | 3349.35 | 602.88 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -110774.19 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 690 | 7.5 | 0 | 5175 | 931.5 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -326705.08 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 382.52 | 7.5 | 0 | 2868.9 | 516.4 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329011.18 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Southside Acrylic Texture Paint | 1203 | 7.5 | 0 | 9022.5 | 1624.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322857.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Westside Acrylic Texture Paint | 621.84 | 7.5 | 0 | 4663.8 | 839.48 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327216.28 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 594 | 3.5 | 0 | 2079 | 374.22 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329801.08 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 369.12 | 7.5 | 0 | 2768.4 | 498.32 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329111.68 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 455.02 | 7.5 | 0 | 3412.65 | 614.28 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -328467.43 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Westside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for West side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329784.105 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 539.77 | 7.5 | 0 | 4048.275 | 728.7 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327831.805 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 785.12 | 7.5 | 0 | 5888.4 | 1059.92 | 2024-05-31 15:36 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -325991.68 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Southside Acrylic Texture Paint | 1203 | 7.5 | 0 | 9022.5 | 1624.06 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -322857.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 133.87 | 7.5 | 0 | 1004.025 | 180.72 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -330876.055 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Westside Acrylic Texture Paint | 616.03 | 7.5 | 0 | 4620.225 | 831.64 | 2024-05-31 16:09 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -327259.855 | RAHUL PATIL
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Southside Acrylic Texture Paint | 701 | 3.5 | 0 | 2453.5 | 441.64 | 2024-06-02 11:22 | Labour charges for Scaffolding fixing & Removing work for South side External Texture Painting work for D-Bldg. | 100 |  | 107910 | 2024-06-03 | 331880.08 | 2024-06-24 12:28 | -329426.58 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 300 | 7.5 | 0 | 2250 | 405 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg West side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -111873.54 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 98.41 | 7.5 | 0 | 738.075 | 132.86 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113385.465 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 59.3 | 7.5 | 0 | 444.75 | 80.06 | 2024-04-17 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113678.79 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 199.09 | 7.5 | 0 | 1493.175 | 268.78 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112630.365 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 59.3 | 7.5 | 0 | 444.75 | 80.06 | 2024-04-16 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg South side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -113678.79 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Eastside Acrylic Texture Paint | 262.7 | 7.5 | 0 | 1970.25 | 354.64 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -112153.29 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 286.52 | 7.5 | 0 | 2148.9 | 386.8 | 2024-04-15 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 106985 | 2024-04-22 | 114123.54 | 2024-05-06 12:55 | -111974.64 | RAHUL PATIL
Water Base Primer (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P1 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5121.45 | 1 | 0 | 5121.45 | 921.86 | 2024-06-14 10:45 | Labour charges for Applying 1 coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -45787.53 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P2 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5121.45 | 1.5 | 0 | 7682.175 | 1382.8 | 2024-06-14 10:47 | Labour charges for Applying 1 Coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -43226.805 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P3 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 4998.627 | 1.5 | 0 | 7497.9405 | 1349.62 | 2024-06-14 10:47 | Labour charges for Applying 1 Coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -43411.0395 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P5 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5122.062 | 1.5 | 0 | 7683.093 | 1382.96 | 2024-06-14 10:47 | Labour charges for Applying 1 Coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -43225.887 | RAHUL PATIL
Water Base Primer (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P5 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5122.062 | 1 | 0 | 5122.062 | 921.98 | 2024-06-14 10:45 | Labour charges for Applying 1 coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -45786.918 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P1 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5121.45 | 1.5 | 0 | 7682.175 | 1382.8 | 2024-06-14 10:47 | Labour charges for Applying 1 Coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -43226.805 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P2 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7505.172 | 1 | 0 | 7505.172 | 1350.94 | 2024-06-01 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -179411.318 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P3 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8959.806 | 1 | 0 | 8959.806 | 1612.76 | 2024-06-01 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -177956.684 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P1 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7919.333 | 1.5 | 0 | 11878.9995 | 2138.22 | 2024-06-02 13:42 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -175037.4905 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P2 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7922.126 | 1.5 | 0 | 11883.189 | 2138.98 | 2024-06-02 13:42 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -175033.301 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P5 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7947.909 | 1.5 | 0 | 11921.8635 | 2145.94 | 2024-06-02 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -174994.6265 | RAHUL PATIL
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | LG Floor D-Parking Wall Above 1.1m Ht Painting Work | 14073.1955 | 7.5 | 0 | 105548.9662 | 18998.82 | 2024-06-02 13:28 | Labour Charges for Applying Texture Paint for D-Bldg Parking area Above 1.1m Height. | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -81367.5237 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P1 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7502.526 | 1 | 0 | 7502.526 | 1350.46 | 2024-06-01 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -179413.964 | RAHUL PATIL
1st Coat Acrylic Paint (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P3 Floor D-Parking Wall Above 1.1m Ht Painting Work | 9457.573 | 1.5 | 0 | 14186.3595 | 2553.54 | 2024-06-02 13:42 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -172730.1305 | RAHUL PATIL
1 Coat Primer (Water Base) (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | P5 Floor D-Parking Wall Above 1.1m Ht Painting Work | 7529.598 | 1 | 0 | 7529.598 | 1355.32 | 2024-06-01 | Labour charges for Applying 1 Coat Water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 107919 | 2024-06-03 | 186916.49 | 2024-06-15 11:52 | -179386.892 | RAHUL PATIL
Water Base Primer (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P3 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 4998.627 | 1 | 0 | 4998.627 | 899.76 | 2024-06-14 10:45 | Labour charges for Applying 1 coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -45910.353 | RAHUL PATIL
Water Base Primer (L) | N/C | N/C | RAHUL PATIL | 910 | 2024-01-19 | D-Bldg P2 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5121.45 | 1 | 0 | 5121.45 | 921.86 | 2024-06-14 10:45 | Labour charges for Applying 1 coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108383 | 2024-06-17 | 50908.98 | 2024-06-24 12:19 | -45787.53 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 701.67 | 8 | 0 | 5613.36 | 1010.4 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -223989.44 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Southside Acrylic Texture Paint | 1203 | 8 | 0 | 9624 | 1732.32 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219978.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Westside Acrylic Texture Paint | 382.52 | 8 | 0 | 3060.16 | 550.82 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226542.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 149.25 | 8 | 0 | 1194 | 214.92 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -228408.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 459.52 | 8 | 0 | 3676.16 | 661.7 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225926.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 561 | 8 | 0 | 4488 | 807.84 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225114.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 459.52 | 8 | 0 | 3676.16 | 661.7 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225926.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 469 | 8 | 0 | 3752 | 675.36 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225850.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 382.96 | 8 | 0 | 3063.68 | 551.46 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226539.12 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Westside Acrylic Texture Paint | 616.03 | 8 | 0 | 4928.24 | 887.08 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 539.77 | 8 | 0 | 4318.16 | 777.26 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225284.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Westside Acrylic Texture Paint | 482.37 | 8 | 0 | 3858.96 | 694.62 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225743.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 158.25 | 8 | 0 | 1266 | 227.88 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -228336.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Northside Acrylic Texture Paint | 446.58 | 8 | 0 | 3572.64 | 643.08 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -183091.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Eastside Acrylic Texture Paint | 219.44 | 8 | 0 | 1755.52 | 316 | 2024-04-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184908.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 262.7 | 8 | 0 | 2101.6 | 378.28 | 2024-04-15 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184562.24 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 199.09 | 8 | 0 | 1592.72 | 286.68 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185071.12 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 335.84 | 8 | 0 | 2686.72 | 483.6 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -183977.12 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Eastside Acrylic Texture Paint | 59.3 | 8 | 0 | 474.4 | 85.4 | 2024-04-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186189.44 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 668.25 | 8 | 0 | 5346 | 962.28 | 2024-04-18 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -181317.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 323.75 | 8 | 0 | 2590 | 466.2 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -123285.47 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Eastside Acrylic Texture Paint | 934.99 | 8 | 0 | 7479.92 | 1346.38 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -118395.55 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Eastside Acrylic Texture Paint | 496.11 | 8 | 0 | 3968.88 | 714.4 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -121906.59 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 133.86 | 8 | 0 | 1070.88 | 192.76 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185592.96 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Eastside Acrylic Texture Paint | 262.72 | 8 | 0 | 2101.76 | 378.32 | 2024-04-15 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184562.08 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 157.63 | 8 | 0 | 1261.04 | 226.98 | 2024-04-18 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185402.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Westside Acrylic Texture Paint | 133 | 8 | 0 | 1064 | 191.52 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185599.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Eastside Acrylic Texture Paint | 219.44 | 8 | 0 | 1755.52 | 316 | 2024-04-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184908.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 188.19 | 8 | 0 | 1505.52 | 271 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185158.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 208.04 | 8 | 0 | 1664.32 | 299.58 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184999.52 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 98.39 | 8 | 0 | 787.12 | 141.68 | 2024-04-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185876.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 286.52 | 8 | 0 | 2292.16 | 412.58 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184371.68 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 219.36 | 8 | 0 | 1754.88 | 315.88 | 2024-04-18 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184908.96 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 133.8 | 8 | 0 | 1070.4 | 192.68 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185593.44 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Westside Acrylic Texture Paint | 133.17 | 8 | 0 | 1065.36 | 191.76 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -124810.11 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 219.44 | 8 | 0 | 1755.52 | 316 | 2024-04-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184908.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 668.25 | 8 | 0 | 5346 | 962.28 | 2024-04-18 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -181317.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 310.95 | 8 | 0 | 2487.6 | 447.76 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184176.24 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 316.8 | 8 | 0 | 2534.4 | 456.2 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184129.44 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Southside Acrylic Texture Paint | 1203.48 | 8 | 0 | 9627.84 | 1733.02 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219974.96 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 369.12 | 8 | 0 | 2952.96 | 531.54 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226649.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Westside Acrylic Texture Paint | 538.32 | 8 | 0 | 4306.56 | 775.18 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225296.24 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 509.75 | 8 | 0 | 4078 | 734.04 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225524.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Westside Acrylic Texture Paint | 616 | 8 | 0 | 4928 | 887.04 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Westside Acrylic Texture Paint | 621.84 | 8 | 0 | 4974.72 | 895.44 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224628.08 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Westside Acrylic Texture Paint | 616.03 | 8 | 0 | 4928.24 | 887.08 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Westside Acrylic Texture Paint | 616.03 | 8 | 0 | 4928.24 | 887.08 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Southside Acrylic Texture Paint | 1203 | 8 | 0 | 9624 | 1732.32 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219978.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Westside Acrylic Texture Paint | 382.52 | 8 | 0 | 3060.16 | 550.82 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226542.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Westside Acrylic Texture Paint | 382.52 | 8 | 0 | 3060.16 | 550.82 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226542.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Westside Acrylic Texture Paint | 455.02 | 8 | 0 | 3640.16 | 655.22 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225962.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Westside Acrylic Texture Paint | 616.03 | 8 | 0 | 4928.24 | 887.08 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Westside Acrylic Texture Paint | 382.34 | 8 | 0 | 3058.72 | 550.56 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226544.08 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 951 | 8 | 0 | 7608 | 1369.44 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -221994.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Southside Acrylic Texture Paint | 1203 | 8 | 0 | 9624 | 1732.32 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219978.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Westside Acrylic Texture Paint | 616.03 | 8 | 0 | 4928.24 | 887.08 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Southside Acrylic Texture Paint | 1045.74 | 8 | 0 | 8365.92 | 1505.86 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -221236.88 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Southside Acrylic Texture Paint | 1203 | 8 | 0 | 9624 | 1732.32 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219978.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Eastside Acrylic Texture Paint | 943.79 | 8 | 0 | 7550.32 | 1359.06 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -118325.15 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Eastside Acrylic Texture Paint | 1197.71 | 8 | 0 | 9581.68 | 1724.7 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -116293.79 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Eastside Acrylic Texture Paint | 262.72 | 8 | 0 | 2101.76 | 378.32 | 2024-04-15 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184562.08 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 286.52 | 8 | 0 | 2292.16 | 412.58 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -184371.68 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 205.83 | 8 | 0 | 1646.64 | 296.4 | 2024-04-18 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185017.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Southside Acrylic Texture Paint | 882.33 | 8 | 0 | 7058.64 | 1270.56 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -222544.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 459.52 | 8 | 0 | 3676.16 | 661.7 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225926.64 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 690 | 8 | 0 | 5520 | 993.6 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224082.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Westside Acrylic Texture Paint | 616.03 | 8 | 0 | 4928.24 | 887.08 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -224674.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Southside Acrylic Texture Paint | 500 | 8 | 0 | 4000 | 720 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225602.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Southside Acrylic Texture Paint | 1203 | 8 | 0 | 9624 | 1732.32 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219978.8 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 487.06 | 8 | 0 | 3896.48 | 701.36 | 2024-06-02 10:50 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -225706.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Southside Acrylic Texture Paint | 790.91 | 8 | 0 | 6327.28 | 1138.92 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -223275.52 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Southside Acrylic Texture Paint | 1203 | 8 | 0 | 9624 | 1732.32 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -219978.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 413.75 | 8 | 0 | 3310 | 595.8 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226292.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 369.12 | 8 | 0 | 2952.96 | 531.54 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -226649.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Southside Acrylic Texture Paint | 990 | 8 | 0 | 7920 | 1425.6 | 2024-06-02 11:07 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 107945 | 2024-06-03 | 229602.8 | 2024-06-24 12:28 | -221682.8 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Hidden Duct Semi Acrylic Paint | 170 | 1 | 0 | 170 | 30.6 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | Fire duct 1st coat primer | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -10064.6 | TEJASHREE ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Hidden Duct Semi Acrylic Paint | 299.23 | 1 | 0 | 299.23 | 53.86 | 2024-05-17 | Material supply Charges of 1 Coat Water Base Primer for D-Bldg Hidden Duct Semi Acrylic Paint. | 100 | electrical duct 1st coat primer work | 107654 | 2024-05-20 | 10234.6 | 2024-07-15 15:17 | -9935.37 | TEJASHREE ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Northside Acrylic Texture Paint | 446.58 | 8 | 0 | 3572.64 | 643.08 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -183091.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Northside Acrylic Texture Paint | 446.58 | 8 | 0 | 3572.64 | 643.08 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -183091.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 556 | 8 | 0 | 4448 | 800.64 | 2024-04-18 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182215.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 188.19 | 8 | 0 | 1505.52 | 271 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185158.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Eastside Acrylic Texture Paint | 91.69 | 8 | 0 | 733.52 | 132.04 | 2024-04-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185930.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Eastside Acrylic Texture Paint | 354.41 | 8 | 0 | 2835.28 | 510.36 | 2024-02-24 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -58984.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Westside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 258.39 | 8 | 0 | 2067.12 | 372.08 | 2024-02-24 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -59752.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 160.06 | 8 | 0 | 1280.48 | 230.48 | 2024-02-24 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -60538.96 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 160.06 | 8 | 0 | 1280.48 | 230.48 | 2024-02-24 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -60538.96 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 361.11 | 8 | 0 | 2888.88 | 520 | 2024-02-24 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -58930.56 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 418.45 | 8 | 0 | 3347.6 | 602.56 | 2024-02-24 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -58471.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Eastside Acrylic Texture Paint | 1197.71 | 8 | 0 | 9581.68 | 1724.7 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -116293.79 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Eastside Acrylic Texture Paint | 1197.71 | 8 | 0 | 9581.68 | 1724.7 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -116293.79 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 423.8 | 8 | 0 | 3390.4 | 610.28 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -122485.07 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Eastside Acrylic Texture Paint | 843.73 | 8 | 0 | 6749.84 | 1214.98 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -119125.63 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 323.75 | 8 | 0 | 2590 | 466.2 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -123285.47 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 208.15 | 8 | 0 | 1665.2 | 299.74 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -124210.27 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 9th Floor Eastside Acrylic Texture Paint | 843.73 | 8 | 0 | 6749.84 | 1214.98 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -119125.63 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Northside Acrylic Texture Paint | 1340.45 | 8 | 0 | 10723.6 | 1930.24 | 2024-06-09 14:39 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -115151.87 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 323.75 | 8 | 0 | 2590 | 466.2 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -123285.47 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 836.464 | 8 | 0 | 6691.712 | 1204.5 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -119183.758 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Eastside Acrylic Texture Paint | 875.69 | 8 | 0 | 7005.52 | 1261 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -118869.95 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 18th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Westside Acrylic Texture Paint | 581.68 | 8 | 0 | 4653.44 | 837.62 | 2024-04-15 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182010.4 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Eastside Acrylic Texture Paint | 496.11 | 8 | 0 | 3968.88 | 714.4 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -121906.59 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Westside Acrylic Texture Paint | 208.09 | 8 | 0 | 1664.72 | 299.64 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -124210.75 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Eastside Acrylic Texture Paint | 751.61 | 8 | 0 | 6012.88 | 1082.32 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -119862.59 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 205.83 | 8 | 0 | 1646.64 | 296.4 | 2024-04-18 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185017.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Southside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 446.58 | 8 | 0 | 3572.64 | 643.08 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -183091.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Northside Acrylic Texture Paint | 556 | 8 | 0 | 4448 | 800.64 | 2024-04-18 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -182215.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 157.63 | 8 | 0 | 1261.04 | 226.98 | 2024-04-18 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185402.8 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 133 | 8 | 0 | 1064 | 191.52 | 2024-04-18 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -185599.84 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Northside Acrylic Texture Paint | 62.64 | 8 | 0 | 501.12 | 90.2 | 2024-04-15 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 106986 | 2024-04-22 | 186663.84 | 2024-05-06 12:54 | -186162.72 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 323.75 | 8 | 0 | 2590 | 466.2 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -123285.47 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 690.56 | 8 | 0 | 5524.48 | 994.4 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -120350.99 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 496.11 | 8 | 0 | 3968.88 | 714.4 | 2024-06-09 14:35 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -121906.59 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 323.75 | 8 | 0 | 2590 | 466.2 | 2024-06-09 14:27 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 108220 | 2024-06-10 | 125875.47 | 2024-06-15 17:53 | -123285.47 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Westside Acrylic Texture Paint | 127.75 | 8 | 0 | 1022 | 183.96 | 2024-02-24 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -60797.44 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Westside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Eastside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Southside Acrylic Texture Paint | 356.72 | 8 | 0 | 2853.76 | 513.68 | 2024-02-24 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -58965.68 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Southside Acrylic Texture Paint | 516.78 | 8 | 0 | 4134.24 | 744.16 | 2024-02-24 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57685.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Southside Acrylic Texture Paint | 356.72 | 8 | 0 | 2853.76 | 513.68 | 2024-02-24 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -58965.68 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Westside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Eastside Acrylic Texture Paint | 482.16 | 8 | 0 | 3857.28 | 694.32 | 2024-02-24 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57962.16 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Southside Acrylic Texture Paint | 516.78 | 8 | 0 | 4134.24 | 744.16 | 2024-02-24 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -57685.2 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 12th Floor Southside Acrylic Texture Paint | 258.39 | 8 | 0 | 2067.12 | 372.08 | 2024-02-24 | Material supply charges for External Texture Paint for South side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -59752.32 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Westside Acrylic Texture Paint | 248.3 | 8 | 0 | 1986.4 | 357.56 | 2024-02-24 | Material supply charges for External Texture Paint for West side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -59833.04 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 258.39 | 8 | 0 | 2067.12 | 372.08 | 2024-02-24 | Material supply charges for External Texture Paint for North side D-Bldg. | 100 |  | 105559 | 2024-02-26 | 61819.44 | 2024-03-12 14:24 | -59752.32 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P5 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8366.22 | 2.25 | 0 | 18823.995 | 3388.32 | 2024-06-14 | Material supply charges of 1st Coat Acrylic Paint for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -278773.695 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P1 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8336.14 | 2.25 | 0 | 18756.315 | 3376.14 | 2024-06-14 | Material supply charges of 1st Coat Acrylic Paint for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -278841.375 | RAHUL PATIL
Water Base Primer (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P2 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5121.45 | 1 | 0 | 5121.45 | 921.86 | 2024-06-14 10:40 | Material Supply charges for Applying 1st coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -292476.24 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P1 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8336.14 | 1 | 0 | 8336.14 | 1500.5 | 2024-06-14 | Material supply charges of 1 Coat water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -289261.55 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P1 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5690.5 | 2.25 | 0 | 12803.625 | 2304.66 | 2024-06-14 | Material Supply charges for Applying 1st coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -284794.065 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P2 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5690.5 | 2.25 | 0 | 12803.625 | 2304.66 | 2024-06-14 | Material Supply charges for Applying 1st coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -284794.065 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P3 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5554.03 | 2.25 | 0 | 12496.5675 | 2249.38 | 2024-06-14 | Material Supply charges for Applying 1st coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -285101.1225 | RAHUL PATIL
Water Base Primer (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P3 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 4998.627 | 1 | 0 | 4998.627 | 899.76 | 2024-06-14 10:40 | Material Supply charges for Applying 1st coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -292599.063 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P3 Floor D-Parking Wall Above 1.1m Ht Painting Work | 9955.34 | 2.25 | 0 | 22399.515 | 4031.92 | 2024-06-14 | Material supply charges of 1st Coat Acrylic Paint for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -275198.175 | RAHUL PATIL
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | LG Floor D-Parking Wall Above 1.1m Ht Painting Work | 14073.1955 | 8 | 0 | 112585.564 | 20265.4 | 2024-06-14 | Material supply charges of Texture Paint for D-Bldg Parking area above 1.1 meter height. | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -185012.126 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P5 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8366.22 | 1 | 0 | 8366.22 | 1505.92 | 2024-06-14 | Material supply charges of 1 Coat water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -289231.47 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P5 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5691.18 | 2.25 | 0 | 12805.155 | 2304.92 | 2024-06-14 | Material Supply charges for Applying 1st coat Acrylic Paint for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -284792.535 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P2 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8339.08 | 1 | 0 | 8339.08 | 1501.04 | 2024-06-14 | Material supply charges of 1 Coat water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -289258.61 | RAHUL PATIL
Water Base Primer (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P1 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5121.45 | 1 | 0 | 5121.45 | 921.86 | 2024-06-14 10:40 | Material Supply charges for Applying 1st coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -292476.24 | RAHUL PATIL
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P3 Floor D-Parking Wall Above 1.1m Ht Painting Work | 9955.34 | 1 | 0 | 9955.34 | 1791.96 | 2024-06-14 | Material supply charges of 1 Coat water Base Primer for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -287642.35 | RAHUL PATIL
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | P2 Floor D-Parking Wall Above 1.1m Ht Painting Work | 8339.08 | 2.25 | 0 | 18762.93 | 3377.32 | 2024-06-14 | Material supply charges of 1st Coat Acrylic Paint for D-Bldg Parking area above 1.1 meter Height | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -278834.76 | RAHUL PATIL
Water Base Primer (M) | N/C | N/C | RAHUL PATIL | 912 | 2024-01-19 | D-Bldg P5 Floor Acylic Painting On Wall FFL to 1.1m Ht (L) | 5122.062 | 1 | 0 | 5122.062 | 921.98 | 2024-06-14 10:40 | Material Supply charges for Applying 1st coat water Base Primer for D-Bldg Parking area (FFL to 1.1m ht.) | 100 |  | 108368 | 2024-06-17 | 297597.69 | 2024-06-24 12:18 | -292475.628 | RAHUL PATIL
MS Frame (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 25 | 2850 | 0 | 14250 | 2565 | 2024-06-17 | Against Installation | 20 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1010254 | ECOMATRIX SOLUTIONS
Exhaust Setup (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 8455 | 0 | 1691 | 304.38 | 2024-06-17 | After Handover | 10 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1022813 | ECOMATRIX SOLUTIONS
Maintenace Hopper (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 8892 | 0 | 3556.8 | 640.22 | 2024-06-17 | Against Installation | 20 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1020947.2 | ECOMATRIX SOLUTIONS
Exhaust Setup (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 8455 | 0 | 3382 | 608.76 | 2024-06-17 | Against Installation | 20 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1021122 | ECOMATRIX SOLUTIONS
Discharge Piece (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 10260 | 0 | 2052 | 369.36 | 2024-06-17 | After Handover | 10 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1022452 | ECOMATRIX SOLUTIONS
Discharge Piece (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 10260 | 0 | 4104 | 738.72 | 2024-06-17 | Against Installation | 20 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1020400 | ECOMATRIX SOLUTIONS
Hopper (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 50 | 8892 | 0 | 311220 | 56019.6 | 2024-06-17 | Against Material Supply | 70 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -713284 | ECOMATRIX SOLUTIONS
Connector (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 104 | 4360 | 0 | 45344 | 8161.92 | 2024-06-17 | After Handover | 10 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -979160 | ECOMATRIX SOLUTIONS
Hopper (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 50 | 8892 | 0 | 44460 | 8002.8 | 2024-06-17 | After Handover | 10 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -980044 | ECOMATRIX SOLUTIONS
Maintenace Hopper (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 8892 | 0 | 12448.8 | 2240.78 | 2024-06-17 | Against Material Supply | 70 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1012055.2 | ECOMATRIX SOLUTIONS
Exhaust Setup (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 8455 | 0 | 11837 | 2130.66 | 2024-06-17 | Against Material Supply | 70 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1012667 | ECOMATRIX SOLUTIONS
Maintenace Hopper (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 8892 | 0 | 1778.4 | 320.12 | 2024-06-17 | After Handover | 10 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1022725.6 | ECOMATRIX SOLUTIONS
MS Frame (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 25 | 2850 | 0 | 49875 | 8977.5 | 2024-06-17 | Against Material Supply | 70 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -974629 | ECOMATRIX SOLUTIONS
Discharge Piece (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 2 | 10260 | 0 | 14364 | 2585.52 | 2024-06-17 | Against Material Supply | 70 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1010140 | ECOMATRIX SOLUTIONS
MS Frame (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 25 | 2850 | 0 | 7125 | 1282.5 | 2024-06-17 | After Handover | 10 | ECO/24-25/007 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -1017379 | ECOMATRIX SOLUTIONS
Connector (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 104 | 4360 | 0 | 317408 | 57133.44 | 2024-06-17 | Against Material Supply | 70 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -707096 | ECOMATRIX SOLUTIONS
Connector (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 104 | 4360 | 0 | 90688 | 16323.84 | 2024-06-17 | Against Installation | 20 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -933816 | ECOMATRIX SOLUTIONS
Hopper (M+L) | N/C | N/C | ECOMATRIX SOLUTIONS | 917 | 2024-01-27 | D Bldg.-Garbage Chute System | 50 | 8892 | 0 | 88920 | 16005.6 | 2024-06-17 | Against Installation | 20 | ECO/24-25/007 & ECO/24-25/16 | 108405 | 2024-06-17 | 1024504 | 2024-06-27 16:00 | -935584 | ECOMATRIX SOLUTIONS
Fabrication Work (L) - Mkt | N/C | N/C | SURESH RANGNATH SHITOLE | 928 | 2024-02-03 | F-Hook welding work for Lift slab | 78.34 | 12 | 0 | 940.08 | 0 | 2024-02-07 12:22 | Labour charges for ISMC 75mm Cutting work for Huck Making & Welding for F-Bldg Lift Slab. | 100 |  | 105223 | 2024-02-12 | 1280.04 | 2024-03-12 14:37 | -339.96 | SURESH RANGNATH SHITOLE
Fabrication Work (L) - Mkt | N/C | N/C | SURESH RANGNATH SHITOLE | 928 | 2024-02-03 | F-Hook welding work for Lift slab | 28.33 | 12 | 0 | 339.96 | 0 | 2024-02-07 12:22 | Labour charges for 20mm Dia steel Bar Huck Making & Welding work for F-Bldg Lift Slab. | 100 |  | 105223 | 2024-02-12 | 1280.04 | 2024-03-12 14:37 | -940.08 | SURESH RANGNATH SHITOLE
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 16th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 18th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 9th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 15th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 16th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 17th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 4th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 5th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 1st Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 13th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 6th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 17th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 20th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 6th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | Stilt Fl Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 11th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 12th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 14th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 15th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 16th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 21st Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 8th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | Stilt Fl Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | Stilt Fl Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 1st Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 2nd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 15th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 18th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 19th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 7th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 14th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 9th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 4th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 3rd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 21st Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 16th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 6th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 5th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 8th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 10th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 2nd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 3rd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 10th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 5th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 15th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 10th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 11th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 12th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 13th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 18th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 7th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 14th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 7th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 4th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 23rd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 8th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 9th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 20th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 21st Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 22nd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 20th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 22nd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 13th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 18th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 19th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 2nd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 3rd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 19th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 1st Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 5th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 22nd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 23rd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Common Staircase- 02. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core (Rate Diff.) | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 9th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 1500 | 0 | 1500 | 270 | 2024-05-25 | Labour Charges & Rate Diff. for Gypsum Dhar Core Work for D-Bldg Fire Staircase- 01. | 100 |  | 107789 | 2024-05-27 | 72000 | 2024-06-03 12:35 | -70500 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 13th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 12th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 14th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 17th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 8th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 11th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 17th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 12th Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-02-24 17:52 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 105566 | 2024-02-26 | 46000 | 2024-03-23 12:19 | -44000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 20th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 4th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 6th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 19th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 22nd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 23rd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 2nd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 11th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 1st Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 7th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | Stilt Fl Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 23rd Fl-Lobby Fire Staircase- 01 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Fire Staircase-01. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 10th Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 3rd Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Tikki Dhada (L) No. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | D-Pressurization Duct Tikki Dhada Work(L | 24 | 1200 | 0 | 28800 | 0 | 2024-06-01 | Labour charges for Applying Gypsum Tikki Dhada work for D-Bldg Pressurization Blockwork wall from LG Floor to 24th Floor. | 100 |  | 107921 | 2024-06-03 | 28800 | 2024-06-15 11:44 | 0 | G M ENTERPRISES
Dhar Core. | N/C | N/C | G M ENTERPRISES | 934 | 2024-02-06 | 21st Fl-Lobby Common Staircase- 02 Dhar Core | 1 | 2000 | 0 | 2000 | 360 | 2024-03-16 | Labour charges for Gypsum Dhar Core Work for D-Bldg Common Staircase-02. | 100 |  | 106108 | 2024-03-18 | 50000 | 2024-03-23 12:19 | -48000 | G M ENTERPRISES
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 5th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 21st Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 7th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 14th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 23rd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 15th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 10th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 24th Fl-Lobby Fire Staircase- 01 Dhar Core | 0.2491 | 285 | 0 | 70.9935 | 3.54 | 2024-07-08 15:28 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 | LSF/363/2024-25 | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -28499.9965 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 20th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 6th Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 7th Fl-Lobby Common Staircase- 02 Dhar Core | 2 | 285 | 0 | 570 | 28.5 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -28000.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 1st Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 11th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 12th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | Terrace Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 16th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 3rd Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 3rd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 4th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 5th Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 8th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 2nd Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 13th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 22nd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | Stilt Fl Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 1st Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 2nd Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 17th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 18th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 6th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 9th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 19th Fl-Lobby Fire Staircase- 01 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 4th Fl-Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | 24th Fl-Lobby Fire Staircase- 01 Dhar Core | 2 | 285 | 0 | 570 | 28.5 | 2024-07-08 15:14 | Material supply charges of Gypsum for Fire Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -28000.99 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | YUGESH KUMAR | 941 | 2024-02-22 | Stilt Fl Lobby Common Staircase- 02 Dhar Core | 3 | 285 | 0 | 855 | 42.76 | 2024-07-09 17:31 | Material supply charges of Gypsum for Common Staircase Gypsum Dhar Core Katch Work (Thickness 4mm). | 100 |  | 108979 | 2024-07-09 | 28570.99 | 1900-01-01 | -27715.99 | LAXMI STRUCTURES & FIXTURES LLP
PWD license Charges | N/C | N/C | P. R. ENTERPRISES | 956 | 2024-03-26 | D Bldg.-Lift License Charges | 1 | 31600 | 0 | 31600 | 5688 | 2024-05-22 | Charges for D-Bldg 8 Passanger Kone lift PWD License fees. | 100 |  | 107739 | 2024-03-31 | 31600 | 2024-06-17 12:49 | 0 | P. R. ENTERPRISES
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-403-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-502-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-503-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-006-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-207-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-302-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-506-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-107-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-201-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-208-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-308-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-507-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-508-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-101-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-203-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-207-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-501-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-307-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-308-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-504-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-004-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-104-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-007-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-101-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-108-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-406-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-407-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-006-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-106-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-202-2BHK(Near Refuse Area) Alu. Sliding Window | 17.768 | 74 | 0 | 1314.832 | 236.66 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -273849.658 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-405-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-408-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-402-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-402-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-508-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-001-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-002-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-107-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-206-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-302-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-303-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-404-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-002-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-008-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-008-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-201-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-301-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-005-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-304-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-306-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-501-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-505-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-001-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-103-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-303-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-404-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-104-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-204-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-204-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-305-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-102-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-105-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-106-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-203-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-206-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-408-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-503-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-401-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-506-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-507-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-202-2BHK(Near Refuse Area) Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-307-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-405-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-502-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-504-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-004-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-005-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-105-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-305-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-403-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-003-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-304-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-306-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-003-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-103-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-205-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-205-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-505-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-007-2BHK Alu. Sliding Window | 60.448 | 69 | 0 | 4170.912 | 750.76 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -270993.578 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-102-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-401-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-406-3BHK Alu. Sliding Window | 90.672 | 69 | 0 | 6256.368 | 1126.14 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E Building Bed room | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -268908.122 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-407-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-108-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-208-2BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Labour) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 964 | 2024-04-12 | E-301-3BHK Alu. Sliding Window | 6.784 | 74 | 0 | 502.016 | 90.36 | 2024-06-07 | Labour charges for Fixing of Aluminium Sliding Window having 3 Track Bottom, 5mm Toughened glass,lock concealed, wool pile & Powder coating for E-Building Kitchen Window. | 100 |  | 108200 | 2024-06-10 | 275164.49 | 1900-01-01 | -274662.474 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-302-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-505-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-806-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-107-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-503-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-008-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-207-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-504-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-401-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-108-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-508-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-006-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-304-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-104-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-301-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-1002-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-408-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-103-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-503-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-504-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-407-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-208-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-305-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-402-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-405-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-204-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-003-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-005-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-205-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-502-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-102-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-105-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-106-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-506-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-705-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-407-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-706-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-004-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-007-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-003-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-203-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-204-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-008-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-303-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-906-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-207-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-307-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-002-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-101-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-406-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-501-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-403-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-404-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-001-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-905-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-203-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-004-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-802-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-208-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-507-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-103-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-408-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-303-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-201-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-801-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-404-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-306-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-902-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-1001-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-308-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-901-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-104-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-007-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-805-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-307-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-304-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-507-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-308-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-107-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-108-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-206-3BHK Alu. Sliding Window | 90.672 | 277 | 0 | 25116.144 | 4520.9 | 2024-06-09 10:43 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5 mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1303675.156 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-403-2BHK Alu. Sliding Window | 60.448 | 277 | 0 | 16744.096 | 3013.94 | 2024-06-09 10:50 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Bed room Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1312047.204 | K K POWER CONTROL WIRES PVT LTD
Al Window (Material) BC | N/C | N/C | K K POWER CONTROL WIRES PVT LTD | 965 | 2024-04-12 | E-508-2BHK Alu. Sliding Window | 6.784 | 294 | 0 | 1994.496 | 359.02 | 2024-06-09 11:00 | Material Supply charges for 3 Track Bottom Aluminium Sliding window with 5mm thick Toughened glass,Bearing,Lock Concealed,Wool Pile,PVC,Powder coating including loading,unloading,transport,Mathadi & supervision charges for E-Bldg Kitchen Window. | 100 |  | 108218 | 2024-06-10 | 1328791.3 | 1900-01-01 | -1326796.804 | K K POWER CONTROL WIRES PVT LTD
Rebarring work 12mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 966 | 2024-04-24 | D-Rebaring Work at Refuge Area,Staircase | 32 | 125 | 0 | 4000 | 720 | 2024-05-18 17:56 | Labour charegs for 12mm Dia. Bar Rebarring work with 100mm Depth using Hilti RE-500 for D-Bldg Refuge area lintel casting for Door opening. | 100 |  | 107662 | 2024-05-20 | 25310 | 2024-07-05 11:37 | -21310 | AVCON TECHNICS PVT LTD
Rebarring work 12mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 966 | 2024-04-24 | D-Rebaring Work at Refuge Area,Staircase | 22 | 180 | 0 | 3960 | 712.8 | 2024-05-18 17:56 | Labour charegs for 12mm Dia. Bar Rebarring work with 150mm Depth using Hilti RE-500 for D-Bldg Fire & regular staircase. | 100 |  | 107662 | 2024-05-20 | 25310 | 2024-07-05 11:37 | -21350 | AVCON TECHNICS PVT LTD
Rebaring work 8mm dia.- DTR | N/C | N/C | AVCON TECHNICS PVT LTD | 966 | 2024-04-24 | D-Rebaring Work at Refuge Area,Staircase | 56 | 150 | 0 | 8400 | 1512 | 2024-05-18 17:56 | Labour charegs for 8mm Dia. Bar Rebarring work with 150mm Depth using Hilti RE-500 for D-Bldg Top Terrace to Parapet wall. | 100 |  | 107662 | 2024-05-20 | 25310 | 2024-07-05 11:37 | -16910 | AVCON TECHNICS PVT LTD
Rebarring work 16mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 966 | 2024-04-24 | D-Rebaring Work at Refuge Area,Staircase | 3 | 500 | 0 | 1500 | 270 | 2024-05-18 17:56 | Labour charegs for 16mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Ground Floor (Beam Near PC38) | 100 |  | 107662 | 2024-05-20 | 25310 | 2024-07-05 11:37 | -23810 | AVCON TECHNICS PVT LTD
Rebarring work 12mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 966 | 2024-04-24 | D-Rebaring Work at Refuge Area,Staircase | 3 | 260 | 0 | 780 | 140.4 | 2024-05-18 17:56 | Labour charegs for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D-Bldg Ground Floor (Beam Near PC38) | 100 |  | 107662 | 2024-05-20 | 25310 | 2024-07-05 11:37 | -24530 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 966 | 2024-04-24 | D-Rebaring Work at Refuge Area,Staircase | 58 | 115 | 0 | 6670 | 1200.6 | 2024-05-18 17:56 | Labour charegs for 10mm Dia. Bar Rebarring work with 100mm Depth using Hilti RE-500 for D-Bldg Refuge area. | 100 |  | 107662 | 2024-05-20 | 25310 | 2024-07-05 11:37 | -18640 | AVCON TECHNICS PVT LTD
Rebarring work 12mm dia- BPo | N/C | N/C | AVCON TECHNICS PVT LTD | 967 | 2024-04-24 | E-Rebaring Work at Refuge Area,Staircase | 40 | 180 | 0 | 7200 | 1296 | 2024-05-14 18:32 | Labour charges for 12mm Dia. Bar Rebarring work with 150mm Depth using Hilti RE-500 for E-Bldg Regular & Fire staircase. | 100 |  | 107645 | 2024-05-20 | 7200 | 2024-06-15 11:45 | 0 | AVCON TECHNICS PVT LTD
Breaking Work - Dld | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | F-Wall breaking work at Strecher Lift | 5 | 4000 | 0 | 20000 | 3600 | 2024-06-18 17:32 | Labour charges for Blockwork Wall Breaking work for F-Bldg Streacher Lift from LG to 3rd Floor. | 100 |  | 108507 | 2024-06-24 | 20000 | 2024-07-15 11:05 | 0 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
PVC Pipe fixing 4"- SO | N/C | N/C | SAI PLUMBING WORKS | 969 | 2024-04-24 | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | 890 | 40 | 0 | 35600 | 6408 | 2024-07-12 19:08 | Labour charges for Laying of PVC Pipe 4 inch for storm water line at D & E Parking area. | 100 |  | 109091 | 2024-07-15 | 53100 | 2024-08-05 13:57 | -17500 | SAI PLUMBING WORKS
PVC Pipe fixing 6"- SO | N/C | N/C | SAI PLUMBING WORKS | 969 | 2024-04-24 | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | 250 | 50 | 0 | 12500 | 2250 | 2024-07-12 19:08 | Labour charges for Laying of PVC Pipe 6 inch for storm water line at D & E Parking area. | 100 |  | 109091 | 2024-07-15 | 53100 | 2024-08-05 13:57 | -40600 | SAI PLUMBING WORKS
Bullet Fastner Fixing (L) | N/C | N/C | SAI PLUMBING WORKS | 969 | 2024-04-24 | D,Podium Between D&E,E- P-3 Rainwater Hanging Lines | 250 | 20 | 0 | 5000 | 900 | 2024-07-12 19:08 | Labour charges for Bullet Fastner Fixing for Drainage line & Storm water line pipe fixing at D & E Parking area. | 100 |  | 109091 | 2024-07-15 | 53100 | 2024-08-05 13:57 | -48100 | SAI PLUMBING WORKS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-404-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-604-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-606-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-007-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-105-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-603-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-406-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-502-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1906-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2108-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1005-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-18 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1204-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1405-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1508-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2103-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1305-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1306-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1607-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2001-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2204-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1208-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1304-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1606-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1608-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1703-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2003-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2203-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2207-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1401-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1403-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1502-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1804-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1903-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1907-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2201-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1006-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-18 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1007-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-18 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2002-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2205-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1203-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1205-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1207-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1404-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1507-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1802-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1805-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1008-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-18 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1102-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1104-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1505-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-306-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-405-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-503-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-602-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-902-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-303-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-504-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-707-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-708-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-801-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1002-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-006-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-703-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-705-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-802-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-905-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-304-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-002-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-003-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-004-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-206-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-305-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-307-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-601-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-106-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-803-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-301-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-302-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1605-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1905-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1301-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1303-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1402-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1503-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1604-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1307-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1504-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1908-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1206-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1406-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1506-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1807-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2008-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-704-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-501-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-001-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-507-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-205-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-207-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-308-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-701-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-805-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-904-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-906-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-102-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-807-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2206-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1101-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1408-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1704-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1706-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1708-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2004-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2107-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1407-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2104-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1103-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1601-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1801-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1806-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1808-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1201-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1308-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1707-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2007-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2005-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2106-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1107-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1904-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2105-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1003-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-18 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1803-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1106-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1603-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-2006-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1004-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-18 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1108-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182484 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1302-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1501-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1602-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1705-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1105-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-21 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108505 | 2024-06-24 | 184452 | 1900-01-01 | -182450 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-505-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-706-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-907-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-908-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-506-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-1001-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-408-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-402-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-605-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-608-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-806-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-901-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-204-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-208-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-008-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-804-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-903-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-201-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-203-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-401-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-403-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-108-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-103-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-104-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-808-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-107-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-101-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-607-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-407-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-005-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 8.008 | 250 | 0 | 2002 | 360.36 | 2024-06-10 11:09 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156798 | HELIOS
S.S. Railing (L)- BC | N/C | N/C | HELIOS | 980 | 2024-05-08 | E-508-2BHK Terrace+Dry Balcony- Railing Work | 7.872 | 250 | 0 | 1968 | 354.24 | 2024-06-10 11:23 | Labour charges for Fixing of SS Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108225 | 2024-06-10 | 158800 | 1900-01-01 | -156832 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-507-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-703-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-705-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-804-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1004-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1005-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-107-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1701-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1704-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1705-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-201-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-204-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-402-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1105-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1306-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1803-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2102-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2104-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2107-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-302-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-902-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1003-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-008-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1502-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1608-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-408-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-403-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-707-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1305-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1307-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1508-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1601-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2103-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1504-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1801-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1808-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2001-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2008-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-208-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1401-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1507-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2005-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-308-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-405-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-601-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-606-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-104-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1106-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2003-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1203-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1505-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1708-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-304-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-602-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-603-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-605-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-808-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-901-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-607-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-704-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-805-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-904-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-007-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1007-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-101-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1102-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1301-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1501-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1707-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-307-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-701-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-906-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1907-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2201-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-406-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-506-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-108-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1308-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1503-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1506-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2006-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-002-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-003-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-103-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1103-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1108-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1302-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1002-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1101-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1706-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1901-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2007-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-207-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-306-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-608-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-905-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-508-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-803-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2108-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-301-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1403-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1408-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1604-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1606-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1807-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1006-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-105-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1205-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1208-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1906-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2203-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2205-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-806-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1908-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2101-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1802-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1804-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1805-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-303-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-604-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-005-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1104-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1107-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1304-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1602-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1603-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-502-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-503-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-505-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-706-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-708-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-907-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1402-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-802-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-903-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1206-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2206-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-401-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-504-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-801-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-006-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1404-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1405-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1406-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1407-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1703-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1903-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1904-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-203-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2207-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-908-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-102-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2002-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2004-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2105-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2106-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-807-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-004-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-001-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1207-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-106-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1902-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1905-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-205-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-404-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1001-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1008-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1201-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1204-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1303-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1450 | 0 | 14268 | 2568.24 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570553.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1605-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1607-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-1806-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1585 | 0 | 15865.85 | 2855.86 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2568956.05 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-206-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-2204-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1585 | 0 | 15596.4 | 2807.36 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2569225.5 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-305-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1300 | 0 | 13013 | 2342.34 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2571808.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-407-2BHK Terrace+Dry Balcony- Railing Work | 9.84 | 1300 | 0 | 12792 | 2302.56 | 2024-06-22 | Material supply charges of S S Railing Work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2572029.9 | HELIOS
S.S. Railing (M)- BC | N/C | N/C | HELIOS | 981 | 2024-05-08 | E-501-3BHK Terrace+Dry Balcony- Railing Work-(Flat) | 10.01 | 1450 | 0 | 14514.5 | 2612.62 | 2024-06-22 | Material Supply charges of S S Railing work for E-Bldg Internal Flat Living Terrace area. | 100 |  | 108533 | 2024-06-24 | 2584821.9 | 1900-01-01 | -2570307.4 | HELIOS
Horizontal 4" Core cutting | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 991 | 2024-05-24 | D-OHWT Core Cutting Work | 5 | 265 | 0 | 1325 | 238.5 | 2024-06-22 | Charges for 4" Horizontal Core cutting for D-Bldg OHWT Inlet & Outlet , Top Terrace Rainwater outlet , Lift Core cutting for Electric supply at 24th floor for D-Bldg | 100 |  | 108536 | 2024-06-24 | 5335 | 2024-07-15 11:05 | -4010 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Horizontal core cutting 5" | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 991 | 2024-05-24 | D-OHWT Core Cutting Work | 14 | 265 | 0 | 3710 | 667.8 | 2024-06-22 | Charges for 5" Horizontal Core cutting for D-Bldg OHWT Inlet & Outlet , Top Terrace Rainwater outlet , Lift Core cutting for Electric supply at 24th floor for D-Bldg | 100 |  | 108536 | 2024-06-24 | 5335 | 2024-07-15 11:05 | -1625 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Horizontal 3" Core cutting | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 991 | 2024-05-24 | D-OHWT Core Cutting Work | 20 | 265 | 0 | 5300 | 954 | 2024-06-22 | Charges for 3" Horizontal Core cutting for D-Bldg OHWT Inlet & Outlet , Top Terrace Rainwater outlet , Lift Core cutting for Electric supply at 24th floor for D-Bldg | 100 |  | 108528 | 2024-06-24 | 5300 | 1900-01-01 | 0 | PATIL CONSTRUCTION
Horizontal core cutting 8" | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 991 | 2024-05-24 | D-OHWT Core Cutting Work | 1 | 300 | 0 | 300 | 54 | 2024-06-22 | Charges for 8" Horizontal Core cutting for D-Bldg OHWT Inlet & Outlet , Top Terrace Rainwater outlet , Lift Core cutting for Electric supply at 24th floor for D-Bldg | 100 |  | 108536 | 2024-06-24 | 5335 | 2024-07-15 11:05 | -5035 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
PWD license Charges | N/C | N/C | OTIS ELEVATOR COMPANY (INDIA) LIMITED | 998 | 2024-05-27 | F-Lift License Charges | 1 | 50000 | 0 | 50000 | 0 | 2024-06-21 | PWD License Charges for F Building lift | 100 |  | 108478 | 2024-06-21 | 50000 | 2024-06-21 10:55 | 0 | ANAND PUNDLIK JADHAV
PWD license Charges | N/C | N/C | OTIS ELEVATOR COMPANY (INDIA) LIMITED | 998 | 2024-05-27 | F-Lift License Charges | 1 | 24500 | 0 | 24500 | 0 | 2024-05-30 | PWD License Charges for F Building lift | 100 |  | 107872 | 2024-05-30 | 24500 | 2024-05-30 11:55 | 0 | ANAND PUNDLIK JADHAV