## Work_Completion_Browse638587244
Work Completion Browse
Project : GANGA ALTUS
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 258 Records 1 to 258
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
H.R.C. Consultancy | N/C | N/C | GLOBAL GEOTECHNICS | 106 | 2020-09-28 | Highrise Clearance | 1 | 25000 | 0 | 25000 | 4500 | 2020-11-01 | Charges for attending HRC meeting & Presentation | 100 |  | 87948 | 2020-11-01 | 25000 | 2020-11-01 11:45 | 0 | GLOBAL GEOTECHNICS
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2022-10-06 | Completion of 13 to OHWT & MC Room | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1206546 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222075 | 6 | 0 | 133245 | 23984.1 | 2022-10-06 | Completion of 1st to 4th Floor | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1208993 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2022-10-06 | Issue of Completion Certificate & As Built drawing | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1206546 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222075 | 6 | 0 | 133245 | 23984.1 | 2022-10-06 | Completion of Parking | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1208993 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222075 | 6 | 0 | 133245 | 23984.1 | 2022-10-06 | Completion of 13 to OHWT & MC Room | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1208993 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2022-10-06 | Issue of Completion Certificate & As Built drawing | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1206546 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2022-10-06 | Completion of 13 to OHWT & MC Room | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1206546 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222075 | 6 | 0 | 133245 | 23984.1 | 2022-10-06 | Completion of 9th to 12th Floor | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1208993 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222075 | 6 | 0 | 133245 | 23984.1 | 2022-10-06 | Completion of 5th to 8th Floor | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1208993 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222075 | 6 | 0 | 133245 | 23984.1 | 2022-10-06 | Issue of Completion Certificate & As Built drawing | 10 |  | 96576 | 2022-10-06 | 1342238 | 2022-10-15 11:53 | -1208993 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 3861.6 | 695.08 | 2023-07-08 | Appointment Letter | 5 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -296138.4 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 19308 | 3475.44 | 2023-07-08 | Issue of all Drawings | 25 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -280692 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 1st Floor to 4th Floor | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg - F RCC Consultancy | 41849 | 6 | 0 | 62773.5 | 11299.24 | 2023-07-08 | Issue of all Drawings | 25 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -237226.5 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 9th Floor to 12th Floor | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 5th Floor to 8th Floor | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 13th Floor to OHWT & MC Room | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 5th Floor to 8th Floor | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg - F RCC Consultancy | 13395.3333 | 6 | 0 | 20093 | 3616.74 | 2023-07-08 | Issue of Completion Certificate & as built Drawing | 25 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -279907 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of Parking | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg - F RCC Consultancy | 41779.6667 | 6 | 0 | 62669.5001 | 11280.52 | 2023-07-08 | Issue of Column Position & Calculation | 25 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -237330.4999 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of Parking | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 3861.6 | 695.08 | 2023-07-08 | Appointment Letter | 5 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -296138.4 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226154 | 6 | 0 | 135692.4 | 24424.64 | 2020-11-01 | Issue of Column Position & Calaculation | 10 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -622989.6 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 33311.4 | 6 | 0 | 49967.1 | 8994.08 | 2020-11-01 | Issue of All RCC Drawings | 25 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -708714.9 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226154 | 6 | 0 | 135692.4 | 24424.64 | 2020-11-01 | Issue of Column Position & Calaculation | 10 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -622989.6 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226154 | 6 | 0 | 67846.2 | 12212.32 | 2020-11-01 | Appointment Letter | 5 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -690835.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222076 | 6 | 0 | 133245.6 | 23984.2 | 2020-11-01 | Issue of Column Position & Calaculation | 10 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -625436.4 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 33923.1 | 6 | 0 | 50884.65 | 9159.24 | 2020-11-01 | Issue of All RCC Drawings | 25 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -707797.35 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 222076 | 6 | 0 | 66622.8 | 11992.1 | 2020-11-01 | Appointment Letter | 5 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -692059.2 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226154 | 6 | 0 | 67846.2 | 12212.32 | 2020-11-01 | Appointment Letter | 5 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -690835.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 33923.1 | 6 | 0 | 50884.65 | 9159.24 | 2020-11-01 | Issue of All RCC Drawings | 25 |  | 87949 | 2020-11-01 | 758682 | 2020-11-02 12:01 | -707797.35 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | RCC Consultancy - OHWT D & E | 329800 | 0.15 | 0 | 49470 | 8904.6 | 2023-04-17 | Charges for RCC Consultancy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -313045.55 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Club House - RCC Consultancy | 16344 | 5.25 | 0 | 21451.5 | 3861.28 | 2023-04-17 | Issue of all Drawings | 25 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -341064.05 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg - F RCC Consultancy | 69.3333 | 6 | 0 | 103.9999 | 18.72 | 2023-04-17 | Issue of Column Position & Calculation | 25 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -362411.5501 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Club House - RCC Consultancy | 16344 | 5.25 | 0 | 21451.5 | 3861.28 | 2023-04-17 | Issue of Completion Certificate & as built Drawing | 25 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -341064.05 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | RCC Consultancy - UGWT F | 42076 | 0.15 | 0 | 6311.4 | 1136.06 | 2023-04-17 | Charges for RCC Consultancy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -356204.15 | G.A.BHILARE CONSULTANTS PVT LTD
Consultancy Charges | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Consultancy Charges - Compound Wall details | 1 | 10000 | 0 | 10000 | 1800 | 2023-04-17 | Charges for RCC Consultacy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -352515.55 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg - F RCC Consultancy | 41849 | 6 | 0 | 62773.5 | 11299.24 | 2023-04-17 | Appointment Letter | 25 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -299742.05 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Club House - RCC Consultancy | 16344 | 5.25 | 0 | 21451.5 | 3861.28 | 2023-04-17 | Issue of Column Position & Calculation | 25 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -341064.05 | G.A.BHILARE CONSULTANTS PVT LTD
Consultancy Charges | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Consultancy Charges - Well covering details | 1 | 25000 | 0 | 25000 | 4500 | 2023-04-17 | Charges for RCC Consultancy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -337515.55 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | RCC Consultancy - UGWT D & E | 608206 | 0.15 | 0 | 91230.9 | 16421.56 | 2023-04-17 | Charges for RCC Consultancy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -271284.65 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | RCC Consultancy - OHWT F | 45465 | 0.15 | 0 | 6819.75 | 1227.56 | 2023-04-17 | Charges for RCC Consultancy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -355695.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Club House - RCC Consultancy | 16344 | 5.25 | 0 | 21451.5 | 3861.28 | 2023-04-17 | Appointment Letter | 25 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -341064.05 | G.A.BHILARE CONSULTANTS PVT LTD
Consultancy Charges | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Consultancy Charges - Entrance Gate | 1 | 25000 | 0 | 25000 | 4500 | 2023-04-17 | Charges for RCC Consultancy | 100 |  | 99204 | 2023-04-17 | 362515.55 | 2023-04-18 14:35 | -337515.55 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 19308 | 3475.44 | 2023-07-08 | Issue of all Drawings | 25 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -280692 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Issue of Column Position & Calculation | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Issue of Column Position & Calculation | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 13th Floor to OHWT & MC Room | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 9th Floor to 12th Floor | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Issue of Completion Certificate & as built Drawing | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Completion of 1st Floor to 4th Floor | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy Area Diff. | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy (Area Diff.) | 12872 | 6 | 0 | 7723.2 | 1390.18 | 2023-07-08 | Issue of Completion Certificate & as built Drawing | 10 |  | 100552 | 2023-07-08 | 300000 | 2023-07-11 12:46 | -292276.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 188764 | 6 | 0 | 283146 | 50966.28 | 2020-11-06 | Issue of All RCC Drawings | 25 |  | 88080 | 2020-11-06 | 571492 | 2020-11-06 17:22 | -288346 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D&E Parking RCC Consultancy | 0.6 | 6 | 0 | 0.9 | 0.16 | 2021-10-20 | Issue of All RCC Drawings | 25 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1373883.9 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 0.233 | 6 | 0 | 0.3495 | 0.06 | 2021-10-20 | Issue of All RCC Drawings | 25 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1373884.4505 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226154 | 6 | 0 | 135692.4 | 24424.64 | 2021-10-14 | Completion of 5th to 8th Floor | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.4 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2021-10-14 | Completion of 9th to 12th Floor | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226154 | 6 | 0 | 135692.4 | 24424.64 | 2021-10-14 | Completion of Parking | 10 | Completion of parking. | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.4 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 192230.9 | 6 | 0 | 288346.35 | 51902.34 | 2021-10-20 | Issue of All RCC Drawings | 25 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1085538.45 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 192230.6667 | 6 | 0 | 288346 | 51902.28 | 2020-11-06 | Issue of All RCC Drawings | 25 |  | 88080 | 2020-11-06 | 571492 | 2020-11-06 17:22 | -283146 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2021-10-18 | Completion of Parking | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2021-10-18 | Completion of 1st to 4th Floor | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-D RCC Consultancy | 226154 | 6 | 0 | 135692.4 | 24424.64 | 2021-10-14 | Completion of 1st to 4th Floor | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.4 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2021-10-18 | Completion of 5th to 8th Floor | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.8 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 114 | 2020-10-31 | Bldg-E RCC Consultancy | 226153.3333 | 6 | 0 | 135692 | 24424.56 | 2021-10-18 | Completion of 9th to 12th Floor | 10 |  | 92123 | 2021-10-20 | 1373884.8 | 2021-10-25 13:29 | -1238192.8 | G.A.BHILARE CONSULTANTS PVT LTD
Professional Fees. | N/C | N/C | AMIT KUMAR PODDAR | 121 | 2020-12-03 | Professional Consultancy (Commercial F-Bldg) | 1 | 13000 | 0 | 13000 | 0 | 2020-12-10 | RERA Registration Certificate | 100 |  | 88342 | 2020-12-10 | 13000 | 2020-12-10 18:01 | 0 | AMIT KUMAR PODDAR
B.O.C.W. Act Registration &Compliance. | N/C | N/C | VISION MANAGEMENT SERVICES | 139 | 2021-02-16 | Contract Labour act Registration & Compliance | 1 | 18500 | 0 | 18500 | 0 | 2021-03-05 | Company Registration under Contract Labour Act Registration for the Year 2021 (01/01/2021 to 31/12/2021) | 100 |  | 89194 | 2021-03-05 | 18500 | 2021-03-08 12:13 | 0 | VISION MANAGEMENT SERVICES
Consultancy Charges | N/C | N/C | VISION MANAGEMENT SERVICES | 139 | 2021-02-16 | Contract Labour act Registration & Compliance | 1 | 5000 | 0 | 5000 | 900 | 2021-03-05 | Consultancy Charges for Company Registration for the Year -2021 | 100 |  | 89195 | 2021-03-05 | 5000 | 2021-03-08 12:14 | 0 | VISION MANAGEMENT SERVICES
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-12-22 | Charges for Legal Consultancy for the month of OCT-2023 | 100 |  | 104085 | 2023-12-22 | 66666 | 2023-12-22 18:22 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 8.3225 | 51000 | 0.09 | 35370.908 | 0 | 2021-03-31 | MAR 2021 | 8.3334 |  | 89806 | 2021-03-31 | 35371 | 2021-04-13 11:30 | -0.092035 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 25865 | 0 | 25865 | 0 | 2022-08-04 | Charges for- Legal Consultancy for the month of APRIL-2022 | 100 |  | 95790 | 2022-08-04 | 109846 | 2022-08-09 11:44 | -83981 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 17315 | 0 | 17315 | 0 | 2022-08-04 | Charges for- Legal Consultancy for the month of MAY-2022 | 100 |  | 95790 | 2022-08-04 | 109846 | 2022-08-09 11:44 | -92531 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2022-08-04 | Charges for- Legal Consultancy for the month of JUNE-2022 | 100 |  | 95790 | 2022-08-04 | 109846 | 2022-08-09 11:44 | -43180 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-01-03 | Charges for Legal Consultancy for the month of DEC-2023 | 100 |  | 104325 | 2024-01-03 | 66666 | 2024-01-04 15:45 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2022-09-12 | Charges for- Legal Consultancy for the month of AUGUST-2022 | 100 |  | 96217 | 2022-09-12 | 66666 | 2022-09-24 10:54 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-05-06 | Charges for Legal Consultancy for the month of APR-2023 | 100 |  | 99495 | 2023-05-06 | 66666 | 2024-01-15 11:42 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-03-04 | Charges for Legal Consultancy for the month of FEB-2023 | 100 |  | 98493 | 2023-03-04 | 66666 | 2023-03-06 18:13 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-07-09 | Charges for Legal Consultancy for the month of JUNE-2024 | 100 |  | 108952 | 2024-07-09 | 66666 | 2024-07-09 14:35 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 11.6128 | 51000 | 0.21 | 49354.7948 | 0 | 2022-06-06 | May 2022 | 8.3334 |  | 95017 | 2022-06-06 | 49355 | 2022-06-07 14:58 | -0.20516 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 0.5 | 66666 | 0 | 33333 | 0 | 2024-01-15 | Charges for Legal Consultancy for the month of MAY-2023 | 100 |  | 104569 | 2024-01-15 | 33333 | 2024-01-15 11:56 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-07-05 | Charges for Legal Consultancy for the month of JUNE-2023 | 100 |  | 100470 | 2023-07-05 | 66666 | 2023-07-11 12:49 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2022-12-08 | Charges for- Legal Consultancy for the month of NOVEMBER-2022 | 100 |  | 97284 | 2022-12-08 | 66666 | 2022-12-23 10:54 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-01-05 | Charges for- Legal Consultancy for the month of DECEMBER-2022 | 100 |  | 97645 | 2023-01-05 | 66666 | 2023-01-05 16:50 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-03-07 | Charges for Legal Consultancy for the month of FEBRUARY-2024 | 100 |  | 105798 | 2024-03-07 | 66666 | 2024-03-07 12:51 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-08-04 | Charges for Legal Consultancy for the month of JULY-2023 | 100 |  | 101005 | 2023-08-04 | 66666 | 2023-08-07 12:34 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-06-04 | Charges for Legal Consultancy for the month of MAY-2024 | 100 |  | 108036 | 2024-06-04 | 66666 | 2024-06-04 12:34 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 9.5999 | 51000 | 0.1 | 40799.9014 | 0 | 2022-05-18 | April 2022 | 8.3334 |  | 94808 | 2022-05-18 | 40800 | 2022-05-18 16:52 | -0.098603 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-12-22 | Charges for Legal Consultancy for the month of NOV-2023 | 100 |  | 104086 | 2023-12-22 | 66666 | 2023-12-22 18:22 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 0.5 | 66666 | 0 | 33333 | 0 | 2023-06-06 | Charges for Legal Consultancy for the month of MAY-2023 | 100 |  | 99938 | 2023-06-06 | 33333 | 2023-06-06 14:20 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-02-03 | Charges for Legal Consultancy for the month of JANUARY-2024 | 100 |  | 104940 | 2024-02-03 | 66666 | 2024-02-05 17:19 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2022-10-10 | Charges for- Legal Consultancy for the month of SEPTEMBER-2022 | 100 |  | 96634 | 2022-10-10 | 66666 | 2022-10-12 19:08 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-03-29 | Charges for Legal Consultancy for the month of MARCH-2024 | 100 |  | 106408 | 2024-03-29 | 66666 | 2024-03-29 14:09 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-12-22 | Charges for Legal Consultancy for the month of SEPT-2023 | 100 |  | 104084 | 2023-12-22 | 66666 | 2023-12-22 18:17 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2022-11-08 | Charges for- Legal Consultancy for the month of OCTOBER-2022 | 100 |  | 96979 | 2022-11-08 | 66666 | 2022-11-16 10:39 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2024-05-04 | Charges for Legal Consultancy for the month of APRIL-2024 | 100 |  | 107280 | 2024-05-04 | 66666 | 2024-05-04 16:37 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2022-08-04 | Charges for- Legal Consultancy for the month of JULY-2022 | 100 |  | 95791 | 2022-08-04 | 66666 | 2022-08-09 11:43 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 6.3999 | 51000 | 0.21 | 27199.7926 | 0 | 2021-05-14 | APR 2021 | 8.3334 |  | 90246 | 2021-05-17 | 27200 | 2021-05-17 12:47 | -0.2074 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-02-04 | Charges for Legal Consultancy for the month of JAN-2023 | 100 |  | 98032 | 2023-02-04 | 66666 | 2023-02-06 15:17 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-12-22 | Charges for Legal Consultancy for the month of AUG-2023 | 100 |  | 104083 | 2023-12-22 | 66666 | 2023-12-22 18:17 | 0 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 11.5714 | 51000 | 0.16 | 49178.8434 | 0 | 2021-03-06 | FEB 2021 | 8.3334 |  | 89257 | 2021-03-08 | 49179 | 2021-03-08 11:45 | -0.15657 | BHASKAR VITTAL SONPARATE
Legal Consultancy | N/C | N/C | BHASKAR VITTAL SONPARATE | 145 | 2021-02-23 | Legal Consultancy | 1 | 66666 | 0 | 66666 | 0 | 2023-03-31 | Charges for Legal Consultancy for the month of MAR-2023 | 100 |  | 99038 | 2023-03-31 | 66666 | 2023-04-08 11:20 | 0 | BHASKAR VITTAL SONPARATE
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-11-19 | AUG 2021 | 8.3334 |  | 92399 | 2021-11-19 | 60000.48 | 2021-11-23 15:38 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-11-19 | OCT 2021 | 8.3334 |  | 92401 | 2021-11-19 | 60000.48 | 2021-11-23 15:40 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 59994.72 | 0 | 2022-01-12 | DEC 2021 | 8.3326 |  | 93104 | 2022-01-13 | 59994.72 | 2022-01-13 13:12 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-05-14 | MAR-2021 | 8.3334 |  | 90248 | 2021-05-17 | 60000.48 | 2021-05-17 12:49 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-05-06 | APR-2023 | 8.33 |  | 99487 | 2023-05-06 | 49980 | 2023-05-10 13:10 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-09-06 | AUG-2023 | 8.33 |  | 101674 | 2023-09-06 | 49980 | 2023-09-06 12:24 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-03-31 | MAR 2022 | 8.33 |  | 94304 | 2022-03-31 | 49980 | 2022-04-11 16:15 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-03-29 | FEB 2024 | 8.333 |  | 106415 | 2024-03-29 | 49998 | 2024-03-29 14:09 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-02-04 | JAN-2023 | 8.33 |  | 98033 | 2023-02-04 | 49980 | 2023-02-06 15:19 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-03-29 | MARCH 2024 | 8.333 |  | 106405 | 2024-03-29 | 49998 | 2024-03-29 14:09 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 50220 | 0 | 2023-01-05 | DEC 2022 | 8.37 |  | 97644 | 2023-01-05 | 50220 | 2023-01-05 16:50 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-09-12 | AUG 2022 | 8.33 |  | 96216 | 2022-09-12 | 49980 | 2022-09-24 10:53 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-06-04 | MAY 2024 | 8.333 |  | 108039 | 2024-06-04 | 49998 | 2024-06-04 12:34 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-07-13 | May-2021 | 8.3334 |  | 90900 | 2021-07-14 | 60000.48 | 2021-07-14 11:57 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 11.9999 | 60000 | 0.02 | 59999.98 | 0 | 2021-12-11 | NOV 2021 | 8.3334 |  | 92707 | 2021-12-13 | 60000 | 2021-12-13 19:56 | -0.020004 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-03-31 | MAR-2023 | 8.33 |  | 99040 | 2023-03-31 | 49980 | 2023-04-08 11:20 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-11-08 | OCT 2022 | 8.33 |  | 96977 | 2022-11-08 | 49980 | 2022-11-16 10:39 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-03-04 | FEB-2023 | 8.33 |  | 98495 | 2023-03-04 | 49980 | 2023-03-06 18:16 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-02-03 | JAN 2024 | 8.333 |  | 104939 | 2024-02-03 | 49998 | 2024-02-05 17:19 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-12-07 | NOV-2023 | 8.33 |  | 103697 | 2023-12-07 | 49980 | 2023-12-11 14:18 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-11-02 | OCT-2023 | 8.33 |  | 103181 | 2023-11-02 | 49980 | 2023-11-03 16:01 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-11-19 | SEP 2021 | 8.3334 |  | 92400 | 2021-11-19 | 60000.48 | 2021-11-23 15:41 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-07-14 | JUNE 2022 | 8.33 |  | 95510 | 2022-07-14 | 49980 | 2022-07-14 17:36 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-08-09 | JULY-2023 | 8.33 |  | 101136 | 2023-08-09 | 49980 | 2023-08-10 15:35 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-06-06 | MAY 2022 | 8.33 |  | 95015 | 2022-06-06 | 49980 | 2022-06-07 14:59 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-05-04 | APRIL 2024 | 8.333 |  | 107281 | 2024-05-04 | 49998 | 2024-05-04 16:36 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 11.9999 | 60000 | 0.02 | 59999.98 | 0 | 2021-08-14 | JUL-2021 | 8.3334 |  | 91204 | 2021-08-14 | 60000 | 2021-09-09 13:12 | -0.020004 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-02-26 | JAN 2022 | 8.33 |  | 93608 | 2022-02-26 | 49980 | 2022-02-26 16:26 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-03-08 | FEB 2022 | 8.33 |  | 93758 | 2022-03-08 | 49980 | 2022-03-09 12:21 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-03-06 | FEB-2021 | 8.3334 |  | 89256 | 2021-03-08 | 60000.48 | 2021-03-08 11:45 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-12-08 | NOV 2022 | 8.33 |  | 97285 | 2022-12-08 | 49980 | 2022-12-23 10:54 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-08-04 | JUL 2022 | 8.33 |  | 95788 | 2022-08-04 | 49980 | 2022-08-09 11:41 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49998 | 0 | 2024-07-09 | JUNE 2024 | 8.333 |  | 108960 | 2024-07-09 | 49998 | 2024-07-09 14:38 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 50220 | 0 | 2024-01-03 | DEC-2023 | 8.37 |  | 104328 | 2024-01-03 | 50220 | 2024-01-04 15:45 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-10-10 | SEP 2022 | 8.33 |  | 96635 | 2022-10-10 | 49980 | 2022-10-12 19:07 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2023-10-04 | SEPT-2023 | 8.33 |  | 102234 | 2023-10-04 | 49980 | 2023-10-04 17:15 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 50000 | 0 | 49980 | 0 | 2022-05-06 | APR 2022 | 8.33 |  | 94686 | 2022-05-06 | 49980 | 2022-05-06 12:55 | 0 | MADHAVI ANJAN GHOSH
Professional Fees | N/C | N/C | MADHAVI ANJAN GHOSH | 146 | 2021-02-23 | G CUBE- Professional Consultancy | 12 | 60000 | 0 | 60000.48 | 0 | 2021-07-13 | JUN-2021 | 8.3334 |  | 90901 | 2021-07-14 | 60000.48 | 2021-07-14 11:57 | 0 | MADHAVI ANJAN GHOSH
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 1 | 350000 | 0 | 35000 | 0 | 2021-07-13 | Final Sketch | 10 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -115000 | SKETCH MARK
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 0.2857 | 350000 | 0.5 | 9999.5 | 0 | 2021-07-13 | Completion LG,GL | 10 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -140000.5 | SKETCH MARK
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 1 | 350000 | 0 | 17500 | 0 | 2021-07-13 | Advance | 5 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -132500 | SKETCH MARK
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 1 | 350000 | 0 | 35000 | 0 | 2021-07-13 | Building Approval | 10 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -115000 | SKETCH MARK
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 1 | 350000 | 0 | 17500 | 0 | 2021-07-13 | Plinth | 5 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -132500 | SKETCH MARK
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 1 | 350000 | 0 | 17500 | 0 | 2021-07-13 | NOC Approval | 5 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -132500 | SKETCH MARK
Consultancy Charges | N/C | N/C | SKETCH MARK | 168 | 2021-03-26 | Architectural & Liasoning Consultancy | 1 | 350000 | 0 | 17500 | 0 | 2021-07-13 | NOC for Completion | 5 |  | 90898 | 2021-07-13 | 150000 | 2021-07-13 12:05 | -132500 | SKETCH MARK
ECBC Compliance | N/C | N/C | KAKADE RASHMI RAVINDRA | 2 | 2020-02-08 | ECBC compliance report | 1 | 35000 | 0 | 7000 | 0 | 2020-07-23 | Final EC Certificate | 20 |  | 86768 | 2020-08-03 | 35000 | 2020-08-17 12:14 | -28000 | KAKADE RASHMI RAVINDRA
ECBC Compliance | N/C | N/C | KAKADE RASHMI RAVINDRA | 2 | 2020-02-08 | ECBC compliance report | 1 | 35000 | 0 | 5250 | 0 | 2020-07-23 | On Attendance of EC Meeting-1 | 15 |  | 86768 | 2020-08-03 | 35000 | 2020-08-17 12:14 | -29750 | KAKADE RASHMI RAVINDRA
ECBC Compliance | N/C | N/C | KAKADE RASHMI RAVINDRA | 2 | 2020-02-08 | ECBC compliance report | 1 | 35000 | 0 | 7000 | 0 | 2020-07-23 | On Submmision of EC | 20 |  | 86768 | 2020-08-03 | 35000 | 2020-08-17 12:14 | -28000 | KAKADE RASHMI RAVINDRA
ECBC Compliance | N/C | N/C | KAKADE RASHMI RAVINDRA | 2 | 2020-02-08 | ECBC compliance report | 1 | 35000 | 0 | 5250 | 0 | 2020-07-23 | On Attendance of EC Meeting-2 | 15 |  | 86768 | 2020-08-03 | 35000 | 2020-08-17 12:14 | -29750 | KAKADE RASHMI RAVINDRA
ECBC Compliance | N/C | N/C | KAKADE RASHMI RAVINDRA | 2 | 2020-02-08 | ECBC compliance report | 1 | 35000 | 0 | 7000 | 0 | 2020-07-23 | On Submission of Report | 20 |  | 86768 | 2020-08-03 | 35000 | 2020-08-17 12:14 | -28000 | KAKADE RASHMI RAVINDRA
ECBC Compliance | N/C | N/C | KAKADE RASHMI RAVINDRA | 2 | 2020-02-08 | ECBC compliance report | 1 | 35000 | 0 | 3500 | 0 | 2020-07-23 | As Advance with Acceptance Letter | 10 |  | 86768 | 2020-08-03 | 35000 | 2020-08-17 12:14 | -31500 | KAKADE RASHMI RAVINDRA
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | E- Project Services Consultancy | 199893.99 | 0.95 | 0 | 56969.7871 | 10254.56 | 2021-07-06 | Advance Along with Work Order | 30 |  | 90802 | 2021-07-06 | 113939.38 | 2021-07-09 12:25 | -56969.5929 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | D- Project Services Consultancy | 199893.29 | 0.95 | 0 | 56969.5877 | 10254.52 | 2021-07-06 | Advance Along with Work Order | 30 |  | 90802 | 2021-07-06 | 113939.38 | 2021-07-09 12:25 | -56969.7924 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | D- Project Services Consultancy | 199893.2331 | 0.95 | 0 | 132929 | 23927.22 | 2021-09-16 | After Completion of Work | 70 |  | 91562 | 2021-09-16 | 150113.88 | 2021-10-08 15:56 | -17184.88 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | D- Project Services Consultancy | 18089.35 | 0.95 | 0 | 5155.4648 | 927.98 | 2021-09-16 | Advance Along with Work Order | 30 |  | 91562 | 2021-09-16 | 150113.88 | 2021-10-08 15:56 | -144958.4152 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | D- Project Services Consultancy | 18089.35 | 0.95 | 0 | 12029.4178 | 2165.3 | 2021-09-16 | After Completion of Work | 70 |  | 91562 | 2021-09-16 | 150113.88 | 2021-10-08 15:56 | -138084.4623 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | E- Project Services Consultancy | 199893.99 | 0.95 | 0 | 132929.5034 | 23927.32 | 2021-09-16 | After Completion of Work | 70 |  | 91563 | 2021-09-16 | 151573.31 | 2021-10-08 15:57 | -18643.8066 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | E- Project Services Consultancy | 19625.28 | 0.95 | 0 | 13050.8112 | 2349.14 | 2021-09-16 | After Completion of Work | 70 |  | 91563 | 2021-09-16 | 151573.31 | 2021-10-08 15:57 | -138522.4988 | PERITUS REALITY SOLUTIONS LLP
Consultancy Charges | N/C | N/C | PERITUS REALITY SOLUTIONS LLP | 226 | 2021-06-22 | E- Project Services Consultancy | 19624.5614 | 0.95 | 0 | 5593 | 1006.74 | 2021-09-16 | Advance Along with Work Order | 30 |  | 91563 | 2021-09-16 | 151573.31 | 2021-10-08 15:57 | -145980.31 | PERITUS REALITY SOLUTIONS LLP
Professional Fees. | N/C | N/C | SSAP ADVISORS LLP | 25 | 2020-03-19 | Professional Consultancy (RERA) (D Bldg) - 1 Job | 1 | 7500 | 0 | 7500 | 1350 | 2020-07-11 | Professional Fee for RERA Registration Compliance | 100 | RERA CA CERTIFICATE RECEIVED | 86533 | 2020-07-22 | 7500 | 2020-08-26 15:41 | 0 | SSAP ADVISORS LLP
Professional Fees. | N/C | N/C | SSAP ADVISORS LLP | 26 | 2020-03-19 | Professional Consultancy (RERA) (E Bldg) - 1 Job | 1 | 7500 | 0 | 7500 | 1350 | 2020-07-11 | Professional Fee for RERA Registration Compliance | 100 | ALTUS CA CERTIFICATE RECEIVED | 86534 | 2020-07-22 | 7500 | 2020-08-26 15:39 | 0 | SSAP ADVISORS LLP
Vastu Consultancy | N/C | N/C | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | 282 | 2021-10-22 | Vastu Consultancy | 1 | 33898.3 | 0 | 33898.3 | 6101.7 | 2021-10-28 | Vastu Consultant Visiting Charges. | 100 |  | 92255 | 2021-10-28 | 33898.3 | 2021-10-29 18:35 | 0 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD
Detailed Traffic & Transportation study | N/C | N/C | KAKADE RASHMI RAVINDRA | 3 | 2020-02-08 | Traffic Analysis Report | 1 | 65000 | 0 | 9750 | 0 | 2020-07-23 | On Attendance of EC Meeting-1 | 15 |  | 86769 | 2020-08-03 | 65000 | 2020-08-17 12:14 | -55250 | KAKADE RASHMI RAVINDRA
Detailed Traffic & Transportation study | N/C | N/C | KAKADE RASHMI RAVINDRA | 3 | 2020-02-08 | Traffic Analysis Report | 1 | 65000 | 0 | 9750 | 0 | 2020-07-23 | On Attendance of EC Meeting-2 | 15 |  | 86769 | 2020-08-03 | 65000 | 2020-08-17 12:14 | -55250 | KAKADE RASHMI RAVINDRA
Detailed Traffic & Transportation study | N/C | N/C | KAKADE RASHMI RAVINDRA | 3 | 2020-02-08 | Traffic Analysis Report | 1 | 65000 | 0 | 6500 | 0 | 2020-07-23 | As Advance with Acceptance Letter | 10 |  | 86769 | 2020-08-03 | 65000 | 2020-08-17 12:14 | -58500 | KAKADE RASHMI RAVINDRA
Detailed Traffic & Transportation study | N/C | N/C | KAKADE RASHMI RAVINDRA | 3 | 2020-02-08 | Traffic Analysis Report | 1 | 65000 | 0 | 13000 | 0 | 2020-07-23 | On Submmision of EC | 20 |  | 86769 | 2020-08-03 | 65000 | 2020-08-17 12:14 | -52000 | KAKADE RASHMI RAVINDRA
Detailed Traffic & Transportation study | N/C | N/C | KAKADE RASHMI RAVINDRA | 3 | 2020-02-08 | Traffic Analysis Report | 1 | 65000 | 0 | 13000 | 0 | 2020-07-23 | Final EC Certificate | 20 |  | 86769 | 2020-08-03 | 65000 | 2020-08-17 12:14 | -52000 | KAKADE RASHMI RAVINDRA
Detailed Traffic & Transportation study | N/C | N/C | KAKADE RASHMI RAVINDRA | 3 | 2020-02-08 | Traffic Analysis Report | 1 | 65000 | 0 | 13000 | 0 | 2020-07-23 | On Submission of Report | 20 |  | 86769 | 2020-08-03 | 65000 | 2020-08-17 12:14 | -52000 | KAKADE RASHMI RAVINDRA
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E (Comm) MEP Consultancy | 6460 | 4 | 0 | 5168 | 930.24 | 2022-10-14 | Completion of Stage V- Executions completion of Ground servises / Development work | 20 |  | 96770 | 2022-10-15 | 200000.6 | 2022-10-17 11:22 | -194832.6 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D (Comm) MEP Consultancy | 4906.25 | 4 | 0 | 3925 | 706.5 | 2021-10-20 | Completion of Stage III- Tender / Budget Drawings Good for Construction drawings | 20 |  | 92109 | 2021-10-20 | 389999 | 2021-10-21 16:11 | -386074 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 204565 | 4 | 0 | 163652 | 29457.36 | 2021-10-20 | Completion of Stage III- Tender / Budget Drawings Good for Construction drawings | 20 |  | 92109 | 2021-10-20 | 389999 | 2021-10-21 16:11 | -226347 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | F (Comm) MEP Consultancy | 44741.25 | 4 | 0 | 35793 | 6442.74 | 2021-10-20 | Completion of Stage III- Tender / Budget Drawings Good for Construction drawings | 20 |  | 92109 | 2021-10-20 | 389999 | 2021-10-21 16:11 | -354206 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 204565 | 4 | 0 | 163652 | 29457.36 | 2022-10-14 | Completion of Stage V- Executions completion of Ground servises / Development work | 20 |  | 96770 | 2022-10-15 | 200000.6 | 2022-10-17 11:22 | -36348.6 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 34068.75 | 4 | 0 | 27255 | 4905.9 | 2022-10-15 | Completion of Stage V- Executions completion of Ground servises / Development work | 20 |  | 96770 | 2022-10-15 | 200000.6 | 2022-10-17 11:22 | -172745.6 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 204565 | 4 | 0 | 163652 | 29457.36 | 2021-10-20 | Completion of Stage III- Tender / Budget Drawings Good for Construction drawings | 20 |  | 92109 | 2021-10-20 | 389999 | 2021-10-21 16:11 | -226347 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E (Comm) MEP Consultancy | 6460 | 4 | 0 | 5168 | 930.24 | 2021-10-20 | Completion of Stage III- Tender / Budget Drawings Good for Construction drawings | 20 |  | 92109 | 2021-10-20 | 389999 | 2021-10-21 16:11 | -384831 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | F (Comm) MEP Consultancy | 44522.5 | 4 | 0 | 17809 | 3205.62 | 2021-10-20 | Completion of Stage II- Tender / Budget Drawings and Advance copy of working drawing | 10 |  | 92109 | 2021-10-20 | 389999 | 2021-10-21 16:11 | -372190 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D (Comm) MEP Consultancy | 4907 | 4 | 0 | 3925.6 | 706.6 | 2022-10-14 | Completion of Stage V- Executions completion of Ground servises / Development work | 20 |  | 96770 | 2022-10-15 | 200000.6 | 2022-10-17 11:22 | -196075 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 40913 | 4 | 0 | 40913 | 7364.34 | 2023-02-18 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 98248 | 2023-02-18 | 300000 | 2023-02-25 11:41 | -259087 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 170435 | 4 | 0 | 136348 | 24542.64 | 2023-02-18 | Completion of Stage V- Executions completion of Ground servises / Development work | 20 |  | 98248 | 2023-02-18 | 300000 | 2023-02-25 11:41 | -163652 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 204565 | 4 | 0 | 81826 | 14728.68 | 2023-02-18 | As Built Drawing | 10 |  | 98248 | 2023-02-18 | 300000 | 2023-02-25 11:41 | -218174 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 40913 | 4 | 0 | 40913 | 7364.34 | 2023-02-18 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 98248 | 2023-02-18 | 300000 | 2023-02-25 11:41 | -259087 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 204565 | 4 | 0 | 40913 | 7364.34 | 2020-06-26 | Appointment Letter | 5 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -238230.4 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 204565 | 4 | 0 | 81826 | 14728.68 | 2020-06-26 | Completion of Stage I- Design Brief report AND EC Approval | 10 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -197317.4 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E (Comm) MEP Consultancy | 6460 | 4 | 0 | 1292 | 232.56 | 2020-06-26 | Appointment Letter | 5 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -277851.4 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E (Comm) MEP Consultancy | 6460 | 4 | 0 | 2584 | 465.12 | 2020-06-26 | Completion of Stage I- Design Brief report AND EC Approval | 10 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -276559.4 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 204565 | 4 | 0 | 81826 | 14728.68 | 2020-06-26 | Completion of Stage I- Design Brief report AND EC Approval | 10 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -197317.4 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 204565 | 4 | 0 | 40913 | 7364.34 | 2020-06-26 | Appointment Letter | 5 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -238230.4 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D (Comm) MEP Consultancy | 4907 | 4 | 0 | 981.4 | 176.66 | 2020-06-26 | Appointment Letter | 5 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -278162 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | F (Comm) MEP Consultancy | 44742 | 4 | 0 | 17896.8 | 3221.42 | 2020-06-26 | Completion of Stage I- Design Brief report AND EC Approval | 10 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -261246.6 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D (Comm) MEP Consultancy | 4907 | 4 | 0 | 1962.8 | 353.3 | 2020-06-26 | Completion of Stage I- Design Brief report AND EC Approval | 10 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -277180.6 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | F (Comm) MEP Consultancy | 44742 | 4 | 0 | 8948.4 | 1610.72 | 2020-06-26 | Appointment Letter | 5 |  | 86006 | 2020-06-26 | 279143.4 | 2020-06-26 17:38 | -270195 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D (Comm) MEP Consultancy | 4907 | 4 | 0 | 1962.8 | 353.3 | 2020-11-01 | Completion of Stage II- Tender / Budget Drawings and Advance copy of working drawing | 10 |  | 87945 | 2020-11-01 | 168198.8 | 2020-11-01 11:05 | -166236 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 204565 | 4 | 0 | 81826 | 14728.68 | 2020-11-01 | Completion of Stage II- Tender / Budget Drawings and Advance copy of working drawing | 10 |  | 87945 | 2020-11-01 | 168198.8 | 2020-11-01 11:05 | -86372.8 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 204565 | 4 | 0 | 81826 | 14728.68 | 2020-11-01 | Completion of Stage II- Tender / Budget Drawings and Advance copy of working drawing | 10 |  | 87945 | 2020-11-01 | 168198.8 | 2020-11-01 11:05 | -86372.8 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E (Comm) MEP Consultancy | 6460 | 4 | 0 | 2584 | 465.12 | 2020-11-01 | Completion of Stage II- Tender / Budget Drawings and Advance copy of working drawing | 10 |  | 87945 | 2020-11-01 | 168198.8 | 2020-11-01 11:05 | -165614.8 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D MEP Consultancy | 163652 | 4 | 0 | 163652 | 29457.36 | 2022-10-04 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 96539 | 2022-10-04 | 372190 | 2022-10-12 11:45 | -208538 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E (Comm) MEP Consultancy | 5168 | 4 | 0 | 5168 | 930.24 | 2022-10-04 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 96539 | 2022-10-04 | 372190 | 2022-10-12 11:45 | -367022 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | F (Comm) MEP Consultancy | 35793 | 4 | 0 | 35793 | 6442.74 | 2022-10-04 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 96539 | 2022-10-04 | 372190 | 2022-10-12 11:45 | -336397 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | E MEP Consultancy | 163652 | 4 | 0 | 163652 | 29457.36 | 2022-10-04 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 96539 | 2022-10-04 | 372190 | 2022-10-12 11:45 | -208538 | UNICORN M.E.P. CONSULTANTS PVT LTD
MEP Consultancy | N/C | N/C | UNICORN M.E.P. CONSULTANTS PVT LTD | 33 | 2020-05-25 | D (Comm) MEP Consultancy | 3925 | 4 | 0 | 3925 | 706.5 | 2022-10-04 | Completion of Stage IV- Executions Completion of OHWT | 25 |  | 96539 | 2022-10-04 | 372190 | 2022-10-12 11:45 | -368265 | UNICORN M.E.P. CONSULTANTS PVT LTD
Registration Charges | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 396 | 2022-03-15 | Contract Labour act Registration & Compliance | 1 | 300 | 0 | 300 | 54 | 2022-04-11 | Registration Charges for BOCW for the Year-2022. | 100 |  | 94325 | 2022-04-11 | 54300 | 2022-04-11 19:32 | -54000 | NIKISHA CONSULTANCY SERVICES
Registration of Company (RC) | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 396 | 2022-03-15 | Contract Labour act Registration & Compliance | 1 | 34250 | 0 | 34250 | 6165 | 2022-04-11 | Company Registration (RC) under contract Labour Act Registration for the year 2022 (137 Nos x 250) | 100 |  | 94325 | 2022-04-11 | 54300 | 2022-04-11 19:32 | -20050 | NIKISHA CONSULTANCY SERVICES
Registration Charges | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 396 | 2022-03-15 | Contract Labour act Registration & Compliance | 1 | 5000 | 0 | 5000 | 900 | 2022-04-11 | Registration Charges for RC for Year-2022 | 100 |  | 94325 | 2022-04-11 | 54300 | 2022-04-11 19:32 | -49300 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 396 | 2022-03-15 | Contract Labour act Registration & Compliance | 1 | 14750 | 0 | 14750 | 2655 | 2022-04-11 | BOCW Registration under contract Labour Act Registration for the Year-2022 (59 Nos x 250) | 100 |  | 94325 | 2022-04-11 | 54300 | 2022-04-11 19:32 | -39550 | NIKISHA CONSULTANCY SERVICES
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 425000 | 0 | 106250 | 19125 | 2020-08-03 | After Online Submission of application | 25 |  | 86924 | 2020-08-10 | 425000 | 2020-09-24 16:46 | -318750 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 425000 | 0 | 85000 | 15300 | 2020-08-03 | After First Presentation at SEAC | 20 |  | 86924 | 2020-08-10 | 425000 | 2020-09-24 16:46 | -340000 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 425000 | 0 | 85000 | 15300 | 2020-08-03 | After Obtaining Recommendation from SEAC | 20 |  | 86924 | 2020-08-10 | 425000 | 2020-09-24 16:46 | -340000 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 425000 | 0 | 106250 | 19125 | 2020-08-03 | Advance along with Work Order | 25 |  | 86924 | 2020-08-10 | 425000 | 2020-09-24 16:46 | -318750 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 425000 | 0 | 42500 | 7650 | 2020-08-03 | After Obtaining EC Letter | 10 |  | 86924 | 2020-08-10 | 425000 | 2020-09-24 16:46 | -382500 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 595000 | 0 | 119000 | 21420 | 2022-10-06 | After First Presentation at SEAC | 20 |  | 96578 | 2022-10-06 | 119000 | 2022-10-12 11:52 | 0 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 595000 | 0 | 148750 | 26775 | 2021-10-14 | Advance Along with Work Order | 25 | Advance along with work order. | 92049 | 2021-10-14 | 297500 | 2021-10-18 16:44 | -148750 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 595000 | 0 | 148750 | 26775 | 2021-10-14 | After Online Submission of Application | 25 | After online submission of application. | 92049 | 2021-10-14 | 297500 | 2021-10-18 16:44 | -148750 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 595000 | 0 | 119000 | 21420 | 2022-10-04 | After Obtaining Recommendation from SEAC | 20 |  | 96735 | 2022-10-13 | 178500 | 2022-10-13 15:36 | -59500 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Environmental Clearance- SEAC & SEIAA | N/C | N/C | SUSTAINERA SOLUTIONS PRIVATE LIMITED | 4 | 2020-02-08 | Environmental Clearance Consultancy | 1 | 595000 | 0 | 59500 | 10710 | 2022-10-04 | After Obtaining EC Letter | 10 |  | 96735 | 2022-10-13 | 178500 | 2022-10-13 15:36 | -119000 | SUSTAINERA SOLUTIONS PRIVATE LIMITED
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 289760 | 3 | 0 | 173856 | 0 | 2023-10-17 | Completion of All Slabs | 20 |  | 102717 | 2023-10-17 | 173856 | 2023-10-18 11:38 | 0 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 724400 | 3 | 0 | 108660 | 0 | 2022-06-29 | Issue of Appointment letter | 5 |  | 95282 | 2022-06-29 | 977943 | 2022-07-30 19:25 | -869283 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 724403.3333 | 3 | 0 | 217321 | 0 | 2022-06-29 | Set Back Approval and Plinth Checking | 10 |  | 95282 | 2022-06-29 | 977943 | 2022-07-30 19:25 | -760622 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 180000 | 3 | 0 | 54000 | 0 | 2024-05-14 | Receipt of Completion Certificate | 10 |  | 107580 | 2024-05-14 | 97465 | 2024-05-14 15:27 | -43465 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 72441.6667 | 3 | 0 | 43465 | 0 | 2024-05-14 | Completion of All Slabs | 20 |  | 107580 | 2024-05-14 | 97465 | 2024-05-14 15:27 | -54000 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 362201.6667 | 3 | 0 | 217321 | 0 | 2023-04-17 | Completion of All Slabs | 20 |  | 99205 | 2023-04-17 | 217321 | 2023-04-18 15:05 | 2e-05 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 724402.2222 | 3 | 0 | 325981 | 0 | 2022-06-29 | Project Sanction and Certified Copies | 15 |  | 95282 | 2022-06-29 | 977943 | 2022-07-30 19:25 | -651962 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 438 | 2022-06-03 | Professional fees for liaisoning | 724402.2222 | 3 | 0 | 325981 | 0 | 2022-06-29 | Submission of Drawing for Sanction | 15 |  | 95282 | 2022-06-29 | 977943 | 2022-07-30 19:25 | -651962 | AYAZ RAFIK SHAIKH
Legal Consultancy.- | N/C | N/C | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | 466 | 2022-07-05 | Legal Consultancy for CGWB | 1 | 40000 | 0 | 32000 | 5760 | 2022-07-22 | Against Mobilization Advance | 80 |  | 95612 | 2022-07-22 | 40000 | 2022-07-26 12:01 | -8000 | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED
Legal Consultancy.- | N/C | N/C | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | 466 | 2022-07-05 | Legal Consultancy for CGWB | 1 | 40000 | 0 | 8000 | 1440 | 2022-07-22 | Against Obtaining CGWA Letter | 20 |  | 95612 | 2022-07-22 | 40000 | 2022-07-26 12:01 | -32000 | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 294 | 350 | 0 | 102900 | 18522 | 2024-04-08 | BOCW Registration under Contract Labour Act Registration from 1st March 2024 to 31st December 2024. | 100 |  | 106656 | 2024-04-08 | 234150 | 2024-04-09 14:47 | -131250 | NIKISHA CONSULTANCY SERVICES
Registration of Company (RC) | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 375 | 350 | 0 | 131250 | 23625 | 2024-04-08 | Company Registration (RC) under contract Labour Act Registration from 1st March 2024 to 31st December 2025. | 100 |  | 106656 | 2024-04-08 | 234150 | 2024-04-09 14:47 | -102900 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 81 | 350 | 0 | 28350 | 5103 | 2024-04-08 | BOCW Registration under Contract Labour Act Registration from 1st March 2024 to 31st December 2024. | 100 |  | 106655 | 2024-04-08 | 28350 | 2024-04-09 14:47 | 0 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 1 | 34000 | 0 | 34000 | 6120 | 2023-04-10 | BOCW Registration under contract Labour Act Registration for the year- 2023 (136 Nos x 250) | 100 |  | 99110 | 2023-04-11 | 106250 | 2023-04-11 11:50 | -72250 | NIKISHA CONSULTANCY SERVICES
Registration of Company (RC) | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 651 | 2023-04-07 | Contract Labour act Registration & Compliance | 1 | 72250 | 0 | 72250 | 13005 | 2023-04-10 | Company Registration (RC) under contract Labour Act Registration for the year 2023 (289 Nos x 250) | 100 |  | 99110 | 2023-04-11 | 106250 | 2023-04-11 11:50 | -34000 | NIKISHA CONSULTANCY SERVICES
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-03-07 | Professional Fees for the Month of FEB-2024 | 100 |  | 105795 | 2024-03-07 | 100000 | 2024-03-07 12:50 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-01-03 | Professional Fees for the Month of DEC-2023 | 100 |  | 104321 | 2024-01-03 | 100000 | 2024-01-04 15:45 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-11-02 | Professional Fees for the Month of OCT-2023 | 100 |  | 103170 | 2023-11-02 | 100000 | 2023-11-03 16:01 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-03-29 | Professional Fees for the Month of MAR-2024 | 100 |  | 106409 | 2024-03-29 | 100000 | 2024-03-29 14:09 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-12-07 | Professional Fees for the Month of NOV-2023 | 100 |  | 103699 | 2023-12-07 | 100000 | 2023-12-11 14:20 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-02-03 | Professional Fees for the Month of JAN-2024 | 100 |  | 104938 | 2024-02-03 | 100000 | 2024-02-05 17:19 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-06-04 | Professional Fees for the Month of MAY-2024 | 100 |  | 108032 | 2024-06-04 | 100000 | 2024-06-04 12:34 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-09-08 | Professional Fees for the Month of AUG-2023 | 100 |  | 101748 | 2023-09-08 | 200000 | 2023-09-08 14:35 | -100000 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-09-08 | Professional Fees for the Month of JULY-2023 | 100 |  | 101748 | 2023-09-08 | 200000 | 2023-09-08 14:35 | -100000 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-05-04 | Professional Fees for the Month of APR-2024 | 100 |  | 107278 | 2024-05-04 | 100000 | 2024-05-04 16:37 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | TARUSH ATUL GOEL | 766 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-07-09 | Professional Fees for the Month of JUNE-2024 | 100 |  | 108953 | 2024-07-09 | 100000 | 2024-07-09 14:36 | 0 | TARUSH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-03-07 | Professional Fees for the Month of FEB-2024 | 100 |  | 105796 | 2024-03-07 | 100000 | 2024-03-07 12:50 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-12-07 | Professional Fees for the Month of NOV-2023 | 100 |  | 103700 | 2023-12-07 | 100000 | 2023-12-11 14:19 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-05-04 | Professional Fees for the Month of APR-2024 | 100 |  | 107279 | 2024-05-04 | 100000 | 2024-05-04 16:37 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-03-29 | Professional Fees for the Month of MAR-2024 | 100 |  | 106410 | 2024-03-29 | 100000 | 2024-03-29 14:10 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-06-04 | Professional Fees for the Month of MAY-2024 | 100 |  | 108034 | 2024-06-04 | 100000 | 2024-06-04 12:34 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-07-09 | Professional Fees for the Month of JUNE-2024 | 100 |  | 108954 | 2024-07-09 | 100000 | 2024-07-09 14:36 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-09-08 | Professional Fees for the Month of JULY-2023 | 100 |  | 101749 | 2023-09-08 | 200000 | 2023-09-08 14:35 | -100000 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-09-08 | Professional Fees for the Month of AUG-2023 | 100 |  | 101749 | 2023-09-08 | 200000 | 2023-09-08 14:35 | -100000 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-01-03 | Professional Fees for the Month of DEC-2023 | 100 |  | 104319 | 2024-01-03 | 100000 | 2024-01-04 15:45 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2023-11-02 | Professional Fees for the Month of OCT-2023 | 100 |  | 103169 | 2023-11-02 | 100000 | 2023-11-03 16:01 | 0 | KRITESH ATUL GOEL
Professional Fees | N/C | N/C | KRITESH ATUL GOEL | 767 | 2023-09-06 | Professional Fees | 1 | 100000 | 0 | 100000 | 0 | 2024-02-03 | Professional Fees for the Month of JAN-2024 | 100 |  | 105071 | 2024-02-05 | 100000 | 2024-02-05 17:20 | 0 | KRITESH ATUL GOEL
Virtual Walkthrough | N/C | N/C | SPACE TECK | 84 | 2020-09-18 | Virtual Walkthrough Consultancy | 1 | 500000 | 0 | 425000 | 76500 | 2020-11-02 | After the delivery of final image & walk through with revision | 85 |  | 87991 | 2020-11-02 | 500000 | 2020-11-06 17:24 | -75000 | SPACE TECK
Virtual Walkthrough | N/C | N/C | SPACE TECK | 84 | 2020-09-18 | Virtual Walkthrough Consultancy | 1 | 500000 | 0 | 25000 | 4500 | 2020-11-02 | Advance before commencement of the Project | 5 |  | 87991 | 2020-11-02 | 500000 | 2020-11-06 17:24 | -475000 | SPACE TECK
Virtual Walkthrough | N/C | N/C | SPACE TECK | 84 | 2020-09-18 | Virtual Walkthrough Consultancy | 1 | 500000 | 0 | 50000 | 9000 | 2020-11-02 | At the time of approval of created content before final output | 10 |  | 87991 | 2020-11-02 | 500000 | 2020-11-06 17:24 | -450000 | SPACE TECK