## Work_Completion_Browse638587245
Work Completion Browse
Project : GANGA ALTUS
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 670 Records 1 to 670
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
12.5 Hp Booster Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 1001 | 2024-05-31 | D-Terrace Booster Pump Supply & Installation | 1 | 63705 | 0 | 44593.5 | 8026.84 | 2024-06-26 | Against Material Supply | 70 | Challan No- 18403 DT12.06.24 | 108664 | 2024-07-01 | 44593.5 | 2024-07-15 12:41 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
6 Sqmm x 4C Copper Flexible Cable (M) - Mtrs | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 1001 | 2024-05-31 | D-Terrace Booster Pump Supply & Installation | 100 | 289 | 0 | 20230 | 3641.4 | 2024-06-17 | Against Material Supply | 70 | DC No-18413 DT-14/6/2024 | 108426 | 2024-06-17 | 20230 | 2024-07-05 11:33 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
RMU Installation | N/C | N/C | ANAND PUNDLIK JADHAV | 1012 | 2024-06-11 | Electricity Infrastructure | 1 | 65000 | 0 | 65000 | 0 | 2024-06-11 | Charges for RMU Installation work. | 100 |  | 108283 | 2024-06-11 | 65000 | 2024-06-11 13:26 | 0 | ANAND PUNDLIK JADHAV
Concreting Work | N/C | N/C | UPRISEN CONSTRUCTION | 1026 | 2024-06-25 | Making of Foundation for D.G Set Near F Bldg. | 23.1 | 300 | 0 | 6930 | 1247.4 | 2024-07-11 19:40 | Charges for Concreting work (M25) for making of Foundation for DG to F-Bldg | 100 |  | 109088 | 2024-07-15 | 16307.5 | 2024-08-05 14:06 | -9377.5 | UPRISEN CONSTRUCTION
Shuttering Work-Dev | N/C | N/C | UPRISEN CONSTRUCTION | 1026 | 2024-06-25 | Making of Foundation for D.G Set Near F Bldg. | 17.05 | 550 | 0 | 9377.5 | 1687.96 | 2024-07-11 19:40 | Charges for Shuttering work for making of Foundation for DG to F-Bldg | 100 |  | 109088 | 2024-07-15 | 16307.5 | 2024-08-05 14:06 | -6930 | UPRISEN CONSTRUCTION
Chamber 36" x 18" (3ft Ht) - UDR | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 2 | 2200 | 0 | 4400 | 792 | 2024-07-16 12:23 | Charges for 1ft 6 inch x 3ft x 1m Construction of Chamber for LT Line. | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -18300 | SAI PLUMBING WORKS
Chamber 24" x 24" (3ft Ht) USL | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 3 | 2100 | 0 | 6300 | 1134 | 2024-07-16 12:20 | Charges for 2ft x 2ft x 1m Construction of Chamber for LT Line | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -16400 | SAI PLUMBING WORKS
Chamber 48" x 48" (5ft Ht) - UTI | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 3 | 4000 | 0 | 12000 | 2160 | 2024-07-16 12:17 | Charges for 4ft x 4ft x 1.5m Construction of Chamber near UGWT, near Pride Transformer Room, near F-Bldg. | 100 |  | 109230 | 2024-07-22 | 22700 | 1900-01-01 | -10700 | SAI PLUMBING WORKS
12" RCC Pipe Laying-USL | N/C | N/C | SAI PLUMBING WORKS | 1048 | 2024-07-06 | Laying HT,LT Line & Chamber Const.Transformer Room to UGWT | 391.9696 | 30 | 0 | 11759.088 | 2116.64 | 2024-07-28 18:38 | Labour charges for 12" RCC Pipe laying for HT & LT Line laying & for Construction of Chamber from Transformer Room to UGWT. | 100 |  | 109409 | 2024-07-29 | 11759.09 | 1900-01-01 | -0.002 | SAI PLUMBING WORKS
Earthing work(m+l)- BC | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 118 | 2020-11-27 | Earthing Work | 5 | 4000 | 0 | 20000 | 3600 | 2020-12-28 | Earthing work for Construction Meter,D Building Electrical Panel,Steel yard bending & cutting machine,CTM Machine | 100 |  | 88508 | 2020-12-29 | 20000 | 2021-01-11 14:34 | 0 | HARISH CHANDRA JADHAV ELECTRICALS
Perma Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 122 | 2020-12-08 | UGWT mambrane waterproofing at Base | 395.11 | 10 | 0 | 3951.1 | 711.2 | 2021-12-18 13:25 | RCC Pardi External Waterproofing work in F Bldg UGWT. Horizontal Waterproofing. | 100 |  | 92778 | 2021-12-20 | 13928.5 | 2022-01-28 18:12 | -9977.4 | AQUARIUS WATERPROOFING
Perma Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 122 | 2020-12-08 | UGWT RCC Pardi External W/P | 831.45 | 12 | 0 | 9977.4 | 1795.94 | 2021-12-18 13:25 | Vertical Waterproofing Treatment incl Cleaning and Grinding all vertical surface,Removing all binding wire and nails from RCC wall,Open all cold Concrete joint in V shape and treat by perma polycreate plus SBR Bond | 100 |  | 92778 | 2021-12-20 | 13928.5 | 2022-01-28 18:12 | -3951.1 | AQUARIUS WATERPROOFING
Perma Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 123 | 2020-12-08 | UGWT RCC Pardi External W/P | 831.45 | 30 | 0 | 24943.5 | 4489.84 | 2022-01-05 15:56 | Material Supply for Waterproofing Treatment with NEOPROOF RC-202 plus 50 GSM Coating. | 100 |  | 93007 | 2022-01-05 | 35611.47 | 2022-01-28 18:12 | -10667.97 | AQUARIUS WATERPROOFING
Perma Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 123 | 2020-12-08 | UGWT mambrane waterproofing at Base | 395.11 | 27 | 0 | 10667.97 | 1920.24 | 2022-01-05 15:56 | Material Supply for RCC Pardi External Waterproofing work in F Bldg UGWT. Horizontal Waterproofing. | 100 |  | 93007 | 2022-01-05 | 35611.47 | 2022-01-28 18:12 | -24943.5 | AQUARIUS WATERPROOFING
Sewage Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 128 | 2020-12-16 | STP-265 KLD | 1 | 1365000 | 0 | 389994.15 | 70198.94 | 2024-04-12 | Before Dispatch | 28.571 |  | 107198 | 2024-04-29 | 389994.15 | 2024-05-21 12:27 | 0 | GREENSOL TECH
Sewage Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 128 | 2020-12-16 | STP-265 KLD | 1 | 1365000 | 0 | 877503.9 | 157950.7 | 2024-04-12 | After Material Reciept at Site | 64.286 |  | 107199 | 2024-04-29 | 877503.9 | 2024-05-21 12:27 | 0 | GREENSOL TECH
Sewage Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 128 | 2020-12-16 | STP-265 KLD | 1 | 1365000 | 0 | 97501.95 | 17550.36 | 2024-04-12 | As Advance | 7.143 |  | 107197 | 2024-04-29 | 97501.95 | 2024-05-21 12:27 | 0 | GREENSOL TECH
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 135.5 | 60 | 0 | 8130 | 0 | 2023-05-09 | Charges for Excavation of STP & ETP in all type of Earth soil,Sand,Gravel and soft murum upto the required depth by Bucket including all leads & lifts,stacking with all tool machinery & Equipment. | 100 |  | 99565 | 2023-05-10 | 34947.2 | 2023-06-10 10:35 | -26817.2 | SHIVAM ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Transformer Room Loose material excavation work | 60.75 | 60 | 0 | 3645 | 0 | 2023-02-01 | Charges for Excavation of Transformer Room in all type of Earth soil,Sand,Gravel and soft murum upto the required depth by Bucket including all leads & lifts,stacking with all tool machinery & Equipment. | 100 |  | 97977 | 2023-02-01 | 4860 | 1900-01-01 | -1215 | SHIVAM ENTERPRISES
Spreading & Levelling | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 74.88 | 15 | 0 | 1123.2 | 0 | 2023-05-09 | Charges for Spreading and Levelling of Excavated material by Needle at STP & ETP | 100 |  | 99565 | 2023-05-10 | 34947.2 | 2023-06-10 10:35 | -33824 | SHIVAM ENTERPRISES
Spreading & Levelling | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 348.7 | 20 | 0 | 6974 | 0 | 2023-05-09 | Charges for Spreading and Levelling of Excavated material by Bucket at STP & ETP | 100 |  | 99565 | 2023-05-10 | 34947.2 | 2023-06-10 10:35 | -27973.2 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Transformer Room Loose material excavation work | 60.75 | 20 | 0 | 1215 | 0 | 2023-02-01 | Charges for Spreading and Levelling of Excavated material by Bucket for Transformer Room | 100 |  | 97977 | 2023-02-01 | 4860 | 1900-01-01 | -3645 | SHIVAM ENTERPRISES
Excavation By Needle | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 74.88 | 250 | 0 | 18720 | 0 | 2023-05-09 | Charges for Excavation of STP & ETP in soft & rock upto the required depth by Needle including all leads & lifts,stacking with all tool machinery & Equipment. | 100 |  | 99565 | 2023-05-10 | 34947.2 | 2023-06-10 10:35 | -16227.2 | SHIVAM ENTERPRISES
Breaking By Needle -BC | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Bldg D,E & Podium UGWT Excavation work | 968.9905 | 210 | 0 | 203488.005 | 36627.84 | 2022-06-07 | Fire Water Tank,Pump Room & Raw and Domestic water tank Excavation by Needle | 100 |  | 95028 | 2022-06-07 | 218023.01 | 2022-10-17 19:25 | -14535.005 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Bldg D,E & Podium UGWT Excavation work | 969 | 15 | 0 | 14535 | 2616.3 | 2022-06-07 | Spreading & Levelling Work | 100 |  | 95028 | 2022-06-07 | 218023.01 | 2022-10-17 19:25 | -203488.01 | SS ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 213.1 | 60 | 0 | 12786 | 2301.48 | 2022-10-14 | Charges for Excavation of STP & ETP in all type of Earth soil,Sand,Gravel and soft murum upto the required depth by Bucket including all leads & lifts,stacking with all tool machinery & Equipment. | 100 |  | 96767 | 2022-10-15 | 12786 | 1900-01-01 | 0 | SS ENTERPRISES
Excavation by Needle (Rate Diff.) | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Bldg D,E & Podium UGWT Excavation work | 1908.08 | 100 | 0 | 190808 | 34345.44 | 2023-04-17 | Labour charges for Excavation work by Needle for UGWT Fire Water Tank, Pump Room, Raw & Domestic water tank. | 100 |  | 99210 | 2023-04-18 | 190808 | 2023-05-04 14:46 | 0 | SS ENTERPRISES
Breaking By Needle -BC | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Bldg D,E & Podium UGWT Excavation work | 939.081 | 210 | -0.01 | 197207.01 | 35497.26 | 2022-08-17 | Fire Water Tank,Pump Room & Raw and Domestic water tank Excavation by Needle | 100 |  | 95914 | 2022-08-18 | 211293 | 2022-10-17 19:24 | -14085.99 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | Bldg D,E & Podium UGWT Excavation work | 939.0667 | 15 | 0 | 14086.0005 | 2535.48 | 2022-08-17 | Spreading & Levelling Work | 100 |  | 95914 | 2022-08-18 | 211293 | 2022-10-17 19:24 | -197206.9995 | SS ENTERPRISES
Excavation by Bucket | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 475 | 60 | 0 | 28500 | 5130 | 2022-09-26 | Charges for Excavation of STP & ETP in all type of Earth soil,Sand,Gravel and soft murum upto the required depth by Bucket including all leads & lifts,stacking with all tool machinery & Equipment. | 100 |  | 96383 | 2022-09-27 | 38000 | 2022-10-17 10:39 | -9500 | SS ENTERPRISES
Spreading & Levelling | N/C | N/C | SS ENTERPRISES | 175 | 2021-04-08 | F-Building STP & ETP Excavation Work | 475 | 20 | 0 | 9500 | 1710 | 2022-09-26 | Charges for Spreading and Levelling of Excavated material by Bucket at STP & ETP | 100 |  | 96383 | 2022-09-27 | 38000 | 2022-10-17 10:39 | -28500 | SS ENTERPRISES
Brickwork 9" BC | GLAZING SERVICES | N/C | PRAKASH CONTRACTOR | 215 | 2021-06-18 | DG 125 KVA Foundation Work | 69 | 15 | 0 | 1035 | 0 | 2021-07-22 | 9" thk Brickwork for DG Foundation | 100 |  | 90951 | 2021-07-23 | 2357 | 2021-08-13 18:19 | -1322 | PRAKASH CONTRACTOR
Murum filling Dld | N/C | N/C | PRAKASH CONTRACTOR | 215 | 2021-06-18 | DG 125 KVA Foundation Work | 172 | 3.5 | 0 | 602 | 0 | 2021-07-22 | Murrum Filling work | 100 |  | 90951 | 2021-07-23 | 2357 | 2021-08-13 18:19 | -1755 | PRAKASH CONTRACTOR
PCC Work | N/C | N/C | PRAKASH CONTRACTOR | 215 | 2021-06-18 | DG 125 KVA Foundation Work | 180 | 4 | 0 | 720 | 0 | 2021-07-22 | 3" thk PCC Work for DG Foundation | 100 |  | 90951 | 2021-07-23 | 2357 | 2021-08-13 18:19 | -1637 | PRAKASH CONTRACTOR
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 500 | 450 | 0 | 225000 | 40500 | 2023-04-18 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99232 | 2023-04-19 | 419250 | 2023-04-24 10:50 | -194250 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 260 | 300 | 0 | 78000 | 14040 | 2023-04-18 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99232 | 2023-04-19 | 419250 | 2023-04-24 10:50 | -341250 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 15500 | 7.5 | 0 | 116250 | 20925 | 2023-04-18 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99232 | 2023-04-19 | 419250 | 2023-04-24 10:50 | -303000 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 216.6311 | 450 | 0 | 97483.995 | 17547.12 | 2022-10-08 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 96627 | 2022-10-10 | 143386 | 2022-10-17 10:35 | -45902.005 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 65.03 | 300 | 0 | 19509 | 3511.62 | 2022-10-08 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 96627 | 2022-10-10 | 143386 | 2022-10-17 10:35 | -123877 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 6862.2667 | 7.5 | 0 | 51467.0002 | 9264.06 | 2023-05-04 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99418 | 2023-05-04 | 403150 | 2023-05-16 12:29 | -351682.9998 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 82.6 | 300 | 0 | 24780 | 4460.4 | 2023-05-04 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99418 | 2023-05-04 | 403150 | 2023-05-16 12:29 | -378370 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 3519.0667 | 7.5 | 0 | 26393.0003 | 4750.74 | 2022-10-08 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 96627 | 2022-10-10 | 143386 | 2022-10-17 10:35 | -116992.9998 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 726.4511 | 450 | 0 | 326902.995 | 58842.54 | 2023-05-04 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99418 | 2023-05-04 | 403150 | 2023-05-16 12:29 | -76247.005 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 170 | 450 | 0 | 76500 | 13770 | 2023-10-02 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 102186 | 2023-10-03 | 115388 | 2023-10-17 12:48 | -38888 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 3385.0667 | 7.5 | 0 | 25388.0003 | 4569.84 | 2023-10-02 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 102186 | 2023-10-03 | 115388 | 2023-10-17 12:48 | -89999.9998 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 45 | 300 | 0 | 13500 | 2430 | 2023-10-02 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 102186 | 2023-10-03 | 115388 | 2023-10-17 12:48 | -101888 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 12481.0667 | 7.5 | 0 | 93608.0002 | 16849.44 | 2023-01-02 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 97592 | 2023-01-03 | 345226 | 2023-01-23 18:38 | -251617.9997 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 493.1511 | 450 | 0 | 221917.995 | 39945.24 | 2023-01-02 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 97592 | 2023-01-03 | 345226 | 2023-01-23 18:38 | -123308.005 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 99 | 300 | 0 | 29700 | 5346 | 2023-01-02 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 97592 | 2023-01-03 | 345226 | 2023-01-23 18:38 | -315526 | RITU ENTERPRISES
Excavation Work | N/C | N/C | SS ENTERPRISES | 299 | 2021-12-09 | LG Floor Drainage line Excavation work (L) | 139.45 | 100 | 0 | 13945 | 2510.1 | 2022-03-20 | Drainline Trench Excavation work. | 100 |  | 95911 | 2022-08-18 | 13945 | 2022-08-18 11:15 | 0 | SS ENTERPRISES
RCC Work STP | N/C | N/C | RITU ENTERPRISES | 344 | 2022-01-15 | F - Bldg STP RCC Work ( L) | 41496 | 4 | 0 | 165984 | 29877.12 | 2023-03-13 | Labour Charges for- RCC Work of STP-45 KLD including PCC, Plum Concrete, Raft,Pardi,Top Slab,Columns,Beams,Sump pit Reinfocements,Shuttering & Concrete work etc complete. | 100 |  | 98647 | 2023-03-14 | 165984 | 2023-03-30 12:43 | 0 | RITU ENTERPRISES
RCC Work STP | N/C | N/C | RITU ENTERPRISES | 344 | 2022-01-15 | F - Bldg STP RCC Work ( L) | 16598.5 | 4 | 0 | 66394 | 11950.92 | 2023-05-04 | Labour Charges for- RCC Work of STP-45 KLD including PCC, Plum Concrete, Raft,Pardi,Top Slab,Columns,Beams,Sump pit Reinfocements,Shuttering & Concrete work etc complete. | 100 |  | 99417 | 2023-05-04 | 66394 | 2023-05-16 12:29 | 0 | RITU ENTERPRISES
RCC Work STP | N/C | N/C | RITU ENTERPRISES | 344 | 2022-01-15 | F - Bldg STP RCC Work ( L) | 8299.25 | 4 | 0 | 33197 | 5975.46 | 2023-05-26 | Labour Charges for- RCC Work of STP-45 KLD including PCC, Plum Concrete, Raft,Pardi,Top Slab,Columns,Beams,Sump pit Reinfocements,Shuttering & Concrete work etc complete. | 100 |  | 99807 | 2023-05-27 | 33197 | 2023-06-10 10:33 | 0 | RITU ENTERPRISES
RCC Work STP | N/C | N/C | RITU ENTERPRISES | 344 | 2022-01-15 | F - Bldg STP RCC Work ( L) | 16598 | 4 | 0 | 66392 | 11950.56 | 2023-09-13 | Labour Charges for- RCC Work of STP-45 KLD including PCC, Plum Concrete, Raft,Pardi,Top Slab,Columns,Beams,Sump pit Reinfocements,Shuttering & Concrete work etc complete. | 100 |  | 101826 | 2023-09-13 | 66392 | 2023-09-20 11:59 | 0 | RITU ENTERPRISES
RCC work - UWT | N/C | N/C | RITU ENTERPRISES | 344 | 2022-01-15 | F-Bldg UGWT - RCC Work | 45000 | 3.5 | 0 | 157500 | 28350 | 2022-01-28 | Construction of RCC UGWT at F building inclu. PCC, Plum Concrete, Raft, Pardi, Reinforcement, Top Slab & Other RCC Work etc. | 100 |  | 93232 | 2022-01-28 | 157500 | 2022-02-14 16:14 | 0 | RITU ENTERPRISES
Chemical W/P-UWT- | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 347 | 2022-01-15 | UGWT RCC Pardi Internal-Chemical W/P | 806.89 | 22 | 0 | 17751.58 | 3195.28 | 2023-01-06 | UGWT Internal Chemical Waterproofing Work. (For Bottom Area & All Vertical Sides ) | 100 |  | 97683 | 2023-01-07 | 27434.26 | 2023-01-31 12:05 | -9682.68 | GANGAPRASAD K VARMA
Cement Ghotai inside W/P-UWT- | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 347 | 2022-01-15 | UGWT RCC Pardi Internal-Chemical W/P | 645.512 | 15 | 0 | 9682.68 | 1742.88 | 2023-01-06 | UGWT Cement Ghotai Work. (For Bottom Area & All Vertical Sides ) | 100 |  | 97683 | 2023-01-07 | 27434.26 | 2023-01-31 12:05 | -17751.58 | GANGAPRASAD K VARMA
Cement Ghotai inside W/P-UWT- | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 347 | 2022-01-15 | UGWT RCC Pardi Internal-Chemical W/P | 161.378 | 15 | 0 | 2420.67 | 0 | 2024-06-28 16:42 | UGWT Cement Ghotai Work. (For Bottom Area & All Vertical Sides ) | 100 |  | 108684 | 2024-07-01 | 2420.67 | 1900-01-01 | 0 | PRABHURAM VERMA
Sewage Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 379 | 2022-02-18 | STP-45 KLD | 1 | 616000 | 0 | 423500 | 76230 | 2023-05-05 | After Material reciept at Site | 68.75 |  | 99449 | 2023-05-05 | 423500 | 2023-09-12 12:48 | 0 | GREENSOL TECH
Sewage Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 379 | 2022-02-18 | STP-45 KLD | 1 | 616000 | 0 | 154000 | 27720 | 2023-04-13 | Before Dispatch of Material | 25 |  | 99177 | 2023-04-14 | 192500 | 2023-04-24 10:50 | -38500 | GREENSOL TECH
Sewage Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 379 | 2022-02-18 | STP-45 KLD | 1 | 616000 | 0 | 38500 | 6930 | 2023-04-13 | Advance with Work Order | 6.25 |  | 99177 | 2023-04-14 | 192500 | 2023-04-24 10:50 | -154000 | GREENSOL TECH
Sewage Treatment Plant (L) | N/C | N/C | GREENSOL TECH | 380 | 2022-02-18 | STP-45 KLD | 1 | 154000 | 0 | 77000 | 13860 | 2023-08-19 | After Installation | 50 |  | 101332 | 2023-08-19 | 77000 | 1900-01-01 | 0 | GREENSOL TECH
Sewage Treatment Plant (L) | N/C | N/C | GREENSOL TECH | 380 | 2022-02-18 | STP-45 KLD | 1 | 154000 | 0 | 38500 | 6930 | 2023-08-26 | After Handover | 25 |  | 101475 | 2023-08-26 | 38500 | 1900-01-01 | 0 | GREENSOL TECH
Effluenr Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 381 | 2022-02-18 | STP ETP-15 KLD | 1 | 848000 | 0 | 583000 | 104940 | 2023-05-08 | After Material Reciept at Site | 68.75 |  | 99517 | 2023-05-08 | 583000 | 2023-10-24 12:42 | 0 | GREENSOL TECH
Effluenr Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 381 | 2022-02-18 | STP ETP-15 KLD | 1 | 848000 | 0 | 212000 | 38160 | 2023-04-13 | Before Dispatch of Material | 25 |  | 99176 | 2023-04-14 | 212000 | 2023-04-24 10:49 | 0 | GREENSOL TECH
Effluenr Treatment Plant (M) | N/C | N/C | GREENSOL TECH | 381 | 2022-02-18 | STP ETP-15 KLD | 1 | 848000 | 0 | 53000 | 9540 | 2022-10-12 | Advance with Work Order | 6.25 |  | 96709 | 2022-10-12 | 53000 | 2022-10-15 12:17 | 0 | GREENSOL TECH
Effluenr Treatment Plant (L) | N/C | N/C | GREENSOL TECH | 382 | 2022-02-18 | STP ETP-15 KLD | 1 | 212000 | 0 | 106000 | 19080 | 2023-08-29 | After Installation | 50 |  | 101505 | 2023-08-29 | 159000 | 1900-01-01 | -53000 | GREENSOL TECH
Effluenr Treatment Plant (L) | N/C | N/C | GREENSOL TECH | 382 | 2022-02-18 | STP ETP-15 KLD | 1 | 212000 | 0 | 53000 | 9540 | 2023-08-29 | After handover | 25 |  | 101505 | 2023-08-29 | 159000 | 1900-01-01 | -106000 | GREENSOL TECH
Earthing work(m+l)- BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 390 | 2022-02-24 | Earthing Work | 4 | 4000 | 0 | 16000 | 2880 | 2022-04-06 | Earthing work for construction of Meter Room and Shops. | 100 |  | 94192 | 2022-04-06 | 48000 | 2022-04-13 18:56 | -32000 | HARISH CHANDRA JADHAV ELECTRICALS
Earthing work(m+l)- BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 390 | 2022-02-24 | Sparten Lift DG Earthing work | 4 | 4000 | 0 | 16000 | 2880 | 2022-04-06 | Earthing work for Sparten lift DG Set | 100 |  | 94192 | 2022-04-06 | 48000 | 2022-04-13 18:56 | -32000 | HARISH CHANDRA JADHAV ELECTRICALS
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1000 | 15 | 0 | 15000 | 2700 | 2022-09-29 | Labour Charges for-UGWT Vertical RCC Retaining wall Waterproofing work.Remove all binding wire& Nials from wall,cleaning,open all cold joint in V shape,Honeycomb & Tie rod repairing treat by perma polycare + SBR Bond.Apply Neoproof RC 202+50GSM coating. | 100 |  | 96421 | 2022-09-29 | 15000 | 2022-10-01 18:52 | 0 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 3310 | 13 | 0 | 43030 | 7745.4 | 2023-03-13 | Labour Charges for-UGWT Waterproofing work.Cleaning,120 GSM fleeces as A Cushion on entire pcc area,250 GSM Rigidex-F Membrane over Fleece just 300mm,make Rigidex-F Membrane joint waterrproof, After joint treatment lay 120Gsm clothes to porotect Rigidex-F | 100 |  | 98646 | 2023-03-14 | 103030 | 2023-03-30 12:48 | -60000 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 4000 | 15 | 0 | 60000 | 10800 | 2023-03-13 | Labour Charges for-UGWT Vertical RCC Retaining wall Waterproofing work.Remove all binding wire& Nials from wall,cleaning,open all cold joint in V shape,Honeycomb & Tie rod repairing treat by perma polycare + SBR Bond.Apply Neoproof RC 202+50GSM coating. | 100 |  | 98646 | 2023-03-14 | 103030 | 2023-03-30 12:48 | -43030 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1423 | 13 | 0 | 18499 | 3329.82 | 2022-04-25 | Labour Charges for-UGWT Waterproofing work.Cleaning,120 GSM fleeces as A Cushion on entire pcc area,250 GSM Rigidex-F Membrane over Fleece just 300mm,make Rigidex-F Membrane joint waterrproof, After joint treatment lay 120Gsm clothes to porotect Rigidex-F | 100 |  | 94556 | 2022-04-26 | 18499 | 2022-06-04 13:58 | 0 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1792.6667 | 15 | 0 | 26890.0005 | 4840.2 | 2023-05-10 | Labour Charges for-UGWT Vertical RCC Retaining wall Waterproofing work.Remove all binding wire& Nials from wall,cleaning,open all cold joint in V shape,Honeycomb & Tie rod repairing treat by perma polycare + SBR Bond.Apply Neoproof RC 202+50GSM coating. | 100 |  | 99582 | 2023-05-11 | 26890 | 2023-06-28 11:57 | 0.0005 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1183.15 | 13 | 0 | 15380.95 | 2768.58 | 2023-07-13 | Labour Charges for-UGWT Waterproofing work.Cleaning,120 GSM fleeces as A Cushion on entire pcc area,250 GSM Rigidex-F Membrane over Fleece just 300mm,make Rigidex-F Membrane joint waterrproof, After joint treatment lay 120Gsm clothes to porotect Rigidex-F | 100 |  | 100676 | 2023-07-14 | 40850.95 | 2023-10-30 15:43 | -25470 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 408 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1698 | 15 | 0 | 25470 | 4584.6 | 2023-07-13 | Labour Charges for-UGWT Vertical RCC Retaining wall Waterproofing work.Remove all binding wire& Nials from wall,cleaning,open all cold joint in V shape,Honeycomb & Tie rod repairing treat by perma polycare + SBR Bond.Apply Neoproof RC 202+50GSM coating. | 100 |  | 100676 | 2023-07-14 | 40850.95 | 2023-10-30 15:43 | -15380.95 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1423 | 34 | 0 | 48382 | 8708.76 | 2022-04-27 | Material Supply for- UGWT Raft waterproofing with Rigidex-F Membrane. | 100 |  | 94579 | 2022-04-28 | 48382 | 2022-06-04 13:55 | 0 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1000 | 40 | 0 | 40000 | 7200 | 2022-09-29 | Material Supply for- UGWT Vertical RCC Retainig wall waterproofing treatment. | 100 |  | 96422 | 2022-09-29 | 40000 | 2022-10-01 18:54 | 0 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1792.675 | 40 | 0 | 71707 | 12907.26 | 2023-05-10 | Material Supply for- UGWT Vertical RCC Retainig wall waterproofing treatment. | 100 |  | 99583 | 2023-05-11 | 71707 | 2023-06-28 11:55 | 0 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 4000 | 40 | 0 | 160000 | 28800 | 2023-03-14 | Material Supply for- UGWT Vertical RCC Retainig wall waterproofing treatment. | 100 |  | 98650 | 2023-03-14 | 172546 | 2023-03-30 12:49 | -12546 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 369 | 34 | 0 | 12546 | 2258.28 | 2023-03-14 | Material Supply for- UGWT Raft waterproofing with Rigidex-F Membrane. | 100 |  | 98650 | 2023-03-14 | 172546 | 2023-03-30 12:49 | -160000 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1698 | 40 | 0 | 67920 | 12225.6 | 2023-07-13 | Material Supply for- UGWT Vertical RCC Retainig wall waterproofing treatment. | 100 |  | 100677 | 2023-07-14 | 108147.1 | 2023-10-20 10:56 | -40227.1 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 1183.15 | 34 | 0 | 40227.1 | 7240.88 | 2023-07-13 | Material Supply for- UGWT Raft waterproofing with Rigidex-F Membrane. | 100 |  | 100677 | 2023-07-14 | 108147.1 | 2023-10-20 10:56 | -67920 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 409 | 2022-04-07 | UGWT- D&E External waterrproofing work | 2941 | 34 | 0 | 99994 | 17998.92 | 2022-09-28 | Material Supply for- UGWT Raft waterproofing with Rigidex-F Membrane. | 100 |  | 96419 | 2022-09-29 | 99994 | 2022-10-01 18:53 | 0 | AQUARIUS WATERPROOFING
12" RCC Hume Pipe laying & fixing -UTR - | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 420 | 2022-04-27 | Basement level Electrical pipe laying & chamber work (L) | 328 | 19 | 0 | 6232 | 0 | 2022-10-14 | Labour Charges for- Hume Pipe Line work 300mm Dia for electrical lines.For D,E,F Building & Podium | 100 |  | 96765 | 2022-10-15 | 6232 | 2022-10-17 10:53 | 0 | SHINDE PLUMBING CONTRACTOR
12" RCC Hume Pipe laying & fixing -UTR - | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 420 | 2022-04-27 | Basement level Electrical pipe laying & chamber work (L) | 225 | 19 | 0 | 4275 | 769.5 | 2023-04-17 | Labour Charges for- Hume Pipe Line work 300mm Dia for electrical lines.For D,E,F Building & Podium | 100 |  | 99209 | 2023-04-18 | 4275 | 2023-05-04 14:44 | 0 | OM SAI ENTERPRISES (PROP. UMED SHITOLE)
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 65520 | 11793.6 | 2022-10-14 | Retention | 5 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1244880 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 131040 | 23587.2 | 2022-10-14 | File Submission | 10 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1179360 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 196560 | 35380.8 | 2022-10-14 | Site Visit | 15 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1113840 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 655200 | 117936 | 2022-10-14 | Sanction in Hand | 50 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -655200 | ARYA CONSULTANCY
Elect Meters UTI | N/C | N/C | ARYA CONSULTANCY | 507 | 2022-08-02 | Electricity Infrastructure | 500 | 2620.8 | 0 | 262080 | 47174.4 | 2022-10-14 | Sanction Estimate Draft copy | 20 |  | 96759 | 2022-10-14 | 1310400 | 2022-10-14 12:25 | -1048320 | ARYA CONSULTANCY
Tar Plaster-Dld | N/C | N/C | SURESH KUMAR MURALIDHAR | 51 | 2020-07-28 | DG Plinth work | 40 | 12 | 0 | 480 | 0 | 2021-08-03 | Tar Plaster Work for DG Plinth Work | 100 |  | 91096 | 2021-08-04 | 1260 | 1900-01-01 | -780 | SURESH KUMAR MURALIDHAR
Brickwork 9"- UDG | N/C | N/C | SURESH KUMAR MURALIDHAR | 51 | 2020-07-28 | DG Plinth work | 40 | 15 | 0 | 600 | 0 | 2021-08-03 | 9 inch brickwork for DG Plinth | 100 |  | 91096 | 2021-08-04 | 1260 | 1900-01-01 | -660 | SURESH KUMAR MURALIDHAR
PCC - UDG | N/C | N/C | SURESH KUMAR MURALIDHAR | 51 | 2020-07-28 | DG Plinth work | 36 | 5 | 0 | 180 | 0 | 2021-08-03 | PCC work for DG Plinth work | 100 |  | 91096 | 2021-08-04 | 1260 | 1900-01-01 | -1080 | SURESH KUMAR MURALIDHAR
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Int Chemical Waterproofing+Ghotai Plaster | 2191.184 | 22 | 0 | 48206.048 | 8677.08 | 2023-07-14 | material & Labour charges for Chemical waterproofing work for STP- Internal RCC Pardi & Bottom for Screen Chamber,O & G Tank,Equilization Tank, Anoxic Tank, aeration Tank, Tube Settler, Intermediates storage tank, Sludge Tank & Treated Water Storage Tank. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GANGAPRASAD K VARMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Int Chemical Waterproofing+Ghotai Plaster | 302.4 | 15 | 0 | 4536 | 816.48 | 2023-07-14 | Labour charges for Screeding work for STP- Internal waterproofing Screen Chamber, O & G Tank, Equilization Tank, Anoxic Tank, aeration Tank, Tube Settler, Intermediates storage tank, Sludge Tank & Treated Water Storage Tank. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GANGAPRASAD K VARMA
Cement Ghotai Plaster | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | 1910.4 | 15 | 0 | 28656 | 5158.08 | 2023-07-14 | Labour charges for Cement Ghotai Plaster work for ETP-15 KLD Internal RCC Pardi-Screen Chamber, O & G Tank, Neutralization Tank,Collection cum settling tank, Aeration Tank,Tube Settler, Intermediates storage tank & Treated Water Storage tank. | 100 |  | 100759 | 2023-07-19 | 62723.76 | 2023-07-29 10:56 | -34067.76 | GANGAPRASAD K VARMA
Cement Ghotai Plaster | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Int Chemical Waterproofing+Ghotai Plaster | 1888.784 | 15 | 0 | 28331.76 | 5099.72 | 2023-07-14 | Labour charges for Cement Ghotai Plaster work for STP- Internal RCC Pardi- Screen Chamber, O & G Tank, Equilization Tank, Anoxic Tank, aeration Tank, Tube Settler, Intermediates storage tank, Sludge Tank & Treated Water Storage Tank. | 100 |  | 100759 | 2023-07-19 | 62723.76 | 2023-07-29 10:56 | -34392 | GANGAPRASAD K VARMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg ETP-Int Chemical Waterproofing+Ghotai Plaster | 382.4 | 15 | 0 | 5736 | 1032.48 | 2023-07-14 | Labour charges for Screeding work for ETP-15 KLD Internal RCC Pardi-Screen Chamber, O & G Tank, Neutralization Tank,Collection cum settling tank, Aeration Tank,Tube Settler, Intermediates storage tank & Treated Water Storage tank. | 100 |  | 100759 | 2023-07-19 | 62723.76 | 2023-07-29 10:56 | -56987.76 | GANGAPRASAD K VARMA
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP External Waterproofing Work | 593.26 | 13 | 0 | 7712.38 | 1388.22 | 2024-02-17 17:52 | Labour charges for STP Horizontal Waterproofing,Cleaning 120GSM fleeces as cushion on entire pcc area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,After joint treatment lay 120GSM Clothes to protect Rigidex-F. | 100 |  | 105402 | 2024-06-28 | 11090.98 | 2024-07-05 11:30 | -3378.6 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP External Waterproofing Work | 726.4 | 15 | 0 | 10896 | 1961.28 | 2023-05-10 | Labour charges for STP Vertical RCC Retaining wall waterproofing work remove all binding wire & nails from wall,cleaning,open all cold joint in v shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond. Apply Neoproof RC 202+50 GSM coating. | 100 |  | 99585 | 2023-05-11 | 24048 | 2023-06-28 11:56 | -13152 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg ETP Ext Waterproofing Work | 876.8 | 15 | 0 | 13152 | 2367.36 | 2023-05-10 | Labour charges for ETP Vertical RCC Retaining wall waterproofing work remove all binding wire & nails from wall,cleaning,open all cold joint in V shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond.Apply Neoproof RC 202+50 GSM coating. | 100 |  | 99585 | 2023-05-11 | 24048 | 2023-06-28 11:56 | -10896 | AQUARIUS WATERPROOFING
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg Top Slab Chemical W/P + Screeding Work | 246 | 15 | 0 | 3690 | 0 | 2023-10-09 11:50 | Labour Charges for Screeding work of ETP top Slab & Pumproom top | 100 |  | 102489 | 2023-10-11 | 9564 | 2023-11-03 15:40 | -5874 | PRABHURAM VERMA
Screeding W/P-BCo | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Top Slab Chemical W/P + Screeding work (L) | 193.6 | 15 | 0 | 2904 | 0 | 2023-10-09 11:50 | Labour charges for Screeding work for STP Top Slab and Pump room top. | 100 |  | 102489 | 2023-10-11 | 9564 | 2023-11-03 15:40 | -6660 | PRABHURAM VERMA
Chemical W/P-DLd | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | F-Bldg Top Slab Chemical W/P + Screeding Work | 135 | 22 | 0 | 2970 | 0 | 2023-10-09 11:50 | Material & Labour Charges for Chemical waterproofing work of ETP top Slab & Pumproom. | 100 |  | 102489 | 2023-10-11 | 9564 | 2023-11-03 15:40 | -6594 | PRABHURAM VERMA
Chemical Waterproofing (M+L).Sq.ft | N/C | N/C | AQUARIUS WATERPROOFING | 555 | 2022-10-13 | STP-Top Slab Chemical W/P + Screeding work (L) | 427 | 22 | 0 | 9394 | 0 | 2023-09-25 | Material & Labour charges for Chemical Waterproofing work for STP Top Slab and Pump room top. | 100 |  | 103062 | 2023-10-30 | 9394 | 2023-10-30 10:57 | 0 | PRABHURAM VERMA
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 556 | 2022-10-13 | F-Bldg ETP Ext Waterproofing Work | 876.8 | 40 | 0 | 35072 | 6312.96 | 2023-05-10 | Material Supply for ETP-15 KLD Vertical RCC Pardi waterproofing treatment. | 100 |  | 99584 | 2023-05-11 | 64128 | 2023-06-28 11:58 | -29056 | AQUARIUS WATERPROOFING
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 556 | 2022-10-13 | STP External Waterproofing Work | 726.4 | 40 | 0 | 29056 | 5230.08 | 2023-05-10 | Material Supply for STP Vertical RCC Pardi waterproofing treatment. | 100 |  | 99584 | 2023-05-11 | 64128 | 2023-06-28 11:58 | -35072 | AQUARIUS WATERPROOFING
Total Statiotn Survey | N/C | N/C | VECTOR SURVEYORS | 559 | 2022-10-19 | UGWT- Surveying Work by total station | 1 | 4500 | 0 | 4500 | 0 | 2022-11-12 | Charges for D & E Building Survey point work for UGWT Fire tank , UGWT Pump room & UGWT Domestic tank. | 100 |  | 97040 | 2022-11-14 | 4500 | 2022-12-03 10:54 | 0 | VECTOR SURVEYORS
Lumpsum work- DCW | N/C | N/C | VEDANT CONSTRUCTION | 574 | 2022-11-25 | STP - 265 KLD Slab Cutting work | 1 | 65000 | 0 | 65000 | 11700 | 2023-01-10 | Lumpsum Charges for - Slab Cutting work of STP 265 KLD | 100 |  | 97734 | 2023-01-10 | 65000 | 2023-01-23 18:47 | 0 | VEDANT CONSTRUCTION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 11 | 900 | 0 | 9900 | 1782 | 2022-12-21 | Labour charges for Pile Drilling/ Boring work 500 mm dia. forTransformer Room. | 100 |  | 97475 | 2022-12-21 | 44900 | 2022-12-23 11:24 | -35000 | MASKE PILE FOUNDATION
Mobilisation - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 1 | 35000 | 0 | 35000 | 6300 | 2022-12-21 | Charges for one time Transportation including crane for Transformer Room. | 100 |  | 97475 | 2022-12-21 | 44900 | 2022-12-23 11:24 | -9900 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 12.25 | 100 | 0 | 1225 | 0 | 2023-06-22 | Labour charges for Pile Concreting work 500 mm dia. for Transformer Room. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -155012 | MASKE PILE FOUNDATION
Piling work 600 mm. dia.(Machine Pile) | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 54.95 | 1000 | 0 | 54950 | 0 | 2023-06-22 | Charges for Drilling/Boring of 600mm Dia pile work for UGWT near well E Building podium | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -101287 | MASKE PILE FOUNDATION
Piling Work 500mm dia rate diff. | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 10 | 26079 | 0 | 260790 | 46942.2 | 2024-02-02 15:59 | Labour charges and Rate Diff. for pile Drilling / Boring work 500mm dia. for Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -91183 | MASKE PILE FOUNDATION
Mobilisation - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 2 | 35000 | 0 | 70000 | 12600 | 2024-02-02 15:59 | Charges for one time Transportation including crane for Transformer room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -281973 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 11.55 | 100 | 0 | 1155 | 207.9 | 2024-02-02 15:59 | Labour charges for Reinforcement Cutting,Bending & Fixing for Piling work Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -350818 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 32.57 | 900 | 0 | 29313 | 0 | 2023-06-22 | Labour charges for Pile Drilling/ Boring work 500 mm dia. forTransformer Room. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -126924 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 57.2 | 100 | 0 | 5720 | 1029.6 | 2024-02-02 15:59 | Labour charges for Pile Concreting work 500 mm dia. for Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -346253 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 71.64 | 100 | 0 | 7164 | 0 | 2023-06-22 | Labour Charges for Reinforcement of 600mm dia pile work for UGWT Pile near well. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -149073 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 57.97 | 100 | 0 | 5797 | 0 | 2023-06-22 | Labour charges for Reinforcement Cutting, Bending and Fixing for Piling work Transformer Room. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -150440 | MASKE PILE FOUNDATION
Chiseling work for Piling - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 40 | 500 | 0 | 20000 | 0 | 2023-06-22 | Labour Charges for Chiseling work of 600mm dia pile for UGWT Pile near well. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -136237 | MASKE PILE FOUNDATION
Transport Charges | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 1 | 35000 | 0 | 35000 | 0 | 2023-06-22 | Transport Charges for 600mm Dia pile work for UGWT (Only one time transport Charges) | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -121237 | MASKE PILE FOUNDATION
Chiseling work for Piling - DEn | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Transformer Room- Pile Excavation Work | 35.77 | 400 | 0 | 14308 | 2575.44 | 2024-02-02 15:59 | Labour charges for Chiselling work for piling work for Transformer Room. | 100 |  | 104926 | 2024-02-02 | 351973 | 2024-02-19 15:28 | -337665 | MASKE PILE FOUNDATION
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 575 | 2022-11-28 | Near Well Pile Work-Near Well (L) - 1 No. | 27.88 | 100 | 0 | 2788 | 0 | 2023-06-22 | Labour Charges for Concreting of 600mm dia pile work for UGWT Pile near well. | 100 |  | 101684 | 2023-09-06 | 156237 | 2023-09-06 15:50 | -153449 | MASKE PILE FOUNDATION
Organic Waste Composter Machine (M+L) | N/C | N/C | GREEN PLANET SOLUTION | 579 | 2022-12-08 | Organic Waste Composter | 1 | 835000 | 0 | 584500 | 70140 | 2023-10-13 | Before Dispatch of Material at Site | 70 |  | 102941 | 2023-10-24 | 668000 | 2023-11-03 15:43 | -83500 | GREEN PLANET SOLUTION
Organic Waste Composter Machine (M+L) | N/C | N/C | GREEN PLANET SOLUTION | 579 | 2022-12-08 | Organic Waste Composter | 1 | 835000 | 0 | 83500 | 10020 | 2023-10-12 | Advance along with Work order | 10 |  | 102941 | 2023-10-24 | 668000 | 2023-11-03 15:43 | -584500 | GREEN PLANET SOLUTION
Backfilling - UDR | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 4285.7143 | 3.5 | 0 | 15000.0001 | 0 | 2023-10-18 | Labour charges for Manually Backfilling work for Electrical Line, Storm water Line and Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 102790 | 2023-10-19 | 47000 | 2023-11-06 16:14 | -32000 | SHIVAM ENTERPRISES
Excavation Manually | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 177.7778 | 180 | 0 | 32000.004 | 0 | 2023-10-18 | Labour charges for Manually Excavation work for electrical Line, Storm water Line & Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 102790 | 2023-10-19 | 47000 | 2023-11-06 16:14 | -14999.996 | SHIVAM ENTERPRISES
Excavation Manually | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 64.6 | 180 | 0 | 11628 | 0 | 2023-01-31 | Labour charges for Manually Excavation work for electrical Line, Storm water Line & Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 97971 | 2023-01-31 | 11628 | 2023-02-23 15:29 | 0 | SHIVAM ENTERPRISES
Backfilling - UDR | N/C | N/C | SHIVAM ENTERPRISES | 584 | 2022-12-10 | LG Floor- Excavation Work for Service line | 2822 | 3.5 | 0 | 9877 | 0 | 2023-04-13 | Labour charges for Manually Backfilling work for Electrical Line, Storm water Line and Fire Line for LG Floor D,E,F- Bldg. | 100 |  | 99171 | 2023-04-14 | 9877 | 2023-04-24 10:52 | 0 | SHIVAM ENTERPRISES
Chamber Cleaning Work | N/C | N/C | DURGARAM CHANDURAM BHATEE | 585 | 2022-12-12 | Drainage Chamber Cleaning Work | 14 | 100 | 0 | 1400 | 0 | 2023-03-13 | Labour charges for Drainage Line Chamber Cleaning work. | 100 |  | 98648 | 2023-03-14 | 1400 | 1900-01-01 | 0 | DURGARAM CHANDURAM BHATEE
Sleeve Fixing UWT | N/C | N/C | K B N FABRICATION | 586 | 2022-12-12 | UGWT- MS Sleeves Work | 21 | 400 | 0 | 8400 | 0 | 2022-12-30 | Labour charges for G.I sleeve Fixing work for D and E Building UGWT Domestic Tank Side Sleeves and Fire Tank Side Sleeves. | 100 |  | 97569 | 2022-12-31 | 8400 | 2023-01-31 11:44 | 0 | IZHAR MANSOOR SHAIKH
Sleeve Fixing UWT | N/C | N/C | K B N FABRICATION | 586 | 2022-12-12 | UGWT- MS Sleeves Work | 9 | 400 | 0 | 3600 | 0 | 2023-02-24 | Labour charges for G.I sleeve Fixing work for D and E Building UGWT Domestic Tank Side Sleeves and Fire Tank Side Sleeves. | 100 |  | 98325 | 2023-02-24 | 3600 | 2023-03-14 18:54 | 0 | IZHAR MANSOOR SHAIKH
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 1450 | 0 | 80620 | 14511.6 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -245846.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.704 | 500 | 0 | 8963 | 1613.34 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -317503.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 444.0457 | 350 | 0 | 38853.9987 | 6993.72 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -287612.0112 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 450 | 0 | 1350 | 243 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325116.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4286 | 350 | 0 | 4960.0005 | 892.8 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -321506.0095 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4154 | 650 | 0 | 1606.0005 | 289.08 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324860.0095 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.701 | 2100 | -0.02 | 43943.025 | 7909.74 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -282522.985 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7.0011 | 1850 | -0.01 | 3238.0087 | 582.84 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -323228.0012 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.36 | 500 | 0 | 209 | 37.62 | 2024-02-12 | Before Submission of Noc File | 5 | For Shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -326257.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.56 | 450 | 0 | 6138 | 1104.84 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -320328.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 1000 | 0 | 10250 | 1845 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -316216.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 444.0571 | 350 | 0 | 7770.9992 | 1398.78 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -318695.0108 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 380 | 0 | 9690 | 1744.2 | 2024-02-12 | After Installation & Pressure Testing | 25 | For Shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -316776.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 380 | 0 | 1938 | 348.84 | 2024-02-12 | Before Submission of Noc File | 5 | For Shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324528.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 450 | 0 | 22005 | 3960.9 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -304461.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4286 | 350 | 0 | 24800.0025 | 4464 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -301666.0075 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 1450 | 0 | 16124 | 2902.32 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -310342.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4 | 800 | 0 | 1176 | 211.68 | 2024-02-12 | Before Submission of Noc File | 5 |  | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325290.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.5778 | 450 | 0 | 1228.0005 | 221.04 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325238.0095 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4 | 800 | 0 | 5880 | 1058.4 | 2024-02-12 | After Installation & Pressure Testing | 25 |  | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -320586.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.7048 | 2100 | 0 | 8789.004 | 1582.02 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -317677.006 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7.0054 | 1850 | 0 | 647.9995 | 116.64 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325818.0105 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 1000 | 0 | 2050 | 369 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324416.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.352 | 500 | 0 | 1044 | 187.92 | 2024-02-12 | After Installation & Pressure Testing | 25 |  | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325422.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4031 | 650 | 0 | 8028.0037 | 1445.04 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -318438.0062 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 450 | 0 | 270 | 48.6 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -326196.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 450 | 0 | 4401 | 792.18 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -322065.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 1450 | 0 | 1450 | 261 | 2024-02-12 | Before Submission of Noc File | 5 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -325016.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 1450 | 0 | 7250 | 1305 | 2024-02-12 | After Installation & Pressure Testing | 25 | for shops | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -319216.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.72 | 500 | 0 | 1793 | 322.74 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105287 | 2024-02-12 | 326466.01 | 2024-02-27 10:43 | -324673.01 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket Stand (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Extinguishers - 1 No. | 1 | 639 | 0 | 447.3 | 80.52 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -866343.1 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8 | 1850 | 0 | 10360 | 1864.8 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1352740 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Extinguishers - 1 No. | 4 | 3000 | 0 | 8400 | 1512 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -858390.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 300 | 350 | 0 | 73500 | 13230 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1289600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 120 | 650 | 0 | 54600 | 9828 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1308500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 60 | 450 | 0 | 18900 | 3402 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1344200 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Hydrant Valve 63mm (M). | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 8 | 18500 | 0 | 103600 | 18648 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -763190.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 971 | 350 | 0 | 237895 | 42821.1 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1125205 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 350 | 0 | 24500 | 4410 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1338600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 546.9005 | 1450 | -0.01 | 555104.0075 | 99918.72 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -807995.9925 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 6Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Extinguisher & Signages | 18 | 2010 | 0 | 25326 | 4558.68 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108665 | 2024-07-01 | 30366 | 2024-07-15 15:03 | -5040 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8 | 2100 | 0 | 11760 | 2116.8 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1351340 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 21 | 1450 | 0 | 21315 | 3836.7 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1341785 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 6Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Extinguisher & Signages | 7 | 2010 | 0 | 9849 | 1772.82 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -856941.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 436 | 380 | 0 | 115976 | 20875.68 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1247124 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Orifice Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Internal Hydrant System | 25 | 1400 | 0 | 24500 | 4410 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT-03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -842290.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 298 | 450 | 0 | 93870 | 16896.6 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1269230 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Double Hydrant Valve (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Internal Hydrant System | 25 | 33000 | 0 | 577500 | 103950 | 2024-07-07 | Against Material Supply | 70 | Challan No-18537 DT03.07.24 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -289290.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Vane Type Water Flow (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 7500 | 0 | 131250 | 23625 | 2024-07-07 | Against Material Supply | 70 | Challan No-18598 DT 27.06.2024 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -735540.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 350 | 0 | 24500 | 4410 | 2024-01-12 | Against Material Supply | 70 | challan no-17351 | 104547 | 2024-01-15 | 49000 | 2024-02-08 11:57 | -24500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 2 | 3600 | 0 | 5040 | 907.2 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -364490 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 3600 | 0 | 63000 | 11340 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -306530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 100 | 350 | 0 | 24500 | 4410 | 2024-01-12 | Against Material Supply | 70 | challan no-17351 | 104547 | 2024-01-15 | 49000 | 2024-02-08 11:57 | -24500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 60 | 1000 | 0 | 42000 | 7560 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1321100 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Orifice Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 8 | 1100 | 0 | 6160 | 1108.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -860630.4 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 62 | 800 | 0 | 34720 | 6249.6 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1328380 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Strainer "Y" (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 1 | 7263 | 0 | 5084.1 | 915.14 | 2024-07-07 | Against Material Supply | 70 | Challan No-18493 DT 12.06.2024 | 109133 | 2024-07-16 | 866790.4 | 2024-08-07 11:49 | -861706.3 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Fire Pump Room Equipment | 2 | 3600 | 0 | 5040 | 907.2 | 2024-06-26 | Against Material Supply | 70 | Challan No-18403 DT 18403 | 108665 | 2024-07-01 | 30366 | 2024-07-15 15:03 | -25326 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 128 | 500 | 0 | 44800 | 8064 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1318300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 340 | 0 | 23800 | 4284 | 2023-04-18 | Against Material Supply | 70 |  | 99241 | 2023-04-20 | 1363100 | 2023-04-24 10:50 | -1339300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 357 | 450 | 0 | 112455 | 20241.9 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -1047690 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 180 | 1450 | 0 | 182700 | 32886 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -977445 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 102 | 650 | 0 | 46410 | 8353.8 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -1113735 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 768 | 500 | 0 | 268800 | 48384 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -891345 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 204 | 2100 | 0 | 299880 | 53978.4 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -860265 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 1020 | 350 | 0 | 249900 | 44982 | 2023-01-02 | Against Material Supply | 70 |  | 97589 | 2023-01-03 | 1160145 | 2023-01-11 17:10 | -910245 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 10 | 2100 | 0 | 14700 | 2646 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -711830 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 500 | 0 | 21000 | 3780 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -705530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 340 | 0 | 23800 | 4284 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -702730 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 290 | 2550 | 0 | 517650 | 93177 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -208880 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 100 | 340 | 0 | 23800 | 4284 | 2024-01-01 | Against Material Supply | 70 | Challan No-17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -702730 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 1450 | 0 | 60900 | 10962 | 2023-12-31 | Against Material Supply | 70 | Challan No- 17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -665630 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 96 | 650 | 0 | 43680 | 7862.4 | 2024-01-01 | Against Material Supply | 70 |  | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -682850 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 30 | 1000 | 0 | 21000 | 3780 | 2023-12-31 | Against Material Supply | 70 | Challan No- 17364 | 104290 | 2024-01-01 | 726530 | 2024-02-05 15:39 | -705530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 60 | 800 | 0 | 33600 | 6048 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1857170 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 500 | 0 | 105000 | 18900 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1785770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 750 | 450 | 0 | 236250 | 42525 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1654520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 1020 | 350 | 0 | 249900 | 44982 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1640870 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 9 | 1200 | 0 | 7560 | 1360.8 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1883210 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 9 | 1000 | 0 | 6300 | 1134 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1884470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 498 | 2100 | 0 | 732060 | 131770.8 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1158710 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 600 | 350 | 0 | 147000 | 26460 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -303135 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 1450 | 0 | 304500 | 54810 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1586270 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 300 | 650 | 0 | 136500 | 24570 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT5/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1754270 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 40 | 1000 | 0 | 28000 | 5040 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1862770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 600 | 500 | 0 | 210000 | 37800 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -240135 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 90 | 1000 | 0 | 63000 | 11340 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -387135 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 338 | 450 | 0 | 106470 | 19164.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -147700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 350 | 0 | 14700 | 2646 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -239470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 650 | 0 | 27300 | 4914 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16574 | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -422835 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 9 | 450 | 0 | 2835 | 510.3 | 2023-09-16 | Against Material Supply | 70 | Remaining Qty from Previous Challan . | 101921 | 2023-09-18 | 450135 | 2023-10-23 12:37 | -447300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 73 | 1000 | 0 | 51100 | 9198 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108223 | 2024-06-10 | 1890770 | 2024-06-15 16:16 | -1839670 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 500 | 380 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -121170 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 310 | 1450 | 0 | 314650 | 56637 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -738784 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 120 | 1000 | 0 | 84000 | 15120 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -969434 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 68.9005 | 1450 | -0.01 | 69934.0075 | 12588.12 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -983499.9925 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 30 | 800 | 0 | 16800 | 3024 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -1036634 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 60 | 650 | 0 | 27300 | 4914 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -1026134 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 300 | 350 | 0 | 73500 | 13230 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -979934 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 150 | 2550 | 0 | 267750 | 48195 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -785684 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 500 | 0 | 105000 | 18900 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -948434 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 300 | 450 | 0 | 94500 | 17010 | 2023-08-21 | Against Material Supply | 70 |  | 101361 | 2023-08-21 | 1053434 | 2023-10-11 13:54 | -958934 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 54 | 340 | 0 | 12852 | 2313.36 | 2023-12-11 | Against Material Supply | 70 |  | 103842 | 2023-12-11 | 172102 | 2023-12-25 15:44 | -159250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Drain Valve 25 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 25 | 4500 | 0 | 78750 | 14175 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -290780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 50 | 2100 | 0 | 73500 | 13230 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -296030 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | E-Building Automatic Sprinkler System | 100 | 2100 | 0 | 147000 | 26460 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -222530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 650 | 350 | 0 | 159250 | 28665 | 2023-12-11 | Against Material Supply | 70 |  | 103842 | 2023-12-11 | 172102 | 2023-12-25 15:44 | -12852 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Fire Pump Room Equipment | 1 | 3200 | 0 | 2240 | 403.2 | 2024-01-29 | Against Material Supply | 70 |  | 104870 | 2024-01-29 | 369530 | 2024-02-08 11:57 | -367290 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4 | 400 | 0 | 13832 | 2489.76 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -365475 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.7 | 600 | 0 | 12555 | 2259.9 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -366752 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 550 | 0 | 85624 | 15412.32 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -293683 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 222.4 | 550 | 0 | 30580 | 5504.4 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -348727 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4 | 200 | 0 | 14170 | 2550.6 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -365137 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 200 | 0 | 1000 | 180 | 2024-02-12 | After Final Noc | 25 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378307 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 83.7 | 600 | 0 | 35154 | 6327.72 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -344153 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.56 | 250 | 0 | 3410 | 613.8 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -375897 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7 | 200 | 0 | 350 | 63 | 2024-02-12 | After Final Noc | 25 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378957 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 283.4286 | 200 | 0 | 39680.004 | 7142.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -339626.996 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 49.4 | 400 | 0 | 4940 | 889.2 | 2024-02-12 | After Final Noc | 25 |  | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -374367 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.7 | 300 | 0 | 15057 | 2710.26 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -364250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 350 | 0 | 2940 | 529.2 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -376367 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 250 | 0 | 34230 | 6161.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -345077 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4044 | 450 | 0 | 3307.995 | 595.44 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -375999.005 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 54.56 | 250 | 0 | 9548 | 1718.64 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -369759 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 195.6 | 250 | 0 | 12225 | 2200.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -367082 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 200 | 0 | 14280 | 2570.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -365027 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 102 | 200 | 0 | 5100 | 918 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -374207 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 500 | 0 | 5125 | 922.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -374182 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 29.4 | 450 | 0 | 9261 | 1666.98 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -370046 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 7 | 200 | 0 | 980 | 176.4 | 2024-02-12 | After Installation & Pressure Testing | 70 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378327 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 71.7067 | 300 | 0 | 5378.0025 | 968.04 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -373928.9975 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 12 | 350 | 0 | 1050 | 189 | 2024-02-12 | After Final Noc | 25 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378257 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 184 | 200 | 0 | 25760 | 4636.8 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1138445 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 65mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 28 | 450 | 0 | 8820 | 1587.6 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1155385 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Drain Valve 25 mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 23 | 350 | 0 | 5635 | 1014.3 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1158570 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 138 | 750 | 0 | 72450 | 13041 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106228 | 2024-03-18 | 74634 | 2024-03-28 12:36 | -2184 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 1432 | 200 | 0 | 200480 | 36086.4 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -963725 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 1206 | 200 | 0 | 168840 | 30391.2 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -995365 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 294.901 | 750 | -0.02 | 154823.025 | 27868.14 | 2023-08-22 | After Installation & Pressure Testing | 70 |  | 101390 | 2023-08-23 | 154823.01 | 2023-09-20 11:58 | 0.015 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 1350 | 300 | 0 | 283500 | 51030 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -880705 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 711 | 550 | 0 | 273735 | 49272.3 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -890470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Infra Work- Fire Hydrant System - 1 No. | 5.2 | 600 | 0 | 2184 | 393.12 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106228 | 2024-03-18 | 74634 | 2024-03-28 12:36 | -72450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 357 | 250 | 0 | 62475 | 11245.5 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1101730 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 32mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 19 | 250 | 0 | 3325 | 598.5 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1160880 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 196 | 500 | 0 | 68600 | 12348 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1095605 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 205 | 400 | 0 | 57400 | 10332 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1106805 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 23 | 350 | 0 | 5635 | 1014.3 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106231 | 2024-03-18 | 1164205 | 2024-03-28 12:35 | -1158570 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 6.5455 | 550 | -0.02 | 2520.0175 | 0 | 2023-10-11 | After Installation & Pressure Testing | 70 | Debit for Shivappa Pawar (Housekeeping ) | 102552 | 2023-10-12 | 2520 | 2023-11-06 16:16 | 0.0175 | PAWAR SHIVAPPA TARANAIK
SITC GI- 100mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 550 | 0 | 23100 | 4158 | 2024-03-18 | After Installation & Pressure Testing | 70 | Hydrant Riser Lower | 106230 | 2024-03-18 | 174300 | 2024-03-30 12:28 | -151200 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 180 | 600 | 0 | 75600 | 13608 | 2024-03-18 | After Installation & Pressure Testing | 70 |  | 106230 | 2024-03-18 | 174300 | 2024-03-30 12:28 | -98700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 180 | 600 | 0 | 75600 | 13608 | 2024-03-18 | After Installation & Pressure Testing | 70 | Hydrant Riser Lower + Upper | 106230 | 2024-03-18 | 174300 | 2024-03-30 12:28 | -98700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Fire Hydrant System | 41 | 500 | 0 | 14350 | 2583 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -364957 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.3524 | 300 | 0 | 1754.004 | 315.72 | 2024-02-12 | After Installation & Pressure Testing | 70 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -377552.996 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 8.3467 | 300 | 0 | 626.0025 | 112.68 | 2024-02-12 | After Final Noc | 25 | For Shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -378680.9975 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Brass Ball Valve 32mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 200 | 0 | 2800 | 504 | 2024-02-12 | After Installation & Pressure Testing | 70 | for shops | 105288 | 2024-02-12 | 379307 | 2024-02-20 12:21 | -376507 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 23 | 400 | 0 | 6440 | 1159.2 | 2024-03-20 | After Installation & Pressure Testing | 70 |  | 106286 | 2024-03-20 | 41160 | 2024-03-30 12:28 | -34720 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 97 | 400 | 0 | 27160 | 4888.8 | 2024-03-20 | After Installation & Pressure Testing | 70 |  | 106286 | 2024-03-20 | 41160 | 2024-03-30 12:28 | -14000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 150mm Dia. Heavy Grade Pipe | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 591 | 2022-12-14 | D-Building Automatic Sprinkler System | 18 | 600 | 0 | 7560 | 1360.8 | 2024-03-20 | After Installation & Pressure Testing | 70 |  | 106286 | 2024-03-20 | 41160 | 2024-03-30 12:28 | -33600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
RCC Work ETP | N/C | N/C | RITU ENTERPRISES | 625 | 2023-02-24 | ETP RCC Work (L) | 92908.8 | 4 | 0 | 74327.04 | 13378.86 | 2023-05-26 | Upto Raft including all work | 20 |  | 99808 | 2023-05-27 | 74327.04 | 2023-06-10 10:33 | 0 | RITU ENTERPRISES
RCC Work ETP | N/C | N/C | RITU ENTERPRISES | 625 | 2023-02-24 | ETP RCC Work (L) | 116136 | 4 | 0 | 185817.6 | 33447.16 | 2023-09-13 | RCC Work for all Pardi | 40 |  | 101827 | 2023-09-13 | 185817.6 | 2023-09-20 12:01 | 0 | RITU ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 582 | 20 | 0 | 11640 | 0 | 2024-03-15 | Labour charges for Spreading and Levelling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 106095 | 2024-03-18 | 11640 | 1900-01-01 | 0 | SHIVAM ENTERPRISES
Excavation in Soil- UST | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 200 | 60 | 0 | 12000 | 0 | 2023-04-13 | Labour charges for Excavation work in Soft soil for E-Bldg Domestic tank side column footings. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -52222.4 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 200 | 20 | 0 | 4000 | 0 | 2023-04-13 | Labour charges for Spreading and levelling work for domestic tank side column footings E-Bldg. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -60222.4 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 210 | 60 | 0 | 12600 | 0 | 2023-04-13 | Labour charges for Backfilling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -51622.4 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 210 | 20 | 0 | 4200 | 0 | 2023-04-13 | Labour charges for Spreading & Levelling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -60022.4 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 289.04 | 60 | 0 | 17342.4 | 0 | 2023-04-13 | Labour charges for Back filling work for D-Bldg Fire Tank side column & Fire Tank side footings. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -46880 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 176 | 20 | 0 | 3520 | 0 | 2023-04-13 | Labour charges for Spreading and Levelling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -60702.4 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 176 | 60 | 0 | 10560 | 0 | 2023-04-13 | Labour charges for Backfilling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 99172 | 2023-04-14 | 64222.4 | 2023-04-24 10:52 | -53662.4 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 346.75 | 20 | 0 | 6935 | 0 | 2023-07-05 | Labour charges for Spreading and levelling work for domestic tank side column footings E-Bldg. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -72380.8 | SHIVAM ENTERPRISES
Excavation in Hard Rock | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 309.39 | 210 | 0 | 64971.9 | 0 | 2024-05-13 12:25 | Labour charges for Hard Rock Excavation work for UGWT D & E Ramp column footing. | 100 |  | 107566 | 2024-05-13 | 73018.56 | 2024-06-26 11:45 | -8046.66 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 289.04 | 20 | 0 | 5780.8 | 0 | 2023-07-05 | Labour charges for Spreading & Levelling work for D-Bldg Fire Tank side column & Fire Tank side footings. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -73535 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 582 | 60 | 0 | 34920 | 0 | 2023-07-05 | Labour charges for Backfilling work for UGWT D & E Fire tank, pump room, Domestic tank,raft toe. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -44395.8 | SHIVAM ENTERPRISES
Excavation in Soil- UST | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 346.75 | 60 | 0 | 20805 | 0 | 2023-07-05 | Labour charges for Excavation work in Soft soil for E-Bldg Domestic tank side column footings. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -58510.8 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 134.111 | 60 | 0 | 8046.66 | 0 | 2024-05-13 12:40 | Labour charges for Backfilling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 107566 | 2024-05-13 | 73018.56 | 2024-06-26 11:45 | -64971.9 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 312 | 20 | 0 | 6240 | 0 | 2023-07-05 | Labour charges for Spreading & Levelling work for Domestic tank side column & Domestic tank footings for E-Bldg side ramp. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -73075.8 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 631 | 2023-03-02 | Ramp footing Excavation & UGWT- Side Filling | 309 | 15 | 0 | 4635 | 0 | 2023-07-05 | Labour charges for Spreading and Levelling work for UGWT D & E Ramp column footings. | 100 |  | 100531 | 2023-07-07 | 79315.8 | 2023-07-26 12:26 | -74680.8 | SHIVAM ENTERPRISES
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 8 | 3200 | 0 | 17920 | 3225.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18613 DT 18/07/2024 | 109433 | 2024-07-29 | 20300 | 2024-08-08 11:24 | -2380 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 200mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 3400 | 0 | 2380 | 428.4 | 2024-07-29 | Against Material Supply | 70 | Total Challan Qty-30 Mtrs. RA Bill Released Qty-29 Mtrs(RA-108232 Challan No-18352 (Amendment Qty 1 Mtrs released from this Completion) | 109433 | 2024-07-29 | 20300 | 2024-08-08 11:24 | -17920 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 7500 | 0 | 31500 | 5670 | 2023-04-18 | Against Material Supply | 70 |  | 99228 | 2023-04-18 | 31500 | 2023-07-19 11:38 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6500 | 0 | 4550 | 819 | 2023-04-10 | Against Material Supply | 70 |  | 99105 | 2023-04-11 | 9450 | 2023-04-15 16:20 | -4900 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 7000 | 0 | 4900 | 882 | 2023-04-10 | Against Material Supply | 70 |  | 99105 | 2023-04-11 | 9450 | 2023-04-15 16:20 | -4550 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 4 | 1000 | 0 | 2800 | 504 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT 27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -93100 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 43500 | 0 | 91350 | 16443 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -4550 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Bucket Stand (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 2500 | 0 | 1750 | 315 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT 27/06/2024 | 108670 | 2024-07-01 | 95900 | 2024-07-15 15:03 | -94150 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 200mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 29 | 3400 | 0 | 69020 | 12423.6 | 2024-06-10 | Against Material Supply | 70 | DT5/06/2024 1 Mtr Balance Due to less quantity in WO | 108232 | 2024-06-10 | 78820 | 2024-06-15 16:30 | -9800 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 80mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 14 | 1000 | 0 | 9800 | 1764 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-05/06/2024 | 108232 | 2024-06-10 | 78820 | 2024-06-15 16:30 | -69020 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 150mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 10000 | 0 | 21000 | 3780 | 2024-07-16 | Against Material Supply | 70 | Challan No-18548 DT 04.07.2024 | 109155 | 2024-07-18 | 35770 | 2024-08-07 11:26 | -14770 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
4 Way 63mm,Fire Service inlet (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 7200 | 0 | 10080 | 1814.4 | 2024-07-16 | Against Material Supply | 70 | Challan No-18537 DT 03.07.2024 | 109155 | 2024-07-18 | 35770 | 2024-08-07 11:26 | -25690 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 7500 | 0 | 2250 | 405 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -14950 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 7500 | 0 | 11250 | 2025 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -5950 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Jockey Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 205000 | 0 | 287000 | 51660 | 2024-01-24 | Against Material Supply | 70 | Challan No- 17569 | 104856 | 2024-01-29 | 2212000 | 2024-02-08 11:56 | -1925000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Motor Driven Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 1375000 | 0 | 1925000 | 346500 | 2024-01-24 | Against Material Supply | 70 | Challan No- 17569 | 104856 | 2024-01-29 | 2212000 | 2024-02-08 11:56 | -287000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6700 | 0 | 4690 | 844.2 | 2024-07-16 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109155 | 2024-07-18 | 35770 | 2024-08-07 11:26 | -31080 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Switch (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 2350 | 0 | 16450 | 2961 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT03.07.24 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -400330 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 150mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 10000 | 0 | 21000 | 3780 | 2024-07-14 | Against Material Supply | 70 | Challan No-18548 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -395780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
C.I.Basket Strainer 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 29200 | 0 | 40880 | 7358.4 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -375900 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Strainer "Y" (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 5900 | 0 | 8260 | 1486.8 | 2024-07-10 | Against Material Supply | 70 | Challan No-18546 DT 04.07.24 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -408520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 6500 | 0 | 13650 | 2457 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -403130 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 25500 | 0 | 35700 | 6426 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -381080 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 7000 | 0 | 1750 | 315 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -15450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6500 | 0 | 1625 | 292.5 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -15575 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 6500 | 0 | 325 | 58.5 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105278 | 2024-02-12 | 17200 | 2024-02-27 10:43 | -16875 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 250mm dia-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 4400 | 0 | 30800 | 5544 | 2024-07-07 | Against Material Supply | 70 | Challan No-18542 DT-03.07.2024 Received - 12 mtrs. (2 Mtrs Balance) | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -385980 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Air Vessel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 27000 | 0 | 37800 | 6804 | 2024-07-07 | Against Material Supply | 70 | Challan No-18541 DT03.07.24 (2 balance =Received -4 Nos.) | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -378980 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Foot Valve 150 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 17500 | 0 | 12250 | 2205 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT04.07.24 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -404530 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 4 | 7500 | 0 | 21000 | 3780 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -395780 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
CI Strainer 150 mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 3 | 8900 | 0 | 18690 | 3364.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -398090 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 250mm dia-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 4400 | 0 | 6160 | 1108.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18542 DT 03.07.2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -410620 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 200mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 2 | 16500 | 0 | 23100 | 4158 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -393680 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 14 | 12000 | 0 | 117600 | 21168 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -299180 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 3200 | 0 | 13440 | 2419.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18541 DT 03.07.24 | 109134 | 2024-07-16 | 416780 | 2024-08-07 11:48 | -403340 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Diesel Engine Driven Pump (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 1717410 | 0 | 1202187 | 216393.66 | 2024-04-08 | Against Material Supply | 70 |  | 106672 | 2024-04-08 | 1202187 | 2024-04-10 17:55 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1.008 | 250 | 0 | 63 | 11.34 | 2024-02-12 | After Final Noc | 25 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1838 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 250 | 0 | 1050 | 189 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -851 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 250 | 0 | 175 | 31.5 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1726 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 6 | 250 | 0 | 375 | 67.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1526 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 250 | 0 | 175 | 31.5 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1726 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 80mm-(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 636 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1.008 | 250 | 0 | 63 | 11.34 | 2024-02-12 | After Final Noc | 25 | For F Building | 105277 | 2024-02-12 | 1901 | 2024-02-21 11:36 | -1838 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 539.47 | 100 | 0 | 53947 | 0 | 2023-09-13 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 101847 | 2023-09-15 | 53947 | 1900-01-01 | 0 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 653.72 | 290 | 0 | 189578.8 | 0 | 2023-10-20 15:06 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 |  | 102866 | 2023-10-20 | 201003.8 | 2023-11-01 14:27 | -11425 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 114.25 | 100 | 0 | 11425 | 0 | 2023-10-20 15:06 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 102866 | 2023-10-20 | 201003.8 | 2023-11-01 14:27 | -189578.8 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 115.913 | 290 | 0 | 33614.77 | 6050.66 | 2024-07-13 18:54 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 |  | 109094 | 2024-07-15 | 33614.77 | 2024-07-26 12:27 | 0 | ROHIT CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 219.7855 | 290 | 0 | 63737.795 | 0 | 2024-06-17 20:05 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 | Final Bill For Remaining 20% | 108503 | 2024-06-24 | 63737.8 | 2024-07-05 11:37 | -0.005 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 408.57 | 100 | 0 | 40857 | 0 | 2024-06-16 12:33 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -123486.75 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 817.15 | 145 | 0 | 118486.75 | 0 | 2024-06-16 12:27 | Labour charges for RCC Work for Superstructure due to increase in height more than 5 Meter. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -45857 | VIJAY MOHITE
Pile Breaking -DCW | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 10 | 500 | 0 | 5000 | 0 | 2024-06-16 12:27 | Labour charges for Pile Breaking Work for Transformer Room. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -159343.75 | VIJAY MOHITE
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-06-08 | JUN-2024 | 8.333 | Report No- 000515 DT 07/06/2024 | 108210 | 2024-06-10 | 735.97 | 2024-06-24 12:28 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-05-09 | MAY-2024 | 8.333 | Report No-000371 DT 08/05/2024 | 107491 | 2024-05-13 | 735.97 | 2024-06-15 11:45 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-07-10 | JUL-2024 | 8.333 | Report No-000680 DT 09.07.2024 | 109102 | 2024-07-15 | 735.97 | 2024-08-05 14:02 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 641 | 2023-03-25 | 40kva DG servicing kit | 12 | 736 | 0 | 735.9706 | 132.48 | 2024-04-11 | APR-2024 | 8.333 | Report No-000295 DT-08/04/2024 | 106968 | 2024-04-20 | 735.97 | 2024-05-07 12:49 | 0.00056 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-06-08 | JUN-2024 | 8.33 | Report No- 16098 DT04/06/2024 | 108214 | 2024-06-10 | 896.64 | 2024-06-24 12:31 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-04-11 | APR-2024 | 8.33 | Report No-000294 DT-08/04/2024 | 106773 | 2024-04-15 | 4396.59 | 2024-05-21 18:45 | -3499.9488 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-05-23 | MAY-2024 | 8.33 | Report No- 000372 DT08/05/2024 | 107791 | 2024-05-27 | 896.64 | 2024-06-15 11:45 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 642 | 2023-03-25 | 82.5 kva DG servicing kit | 12 | 897 | 0 | 896.6412 | 161.4 | 2024-07-10 | JUL-2024 | 8.33 | Report no-000682 DT 09.07.2024 | 109103 | 2024-07-15 | 896.64 | 2024-08-05 14:02 | 0.0012 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-06-08 | JUN-2024 | 8.33 | Report No-16097 DT 04/06/2024 | 108213 | 2024-06-10 | 919.63 | 2024-06-24 12:29 | 0.002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-07-10 | JUL-2024 | 8.33 | Report No-000679 DT 09.07.2024 | 109101 | 2024-07-15 | 919.63 | 2024-08-05 14:01 | 0.002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-05-09 | MAY-2024 | 8.33 | Report No-00373 DT 08/05/2024 | 107490 | 2024-05-13 | 919.63 | 2024-06-15 11:45 | 0.002 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 643 | 2023-03-25 | 125kva DG servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-04-11 | APR-2024 | 8.33 | Report No-000293 DT-08/04/2024 | 106970 | 2024-04-20 | 919.63 | 2024-05-07 12:49 | 0.002 | MEGAPOWER SOLUTION PVT LTD
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 420 | 154 | 0 | 64680 | 0 | 2023-09-11 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 101803 | 2023-09-11 | 90695 | 2023-10-23 12:37 | -26015 | LAXMI ELECTRICALS
Full round pipe | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 25 | 55 | 0 | 1375 | 0 | 2023-09-11 | Labour charges for Fixing of 8 inch Full Round pipe (2m- 1Pipe) | 100 |  | 101803 | 2023-09-11 | 90695 | 2023-10-23 12:37 | -89320 | LAXMI ELECTRICALS
Excavation & Filling. | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 140 | 176 | 0 | 24640 | 0 | 2023-09-11 | Labour charges for 3 feet Excavation and Filling work (Backside Old Cable removing work) | 100 |  | 101803 | 2023-09-11 | 90695 | 2023-10-23 12:37 | -66055 | LAXMI ELECTRICALS
Excavation & Filling. | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 6 | 176 | 0 | 1056 | 190.08 | 2024-07-03 15:07 | Labour charges for 3 feet Excavation and Filling work (Backside Old Cable removing work) | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -41991.73 | ADITI POWER CARE AND ENTERPRISES
95 sqmm Indoor Jointing Kit (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 0.361 | 6930 | 0 | 2501.73 | 450.32 | 2024-07-03 15:10 | Providing and Fixing of 95 sqmm indoor jointing kit (M+L). | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -40546 | ADITI POWER CARE AND ENTERPRISES
95 sqmm Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-03 15:02 | Labour charges for fixing of 95 sqmm Touchproof Jointing Kit. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -40297.73 | ADITI POWER CARE AND ENTERPRISES
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 190 | 154 | 0 | 29260 | 5266.8 | 2024-07-03 14:58 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -13787.73 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 4 | 1870 | 0 | 7480 | 1346.4 | 2024-07-03 15:02 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 108885 | 2024-07-08 | 43047.73 | 1900-01-01 | -35567.73 | ADITI POWER CARE AND ENTERPRISES
Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-07-29 17:10 | Labour charges for Fixing of 300 sqmm Touchproof jointing kit. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -97130 | ADITI POWER CARE AND ENTERPRISES
300 sqmm Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 115 | 154 | 0 | 17710 | 3187.8 | 2024-07-29 17:10 | Labour charges for 3C x 300 sqmm Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -82170 | ADITI POWER CARE AND ENTERPRISES
300sqmm x 3.5C Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 340 | 99 | 0 | 33660 | 6058.8 | 2024-07-29 17:10 | Labour Charges for 300 sqmm x 3.5C Cable Laying work. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -66220 | ADITI POWER CARE AND ENTERPRISES
LT Earthing Set (m+l) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 7 | 4400 | 0 | 30800 | 5544 | 2024-07-29 17:10 | Supply and Labour Charges for fixing of LT Earthing set including Funnel, GI Patti, Salt, Coal,etc | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -69080 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 8 | 1870 | 0 | 14960 | 2692.8 | 2024-07-29 17:10 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 109423 | 2024-07-29 | 99880 | 1900-01-01 | -84920 | ADITI POWER CARE AND ENTERPRISES
Gland Plate Hole Making (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 14 | 100 | 0 | 1400 | 252 | 2024-06-07 15:04 | Labour charges for Gland Plate Hole Making work. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -55823.46 | LAXMI ELECTRICALS ENTERPRISES
4 Way Feeder Pillar | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-06-07 15:04 | Labour charges for Fixing of 4 way Feeder pillar. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -54473.46 | LAXMI ELECTRICALS ENTERPRISES
95 sqmm Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 2 | 2750 | 0 | 5500 | 990 | 2024-06-07 15:04 | Labour charges for fixing of 95 sqmm Touchproof Jointing Kit. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -51723.46 | LAXMI ELECTRICALS ENTERPRISES
6 way Feeder Piller (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 2 | 3300 | 0 | 6600 | 1188 | 2024-06-07 15:04 | Labour charges for fixing of 6 Way Feeder piller. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -50623.46 | LAXMI ELECTRICALS ENTERPRISES
Touchproof Jointing Kit (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 1 | 2750 | 0 | 2750 | 495 | 2024-06-07 15:04 | Labour charges for Fixing of 300 sqmm Touchproof jointing kit. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -54473.46 | LAXMI ELECTRICALS ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 12 | 1870 | 0 | 22440 | 4039.2 | 2024-06-07 15:04 | Providing and fixing of 300 Sqmm x 3.5 C end termination. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -34783.46 | LAXMI ELECTRICALS ENTERPRISES
95 sqmm Indoor Jointing Kit (M+L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 0.722 | 6930 | 0 | 5003.46 | 900.62 | 2024-06-07 15:04 | Providing and Fixing of 95 sqmm indoor jointing kit (M+L). | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -52220 | LAXMI ELECTRICALS ENTERPRISES
3Cx95 sqmm Cable Laying | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 40 | 121 | 0 | 4840 | 871.2 | 2024-06-07 15:04 | Labour charges for Laying of 3C x 95 sqmm cable. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -52383.46 | LAXMI ELECTRICALS ENTERPRISES
300sqmm x 3.5C Cable Laying (L) | N/C | N/C | LAXMI ELECTRICALS ENTERPRISES | 645 | 2023-03-30 | Electrical Work Electrical Labour work for Transformer Room | 60 | 99 | 0 | 5940 | 1069.2 | 2024-06-07 15:04 | Labour Charges for 300 sqmm x 3.5C Cable Laying work. | 100 |  | 108085 | 2024-06-07 | 57223.46 | 2024-06-24 12:40 | -51283.46 | LAXMI ELECTRICALS ENTERPRISES
Earthing work(m+l)- BC | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 650 | 2023-04-06 | F Building Earthing Work(Temporary earthing work) 1 No. | 4 | 4800 | 0 | 19200 | 3456 | 2023-10-03 | Labour and Material Charges for Earthing work with excavation,Fixing and Supply of Salt,Coal,GI Pipe with Funnel,GI Plate,GI Wire etc material for Elevator. | 100 |  | 102214 | 2023-10-04 | 28800 | 2023-11-01 14:24 | -9600 | HARISH CHANDRA JADHAV ELECTRICALS
Earthing work(m+l)- BC | N/C | N/C | HARISH CHANDRA JADHAV ELECTRICALS | 650 | 2023-04-06 | F Building Earthing Work(Temporary earthing work) 1 No. | 2 | 4800 | 0 | 9600 | 1728 | 2023-10-03 | Labour and Material Charges for Earthing work of meter room including Excavation supply of Coal,Salt,GI Pipe with funnel,GI Plate,GI Wire etc. | 100 |  | 102214 | 2023-10-04 | 28800 | 2023-11-01 14:24 | -19200 | HARISH CHANDRA JADHAV ELECTRICALS
Bobcat Hiring Charges | N/C | N/C | GANESH MAHADU LONDHE | 652 | 2023-04-07 | STP-265 KLD Murum Backfilling Work - 1 No. | 28 | 850 | 0 | 23800 | 0 | 2023-05-16 | Bobcat Hiring charges for levelling work for Old STP 265 KLD Murrum Backfilling work. | 100 |  | 99675 | 2023-05-17 | 23800 | 2023-06-10 10:41 | 0 | GANESH MAHADU LONDHE
Spreading & Levelling Work | N/C | N/C | GANESH MAHADU LONDHE | 652 | 2023-04-07 | STP-265 KLD Murum Backfilling Work - 1 No. | 465 | 15 | 0 | 6975 | 0 | 2023-07-05 | Labour Charges for Spreading and Levelling work for Old STP 265 KLD. | 100 |  | 100532 | 2023-07-07 | 6975 | 2023-07-26 12:26 | 0 | SHIVAM ENTERPRISES
RCC Work - DCH | N/C | N/C | VIJAY MOHITE | 653 | 2023-04-08 | STP-265 KLD RCC Work (L) | 1 | 400000 | 0 | 400000 | 0 | 2023-10-07 17:07 | Labour Charges for PCC Work below raft Slab, Raft Box, RCC Pardi, Beam, Slab, Steel work and shuttering work included for 265 KLD STP of D & E-Bldg. | 100 |  | 102419 | 2023-10-07 | 400000 | 2023-10-11 19:10 | 0 | VIJAY MOHITE
Brickwork 9" - ULT | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | Transformer Room- Brickwork & Plaster Above Plinth Beam (L) | 290.22 | 21 | 0 | 6094.62 | 1097.04 | 2023-08-21 | Labour charges for 9 inch Fly ash Brickwork above Plinth Beam for transformer room outer peripheri. | 100 |  | 101364 | 2023-08-22 | 17341.62 | 2023-09-04 11:40 | -11247 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 318.45 | 20 | 0 | 6369 | 1146.42 | 2023-08-21 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 101364 | 2023-08-22 | 17341.62 | 2023-09-04 11:40 | -10972.62 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 243.9 | 20 | 0 | 4878 | 878.04 | 2023-08-21 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 101364 | 2023-08-22 | 17341.62 | 2023-09-04 11:40 | -12463.62 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 975.648 | 20 | 0 | 19512.96 | 3512.34 | 2023-07-31 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -32919.16 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - UTR | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 1273.808 | 20 | 0 | 25476.16 | 4585.7 | 2023-07-31 | Labour Charges for sand face plaster with proper joint preparation between RCC & Blockwork using chiken mesh etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -26955.96 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 158.5 | 20 | 0 | 3170 | 570.6 | 2023-07-31 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -49262.12 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 213.65 | 20 | 0 | 4273 | 769.14 | 2023-07-31 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100924 | 2023-07-31 | 52432.12 | 2023-08-09 13:02 | -48159.12 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster Rate Diff. - DCH | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 1273.808 | 5 | 0 | 6369.04 | 1146.42 | 2023-12-28 18:31 | Rate Differance Charges for Sand Face Plaster with proper joint preparation between RCC & Blockwork using Chiken mesh etc complete. | 100 |  | 104227 | 2024-01-01 | 7495.91 | 1900-01-01 | -1126.87 | JAI SEVALAL CONSTRUCTION
8" Blockwork Rate Diff. | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 635.944 | 1 | 0 | 635.944 | 114.46 | 2023-12-28 18:31 | Rate Differance Charges for 8 inch Block work. | 100 |  | 104227 | 2024-01-01 | 7495.91 | 1900-01-01 | -6859.966 | JAI SEVALAL CONSTRUCTION
8" Blockwork Rate Diff. | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 490.928 | 1 | 0 | 490.928 | 88.36 | 2023-12-28 18:31 | Rate Differance Charges for 8 inch Block work. | 100 |  | 104227 | 2024-01-01 | 7495.91 | 1900-01-01 | -7004.982 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg STP- 8" Blockwork & Plaster Work (L) | 400 | 20 | 0 | 8000 | 0 | 2023-07-04 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100462 | 2023-07-05 | 20718.88 | 2023-07-26 12:27 | -12718.88 | K RAMU RATHOD
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 635.944 | 20 | 0 | 12718.88 | 0 | 2023-07-04 | Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 100462 | 2023-07-05 | 20718.88 | 2023-07-26 12:27 | -8000 | K RAMU RATHOD
8" Blockwork Rate Diff. | N/C | N/C | K RAMU RATHOD | 676 | 2023-05-08 | F-Bldg ETP - 8" Blockwork & Plaster Work (L) | 158.5 | 1 | 0 | 158.5 | 28.54 | 2024-04-08 | Rate Differance Charges for 8 inch Block work. | 100 |  | 106706 | 2024-04-08 | 158.5 | 1900-01-01 | 0 | JAI SEVALAL CONSTRUCTION
Brickbat W/P-ULT | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | Transformer Room- Terrace Brickbat W/P Work | 522.3431 | 24 | 0 | 12536.2344 | 0 | 2024-05-05 12:15 | Labour charges for Terrace Brickbat Waterproofing work for Transformer Room. | 100 |  | 107393 | 2024-05-07 | 12536.23 | 2024-06-06 12:22 | 0.0044 | PRABHURAM VERMA
IPS W/P | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | Transformer Room- Floor IPS Waterproofing | 350.2 | 15 | 0 | 5253 | 945.54 | 2024-03-02 19:15 | Labour charges for IPS Waterproofing Work for Transformer Room. | 100 |  | 105729 | 2024-03-04 | 5253 | 2024-03-23 12:18 | 0 | JAI SEVALAL CONSTRUCTION
Int. Ghotai Plaster- UWR | N/C | N/C | AJAY KUMAR GUPTA | 684 | 2023-05-27 | Transformer Room- Trench Int. Face Ghotai Work | 499.76 | 15 | 0 | 7496.4 | 1349.36 | 2023-12-28 18:35 | Labour charges for Internal Ghotai Plaster work for Int. face- vertical, Both wall- Top & Horizontal for Transformer Room. | 100 |  | 104233 | 2024-01-01 | 7496.4 | 2024-02-05 11:29 | 0 | JAI SEVALAL CONSTRUCTION
Cable 2.5 sqmm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 39.9865 | 42.3 | 0 | 1184.0003 | 213.12 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83625.4997 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Building Fire Alarm System Work | 291.5 | 40 | 0 | 8162 | 1469.16 | 2023-08-21 | After Installation & Pressure Testing | 70 |  | 101362 | 2023-08-21 | 8162 | 2023-09-20 11:59 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 300 | 0 | 375 | 67.5 | 2024-02-12 | After Final Noc | 25 | For F Building | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -176805 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 300 | 0 | 1050 | 189 | 2024-02-12 | After Installation & Pressure Testing | 70 | For F Building | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -176130 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 100 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 84.4008 | 775.5 | 0.03 | 45816.9743 | 8247.06 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -131363.0257 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 40 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 9.1996 | 423 | 0 | 2724.0016 | 490.32 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -174455.9984 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 100 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 84.3997 | 775.5 | 0.01 | 16362.9918 | 2945.34 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -160817.0082 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Building Fire Alarm System Work | 86 | 40 | 0 | 2408 | 433.44 | 2023-12-04 | After Installation & Pressure Testing | 70 | Installed on 24/11/2023 | 103626 | 2023-12-04 | 2408 | 2024-01-02 11:45 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 50 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 22.999 | 564 | -0.01 | 9080.0052 | 1634.4 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -168099.9948 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 40 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 9.2009 | 423 | 0 | 972.9952 | 175.14 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -176207.0048 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Building Fire Alarm System Work | 566 | 40 | 0 | 15848 | 2852.64 | 2023-09-23 | After Installation & Pressure Testing | 70 |  | 102046 | 2023-09-23 | 15848 | 2023-10-11 11:03 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 32 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 55.4002 | 352.5 | 0 | 13669.9994 | 2460.6 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -163510.0007 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 50 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 23 | 564 | 0 | 3243 | 583.74 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -173937 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 32 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 55.3986 | 352.5 | 0 | 4882.0016 | 878.76 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -172297.9984 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 25 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 294.8936 | 282 | 0 | 20789.9988 | 3742.2 | 2024-02-12 | After Final Noc | 25 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -156390.0012 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Removing & Refixing GI Pipe 25 NB | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 294.8987 | 282 | 0 | 58213.0034 | 10478.34 | 2024-02-12 | After Installation & Pressure Testing | 70 |  | 105281 | 2024-02-12 | 177180 | 2024-02-21 11:36 | -118966.9966 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 188 | 0 | 28294 | 5092.92 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -56515.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 188 | 0 | 10105 | 1818.9 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -74704.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 300 | 0 | 210 | 37.8 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84599.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 300 | 0 | 75 | 13.5 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84734.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 200 | 0 | 18200 | 3276 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -66609.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3290 | 0 | 822.5 | 148.06 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83987 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 3.9991 | 329 | 0.01 | 920.9927 | 165.78 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83888.5073 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0159 | 45 | 0 | 6773.0009 | 1219.14 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -78036.4992 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0222 | 45 | 0 | 2418.9997 | 435.42 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -82390.5002 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3290 | 0 | 2303 | 414.54 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -82506.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 4 | 329 | 0 | 329 | 59.22 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84480.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 1410 | 0 | 987 | 177.66 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83822.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 1034 | 0 | 1292.5 | 232.66 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -83517 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 1410 | 0 | 352.5 | 63.46 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84457 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 42.3 | 0 | 423 | 76.14 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -84386.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 1034 | 0 | 3619 | 651.42 | 2024-02-08 | After Installation & Pressure Testing | 70 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -81190.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (L) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 687 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 200 | 0 | 6500 | 1170 | 2024-02-08 | After Final Noc | 25 |  | 105156 | 2024-02-08 | 84809.5 | 2024-02-09 18:36 | -78309.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Talk Back System (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 4 | 800 | 0 | 2240 | 403.2 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -29925 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable smoke detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 5 | 2400 | 0 | 8400 | 1512 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -23765 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Heat Detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2350 | 0 | 1645 | 296.1 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -30520 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fault Isolator Base / Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 3 | 2500 | 0 | 5250 | 945 | 2024-06-02 | Against Material Supply | 70 |  | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -26915 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Handheld Microphone (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2150 | 0 | 1505 | 270.9 | 2024-06-02 | Against Material Supply | 70 | CH NO-18290 DT 24/05/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -30660 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
6W Ceiling Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 15 | 1250 | 0 | 13125 | 2362.5 | 2024-06-02 | Against Material Supply | 70 | CH NO-18053 DT 16/04/2024 and CH NO-17969 DT 30/03/2024 | 107923 | 2024-06-03 | 32165 | 2024-06-15 16:16 | -19040 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Repeater Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 45000 | 0 | 31500 | 5670 | 2024-07-29 | Against Material Supply | 70 | Challan No-18179 DT 27/7/2024 | 109419 | 2024-07-29 | 40950 | 2024-08-08 11:26 | -9450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Upright (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 30 | 450 | 0 | 9450 | 1701 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/07/2024 Total Received-400 -We have released 338 Nos from D Building Remaining Qty released from F Building (Balance for amendment 32 Nos) | 109419 | 2024-07-29 | 40950 | 2024-08-08 11:26 | -31500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 80mm dia.(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 35 | 1000 | 0 | 24500 | 4410 | 2024-06-10 | Against Material Supply | 70 | DC-18352 DT-10/06/2024 | 108186 | 2024-06-10 | 39529 | 2024-06-26 11:43 | -15029 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher ABC 4Kg (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 6 | 1645 | 0 | 6909 | 1243.62 | 2024-06-10 | Against Material Supply | 70 | DC-18325 DT-31/05/2024 | 108186 | 2024-06-10 | 39529 | 2024-06-26 11:43 | -32620 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 2 | 5800 | 0 | 8120 | 1461.6 | 2024-06-10 | Against Material Supply | 70 | DC-18325 DT-31/05/2024 | 108186 | 2024-06-10 | 39529 | 2024-06-26 11:43 | -31409 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Digital Signal Based Voice Alarm Controller (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 51653 | 0 | 36157.1 | 6508.28 | 2024-05-13 | Against Material Supply | 70 | CHALLAN NO-18140 | 107563 | 2024-05-13 | 86559.9 | 2024-05-28 19:02 | -50402.8 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 90 | 0 | 2520 | 453.6 | 2024-04-08 | Against Material Supply | 70 |  | 106673 | 2024-04-08 | 42112 | 2024-04-10 17:55 | -39592 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 1034 | 0 | 28952 | 5211.36 | 2024-04-08 | Against Material Supply | 70 |  | 106673 | 2024-04-08 | 42112 | 2024-04-10 17:55 | -13160 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 380 | 0 | 10640 | 1915.2 | 2024-04-08 | Against Material Supply | 70 |  | 106673 | 2024-04-08 | 42112 | 2024-04-10 17:55 | -31472 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Talkback Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 66504 | 0 | 46552.8 | 8379.5 | 2024-05-13 | Against Material Supply | 70 | CHALLAN NO-18140 | 107563 | 2024-05-13 | 86559.9 | 2024-05-28 19:02 | -40007.1 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Telephone Jack/Receiver (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 5500 | 0 | 3850 | 693 | 2024-05-13 | Against Material Supply | 70 | CHALLAN NO-18140 | 107563 | 2024-05-13 | 86559.9 | 2024-05-28 19:02 | -82709.9 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Manual call point (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2850 | 0 | 1995 | 359.1 | 2023-12-04 | Against Material Supply | 70 |  | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -329210 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 100mm-(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 6 | 3600 | 0 | 15120 | 2721.6 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 4/07/2024 Against D Building Pump Room | 109135 | 2024-07-16 | 17360 | 2024-08-07 11:45 | -2240 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable smoke detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 100 | 2400 | 0 | 168000 | 30240 | 2023-12-04 | Against Material Supply | 70 | Challan No-17080 | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -163205 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Conventional Sounder cum Strobe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 5 | 1900 | 0 | 6650 | 1197 | 2023-12-04 | Against Material Supply | 70 | Challan No-17080 DT 23/11/2023 | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -324555 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 2650 | 0 | 9275 | 1669.5 | 2024-02-12 | Against Material Supply | 70 | For F Building | 105280 | 2024-02-12 | 13251 | 2024-03-18 12:02 | -3976 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Control Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 3300 | 0 | 2310 | 415.8 | 2023-12-04 | Against Material Supply | 70 |  | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -328895 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5.0008 | 2650 | -0.03 | 3313.03 | 596.34 | 2024-02-12 | After Installation & Pressure Testing | 25 | For F Building | 105280 | 2024-02-12 | 13251 | 2024-03-18 12:02 | -9937.97 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Fire Alarm Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 215000 | 0 | 150500 | 27090 | 2023-12-04 | Against Material Supply | 70 | Challan No-17080 DT 23/11/2023 | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -180705 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 40mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5.0038 | 2650 | 0 | 663.0035 | 119.34 | 2024-02-12 | Before Submission of Noc File | 5 | For F Building | 105280 | 2024-02-12 | 13251 | 2024-03-18 12:02 | -12587.9965 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Non Return Valve 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3200 | 0 | 2240 | 403.2 | 2024-07-15 | Against Material Supply | 70 | Challan No-18546 DT 04/07/2024 Against D Building | 109135 | 2024-07-16 | 17360 | 2024-08-07 11:45 | -15120 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fault Isolator Base / Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 2500 | 0 | 1750 | 315 | 2023-12-04 | Against Material Supply | 70 |  | 103787 | 2023-12-11 | 331205 | 2024-01-02 11:45 | -329455 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 43500 | 0 | 30450 | 5481 | 2024-07-01 | Against Material Supply | 70 | Challan No-18508 DT-27/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -42112 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 1034 | 0 | 28952 | 5211.36 | 2024-07-01 | Against Material Supply | 70 | challan No-18491 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -43610 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 380 | 0 | 10640 | 1915.2 | 2024-07-01 | Against Material Supply | 70 | Challan No-18491DT-25/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -61922 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 17930 | 0 | 62755 | 11295.9 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -404036 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 6241 | 0 | 4368.7 | 786.36 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -462422.3 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0222 | 90 | 0 | 4837.9995 | 870.84 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -461953.0005 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3800 | 0 | 950 | 171 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465841 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 1034 | 0 | 155617 | 28011.06 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -311174 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 122 | 0 | 3416 | 614.88 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -463375 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 122 | 0 | 1220 | 219.6 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465571 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215 | 90 | 0 | 13545 | 2438.1 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -453246 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0097 | 1034 | 0 | 11116.0015 | 2000.88 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -455674.9985 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 380 | 0 | 2470 | 444.6 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -464321 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 6241 | 0 | 312.05 | 56.16 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -466478.95 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 45590 | 0 | 31913 | 5744.34 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -434878 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 45590 | 0 | 11397.5 | 2051.56 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -455393.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 4.0001 | 6392 | -0.05 | 17898.0474 | 3221.64 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -448892.9526 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 17930 | 0 | 4482.5 | 806.86 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -462308.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 4 | 6392 | 0 | 6392 | 1150.56 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -460399 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
7.5 HP Booster Pump- (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 45590 | 0 | 2279.5 | 410.32 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -464511.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Electrical Starter (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 6241 | 0 | 1560.25 | 280.84 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465230.75 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.1111 | 90 | 0 | 968 | 174.24 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465823 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Flexible Hose Pipe 25mm Dia (1mtr length) (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 215.0019 | 1034 | 0.01 | 55577.9912 | 10004.04 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -411213.0088 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Cable 2.5 sqmm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 122 | 0 | 244 | 43.92 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -466547 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 380 | 0 | 12350 | 2223 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -454441 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
GI Single Fire Hose Box (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 5 | 17930 | 0 | 22412.5 | 4034.26 | 2024-02-08 | After Installation & Pressure Testing | 25 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -444378.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rossete Plate (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 40 | 90 | 0 | 2520 | 453.6 | 2024-07-01 | Against Material Supply | 70 | Challan No-18491 DT-25/06/2024 | 108663 | 2024-07-01 | 72562 | 2024-07-15 15:04 | -70042 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3800 | 0 | 190 | 34.2 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -466601 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 130 | 380 | 0 | 34580 | 6224.4 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -432211 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signage Fire Hose Reel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 3.9987 | 6392 | 0.02 | 1277.9845 | 230.04 | 2024-02-08 | Before Submission of Noc File | 5 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -465513.0155 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Butterfly Valve 150mm -(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 1 | 3800 | 0 | 2660 | 478.8 | 2024-02-08 | Against Material Supply | 70 |  | 105155 | 2024-02-08 | 466791 | 2024-02-09 18:35 | -464131 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1000 | 80 | 0 | 56000 | 10080 | 2023-09-16 | Against Material Supply | 70 | Challan No- 16617 | 101922 | 2023-09-18 | 56000 | 2023-10-11 11:03 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm cable for PA System (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 311 | 80 | 0 | 17416 | 3134.88 | 2023-08-21 | Against Material Supply | 70 |  | 101363 | 2023-08-21 | 17416 | 2023-09-20 11:59 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-External Single Coat-Sand Face Plaster Work | 483.26 | 20 | 0 | 9665.2 | 1739.74 | 2024-03-15 | Labour Charges for Sand Face single coat plaster work for External side of transformer room. | 100 | weigh bridge & south side balance plaster consider | 106938 | 2024-04-19 | 18867 | 2024-04-25 11:28 | -9201.8 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-Internal Single Coat-Sand Face Plaster Work | 460.09 | 20 | 0 | 9201.8 | 1656.32 | 2024-03-15 | Labour Charges for Sand Face Single plaster work for internal side of transformer room. | 100 | Parapet inner side & weigh bridge side | 106938 | 2024-04-19 | 18867 | 2024-04-25 11:28 | -9665.2 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-Internal Single Coat-Sand Face Plaster Work | 759.19 | 20 | 0 | 15183.8 | 2733.08 | 2023-12-28 18:29 | Labour Charges for Sand Face Single plaster work for internal side of transformer room. | 100 |  | 104225 | 2024-01-01 | 15183.8 | 2024-01-23 14:19 | 0 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-Internal Single Coat-Sand Face Plaster Work | 112.45 | 20 | 0 | 2249 | 404.82 | 2024-01-17 16:44 | Labour Charges for Sand Face Single plaster work for internal side of transformer room. | 100 |  | 104677 | 2024-01-22 | 9323 | 2024-02-05 11:35 | -7074 | JAI SEVALAL CONSTRUCTION
Sand Face Plaster - ULT | N/C | N/C | K RAMU RATHOD | 693 | 2023-06-07 | Transformer Room-External Single Coat-Sand Face Plaster Work | 353.7 | 20 | 0 | 7074 | 1273.32 | 2024-01-17 16:44 | Labour Charges for Sand Face single coat plaster work for External side of transformer room. | 100 |  | 104677 | 2024-01-22 | 9323 | 2024-02-05 11:35 | -2249 | JAI SEVALAL CONSTRUCTION
Brickwork 15" -DLd | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench 15" Thk Brickwork | 476 | 24 | 0 | 11424 | 2056.32 | 2023-12-02 19:01 | Labour Charges for 15 inch Brickwork for Transformer room Cable trench. | 100 |  | 103620 | 2023-12-04 | 11424 | 1900-01-01 | 0 | JAI SEVALAL CONSTRUCTION
Rough Plaster- ULT | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench Ext. Face Rough Plaster Work | 759.19 | 15 | 0 | 11387.85 | 2049.82 | 2024-03-19 | Labour Charges for Rough plaster work for Transformer room Cable trench. | 100 |  | 106269 | 2024-03-20 | 28164.72 | 1900-01-01 | -16776.87 | JAI SEVALAL CONSTRUCTION
Brickwork 15" -DLd | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench 15" Thk Brickwork | 204.83 | 24 | 0 | 4915.92 | 884.86 | 2024-03-20 | Labour Charges for 15 inch Brickwork for Transformer room Cable trench. | 100 |  | 106269 | 2024-03-20 | 28164.72 | 1900-01-01 | -23248.8 | JAI SEVALAL CONSTRUCTION
Rough Plaster- ULT | N/C | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room- Cable Trench Int. Face Rough Plaster Work | 790.73 | 15 | 0 | 11860.95 | 2134.98 | 2024-03-19 | Labour Charges for Rough plaster work for Transformer room Cable trench. | 100 |  | 106269 | 2024-03-20 | 28164.72 | 1900-01-01 | -16303.77 | JAI SEVALAL CONSTRUCTION
Blockwork 8" - BC | GLAZING SERVICES | N/C | K RAMU RATHOD | 694 | 2023-06-07 | Transformer Room G Fl. to 1st Slab & Parapet -8" Blockwork | 771.81 | 20 | 0 | 15436.2 | 2778.52 | 2024-01-17 16:46 | Labour Charges for 8 inch Blockwork for Transformer room main wall Ground to 1st Slab. | 100 |  | 104678 | 2024-01-22 | 15436.2 | 2024-02-05 11:36 | 0 | JAI SEVALAL CONSTRUCTION
Cement Ghotai-ULT | N/C | N/C | GANGAPRASAD K VARMA | 733 | 2023-07-21 | 265 KLD STP Bottom & Vertical Pardi- W/P Work | 1181 | 15 | 0 | 17715 | 0 | 2023-10-20 | Labour Charges for Cement Ghotai Plaster work for internal vertical RCC Pardi of 265 KLD STP. | 100 |  | 102914 | 2023-10-23 | 17715 | 2024-03-18 12:03 | 0 | PRABHURAM VERMA
Screeding work- BC | N/C | N/C | GANGAPRASAD K VARMA | 733 | 2023-07-21 | 265 KLD STP Bottom & Vertical Pardi- W/P Work | 290.5333 | 15 | 0 | 4357.9995 | 0 | 2024-03-12 | Labour Charges for Screeding work for 265 KLD STP bottom. | 100 |  | 106037 | 2024-03-12 | 32144 | 2024-03-18 12:06 | -27786.0005 | PRABHURAM VERMA
Chemical W/P-DLd | N/C | N/C | GANGAPRASAD K VARMA | 733 | 2023-07-21 | 265 KLD STP Bottom & Vertical Pardi- W/P Work | 290.5 | 22 | 0 | 6391 | 0 | 2024-03-12 | Labour and Material Charges for Chemical waterproofing work for 265 KLD STP Bottom | 100 |  | 106037 | 2024-03-12 | 32144 | 2024-03-18 12:06 | -25753 | PRABHURAM VERMA
Chemical W/P-DLd | N/C | N/C | GANGAPRASAD K VARMA | 733 | 2023-07-21 | 265 KLD STP Bottom & Vertical Pardi- W/P Work | 681.97 | 22 | 0 | 15003.34 | 0 | 2024-03-12 | Material supply & Labour charges for Chemical waterproofing work for vertical pardi area 265 KLD STP in TWT. | 100 |  | 106037 | 2024-03-12 | 32144 | 2024-03-18 12:06 | -17140.66 | PRABHURAM VERMA
Chemical W/P-DLd | N/C | N/C | GANGAPRASAD K VARMA | 733 | 2023-07-21 | 265 KLD STP Bottom & Vertical Pardi- W/P Work | 290.53 | 22 | 0 | 6391.66 | 0 | 2024-03-12 | Material and Labour charges for Chemical waterproofing work for Bottom area 265 KLD STP in TWT. | 100 |  | 106037 | 2024-03-12 | 32144 | 2024-03-18 12:06 | -25752.34 | PRABHURAM VERMA
Rainwater Harvesting System-UTR | N/C | N/C | S.V. ASSOCIATES | 737 | 2023-07-31 | Rain Water Harvesting System | 10466.6666 | 1.75 | 0 | 18316.6666 | 3297 | 2024-05-27 19:13 | Testing and certification of construction Material and structural Test certificate / NOC. (Supply & Installation of Sand Filter media at borwell chamber with depth min. 30m & max. 60m 6Nos. of pit required) | 100 |  | 107909 | 2024-06-03 | 18316.67 | 2024-06-15 11:51 | -0.00345 | S.V. ASSOCIATES
Rainwater Harvesting System-UTR | N/C | N/C | S.V. ASSOCIATES | 737 | 2023-07-31 | Rain Water Harvesting System | 13083.33 | 1.75 | 0 | 22895.8275 | 4121.24 | 2024-03-15 12:46 | Testing and certification of construction Material and structural Test certificate / NOC. (Supply & Installation of Sand Filter media at borwell chamber with depth min. 30m & max. 60m 6Nos. of pit required) | 100 | F bldg Rain water Harvesting Pit -01 No. workdone. | 106097 | 2024-03-18 | 22895.83 | 2024-03-30 19:09 | -0.0025 | S.V. ASSOCIATES
Chemical W/P-UWT- | N/C | N/C | PRABHURAM VERMA | 760 | 2023-08-25 | UGWT- D&E Internal waterproofing work | 4635.3 | 22 | 0 | 101976.6 | 0 | 2023-09-25 | Material and Labour Charges for Chemical Waterproofing work for Fire tank 1, Fire tank 2, Pump room,Domestic Water tank,Utility Water tank,Raw water tank of UGWT of D & E Building. | 100 |  | 102094 | 2023-09-26 | 101976.6 | 2023-11-01 14:25 | 0 | PRABHURAM VERMA
Cement Ghotai inside W/P-UWT- | N/C | N/C | PRABHURAM VERMA | 760 | 2023-08-25 | UGWT- D&E Internal waterproofing work | 12360.8 | 15 | 0 | 185412 | 0 | 2023-10-06 14:58 | Labour Charges for Cement Ghotai plaster work for Fire tank 1, Fire tank 2, Pump room,Domestic Water tank,Utility Water tank,Raw water tank of UGWT of D & E Building. | 100 |  | 102354 | 2023-10-06 | 185412 | 2023-11-01 14:25 | 0 | PRABHURAM VERMA
Chemical W/P-UWT- | N/C | N/C | PRABHURAM VERMA | 760 | 2023-08-25 | UGWT- D&E Internal waterproofing work | 7725.5 | 22 | 0 | 169961 | 0 | 2023-09-06 | Material and Labour Charges for Chemical Waterproofing work for Fire tank 1, Fire tank 2, Pump room,Domestic Water tank,Utility Water tank,Raw water tank of UGWT of D & E Building. | 100 |  | 101689 | 2023-09-07 | 169961 | 2023-09-20 11:59 | 0 | PRABHURAM VERMA
Chipping & Grinding Work - DER | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | STP-265 KLD Grinding Work near 265KLD STP | 3250.62 | 4.5 | 0 | 14627.79 | 0 | 2023-11-28 15:59 | Charges for Grinding, chipping, reinforcement bar cutting & Scaffolding fixing & Removing for slab, Columns, Beams & walls near 265 KLD STP in OWC area & external side of 265 KLD STP. | 100 |  | 103601 | 2023-12-04 | 14627.79 | 2023-12-11 14:12 | 0 | GUFRAN GULZAR SHAIKH
Chipping & Grinding Work - DER | N/C | N/C | GUFRAN GULZAR SHAIKH | 771 | 2023-09-11 | STP-265 KLD Grinding Work near 265KLD STP | 968.78 | 4.5 | 0 | 4359.51 | 0 | 2023-12-09 17:21 | Charges for Grinding, chipping, reinforcement bar cutting & Scaffolding fixing & Removing for slab, Columns, Beams & walls near 265 KLD STP in OWC area & external side of 265 KLD STP. | 100 |  | 103821 | 2023-12-11 | 4359.51 | 2024-01-23 14:19 | 0 | GUFRAN GULZAR SHAIKH
Sand Face Plaster - UTR | N/C | N/C | JAI SEVALAL CONSTRUCTION | 776 | 2023-09-16 | OWC Unit- Single Coat Sand Face Plaster Work (L) | 81.41 | 20 | 0 | 1628.2 | 293.08 | 2024-01-17 16:39 | Labour Charges For Single Coat Sand Face Plaster work for OWC | 100 |  | 104676 | 2024-01-22 | 1628.2 | 2024-02-05 11:35 | 0 | JAI SEVALAL CONSTRUCTION
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | 265KLD STP Rebaring Work | 56 | 200 | 0 | 11200 | 2016 | 2024-07-23 18:09 | Labour Charges for 10mm Dia. Bar Rebarring work with 200mm depth using Hilti RE-500 for 265 KLD STP. | 100 |  | 109388 | 2024-07-29 | 11200 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | 265KLD STP Rebaring Work | 493 | 200 | 0 | 98600 | 17748 | 2024-07-14 14:06 | Labour Charges for 10mm Dia. Bar Rebarring work with 200mm depth using Hilti RE-500 for 265 KLD STP. | 100 |  | 109097 | 2024-07-15 | 98600 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | RCC Work Rebaring-Tie Beam-Transformer Room | 28 | 230 | 0 | 6440 | 1159.2 | 2023-11-30 09:53 | Labour charges for 12mm Bar Rebarring work upto 200mm depth for tie beam in transformer room. | 100 |  | 103602 | 2023-12-04 | 41540 | 2023-12-16 17:30 | -35100 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia-UWT | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | RCC Work Rebaring-Tie Beam-Transformer Room | 45 | 180 | 0 | 8100 | 1458 | 2023-11-30 09:53 | Labour charges for 10mm Bar Rebarring work upto 200mm depth for tie beam in transformer room. | 100 |  | 103602 | 2023-12-04 | 41540 | 2023-12-16 17:30 | -33440 | AVCON TECHNICS PVT LTD
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 809 | 2023-11-17 | RCC Work Rebaring-Tie Beam-Transformer Room | 60 | 450 | 0 | 27000 | 4860 | 2023-11-30 09:53 | Labour charges for 16mm Bar Rebarring work upto 200mm depth for tie beam in transformer room. | 100 |  | 103602 | 2023-12-04 | 41540 | 2023-12-16 17:30 | -14540 | AVCON TECHNICS PVT LTD
Cutting Work-BRE | N/C | N/C | PATIL CONSTRUCTION | 829 | 2023-11-30 | STP-265 KLD Cutting of RCC Wall near 265KLD STP | 1 | 40000 | 0 | 40000 | 7200 | 2024-04-26 16:34 | Labour Charges for RCC Wall Cutting and Crushing work near 265 KLD STP. | 100 |  | 107135 | 2024-04-29 | 40000 | 2024-06-03 12:36 | 0 | PATIL CONSTRUCTION
M.S. Railing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 839 | 2023-12-08 | UGWT-Pump Room-MS Railing Work | 203.14 | 25 | 0 | 5078.5 | 0 | 2023-12-23 18:52 | Labour Charges fo M.S.Railing Work of UGWT Staircase, Pump Room& Openings around. | 100 |  | 104113 | 2023-12-25 | 5078.5 | 2024-01-16 15:04 | 0 | SURESH RANGNATH SHITOLE
Breaking & Removing Work -AIE | N/C | N/C | JAISAN | 840 | 2023-12-08 | STP-265KLD-Breaking of RCC Partition Wall at Top Slab | 0.18 | 85000 | 0 | 15300 | 0 | 2024-02-11 16:06 | Labour Charges for Breaking & Dismentling of partitions (RCC) at Top Slab. | 100 |  | 105254 | 2024-02-12 | 15300 | 2024-03-02 11:56 | 0 | JAISAN
Breaking & Removing Work -AIE | N/C | N/C | JAISAN | 840 | 2023-12-08 | STP-265KLD-Breaking of RCC Partition Wall at Top Slab | 0.82 | 85000 | 0 | 69700 | 0 | 2024-01-15 15:01 | Labour Charges for Breaking & Dismentling of partitions (RCC) at Top Slab. | 100 |  | 104615 | 2024-01-15 | 69700 | 2024-01-27 17:49 | 0 | JAISAN
Shuttering Work-Mkt | N/C | N/C | VIJAY MOHITE | 851 | 2023-12-12 | OWC Unit-Plum Concrete in 265KLD STP & OWC | 8.23 | 550 | 0 | 4526.5 | 0 | 2024-01-26 11:57 | Labour charges for Fixing of Shuttering for Plum Concreting work of Boundry wall in OWC Area. | 100 |  | 104861 | 2024-01-29 | 17531.5 | 2024-03-01 11:42 | -13005 | VIJAY MOHITE
Plum Concrete | N/C | N/C | VIJAY MOHITE | 851 | 2023-12-12 | OWC Unit-Plum Concrete in 265KLD STP & OWC | 35.94 | 300 | 0 | 10782 | 0 | 2024-01-26 11:57 | Labour charges for Plum Concreting work for near TWT in 265 KLD STP. | 100 |  | 104861 | 2024-01-29 | 17531.5 | 2024-03-01 11:42 | -6749.5 | VIJAY MOHITE
Plum Concrete | N/C | N/C | VIJAY MOHITE | 851 | 2023-12-12 | OWC Unit-Plum Concrete in 265KLD STP & OWC | 7.41 | 300 | 0 | 2223 | 0 | 2024-01-26 11:57 | Labour charges for Plum concreting work fo Boundry wall in OWC Area. | 100 |  | 104861 | 2024-01-29 | 17531.5 | 2024-03-01 11:42 | -15308.5 | VIJAY MOHITE
PCC Work | N/C | N/C | VIJAY MOHITE | 852 | 2023-12-12 | OWC Unit-PCC Work near 265KLD STP | 2123 | 8 | 0 | 16984 | 0 | 2024-01-26 12:03 | Labour Charges for PCC in OWC area. | 100 |  | 104863 | 2024-01-29 | 16984 | 2024-03-01 11:43 | 0 | VIJAY MOHITE
Labour Lumpsum | N/C | N/C | YOGESH SANTOSH GAIKWAD | 864 | 2023-12-15 | Excavation Work-PMC Pipeline Connection to UGWT F Bldg. | 1 | 21000 | 0 | 21000 | 0 | 2024-01-18 | Labour Charges for Excavation for Pipeline from Mundwa to Kharadi Bypass Road for Drinkng water Supply (Corporation line Supply) Road to F-Building UGWT. | 100 |  | 104679 | 2024-01-22 | 21000 | 2024-02-05 11:42 | 0 | YOGESH SANTOSH GAIKWAD
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 873 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 477.392 | 80 | 0 | 38191.36 | 6874.44 | 2024-04-07 14:26 | Labour charges for fixing including fabricating, fixtures, such as holdfast, welding, nails, screw etc. & erecting, with one coat of anti-corrosive paint and two coats of oil painting with approved colour with all wastage, leads, lifts. | 100 |  | 106663 | 2024-04-08 | 47331.36 | 2024-05-28 19:06 | -9140 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 873 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 3 | 1800 | 0 | 5400 | 972 | 2024-04-07 14:26 | Labour charges for Fixing of MS Rolling Shutter operating system (Gear Set) for Transformer Room Rolling Shutter work. | 100 |  | 106663 | 2024-04-08 | 47331.36 | 2024-05-28 19:06 | -41931.36 | BHAGYALAXMI ENTERPRISES
Fabrication work-Dld. | N/C | N/C | BHAGYALAXMI ENTERPRISES | 873 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 93.5 | 40 | 0 | 3740 | 673.2 | 2024-04-07 14:26 | Labour charges for Fixing of MS Pipe 3inch x 1.1/2inch 3 mm thick for Transformer Room Rolling shutter work. | 100 |  | 106663 | 2024-04-08 | 47331.36 | 2024-05-28 19:06 | -43591.36 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 873 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 1 | 1800 | 0 | 1800 | 324 | 2024-06-03 17:13 | Labour charges for Fixing of MS Rolling Shutter operating system (Gear Set) for Transformer Room Rolling Shutter work. | 100 |  | 108010 | 2024-06-03 | 11347.84 | 2024-06-27 18:27 | -9547.84 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 873 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 119.348 | 80 | 0 | 9547.84 | 1718.62 | 2024-06-03 17:18 | Labour charges for fixing including fabricating, fixtures, such as holdfast, welding, nails, screw etc. & erecting, with one coat of anti-corrosive paint and two coats of oil painting with approved colour with all wastage, leads, lifts. | 100 |  | 108010 | 2024-06-03 | 11347.84 | 2024-06-27 18:27 | -1800 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 874 | 2023-12-16 | STP-45KLD-Rolling Shutter Fab.Work | 49.64 | 70 | 0 | 3474.8 | 625.46 | 2024-01-27 17:22 | Labour Charges for Fixing of MS Rolling Shutter for STP-45 KLD | 100 |  | 104868 | 2024-01-29 | 3474.8 | 2024-03-30 12:24 | 0 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 874 | 2023-12-16 | ETP-15KLD-Rolling Shutter Fab.Work | 48.735 | 70 | 0 | 3411.45 | 614.06 | 2024-02-01 12:09 | Labour Charges for Fixing of MS Rolling Shutter for ETP-15 KLD | 100 |  | 105039 | 2024-02-05 | 3411.45 | 2024-03-30 12:26 | 0 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 875 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 596.74 | 180 | 0 | 107413.2 | 19334.38 | 2024-04-07 14:12 | Material supply charges of Providing Rolling Shutter including fabricating, fixtures, such as holdfast, welding, nails, screw etc. | 100 |  | 106662 | 2024-04-08 | 133095.7 | 2024-05-28 19:06 | -25682.5 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 875 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 4 | 4200 | 0 | 16800 | 3024 | 2024-04-07 14:12 | Material supply charges of MS Rolling Shutter Operating System (Gear Set) for Transformer Room. | 100 |  | 106662 | 2024-04-08 | 133095.7 | 2024-05-28 19:06 | -116295.7 | BHAGYALAXMI ENTERPRISES
Fabrication work (M)- Rft | N/C | N/C | BHAGYALAXMI ENTERPRISES | 875 | 2023-12-16 | Transformer Room-MS Rolling Shutter Work | 93.5 | 95 | 0 | 8882.5 | 1598.86 | 2024-04-07 14:12 | Material supply charges of MS Pipe 3inch x 1.1/2inch 3mm thick for Transformer Room Rolling shutter work. | 100 |  | 106662 | 2024-04-08 | 133095.7 | 2024-05-28 19:06 | -124213.2 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 876 | 2023-12-16 | ETP-15KLD-Rolling Shutter Fab.Work | 48.735 | 155 | 0 | 7553.925 | 1359.7 | 2024-02-01 12:09 | Material Supply Charges for Hand Operated MS Rolling Shutter(18 Guage CR Strip, MS Bracket, Round Pipe, Galvanised Part, MS Part, L Bottom, Side Guide, Ball Bearing) | 100 |  | 105040 | 2024-02-05 | 7553.93 | 2024-03-30 12:26 | -0.005 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 876 | 2023-12-16 | STP-45KLD-Rolling Shutter Fab.Work | 49.64 | 155 | 0 | 7694.2 | 1384.96 | 2024-01-27 17:22 | Material Supply Charges for Hand Operated MS Rolling Shutter(18 Guage CR Strip, MS Bracket, Round Pipe, Galvanised Part, MS Part, L Bottom, Side Guide, Ball Bearing) | 100 |  | 104869 | 2024-01-29 | 7694.2 | 2024-03-30 12:26 | 0 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 889 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 28.543 | 80 | 0 | 2283.44 | 411.02 | 2024-06-03 17:22 | Labour charges for Fixing including fabricating, fixtures, such as holdfast, welding, nails, screw etc. & erecting, with one coat of anti-corrosive paint and two coats of oil painting with approved colour with all wastage, leads, lifts. | 100 |  | 108011 | 2024-06-03 | 3375.44 | 2024-07-15 14:50 | -1092 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 889 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 0.4 | 1800 | 0 | 720 | 129.6 | 2024-06-03 17:22 | Labour charges for Fixing of MS Rolling Shutter operating system (Gear Set) for OWC. | 100 |  | 108011 | 2024-06-03 | 3375.44 | 2024-07-15 14:50 | -2655.44 | BHAGYALAXMI ENTERPRISES
Fabrication work-Dld. | N/C | N/C | BHAGYALAXMI ENTERPRISES | 889 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 9.3 | 40 | 0 | 372 | 66.96 | 2024-06-03 17:22 | Labour charges for Fixing of MS Pipe 3inch x 1.1/2inch 3mm thick for OWC Rolling Shutter Work. | 100 |  | 108011 | 2024-06-03 | 3375.44 | 2024-07-15 14:50 | -3003.44 | BHAGYALAXMI ENTERPRISES
Fabrication work-Dld. | N/C | N/C | BHAGYALAXMI ENTERPRISES | 889 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 37.2 | 40 | 0 | 1488 | 267.84 | 2024-03-15 14:50 | Labour charges for Fixing of MS Pipe 3inch x 1.1/2inch 3mm thick for OWC Rolling Shutter Work. | 100 |  | 107588 | 2024-05-14 | 13501.76 | 2024-05-28 19:06 | -12013.76 | BHAGYALAXMI ENTERPRISES
Gear Box (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 889 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 1.6 | 1800 | 0 | 2880 | 518.4 | 2024-03-15 14:50 | Labour charges for Fixing of MS Rolling Shutter operating system (Gear Set) for OWC. | 100 |  | 107588 | 2024-05-14 | 13501.76 | 2024-05-28 19:06 | -10621.76 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (L) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 889 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 114.172 | 80 | 0 | 9133.76 | 1644.08 | 2024-03-15 14:50 | Labour charges for Fixing including fabricating, fixtures, such as holdfast, welding, nails, screw etc. & erecting, with one coat of anti-corrosive paint and two coats of oil painting with approved colour with all wastage, leads, lifts. | 100 |  | 107588 | 2024-05-14 | 13501.76 | 2024-05-28 19:06 | -4368 | BHAGYALAXMI ENTERPRISES
Gear Box (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 890 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 2 | 4200 | 0 | 8400 | 1512 | 2024-03-15 14:51 | Material supply charges of MS Rolling Shutter operating system (Gear Set) | 100 |  | 107589 | 2024-05-14 | 38506.2 | 2024-05-28 19:07 | -30106.2 | BHAGYALAXMI ENTERPRISES
Fabrication work (M)- Rft | N/C | N/C | BHAGYALAXMI ENTERPRISES | 890 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 46.5 | 95 | 0 | 4417.5 | 795.16 | 2024-03-15 14:51 | Material supply charges of MS Pipe 3inch x 1.1/2 inch 3mm thick for OWC Rolling shutter work. | 100 |  | 107589 | 2024-05-14 | 38506.2 | 2024-05-28 19:07 | -34088.7 | BHAGYALAXMI ENTERPRISES
Rolling Shutter (M) | N/C | N/C | BHAGYALAXMI ENTERPRISES | 890 | 2023-12-20 | Altus-OWC-MS Rolling Shutter Work | 142.715 | 180 | 0 | 25688.7 | 4623.96 | 2024-03-15 14:51 | Material charges of Providing Rolling Shutter as per drawing including fabricating, fixtures, such as holdfast, welding, nails, screw etc. | 100 |  | 107589 | 2024-05-14 | 38506.2 | 2024-05-28 19:07 | -12817.5 | BHAGYALAXMI ENTERPRISES
1C x 1sqmm Wire (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 9600 | 33.25 | 0 | 223440 | 40219.2 | 2024-06-17 | Against Material Supply | 70 | Ch No-18413 DT-14-06-2024 | 108417 | 2024-06-17 | 223440 | 2024-08-07 11:17 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Zone Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 200 | 3600 | 0 | 504000 | 90720 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3628639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable smoke detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 857 | 2340 | 0 | 1403766 | 252677.88 | 2024-07-07 | Against Material Supply | 70 | Challan No-18534 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -2728873 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Heat Detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 207 | 2300 | 0 | 333270 | 59988.6 | 2024-07-07 | Against Material Supply | 70 | Challan No-18534 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3799369 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
6 zone Voice Alarm controller (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 165000 | 0 | 231000 | 41580 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3901639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Manual call point (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 34 | 5000 | 0 | 119000 | 21420 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4013639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
8 Zone FFT Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 1 | 68915 | 0 | 48240.5 | 8683.3 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4084398.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fault Isolator Base / Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 52 | 3100 | 0 | 112840 | 20311.2 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4019799 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Monitor Module (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 25 | 3135 | 0 | 54862.5 | 9875.26 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4077776.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC Fireman's Phone Jack (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 34 | 3300 | 0 | 78540 | 14137.2 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4054099 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
1C x 1sqmm Wire (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 400 | 33.25 | 0 | 9310 | 1675.8 | 2024-06-11 | Against Material Supply | 70 | DC-18068 DT-20/04/24 | 108309 | 2024-06-11 | 9310 | 2024-06-15 16:36 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Signal initiating devices (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 112 | 750 | 0 | 58800 | 10584 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4073839 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Wall Mounting Kit (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 3200 | 0 | 4480 | 806.4 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4128159 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Battery update & activation card (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 42000 | 0 | 58800 | 10584 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT-03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4073839 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Push to talk Microphone (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 2 | 16500 | 0 | 23100 | 4158 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4109539 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Addressable Combined sounder (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 34 | 4200 | 0 | 99960 | 17992.8 | 2024-07-10 | Against Material Supply | 70 | Challan No-18567 DT 08.07.24 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4032679 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Gas Leakage Detector (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 200 | 3600 | 0 | 504000 | 90720 | 2024-07-07 | Against Material Supply | 70 | Challan No-18534 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3628639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Power Supply unit (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 6 | 8500 | 0 | 35700 | 6426 | 2024-07-07 | Against Material Supply | 70 | Challan No-18535 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4096939 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Telephone Jack/Receiver (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 2 | 5200 | 0 | 7280 | 1310.4 | 2024-07-07 | Against Material Supply | 70 | Challan No-18536 DT 03.07.2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -4125359 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Surface Mounting Modularized Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 2 | 325000 | 0 | 455000 | 81900 | 2024-07-15 | Against Material Supply | 70 | Challan No-18534 DT 03/07/2024 | 109136 | 2024-07-16 | 4132639 | 1900-01-01 | -3677639 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm Armoured cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 1000 | 75 | 0 | 52500 | 9450 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024 | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -215250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 Core x 1.5 Sqmm FRLS Armd. cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 45 | 75 | 0 | 2362.5 | 425.26 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024. | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -265387.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Network Active Repeater (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 1 | 42500 | 0 | 29750 | 5355 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27/07/2024 | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -238000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 5000 | 45 | 0 | 157500 | 28350 | 2024-04-08 | Against Material Supply | 70 |  | 106715 | 2024-04-08 | 210000 | 2024-04-10 17:55 | -52500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm Armoured cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 1000 | 75 | 0 | 52500 | 9450 | 2024-04-08 | Against Material Supply | 70 | for F Building ( Due to unavailability of Qty we have raise completion from D Building | 106715 | 2024-04-08 | 210000 | 2024-04-10 17:55 | -157500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 Core x 1.5 Sqmm FRLS Armd. cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 955 | 75 | 0 | 50137.5 | 9024.76 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024. | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -217612.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
20 Watt Cabinet Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 76 | 2500 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27.07.2024 Total Received-78 Nos. 2 Balnace Relesed from E Building. | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -134750 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 600 | 45 | 0 | 18900 | 3402 | 2024-06-02 | Against Material Supply | 70 | CH NO-17563 DT 20/01/2024(100 Mtrs) and CH NO-17289 DT 15/12/2023 (500 Mtrs) | 108064 | 2024-06-05 | 18900 | 2024-06-15 16:35 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 5000 | 45 | 0 | 157500 | 28350 | 2024-06-10 | Against Material Supply | 70 | DC-18396 DT-10/06/2024 | 108233 | 2024-06-10 | 157500 | 2024-06-15 16:37 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
20 Watt Cabinet Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 916 | 2024-01-27 | E Bldg.-PA System | 2 | 2500 | 0 | 3500 | 630 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27.07.2024 Total Received-78 Nos. 2 Balnace Relesed from E Building.Amendment Needed. | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
1C x 1sqmm Wire (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 916 | 2024-01-27 | E Bldg.-FAS System | 2400 | 33.25 | 0 | 55860 | 10054.8 | 2024-07-15 | Against Material Supply | 70 | Challan No-18558 DT 06.07.2024 Against D building due to unavailabitity of qty in D building. | 109284 | 2024-07-23 | 55860 | 2024-08-08 11:18 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 916 | 2024-01-27 | E Bldg.-FAS System | 5000 | 45 | 0 | 157500 | 28350 | 2024-06-26 | Against Material Supply | 70 | Challan No-18490 DT-25.06.2024 | 108759 | 2024-07-02 | 157500 | 2024-07-15 11:04 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-07-10 | Transportation Charges for material delivery charges for 82.5 kva DG Set Servicing work. | 100 | Challan No- 012913 DT 09.07.2024 | 109128 | 2024-07-15 | 9798 | 2024-08-05 14:02 | -9062 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 9062 | 0 | 9062 | 1631.16 | 2024-07-10 | Material supply charges for B-Check Surveying kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water-01 Ltr , Oil Filter-01 Nos, Fuel Filter-02 Nos) for 82.5 kva DG Set Servicing work. | 100 | Report No-000681 DT 09.07.2024 | 109128 | 2024-07-15 | 9798 | 2024-08-05 14:02 | -736 | MEGAPOWER SOLUTION PVT LTD
Air Filter element | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 2971.6 | 0 | 2971.6 | 534.88 | 2024-05-09 | Material Supply charges for Air Filter Element for 82.5 kva for DG set Servicing work. | 100 | Report No-000372 DT 08/05/2024 | 107715 | 2024-05-20 | 12033.6 | 2024-06-24 12:29 | -9062 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 9062 | 0 | 9062 | 1631.16 | 2024-05-09 | Material supply charges for B-Check Surveying kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water-01 Ltr , Oil Filter-01 Nos, Fuel Filter-02 Nos) for 82.5 kva DG Set Servicing work. | 100 | Report No-000372 | 107715 | 2024-05-20 | 12033.6 | 2024-06-24 12:29 | -2971.6 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 9062 | 0 | 9062 | 1631.16 | 2024-04-15 | Material supply charges for B-Check Surveying kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water-01 Ltr , Oil Filter-01 Nos, Fuel Filter-02 Nos) for 82.5 kva DG Set Servicing work. | 100 | Challan No-11234 DT 08/04/2024 | 107433 | 2024-05-08 | 9062 | 2024-06-24 12:13 | 0 | MEGAPOWER SOLUTION PVT LTD
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-06-08 | Transportation Charges for material delivery charges for 82.5 kva DG Set Servicing work. | 100 | Report No- 000514 DT07/06/2024 | 108286 | 2024-06-11 | 11270 | 2024-06-24 12:29 | -10534 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 9062 | 0 | 9062 | 1631.16 | 2024-06-08 | Material supply charges for B-Check Surveying kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water-01 Ltr , Oil Filter-01 Nos, Fuel Filter-02 Nos) for 82.5 kva DG Set Servicing work. | 100 | Report No-000514 DT07/06/2024 | 108286 | 2024-06-11 | 11270 | 2024-06-24 12:29 | -2208 | MEGAPOWER SOLUTION PVT LTD
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-05-29 | Transportation Charges for material delivery charges for 82.5 kva DG Set Servicing work. | 100 |  | 108286 | 2024-06-11 | 11270 | 2024-06-24 12:29 | -10534 | MEGAPOWER SOLUTION PVT LTD
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 932 | 2024-02-03 | 82.5 kva DG servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-05-29 | Transportation Charges for material delivery charges for 82.5 kva DG Set Servicing work. | 100 |  | 108286 | 2024-06-11 | 11270 | 2024-06-24 12:29 | -10534 | MEGAPOWER SOLUTION PVT LTD
Air Filter element | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 933 | 2024-02-03 | 125kva DG servicing kit | 1 | 4404.04 | 0 | 4404.04 | 792.72 | 2024-06-08 | Material Supply Charges for Air Filter Element 125kva DG Set Servicing work | 100 | Challan No-012951 DT 07/06/2024 | 108287 | 2024-06-11 | 16272.04 | 2024-06-24 12:31 | -11868 | MEGAPOWER SOLUTION PVT LTD
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 933 | 2024-02-03 | 125kva DG servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-06-08 | Transportation Charges for Material delivery charges for 125kva DG Set Servicing work. | 100 | Report No- 000513 DT07/06/2024 | 108287 | 2024-06-11 | 16272.04 | 2024-06-24 12:31 | -15536.04 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 933 | 2024-02-03 | 125kva DG servicing kit | 1 | 11132 | 0 | 11132 | 2003.76 | 2024-06-08 | Material Supply Charges for B-Check servicing kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water-01 Ltr, Oil Filter-01 Nos) for 125kva DG Set Servicing work. | 100 | Report No-000513 DT 07/06/2024 | 108287 | 2024-06-11 | 16272.04 | 2024-06-24 12:31 | -5140.04 | MEGAPOWER SOLUTION PVT LTD
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 935 | 2024-02-08 | ETP-15KLD-External Painting Work | 798.112 | 7.5 | 0 | 5985.84 | 1077.46 | 2024-04-28 15:52 | Labour Charges for applying Texture paint including proper cleaning, all tools & equipments , loading, unloading , shifting of material all in contractors scope. | 100 |  | 107147 | 2024-04-29 | 5985.84 | 1900-01-01 | 0 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 935 | 2024-02-08 | ETP-15KLD-External Painting Work | 199.528 | 7.5 | 0 | 1496.46 | 269.36 | 2024-05-27 18:01 | Labour Charges for applying Texture paint including proper cleaning, all tools & equipments , loading, unloading , shifting of material all in contractors scope. | 100 | STP area | 107859 | 2024-05-27 | 6454.26 | 2024-06-15 17:55 | -4957.8 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 935 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 7.5 | 0 | 4957.8 | 892.4 | 2024-05-27 17:40 | Labour Charges for applying Texture paint including proper cleaning, all tools & equipments , loading, unloading , shifting of material all in contractors scope. | 100 |  | 107859 | 2024-05-27 | 6454.26 | 2024-06-15 17:55 | -1496.46 | VEER BHADRA ENTERPRISES
Final Cleaning & Housekeeping work (L) | N/C | N/C | RAHUL PATIL | 935 | 2024-02-08 | ETP-15KLD-External Painting Work | 990.64 | 0.5 | 0 | 495.32 | 89.16 | 2024-06-06 | Labour charges for Final Cleaning & Housekeeping work after External painting work | 100 |  | 108066 | 2024-06-06 | 8289.9 | 1900-01-01 | -7794.58 | VEER BHADRA ENTERPRISES
Schedule- BC | No category | N/C | RAHUL PATIL | 935 | 2024-02-08 | ETP-15KLD-External Painting Work | 997.64 | 1 | 0 | 997.64 | 179.58 | 2024-06-06 | Charges for Schedule for External Painting for ETP-15KLD. | 100 |  | 108066 | 2024-06-06 | 8289.9 | 1900-01-01 | -7292.26 | VEER BHADRA ENTERPRISES
Final Cleaning & Housekeeping work (L) | N/C | N/C | RAHUL PATIL | 935 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 0.5 | 0 | 330.52 | 59.5 | 2024-06-06 | Labour charges for Final Cleaning & Housekeeping work after External painting work | 100 |  | 108066 | 2024-06-06 | 8289.9 | 1900-01-01 | -7959.38 | VEER BHADRA ENTERPRISES
Scaffolding work | No category | N/C | RAHUL PATIL | 935 | 2024-02-08 | ETP-15KLD-External Painting Work | 997.64 | 3.5 | 0 | 3491.74 | 628.52 | 2024-06-06 | Labour charges for fixing & removing of Scaffolding for ETP-15KLD painting work | 100 |  | 108066 | 2024-06-06 | 8289.9 | 1900-01-01 | -4798.16 | VEER BHADRA ENTERPRISES
Scaffolding work | No category | N/C | RAHUL PATIL | 935 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 3.5 | 0 | 2313.64 | 416.46 | 2024-06-06 | Labour charges for fixing & removing of Scaffolding for STP-45KLD painting work | 100 |  | 108066 | 2024-06-06 | 8289.9 | 1900-01-01 | -5976.26 | VEER BHADRA ENTERPRISES
Schedule- BC | GLAZING SERVICES | N/C | RAHUL PATIL | 935 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 1 | 0 | 661.04 | 118.98 | 2024-06-06 | Charges for Schedule for External Painting for STP-45KLD. | 100 |  | 108066 | 2024-06-06 | 8289.9 | 1900-01-01 | -7628.86 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 8 | 0 | 5288.32 | 951.9 | 2024-06-03 | Material Supply charges for Applying Texture Paint for STP-45KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -17518.53 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | ETP-15KLD-External Painting Work | 997.64 | 1 | 0 | 997.64 | 179.58 | 2024-06-03 | Material Supply charges for Applying 1st coat Water Base Primer for ETP-15KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -21809.21 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 2.5 | 0 | 1652.6 | 297.46 | 2024-06-03 | Material Supply charges for Applying 2nd coat Acrylic Paint for STP-45KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -21154.25 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | ETP-15KLD-External Painting Work | 997.64 | 2.25 | 0 | 2244.69 | 404.04 | 2024-06-03 | Material Supply charges for Applying 1st coat Acrylic Paint for ETP-15KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -20562.16 | VEER BHADRA ENTERPRISES
2nd Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | ETP-15KLD-External Painting Work | 997.64 | 2.5 | 0 | 2494.1 | 448.94 | 2024-06-03 | Material Supply charges for Applying 2nd coat Acrylic Paint for ETP-15KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -20312.75 | VEER BHADRA ENTERPRISES
1st Coat Acrylic Paint (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 2.25 | 0 | 1487.34 | 267.72 | 2024-06-03 | Material Supply charges for Applying 1st coat Acrylic Paint for STP-45KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -21319.51 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | ETP-15KLD-External Painting Work | 997.64 | 8 | 0 | 7981.12 | 1436.6 | 2024-06-03 | Material Supply charges for Applying Texture Paint for ETP-15KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -14825.73 | VEER BHADRA ENTERPRISES
1 Coat Primer (Water Base) (M) | N/C | N/C | RAHUL PATIL | 936 | 2024-02-08 | STP-45KLD-External Painting Work | 661.04 | 1 | 0 | 661.04 | 118.98 | 2024-06-03 | Material Supply charges for Applying 1st coat Water Base Primer for STP-45KLD | 100 |  | 107947 | 2024-06-03 | 22806.85 | 2024-06-15 17:58 | -22145.81 | VEER BHADRA ENTERPRISES
Chamber 24" x 36" (4ft Ht) - UTI | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 2 | 2600 | 0 | 5200 | 936 | 2024-05-17 11:17 | Labour charges for construction of Chamber for strom water line size- 2ft x 3ft upto 4ft Depth for D & E-Bldg External Services. | 100 |  | 107688 | 2024-05-20 | 7400 | 2024-07-05 11:52 | -2200 | SAI PLUMBING WORKS
Chamber 36" x 18" (4ft Ht) - UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 1 | 2200 | 0 | 2200 | 396 | 2024-05-17 11:30 | Labour charges for construction of Chamber for strom water line size- 1.5ft x 3ft upto 4ft Depth for D & E-Bldg External Services. | 100 |  | 107688 | 2024-05-20 | 7400 | 2024-07-05 11:52 | -5200 | SAI PLUMBING WORKS
Chamber Making -USL | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Blockwork & Plaster Work for Rainwater Harvesting Chamber | 2 | 10000 | 0 | 20000 | 3600 | 2024-07-12 19:19 | Charges for Construction of (7ft 6inch x 5ft x 6 inch x 6ft) Rainwater Harvesting Chamber including PCC, Ghotai, Brickwork9", Internal Ghotai Plaster, Outer Chat Plaster, Chamber cover fixing, etc . | 100 |  | 109121 | 2024-07-15 | 20000 | 2024-08-05 13:58 | 0 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | STP Overflow line-265KLD to Nala Line-(L) | 121.6806 | 28 | 0 | 3407.0568 | 613.28 | 2024-07-28 18:47 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for STP Overflow line (From 265 KLD to Nala) | 100 |  | 109410 | 2024-07-29 | 12541.76 | 1900-01-01 | -9134.7032 | SAI PLUMBING WORKS
12" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 304.49 | 30 | 0 | 9134.7 | 1644.24 | 2024-07-29 10:14 | Labour Charges for 12 inch RCC Hume pipe fixing and laying work for storm water line work. | 100 |  | 109410 | 2024-07-29 | 12541.76 | 1900-01-01 | -3407.06 | SAI PLUMBING WORKS
12" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 122.51 | 30 | 0 | 3675.3 | 661.56 | 2024-04-07 16:33 | Labour Charges for 12 inch RCC Hume pipe fixing and laying work for storm water line work. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -47785.43 | SAI PLUMBING WORKS
Round Chamber- UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 4 | 4000 | 0 | 16000 | 2880 | 2024-04-07 16:33 | Labour charges for construction of Round Chamber for Storm Water line upto 1 Mtr depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -35460.73 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UST - | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Drainage Line.-Side of F Bldg.-As per Site Condition | 76.916 | 28 | 0 | 2153.648 | 387.66 | 2024-04-07 16:33 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for Drainage line work. | 100 | D bldg Side Drainage line Qty Released as W.O. is not available | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -49307.082 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Storm Line-D Bldg shop Start to F Bldg Shop Start (Periphery | 132 | 28 | 0 | 3696 | 665.28 | 2024-04-07 16:33 | Labour Charges for 10 inch RCC Hume pipe fixing and Laying work for Storm water line work. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -47764.73 | SAI PLUMBING WORKS
Chamber 24" x 24" (4ft Ht) - USL | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Storm water line (L) | 2 | 2100 | 0 | 4200 | 756 | 2024-04-07 16:33 | Labour charges for construction of Chamber for strom water line size- 2ft x 2ft upto 4ft Depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -47260.73 | SAI PLUMBING WORKS
10" RCC Hume Pipe laying & fixing -UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | STP Overflow line-265KLD to Nala Line-(L) | 61.992 | 28 | 0 | 1735.776 | 312.44 | 2024-04-07 16:33 | Charges for 10 inch RCC NP2 Hume Pipe laying & Fixing work for STP Overflow line (From 265 KLD to Nala) | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -49724.954 | SAI PLUMBING WORKS
Round Chamber- UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Overflow Line (From 265KLD to Na | 2 | 4000 | 0 | 8000 | 1440 | 2024-04-07 16:33 | Labour charges for construction of Round Chamber for overflow line (from 265 KLD to Nala) upto 1 Mtr Depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -43460.73 | SAI PLUMBING WORKS
Round Chamber- UDR | N/C | N/C | SAI PLUMBING WORKS | 938 | 2024-02-17 | Construction of Chamber for Drainage Line (L) | 3 | 4000 | 0 | 12000 | 2160 | 2024-04-07 16:33 | Labour charges for construction of Round Chamber upto 1 Mtr Depth for D & E-Bldg External Services. | 100 |  | 106665 | 2024-04-08 | 51460.73 | 2024-05-06 12:28 | -39460.73 | SAI PLUMBING WORKS
Al. Arm. Cable laying 3.5C 300sqmm-UTI | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 60 | 99 | 0 | 5940 | 1069.2 | 2024-07-29 17:19 | Charges for Laying of 300 Sqmm 3.5 Core Alu. Armoud cable to D, E, F Building | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -86660 | ADITI POWER CARE AND ENTERPRISES
Al. Arm. Cable laying 3.5C 300sqmm-UTI | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 100 | 99 | 0 | 9900 | 1782 | 2024-07-29 17:03 | Charges for Laying of 300 Sqmm 3.5 Core Alu. Armoud cable to D, E, F Building | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -82700 | ADITI POWER CARE AND ENTERPRISES
Meter Panel (L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 14 | 3000 | 0 | 42000 | 7560 | 2024-07-29 17:03 | Charges for Meter Panel fixing (24 Nos of Meter in 1 Pannel)fr D, E & F Bldg. | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -50600 | ADITI POWER CARE AND ENTERPRISES
End Termination 300sqmm X 3.5 core cable (M+L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 8 | 1870 | 0 | 14960 | 2692.8 | 2024-07-29 17:03 | Charges for providing & making of End Termination of 300 Sqmm 3.5 Core Alu. Armoud Cable | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -77640 | ADITI POWER CARE AND ENTERPRISES
End Termination 120sqmm X 3.5 core cable (M+L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 20 | 990 | 0 | 19800 | 3564 | 2024-07-29 17:24 | Charges for providing & making of End Termination of 120 Sqmm 3.5 Core Alu. Armoud Cable | 100 |  | 109420 | 2024-07-29 | 92600 | 1900-01-01 | -72800 | ADITI POWER CARE AND ENTERPRISES
Al. Arm. Cable laying 3.5C 120sqmm-UTI | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 394 | 71.5 | 0 | 28171 | 5070.78 | 2024-06-07 14:23 | Charges for Laying of 120 Sqmm 3.5 Core Alu. Armoud cable to D, E, F Building | 100 |  | 108084 | 2024-06-07 | 214192 | 2024-06-15 11:53 | -186021 | ADITI POWER CARE AND ENTERPRISES
Al. Arm. Cable laying 3.5C 300sqmm-UTI | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 958 | 2024-04-02 | HT & LT Cable Laying with pannel termination | 1879 | 99 | 0 | 186021 | 33483.78 | 2024-06-07 14:09 | Charges for Laying of 300 Sqmm 3.5 Core Alu. Armoud cable to D, E, F Building | 100 |  | 108084 | 2024-06-07 | 214192 | 2024-06-15 11:53 | -28171 | ADITI POWER CARE AND ENTERPRISES
Horizontal Core Cutting 100mm | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | Core Cutting Work-Pump Room-D&E & Ret.Wall | 1 | 265 | 0 | 265 | 47.7 | 2024-06-11 16:12 | Labour Charges for 4 inch Horizontal core cutting work for Services in pump room & Retaining wall. | 100 |  | 108362 | 2024-06-17 | 265 | 1900-01-01 | 0 | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL)
Horizontal Core Cutting 125mm | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | Core Cutting Work-Pump Room-D&E & Ret.Wall | 2 | 265 | 0 | 530 | 0 | 2024-05-14 12:09 | Labour Charges for 5 inch Horizontal core cutting work for Services in pump room & Retaining wall. | 100 |  | 107646 | 2024-05-20 | 3975 | 2024-07-05 11:34 | -3445 | AJAY KUMAR GUPTA
Horizontal Core Cutting 75mm | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | Core Cutting Work-Pump Room-D&E & Ret.Wall | 2 | 265 | 0 | 530 | 0 | 2024-05-14 12:09 | Labour Charges for 5 inch Horizontal core cutting work for Services in pump room & Retaining wall. | 100 |  | 107646 | 2024-05-20 | 3975 | 2024-07-05 11:34 | -3445 | AJAY KUMAR GUPTA
Horizontal Core Cutting 100mm | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | Core Cutting Work-Pump Room-D&E & Ret.Wall | 1 | 265 | 0 | 265 | 0 | 2024-05-14 12:26 | Labour Charges for 4 inch Horizontal core cutting work for Services in pump room & Retaining wall. | 100 |  | 107646 | 2024-05-20 | 3975 | 2024-07-05 11:34 | -3710 | AJAY KUMAR GUPTA
Horizontal Core Cutting 150mm | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | Core Cutting Work-Pump Room-D&E & Ret.Wall | 6 | 265 | 0 | 1590 | 0 | 2024-05-14 12:09 | Labour Charges for 6 inch Horizontal core cutting work for Services in pump room & Retaining wall. | 100 |  | 107646 | 2024-05-20 | 3975 | 2024-07-05 11:34 | -2385 | AJAY KUMAR GUPTA
Horizontal Core Cutting 125mm | N/C | N/C | PATIL CONSTRUCTION (PROP. SWATI GAJENDRA PATIL) | 968 | 2024-04-24 | Core Cutting Work-Pump Room-D&E & Ret.Wall | 4 | 265 | 0 | 1060 | 0 | 2024-05-14 12:09 | Labour Charges for 5 inch Horizontal core cutting work for Services in pump room & Retaining wall. | 100 |  | 107646 | 2024-05-20 | 3975 | 2024-07-05 11:34 | -2915 | AJAY KUMAR GUPTA
Supply of Ball Valve 20mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 54 | 440 | 0 | 16632 | 2993.76 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -754097.4 | SARV ENTERPRISES
Composite Pipe (Size-1216) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 290 | 248 | 0 | 50344 | 9061.92 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -720385.4 | SARV ENTERPRISES
Supply of MS Fabricated Support (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 179.9 | 80 | 0 | 10074.4 | 1813.4 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -760655 | SARV ENTERPRISES
Supply of Pressure reducing valve (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 20 | 5400 | 0 | 75600 | 13608 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -695129.4 | SARV ENTERPRISES
Composite Pipe (Size-2532) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 420 | 460 | 0 | 135240 | 24343.2 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -635489.4 | SARV ENTERPRISES
Supply of Air Vent 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 4 | 950 | 0 | 2660 | 478.8 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -768069.4 | SARV ENTERPRISES
Supply of Spring NRV 25mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 4 | 2400 | 0 | 6720 | 1209.6 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -764009.4 | SARV ENTERPRISES
Supply of Ball Valve 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 150 | 353 | 0 | 37065 | 6671.7 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -733664.4 | SARV ENTERPRISES
Supply of Pressure Relief Valve 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 4 | 3800 | 0 | 10640 | 1915.2 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -760089.4 | SARV ENTERPRISES
Supply of GI Air Pipe 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 70 | 2000 | 0 | 98000 | 17640 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -672729.4 | SARV ENTERPRISES
Composite Pipe (Size-1620) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 110 | 295 | 0 | 22715 | 4088.7 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -748014.4 | SARV ENTERPRISES
Supply of NRV 15mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 140 | 1660 | 0 | 162680 | 29282.4 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -608049.4 | SARV ENTERPRISES
Supply of NRV 32mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 10 | 3060 | 0 | 21420 | 3855.6 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -749309.4 | SARV ENTERPRISES
Composite Pipe (Size-2025) (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 370 | 361 | 0 | 93499 | 16829.82 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -677230.4 | SARV ENTERPRISES
Supply of Ball Valve 32mm (M) | N/C | N/C | SARV ENTERPRISES | 992 | 2024-05-25 | D-Solar Water Heating System | 20 | 1960 | 0 | 27440 | 4939.2 | 2024-07-11 16:06 | Against Material Delivery | 70 |  | 109106 | 2024-07-15 | 770729.4 | 1900-01-01 | -743289.4 | SARV ENTERPRISES