## Work_Completion_Browse638587246
Work Completion Browse
Project : GANGA ALTUS
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 231 Records 1 to 231
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Brickwork Pillar | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1049 | 2024-07-09 | Front Side Compound Wall Brickwork | 12 | 60 | 0 | 720 | 129.6 | 2024-07-14 14:19 | Charges for Construction of 15" thick Brick Pillar for front Side Compound wall | 100 |  | 109099 | 2024-07-15 | 5266.09 | 1900-01-01 | -4546.09 | SHUBHAM SURENDRA BAHADUR SINGH
Brickwork 9" DCW | N/C | N/C | SHUBHAM SURENDRA BAHADUR SINGH | 1049 | 2024-07-09 | Front Side Compound Wall Brickwork | 189.4203 | 24 | 0 | 4546.0872 | 818.3 | 2024-07-14 14:12 | Construction of 9" Brick Work with in-situ 1:6 Cement mortar with Fly ash Brick, Cement, Sand & water etc. with Plumb & Right angle at corner, with proper joint filling & striking joints on unexposed faces, raking out joints on exposed faces etc. | 100 |  | 109099 | 2024-07-15 | 5266.09 | 1900-01-01 | -720.0028 | SHUBHAM SURENDRA BAHADUR SINGH
Murum Filling-DLD | N/C | N/C | SS ENTERPRISES | 141 | 2021-02-17 | Substructure Road Murum filling work | 2083.33 | 60 | 0 | 124999.8 | 0 | 2024-07-17 | D & E Bldg Surrouding area Murrum Filling Work | 100 |  | 109231 | 2024-07-22 | 124999.8 | 2024-08-05 14:00 | 0 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 141 | 2021-02-17 | Substructure Road Murum filling work | 2130 | 15 | 0 | 31950 | 5751 | 2021-03-25 | Spreading & Levelling Work | 100 |  | 89514 | 2021-03-25 | 159750 | 2021-03-30 13:00 | -127800 | SS ENTERPRISES
Murum Filling-DLD | N/C | N/C | SS ENTERPRISES | 141 | 2021-02-17 | Substructure Road Murum filling work | 2130 | 60 | 0 | 127800 | 23004 | 2021-03-25 | D & E Bldg Surrouding area Murrum Filling Work | 100 |  | 89514 | 2021-03-25 | 159750 | 2021-03-30 13:00 | -31950 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 141 | 2021-02-17 | Substructure Road Murum filling work | 1400 | 15 | 0 | 21000 | 0 | 2023-12-09 | Spreading & Levelling Work | 100 | Completion for Ganga Arcadia shifted material leveling work | 103815 | 2023-12-11 | 21000 | 2023-12-29 11:07 | 0 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 141 | 2021-02-17 | Substructure Road Murum filling work | 2333.3333 | 15 | 0 | 34999.9995 | 0 | 2023-10-18 | Spreading & Levelling Work | 100 | Completion for ganga arcadia shifting material leveling work | 102789 | 2023-10-19 | 35000 | 2023-11-07 13:59 | -0.0005 | SHIVAM ENTERPRISES
Trimix Work | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | 2542 | 10 | 0 | 25420 | 4575.6 | 2022-08-11 | Charges for- F buliding front side and slaes office side road trimix work. | 100 |  | 95876 | 2022-08-12 | 25420 | 2022-10-03 11:01 | 0 | JAI SAIRAM CONSTRUCTION
Dressing & Levelling Rate Diff. -DTR | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 3416 | 2.5 | 0 | 8540 | 1537.2 | 2022-03-04 | D,E Bldg Front Road (Levelling, Pressing, Trimix work) Work. process includes Levelling, Dressing, Watering, Rolling, Trimix. | 100 |  | 93723 | 2022-03-05 | 68530 | 2022-03-22 16:18 | -59990 | JAI SAIRAM CONSTRUCTION
Trimix Work-SO | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 3610 | 10 | 0 | 36100 | 6498 | 2022-05-06 | Trimix Work for D,E Bldg front Road | 100 |  | 94697 | 2022-05-07 | 36100 | 2022-06-04 13:51 | 0 | JAI SAIRAM CONSTRUCTION
Levelling, Dressing- DR | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 3092.4 | 2.5 | 0 | 7731 | 1391.58 | 2021-10-09 | Levelling & Dressing Work for D,E Bldg for Road | 100 |  | 91997 | 2021-10-12 | 7731 | 2022-03-19 16:07 | 0 | JAI SAIRAM CONSTRUCTION
Dressing & Levelling Rate Diff. -DTR | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 5154 | 2.5 | 0 | 12885 | 2319.3 | 2022-02-08 | D,E Bldg Front Road (Levelling, Pressing, Trimix work) Work. process includes Levelling, Dressing, Watering, Rolling, Trimix. | 100 |  | 93398 | 2022-02-09 | 30924 | 2022-03-22 16:19 | -18039 | JAI SAIRAM CONSTRUCTION
Groove Cutting & Bituminous filling | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | 97.2 | 40 | 0 | 3888 | 699.84 | 2022-09-17 | Charges for- Groove cutting and Bituman filling for F Building front side road and Sales office side road. | 100 |  | 96288 | 2022-09-19 | 10879 | 2022-10-03 10:59 | -6991 | JAI SAIRAM CONSTRUCTION
Levelling, Dressing- DR | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 7215.6 | 2.5 | 0 | 18039 | 3247.02 | 2022-02-08 | Levelling & Dressing Work for D,E Bldg for Road | 100 |  | 93398 | 2022-02-09 | 30924 | 2022-03-22 16:19 | -12885 | JAI SAIRAM CONSTRUCTION
Dressing,Levelling, Watering & Rolling | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road workdressing,leveling,rolling,trimix,groove cutt | 2542.1818 | 2.75 | 0 | 6991 | 1258.38 | 2022-09-17 | Charges for F Building front side and sales of side road dressing,levelling,watering and proper compaction by rolling. | 100 |  | 96288 | 2022-09-19 | 10879 | 2022-10-03 10:59 | -3888.0001 | JAI SAIRAM CONSTRUCTION
Groove Cutting & Bituminous filling | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 252.875 | 40 | 0 | 10115 | 1820.7 | 2022-08-04 | Groove Cutting 25mm depth with Bitumen Filling | 100 |  | 95815 | 2022-08-05 | 10115 | 2022-08-16 11:41 | 0 | JAI SAIRAM CONSTRUCTION
Trimix Work-SO | N/C | N/C | JAI SAIRAM CONSTRUCTION | 204 | 2021-05-20 | Trimix Road Bldg D to F Shops & Gate- front area road work | 5999 | 10 | 0 | 59990 | 10798.2 | 2022-03-04 | Trimix Work for D,E Bldg front Road | 100 |  | 93723 | 2022-03-05 | 68530 | 2022-03-22 16:18 | -8540 | JAI SAIRAM CONSTRUCTION
Excavation By Needle (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 21 | 2020-03-13 | Driveway & Ramp Excavation, Shifting, Levelling | 244.63 | 225 | 0 | 55041.75 | 9907.52 | 2020-10-06 | Substructure Excavation work by Needle & Shifting inside,including Levelling of Excavated material after unloading | 100 |  | 87645 | 2020-10-07 | 596796.5 | 2020-11-09 17:24 | -541754.75 | SS ENTERPRISES
Excavation By Needle (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 21 | 2020-03-13 | Podium Excavation, Shifting, Levelling | 77.17 | 225 | 0 | 17363.25 | 3125.38 | 2020-10-06 | Substructure Excavation work by Needle & Shifting inside,including Levelling of Excavated material after unloading | 100 |  | 87645 | 2020-10-07 | 596796.5 | 2020-11-09 17:24 | -579433.25 | SS ENTERPRISES
Excavation By Needle (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 21 | 2020-03-13 | Podium Excavation, Shifting, Levelling | 862.06 | 225 | 0 | 193963.5 | 34913.44 | 2020-10-06 | Substructure Excavation work by Needle & shifting inside including levelling of excavated material after unloading. | 100 |  | 87645 | 2020-10-07 | 596796.5 | 2020-11-09 17:24 | -402833 | SS ENTERPRISES
Excavation By Needle (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 21 | 2020-03-13 | Driveway & Ramp Excavation, Shifting, Levelling | 1398.52 | 225 | 0 | 314667 | 56640.06 | 2020-10-06 | Substructure Excavation work by Needle & shifting inside including levelling of excavated material after unloading. | 100 |  | 87645 | 2020-10-07 | 596796.5 | 2020-11-09 17:24 | -282129.5 | SS ENTERPRISES
Excavation By Bucket (Shifting Inside) | N/C | N/C | SS ENTERPRISES | 21 | 2020-03-13 | Driveway & Ramp Excavation, Shifting, Levelling | 210.1467 | 75 | 0 | 15761.0025 | 2836.98 | 2020-10-06 | Substructure Excavation work by Bucket & Shifting inside, including Levelling of Excaveted material after unloading | 100 |  | 87645 | 2020-10-07 | 596796.5 | 2020-11-09 17:24 | -581035.4975 | SS ENTERPRISES
Excavation By Bucket (Shifting Outside) | N/C | N/C | S S ENTERISES (PROP. SOBRAN SINGH) | 262 | 2021-09-08 | Well- Excavation Work | 271 | 60 | 0 | 16260 | 2926.8 | 2021-09-21 | Excavation work by Bucket in soils of all types up to required depth including removing the excavated material all leads and lifts, stacking and spreading with in site boundary etc. complete with all tool, machinery & Equipments. | 100 |  | 91615 | 2021-09-22 | 20325 | 2021-11-01 18:38 | -4065 | SS ENTERPRISES
Spreading & Levelling Work | N/C | N/C | S S ENTERISES (PROP. SOBRAN SINGH) | 262 | 2021-09-08 | Well- Excavation Work | 271 | 15 | 0 | 4065 | 731.7 | 2021-09-21 | Soil Spreading with available/dumped earth material and levelling including Lifting, shifting & unloading at requird Place including all leads and lifts, stacking and spreading with all tool, Equipments etc. complete | 100 |  | 91615 | 2021-09-22 | 20325 | 2021-11-01 18:38 | -16260 | SS ENTERPRISES
Labour Lumpsum-cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | Well RCC Work | 1 | 250000 | 0 | 250000 | 45000 | 2021-10-12 16:54 | Construction of RCC Pardi for Well including Reinforcement, Shuttering & Concreting work - (L). | 100 |  | 92011 | 2021-10-12 | 250000 | 2021-10-16 13:31 | 0 | VNE INFRA PROJECTS P LTD
Crane Charges - | N/C | N/C | R.T.S. STEEL SERVICES | 271 | 2021-09-25 | Well Top Slab Fabrication Work | 1 | 4000 | 0 | 4000 | 720 | 2022-08-27 | Crane Charges. | 100 |  | 96034 | 2022-08-27 | 7500 | 2022-10-06 11:01 | -3500 | R.T.S. STEEL SERVICES
Deck Sheet Fixing | N/C | N/C | R.T.S. STEEL SERVICES | 271 | 2021-09-25 | Well Top Slab Fabrication Work | 500 | 7 | 0 | 3500 | 630 | 2022-08-27 | Deck Sheet Fixing work. | 100 |  | 96034 | 2022-08-27 | 7500 | 2022-10-06 11:01 | -4000 | R.T.S. STEEL SERVICES
Fabrication work (L) | N/C | N/C | R.T.S. STEEL SERVICES | 271 | 2021-09-25 | Well Top Slab Fabrication Work | 710.24 | 17 | 0 | 12074.08 | 2173.34 | 2021-10-07 | Fabrication Work. ISMB 100 (61.76 mtr x 11.5 kg/mtr). | 100 |  | 91935 | 2021-10-08 | 35778.88 | 2021-12-14 18:02 | -23704.8 | R.T.S. STEEL SERVICES
Fabrication work (L) | N/C | N/C | R.T.S. STEEL SERVICES | 271 | 2021-09-25 | Well Top Slab Fabrication Work | 1394.4 | 17 | 0 | 23704.8 | 4266.86 | 2021-10-07 | Fabrication Work. ISMB 300 (28 mtr x 49.8 kg/mtr). | 100 |  | 91935 | 2021-10-08 | 35778.88 | 2021-12-14 18:02 | -12074.08 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | R.T.S. STEEL SERVICES | 272 | 2021-09-25 | Well Top Slab Fabrication Work | 710.24 | 55 | 0 | 39063.2 | 7031.38 | 2021-10-07 | Material Supply Fabrication Work. ISMB 100 (61.76 mtr x 11.5 kg/mtr). | 100 |  | 91936 | 2021-10-08 | 115755.2 | 2022-03-30 13:18 | -76692 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | R.T.S. STEEL SERVICES | 272 | 2021-09-25 | Well Top Slab Fabrication Work | 1394.4 | 55 | 0 | 76692 | 13804.56 | 2021-10-07 | Material Supply for Fabrication work. ISMB 300 (28 mtr x 49.8 kg/mtr). | 100 |  | 91936 | 2021-10-08 | 115755.2 | 2022-03-30 13:18 | -39063.2 | R.T.S. STEEL SERVICES
Aluminium Sliding Window (L) | N/C | N/C | ALFA FACADE SYSTEMS PRIVATE LIMITED | 296 | 2021-12-08 | Goel House Rennovation New window-Extension work | 272.69 | 97 | 0 | 26450.93 | 4761.16 | 2024-05-06 | Labour charges for lift & Slide Sliding window | 100 |  | 107404 | 2024-05-07 | 130592.56 | 2024-07-26 17:28 | -104141.63 | ALFA FACADE SYSTEMS PRIVATE LIMITED
Partly fix/openable window | N/C | N/C | ALFA FACADE SYSTEMS PRIVATE LIMITED | 296 | 2021-12-08 | Goel House Rennovation New window-Extension work | 144.83 | 145.5 | 0 | 21072.765 | 3793.1 | 2024-05-06 | Labour Charges for fixing of curtain wall partly fix partly openable partition | 100 |  | 107404 | 2024-05-07 | 130592.56 | 2024-07-26 17:28 | -109519.795 | ALFA FACADE SYSTEMS PRIVATE LIMITED
Partition Work | N/C | N/C | ALFA FACADE SYSTEMS PRIVATE LIMITED | 296 | 2021-12-08 | Goel House Rennovation New window-Extension work | 570.92 | 145.5 | 0 | 83068.86 | 14952.4 | 2024-05-06 | Fixing labour charges for curtain wall partition with lift and slide sliding and fix partition | 100 |  | 107404 | 2024-05-07 | 130592.56 | 2024-07-26 17:28 | -47523.7 | ALFA FACADE SYSTEMS PRIVATE LIMITED
Aerocon Partition (M+L) BC | N/C | N/C | GREENCON INFRATECH SOLUTION | 297 | 2021-12-09 | Goel House Rennovation Aerocon Panel work | 864 | 150 | 0 | 129600 | 23328 | 2022-02-17 13:18 | AEROCON PANEL 9FTX2FTX32NOS;(M+L) | 100 |  | 93522 | 2022-02-18 | 129600 | 2022-05-06 12:48 | 0 | GREENCON INFRATECH SOLUTION
Roller- BC | N/C | N/C | JAI SAIRAM CONSTRUCTION | 307 | 2021-12-09 | Road Rolling in front of D,E,podium,F-shops | 2 | 4000 | 0 | 8000 | 1440 | 2022-03-20 | Road Roller infront of D,E & F Building shops. | 100 |  | 93967 | 2022-03-21 | 8000 | 1900-01-01 | 0 | JAI SAIRAM CONSTRUCTION
Roller- BC | N/C | N/C | JAI SAIRAM CONSTRUCTION | 307 | 2021-12-09 | Road Rolling in front of D,E,podium,F-shops | 2 | 4000 | 0 | 8000 | 1440 | 2023-07-14 | Road Roller infront of D,E & F Building shops. | 100 |  | 100700 | 2023-07-15 | 8000 | 1900-01-01 | 0 | JAI SAIRAM CONSTRUCTION
Spreading & Levelling Work | N/C | N/C | SS ENTERPRISES | 309 | 2021-12-09 | Well side back filling work | 244 | 15 | 0 | 3660 | 658.8 | 2021-12-25 | Spreading & Levelling work. | 100 |  | 92846 | 2021-12-27 | 18300 | 2022-03-19 11:48 | -14640 | SS ENTERPRISES
Murum Shifting work | N/C | N/C | SS ENTERPRISES | 309 | 2021-12-09 | Well side back filling work | 244 | 60 | 0 | 14640 | 2635.2 | 2021-12-25 | Well side Murum Backfilling work. | 100 |  | 92846 | 2021-12-27 | 18300 | 2022-03-19 11:48 | -3660 | SS ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 281 | 60 | 0 | 16860 | 0 | 2023-07-05 | Backfilling work. | 100 |  | 100533 | 2023-07-07 | 35280 | 2023-07-26 12:26 | -18420 | SHIVAM ENTERPRISES
Murum Dressing & Levelling - Cu.Mtrs | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Amenity Plot Excavation Murum, Levelling,& Dressing Work | 1228 | 15 | 0 | 18420 | 0 | 2023-07-05 | Labour charges for Murum Dressing and Levelling work for Amenity Plot Development Area. | 100 |  | 100533 | 2023-07-07 | 35280 | 2023-07-26 12:26 | -16860 | SHIVAM ENTERPRISES
Excavation work-SO | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 122 | 60 | 0 | 7320 | 0 | 2023-02-01 | Excavation work for Amenity area Compound wall. | 100 |  | 97978 | 2023-02-01 | 7320 | 1900-01-01 | 0 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 147.5167 | 60 | 0 | 8851.002 | 1593.18 | 2022-08-29 | Backfilling work. | 100 |  | 96049 | 2022-08-29 | 18631 | 2022-10-06 11:07 | -9779.998 | SS ENTERPRISES
Excavation work-SO | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 340 | 60 | 0 | 20400 | 3672 | 2022-04-04 | Excavation work for Amenity area Compound wall. | 100 |  | 94150 | 2022-04-05 | 34020 | 2022-04-13 19:19 | -13620 | SS ENTERPRISES
Excavation work-SO | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 163 | 60 | 0 | 9780 | 1760.4 | 2022-08-29 | Excavation work for Amenity area Compound wall. | 100 |  | 96049 | 2022-08-29 | 18631 | 2022-10-06 11:07 | -8851 | SS ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 227 | 60 | 0 | 13620 | 2451.6 | 2022-04-04 | Backfilling work. | 100 |  | 94150 | 2022-04-05 | 34020 | 2022-04-13 19:19 | -20400 | SS ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 225 | 60 | 0 | 13500 | 2430 | 2022-03-20 | Backfilling work. | 100 |  | 94981 | 2022-06-04 | 34500 | 2022-06-04 15:29 | -21000 | SS ENTERPRISES
Excavation work-SO | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 259 | 60 | 0 | 15540 | 2797.2 | 2022-08-29 | Excavation work for Amenity area Compound wall. | 100 |  | 96050 | 2022-08-29 | 15540 | 2022-10-06 11:07 | 0 | SS ENTERPRISES
Excavation work-SO | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 350 | 60 | 0 | 21000 | 3780 | 2022-03-20 | Excavation work for Amenity area Compound wall. | 100 |  | 94981 | 2022-06-04 | 34500 | 2022-06-04 15:29 | -13500 | SS ENTERPRISES
Backfilling | N/C | N/C | SS ENTERPRISES | 316 | 2021-12-10 | Compound wall excavation work | 255.65 | 60 | 0 | 15339 | 0 | 2023-05-09 | Backfilling work. | 100 |  | 99566 | 2023-05-10 | 15339 | 2023-06-10 10:32 | 0 | SHIVAM ENTERPRISES
Housekeeping Work- | N/C | N/C | MMAK PROPERTY MANAGEMENT SERVICES | 324 | 2021-12-17 | Goel House Housekeeping Work | 88.0001 | 466.67 | -0.01 | 41067.0067 | 7392.06 | 2021-12-17 | Housekeeping work for the Month SEPT-2021 (3 Nos X 14000) | 100 |  | 92756 | 2021-12-17 | 41067 | 2021-12-18 12:51 | 0.006667 | MMAK PROPERTY MANAGEMENT SERVICES
Housekeeping Work- | N/C | N/C | MMAK PROPERTY MANAGEMENT SERVICES | 324 | 2021-12-17 | Goel House Housekeeping Work | 78.0009 | 451.61 | 0.01 | 35225.9864 | 6340.68 | 2022-01-18 | Housekeeping work for the Month DEC-2021 (3 Nos X 14000) | 100 |  | 93145 | 2022-01-18 | 35226 | 2022-01-18 14:19 | -0.013551 | MMAK PROPERTY MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 298 | 500 | 0 | 149000 | 26820 | 2022-10-06 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -43978 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 13.98 | 300 | 0 | 4194 | 754.92 | 2022-10-06 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -188784 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 3181 | 8 | 0 | 25448 | 4580.64 | 2022-10-06 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -167530 | VNE INFRA PROJECTS P LTD
PCC Work.- | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 4.0267 | 300 | -0.01 | 1208.01 | 217.44 | 2022-10-06 | PCC Work for Aminity Plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -191769.99 | VNE INFRA PROJECTS P LTD
Plum Concrete | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 21.88 | 300 | 0 | 6564 | 1181.52 | 2022-10-06 | Plum Concrete for Amenity Plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -186414 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 21.88 | 300 | 0 | 6564 | 1181.52 | 2022-10-06 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -186414 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 20.4 | 300 | 0 | 6120 | 1101.6 | 2022-03-05 | Concreting Work Amenity plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -102334 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 345 | 8 | 0 | 2760 | 496.8 | 2022-03-05 | Plum Concrete -Steel ( Shear Connector Steel) for Amenity Plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -105694 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 1500 | 8 | 0 | 12000 | 2160 | 2022-03-05 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -96454 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 60 | 450 | 0 | 27000 | 4860 | 2022-03-05 | Plum Concrete Shuttering Work for Amenity Plot Compound wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -81454 | VNE INFRA PROJECTS P LTD
Plum Concrete | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 11.88 | 300 | 0 | 3564 | 641.52 | 2022-03-05 | Plum Concrete for Amenity Plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -104890 | VNE INFRA PROJECTS P LTD
PCC Work.- | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 1.7 | 300 | 0 | 510 | 91.8 | 2022-03-05 | PCC Work for Aminity Plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -107944 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 113 | 500 | 0 | 56500 | 10170 | 2022-03-05 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -51954 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 110.2 | 500 | 0 | 55100 | 0 | 2022-09-30 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 96434 | 2022-09-30 | 69844 | 2022-10-17 18:45 | -14744 | KANU KALIPADA BALA
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 12 | 300 | 0 | 3600 | 0 | 2022-09-30 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96434 | 2022-09-30 | 69844 | 2022-10-17 18:45 | -66244 | KANU KALIPADA BALA
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 1393 | 8 | 0 | 11144 | 0 | 2022-09-30 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 96434 | 2022-09-30 | 69844 | 2022-10-17 18:45 | -58700 | KANU KALIPADA BALA
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 23.556 | 500 | 0 | 11778 | 2120.04 | 2023-01-27 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 102309 | 2023-10-05 | 19538 | 1900-01-01 | -7760 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 370 | 8 | 0 | 2960 | 532.8 | 2023-01-27 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 102309 | 2023-10-05 | 19538 | 1900-01-01 | -16578 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 16 | 300 | 0 | 4800 | 864 | 2023-01-27 | Concreting Work Amenity plot Compound Wall. | 100 |  | 102309 | 2023-10-05 | 19538 | 1900-01-01 | -14738 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 48.7 | 450 | 0 | 21915 | 3944.7 | 2022-09-30 | Plum Concrete Shuttering Work for Amenity Plot Compound wall. | 100 |  | 96433 | 2022-09-30 | 30561 | 2022-10-17 18:52 | -8646 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 6.5 | 300 | 0 | 1950 | 351 | 2022-09-30 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96433 | 2022-09-30 | 30561 | 2022-10-17 18:52 | -28611 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 837 | 8 | 0 | 6696 | 1205.28 | 2022-09-30 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 96433 | 2022-09-30 | 30561 | 2022-10-17 18:52 | -23865 | VNE INFRA PROJECTS P LTD
External Plaster DEn- | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 1600 | 28 | 0 | 44800 | 0 | 2022-09-26 | External Sand Face Plaster 20mm for Amenity Polt. | 100 |  | 96382 | 2022-09-27 | 46024 | 2022-10-03 11:05 | -1224 | K RAMU RATHOD
Brickwork 6" --DEn | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 68 | 18 | 0 | 1224 | 0 | 2022-09-26 | 6' Brickwork for Amenity Plot. | 100 |  | 96382 | 2022-09-27 | 46024 | 2022-10-03 11:05 | -44800 | K RAMU RATHOD
Brickwork 6" --DEn | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 190 | 18 | 0 | 3420 | 0 | 2022-05-06 | 6' Brickwork for Amenity Plot. | 100 |  | 94703 | 2022-05-07 | 3420 | 2022-05-25 12:08 | 0 | K RAMU RATHOD
Brickwork 6" --DEn | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 560 | 18 | 0 | 10080 | 0 | 2022-08-24 | 6' Brickwork for Amenity Plot. | 100 |  | 95988 | 2022-08-25 | 10080 | 1900-01-01 | 0 | K RAMU RATHOD
External Plaster DEn- | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 2349 | 28 | 0 | 65772 | 0 | 2022-09-17 | External Sand Face Plaster 20mm for Amenity Polt. | 100 |  | 96289 | 2022-09-19 | 65772 | 2022-10-03 11:06 | 0 | K RAMU RATHOD
Plaster Work - BRE | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | 4" Flyash brickwork & Plaster work infront of shop | 475.2 | 15 | 0 | 7128 | 0 | 2022-12-09 | Labour Charges for-Plaster work of 4 Inch Fly Ash brickwork front side of shop D,E,F & Podium. | 100 |  | 97322 | 2022-12-10 | 9718.5 | 2022-12-23 11:27 | -2590.5 | K RAMU RATHOD
Brickwork 4" - SO | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | 4" Flyash brickwork & Plaster work infront of shop | 235.5 | 11 | 0 | 2590.5 | 0 | 2022-12-09 | Labour Charges for- 4 Inch Fly Ash brickwork of front side of shop D,E,F & Podium. | 100 |  | 97322 | 2022-12-10 | 9718.5 | 2022-12-23 11:27 | -7128 | K RAMU RATHOD
Brickwork 6" --DEn | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 568 | 18 | 0 | 10224 | 0 | 2022-07-05 | 6' Brickwork for Amenity Plot. | 100 |  | 95399 | 2022-07-06 | 10224 | 2022-07-18 17:20 | 0 | K RAMU RATHOD
Copping Work DCH | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 275.5 | 12 | 0 | 3306 | 0 | 2022-09-27 | Copping Work for Amenity plot. | 100 |  | 96398 | 2022-09-28 | 3306 | 1900-01-01 | 0 | K RAMU RATHOD
Brickwork 6" --DEn | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 220 | 18 | 0 | 3960 | 0 | 2022-01-17 | 6' Brickwork for Amenity Plot. | 100 |  | 93141 | 2022-01-18 | 6084 | 2022-02-09 16:14 | -2124 | K RAMU RATHOD
Brickwork 6" --DEn | N/C | N/C | K RAMU RATHOD | 329 | 2021-12-28 | Compound wall Brickwork,Plaster,Coping - (L) | 118 | 18 | 0 | 2124 | 0 | 2022-01-18 | 6' Brickwork for Amenity Plot. | 100 |  | 93141 | 2022-01-18 | 6084 | 2022-02-09 16:14 | -3960 | K RAMU RATHOD
Tile Removing work-BRE | N/C | N/C | PRAKASH CONTRACTOR | 342 | 2022-01-12 | Goel House Bedroom 4,5,6,7 Floor Breaking | 0.3846 | 65000 | 1 | 24999 | 0 | 2022-01-12 | Flooring breaking with tools & equipments to prepare plain floor surface, inclu. cleaning & shifting debris at one place inclu. all lead lifts etc. | 100 |  | 93087 | 2022-01-12 | 25000 | 2022-01-12 17:25 | -1 | PRAKASH CONTRACTOR
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 342 | 2022-01-12 | Goel House- New Extension work soling & PCC | 0.3846 | 65000 | 1 | 24999 | 0 | 2022-01-12 | Excavation, Rabbit Shifting, 18 inch Rubble Soling & PCC Work for Ground Floor Extension work | 100 |  | 93088 | 2022-01-12 | 25000 | 2022-01-12 17:25 | -1 | PRAKASH CONTRACTOR
Tile Removing work-BRE | N/C | N/C | PRAKASH CONTRACTOR | 342 | 2022-01-12 | Goel House Bedroom 4,5,6,7 Floor Breaking | 0.4154 | 65000 | -1 | 27001 | 0 | 2022-03-01 | Flooring breaking with tools & equipments to prepare plain floor surface, inclu. cleaning & shifting debris at one place inclu. all lead lifts etc. | 100 |  | 93656 | 2022-03-01 | 27000 | 2022-03-01 17:16 | 1 | PRAKASH CONTRACTOR
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 342 | 2022-01-12 | Goel House- New Extension work soling & PCC | 0.6154 | 65000 | -1 | 40001 | 0 | 2022-01-12 | Excavation, Rabbit Shifting, 18 inch Rubble Soling & PCC Work for Ground Floor Extension work | 100 |  | 93089 | 2022-01-12 | 40000 | 2022-01-12 17:25 | 1 | PRAKASH CONTRACTOR
Labour Lumpsum - BC | N/C | N/C | KADAVATH VENKAT ENTERPRISES | 343 | 2022-01-12 | Goel House Bedroom 5&4 Brickwork & Plaster | 1 | 150000 | 0 | 150000 | 0 | 2022-01-12 | Construction of 9 inch Brickwork, Internal & External Plaster (Double Coat) at Bedroom No- 5 & 4 | 100 |  | 93090 | 2022-01-12 | 150000 | 2022-01-12 17:25 | 0 | JAY GANESH ENTERPRISES
Plantation Work | N/C | N/C | SNEHA GARDEN DEVELOPERS | 363 | 2022-01-24 | Plantation Work | 2300 | 9 | 0 | 20700 | 3726 | 2023-05-19 | Labour charges for Plantation of Iforbia (Height 1.5ft to 2ft) including Old Shrub Removing work, Dibbling Soil, New Plantation and Transportation. | 100 |  | 99723 | 2023-05-20 | 20700 | 2024-03-23 12:15 | 0 | SNEHA GARDEN DEVELOPERS
PVC Casing Work - UTR | N/C | N/C | DEEP MAN ENTERPRISES | 385 | 2022-02-21 | D&E Bldg.Road-Bore drilling for Rainwater Harvesting work | 55 | 350 | 0 | 19250 | 3465 | 2024-03-15 | Charges for PVC Casing work for Rain water Harvesting for D & E-Bldg. | 100 |  | 106056 | 2024-03-15 | 61525 | 2024-03-20 15:29 | -42275 | DEEP MAN ENTERPRISES
Drilling Work (Rft) | N/C | N/C | DEEP MAN ENTERPRISES | 385 | 2022-02-21 | D&E Bldg.Road-Bore drilling for Rainwater Harvesting work | 445 | 95 | 0 | 42275 | 7609.5 | 2024-03-15 | Charges for 6 inch Bore Drilling work for Rain water Harvesting for D & E-Bldg. | 100 |  | 106056 | 2024-03-15 | 61525 | 2024-03-20 15:29 | -19250 | DEEP MAN ENTERPRISES
Excavation By Needle (Shifting Inside) | N/C | N/C | VARSHA ENTERPRISES | 39 | 2020-06-11 | Driveway & Ramp Excavation, Shifting, Levelling | 297.84 | 225 | 0 | 67014 | 12062.52 | 2020-10-06 | Substructure Excavation work by Needle & Shifting inside,including Levelling of Excavated material after unloading | 100 |  | 87647 | 2020-10-07 | 67014 | 2020-11-09 17:43 | 0 | SS ENTERPRISES
Paving block fixing - ULT | N/C | N/C | PAPPU BAGELA | 439 | 2022-06-04 | F Bldg.-Road Work-Paver Block Fixing | 925.704 | 10 | 0 | 9257.04 | 0 | 2024-05-17 19:14 | Paving Block Fixing of heavy duty inter locking concrete Gray paving blocks of 60 mm to 100 thickness of approved quality and shape on a bed of crushed sand of 25 to 30 mm thick including skirting joints and cleaning etc. | 100 |  | 107661 | 2024-05-20 | 9257.04 | 2024-06-15 11:47 | 0 | PAPPU BAGELA
Paving Block Fixing - AIE | N/C | N/C | PAPPU BAGELA | 439 | 2022-06-04 | D,E,F Bldg.Main Road-Paver Block Fixing | 659.5105 | 13 | 0 | 8573.6365 | 0 | 2024-07-15 12:19 | Labour Charges for Fixing of Paving Block with heavy duty inter locking concrete to internal road D,E,F Building and Main road with proper line,level,Approved Quality,Shap,thickness on a bed of Crushed sand including striking joints and cleaning etc. | 100 |  | 109100 | 2024-07-15 | 8573.64 | 2024-08-05 14:01 | -0.0035 | PAPPU BAGELA
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | SEP 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | DEC 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | NOV 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1219.2863 | 219.48 | 2022-03-31 | MARCH 2022 | 8.337 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13405.7038 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | MAY 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | JAN 2022 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | FEB 2022 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | APRIL 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | JULY 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | AUG 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | OCT 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 468 | 2022-07-06 | Goel House 30 KVA -Online UPS System | 12 | 1218.75 | 0 | 1218.7013 | 219.36 | 2022-03-31 | JUNE 2021 | 8.333 |  | 95457 | 2022-03-31 | 14624.99 | 2022-07-09 17:39 | -13406.2887 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | JAN 2022 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | FEB 2022 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | SEP 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | JUNE 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | MAY 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | JULY 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | NOV 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1188.0225 | 213.84 | 2022-03-31 | MARCH 2022 | 8.337 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13061.9475 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | DEC 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | AUG 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | OCT 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
AMC Charges | N/C | N/C | TECHNOVISION ENERGY PVT.LTD. | 469 | 2022-07-06 | AMC Charges for 125KVA Stabilizer | 12 | 1187.5 | 0 | 1187.4525 | 213.74 | 2022-03-31 | APRIL 2021 | 8.333 |  | 95458 | 2022-03-31 | 14249.97 | 2022-07-09 17:40 | -13062.5175 | TECHNOVISION ENERGY PVT.LTD.
Brickwork 9" --DEn | N/C | N/C | K RAMU RATHOD | 483 | 2022-07-11 | Compound wall-9" brickwork,plaster,coping (L) | 288 | 18 | 0 | 5184 | 0 | 2022-09-26 | Labour Charges for- 9 Inch Brickwork with proper joint filling,line,level,right angle & Plumb. | 100 |  | 96378 | 2022-09-27 | 5184 | 2022-10-03 11:04 | 0 | K RAMU RATHOD
Brickwork 9" --DEn | N/C | N/C | K RAMU RATHOD | 483 | 2022-07-11 | Compound wall-9" brickwork,plaster,coping (L) | 288 | 18 | 0 | 5184 | 0 | 2022-08-24 | Labour Charges for- 9 Inch Brickwork with proper joint filling,line,level,right angle & Plumb. | 100 |  | 95989 | 2022-08-25 | 5184 | 1900-01-01 | 0 | K RAMU RATHOD
Kerb stone fixing - Dld | N/C | N/C | SURESH KUMAR MURALIDHAR | 50 | 2020-07-28 | Pathway Kerb stone fixing | 27 | 25 | 0 | 675 | 0 | 2020-10-02 | Kerb Stone Fixing 30 meter road Pathway work | 100 |  | 87583 | 2020-10-03 | 5199 | 2020-10-10 20:11 | -4524 | SURESH KUMAR MURALIDHAR
Sand Face Plaster - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 50 | 2020-07-28 | Pathway Plaster near main gate | 12 | 10 | 0 | 120 | 0 | 2020-10-02 | Sand Face Plaster near Main Gate Pathway | 100 |  | 87583 | 2020-10-03 | 5199 | 2020-10-10 20:11 | -5079 | SURESH KUMAR MURALIDHAR
Sand Face Plaster DLd | N/C | N/C | SURESH KUMAR MURALIDHAR | 50 | 2020-07-28 | Planter Brickwork & Plaster | 220 | 12 | 0 | 2640 | 0 | 2020-10-02 | Plaster Work for planter near main gate & hording | 100 |  | 87583 | 2020-10-03 | 5199 | 2020-10-10 20:11 | -2559 | SURESH KUMAR MURALIDHAR
Brickwork 6" -DLd | N/C | N/C | SURESH KUMAR MURALIDHAR | 50 | 2020-07-28 | Planter Brickwork & Plaster | 147 | 12 | 0 | 1764 | 0 | 2020-10-02 | 6 inch brickwork for planter near main gate & hording | 100 |  | 87583 | 2020-10-03 | 5199 | 2020-10-10 20:11 | -3435 | SURESH KUMAR MURALIDHAR
Total Statiotn Survey | N/C | N/C | VECTOR SURVEYORS | 558 | 2022-10-19 | Amenity Plot- Surveying Work by Total Station | 1 | 4500 | 0 | 4500 | 0 | 2022-11-12 | Charges for Total station survey work for amenity plot area. | 100 |  | 97039 | 2022-11-14 | 4500 | 2022-12-03 10:53 | 0 | VECTOR SURVEYORS
Total Statiotn Survey | N/C | N/C | VECTOR SURVEYORS | 559 | 2022-10-19 | Club House-Survey work by Total Station | 3 | 4500 | 0 | 13500 | 0 | 2024-02-18 12:31 | Charges for Club -house Surveying work by Total Station for Pile Cap Foundation & Plinth Foundation Pile cap work. | 100 |  | 105375 | 2024-02-19 | 13500 | 2024-03-23 12:17 | 0 | VECTOR SURVEYORS
Wet Mix Macadam (L) | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 1200.9785 | 5.11 | 0 | 6137.0001 | 1104.66 | 2023-11-02 | Labour Charges for Wet Mix Macadam of 150mm for Road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -39261.9999 | AMAN ASSOCIATES
GSB 1st Layer (L) | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 2761.0568 | 5.11 | 0 | 14109.0002 | 2539.62 | 2023-11-02 | Labour Charges for 1st Layer of Granular Sub base of 125mm for Road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -31289.9998 | AMAN ASSOCIATES
GSB 2nd Layer (L) | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 2761.0568 | 5.11 | 0 | 14109.0002 | 2539.62 | 2023-11-02 | Labour Charges for 2nd Layer of Granular Sub base of 125mm for Road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -31289.9998 | AMAN ASSOCIATES
Rolling,Compaction,Levelling | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | F-Bldg Side Road Work -PQC Road | 2761 | 4 | 0 | 11044 | 1987.92 | 2023-11-02 | Labour Charges for Rolling,Compaction and levelling work for road work near F Building. | 100 |  | 103209 | 2023-11-02 | 45399 | 1900-01-01 | -34355 | AMAN ASSOCIATES
Rate Difference | N/C | N/C | AMAN ASSOCIATES | 568 | 2022-11-07 | Kharadi DP Road Work Rate Difference | 1 | 2644988 | 0 | 2644988 | 476097.84 | 2022-11-07 | Charges for Rate Difference of Kharadi DP Road Work | 100 |  | 96956 | 2022-11-07 | 2644988 | 2022-11-08 13:02 | 0 | AMAN ASSOCIATES
Excavation by Bucket | N/C | N/C | SHIVAM ENTERPRISES | 587 | 2022-12-12 | F Bldg.-Road Excavation Work | 647.79 | 60 | 0 | 38867.4 | 0 | 2023-12-13 | Charges for Excavation work by Bucket for road near F-Bldg on North Side & East Side. | 100 |  | 103990 | 2023-12-18 | 51823.2 | 2023-12-25 15:37 | -12955.8 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 587 | 2022-12-12 | F Bldg.-Road Excavation Work | 647.79 | 20 | 0 | 12955.8 | 0 | 2023-12-13 | Charges for Spreading & Levelling work for Road near F-Bldg on North Side & East Side. | 100 |  | 103990 | 2023-12-18 | 51823.2 | 2023-12-25 15:37 | -38867.4 | SHIVAM ENTERPRISES
JCB Charges | N/C | N/C | SHIVAM ENTERPRISES | 587 | 2022-12-12 | Filling & Leveling for STP Access road | 16 | 850 | 0 | 13600 | 0 | 2023-01-27 | JCB Charges for Levelling and Filling work for Access Road for STP. | 100 |  | 97946 | 2023-01-28 | 13600 | 2023-02-23 15:29 | 0 | SHIVAM ENTERPRISES
Zebra Crossing marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 104 | 580 | 0 | 60320 | 10857.6 | 2023-03-06 14:51 | Providing and Applying Charges for Zebra Crossing making work with Thermoplastic material and machine of White colour 2.3 or 2.5mm thickness.Road width side 52 meter of all roads of same junction x 4 meter long x 0.5 | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -301687 | AVS TRAFEIC SYSTEMS
Yellow Box Marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 167 | 580 | 0 | 96860 | 17434.8 | 2023-03-06 14:51 | Charges for Qty Diff. for Providing and Applying Charges for Yellow Box making work with Thermoplastic material and machine of Yellow colour 2.3 or 2.5mm thickness. | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -265147 | AVS TRAFEIC SYSTEMS
Yellow Box Marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 200 | 580 | 0 | 116000 | 20880 | 2023-03-06 14:51 | Providing and Applying Charges for Yellow Box making work with Thermoplastic material and machine of Yellow colour 2.3 or 2.5mm thickness. | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -246007 | AVS TRAFEIC SYSTEMS
Zebra Crossing marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 594 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 153.15 | 580 | 0 | 88827 | 15988.86 | 2023-03-06 14:51 | Charges for Qty Diff. of Providing and Applying Charges for Zebra Crossing making work with Thermoplastic material and machine of White colour 2.3 or 2.5mm thickness.Road width side 52 meter of all roads of same junction x 4 meter long x 0.5 | 100 |  | 98537 | 2023-03-06 | 362007 | 2023-03-20 11:53 | -273180 | AVS TRAFEIC SYSTEMS
Yellow Box Marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 595 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 231 | 580 | 0 | 133980 | 24116.4 | 2023-03-06 13:54 | Providing and Applying Charges for Yellow Box making work with Thermoplastic material and machine of Yellow colour 2.3 or 2.5mm thickness. | 100 |  | 98538 | 2023-03-06 | 149390.6 | 2023-03-20 11:53 | -15410.6 | AVS TRAFEIC SYSTEMS
Zebra Crossing marking | N/C | N/C | AVS TRAFEIC SYSTEMS | 595 | 2022-12-19 | Zebra Crossing & Yellow Box marking work | 26.57 | 580 | 0 | 15410.6 | 2773.9 | 2023-03-06 13:54 | Providing and Applying Charges for Zebra Crossing making work with Thermoplastic material and machine of White colour 2.3 or 2.5mm thickness.Road width side 58 meter of all roads of same junction x 4 meter long x 0.5 | 100 |  | 98538 | 2023-03-06 | 149390.6 | 2023-03-20 11:53 | -133980 | AVS TRAFEIC SYSTEMS
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 596 | 2022-12-19 | Road Beautification - Civil work | 0.0982 | 55000 | 0 | 5401 | 0 | 2023-02-01 16:40 | Labour Charges for Excavation for Shrub bed,Poyata Soil filling in Shrub bed,Shrubs Plantation work and Misc. work with required labour and machinery. | 100 |  | 97979 | 2023-02-02 | 5401 | 2023-02-23 14:59 | 0 | PRAKASH CONTRACTOR
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 596 | 2022-12-19 | Road Beautification - Civil work | 0.7709 | 55000 | 0 | 42399.5 | 0 | 2023-01-05 17:22 | Labour Charges for Excavation for Shrub bed,Poyata Soil filling in Shrub bed,Shrubs Plantation work and Misc. work with required labour and machinery. | 100 |  | 97650 | 2023-01-05 | 42399.5 | 2023-01-23 18:36 | 0 | PRAKASH CONTRACTOR
Tractor Trip - DCW | N/C | N/C | PRAKASH CONTRACTOR | 596 | 2022-12-19 | Road Beautification - Civil work | 9.2 | 1000 | 0 | 9200 | 0 | 2023-01-23 | Tractor Trip Charges for Road Beautification Civil work at Vadgaon Chowk.Excavation,Poyata Soil Filling Shrub Plantation work and other misc work. | 100 |  | 97899 | 2023-01-23 | 9200 | 2023-02-27 15:43 | 0 | NAMANNA RATHOD
Street Light Pole fixing (L) | N/C | N/C | LAXMI ELECTRICALS | 597 | 2022-12-19 | Street Light Pole fixing work | 7 | 1000 | 0 | 7000 | 0 | 2023-01-05 18:49 | Charges for 10 Feet Street Light pole Fixing work including excavation of pit,Pole Grouting with concreting etc. At P.L.Deshapande Garden Beautification. | 100 |  | 97663 | 2023-01-06 | 18300 | 2023-01-31 11:54 | -11300 | LAXMI ELECTRICALS
4C 6 sqmm Alu. Cable (L) | N/C | N/C | LAXMI ELECTRICALS | 597 | 2022-12-19 | Street Light Pole fixing work | 20 | 40 | 0 | 800 | 0 | 2023-01-05 18:49 | Labour Charges for 4 Core 6 Sq.mm Cable for Street light pole. Safety of all workers, public & Vehicles is of contractors responsbility. At P.L.Deshapande Garden Beautification. | 100 |  | 97663 | 2023-01-06 | 18300 | 2023-01-31 11:54 | -17500 | LAXMI ELECTRICALS
Street Light Foundation Work - DSL | N/C | N/C | LAXMI ELECTRICALS | 597 | 2022-12-19 | Street Light Pole fixing work | 7 | 1500 | 0 | 10500 | 0 | 2023-01-05 18:49 | Labour and Material Supply Charges for Street light pole foundation Concreting work. Safety of all workers, public & Vehicles is of contractors responsbility.At P.L.Deshapande Garden Beautification. | 100 |  | 97663 | 2023-01-06 | 18300 | 2023-01-31 11:54 | -7800 | LAXMI ELECTRICALS
Installation Charges | N/C | N/C | ABHISHREE LOGISTICS & SERVICES | 598 | 2022-12-19 | Vertical Artificial Green Wall Work | 1 | 40000 | 0 | 40000 | 7200 | 2023-01-06 16:51 | Installation charges for artificial Green Wall/Column. | 100 |  | 98377 | 2023-02-27 | 512965.7 | 2023-02-27 19:29 | -472965.7 | ABHISHREE LOGISTICS & SERVICES
Supply Vertical Green Wall | N/C | N/C | ABHISHREE LOGISTICS & SERVICES | 598 | 2022-12-19 | Vertical Artificial Green Wall Work | 2012.62 | 235 | 0 | 472965.7 | 85133.82 | 2023-01-06 16:51 | Material Charges for Artificial Green wall clading on bridge column as per drawing at Veer pasalkar chowk Vadgaon Flayover.Hilton sheet Adhesive,all scaffolding & other required stagging work to be done by contractor. | 100 |  | 98377 | 2023-02-27 | 512965.7 | 2023-02-27 19:29 | -40000 | ABHISHREE LOGISTICS & SERVICES
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-11-04 | Charges for Garden Maintenance and Watering work for Month SEPT-2023. | 100 |  | 103266 | 2023-11-04 | 8800 | 2023-11-18 14:35 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-11-04 | Charges for Garden Maintenance and Watering work for Month OCT-2023. | 100 |  | 103266 | 2023-11-04 | 8800 | 2023-11-18 14:35 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-07-03 | Charges for Garden Maintenance and Watering work for Month JUNE-2023. | 100 |  | 100442 | 2023-07-04 | 13200 | 2023-08-14 14:34 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-07-03 | Charges for Garden Maintenance and Watering work for Month MAY-2023. | 100 |  | 100442 | 2023-07-04 | 13200 | 2023-08-14 14:34 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-07-03 | Charges for Garden Maintenance and Watering work for Month APR-2023. | 100 |  | 100442 | 2023-07-04 | 13200 | 2023-08-14 14:34 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2024-02-14 | Charges for Garden Maintenance and Watering work for Month NOV-2023. | 100 |  | 105371 | 2024-02-19 | 13200 | 2024-03-12 14:17 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2024-02-14 | Charges for Garden Maintenance and Watering work for Month JAN-2024. | 100 |  | 105371 | 2024-02-19 | 13200 | 2024-03-12 14:17 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2024-02-14 | Charges for Garden Maintenance and Watering work for Month DEC-2023. | 100 |  | 105371 | 2024-02-19 | 13200 | 2024-03-12 14:17 | -8800 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-09-18 15:51 | Charges for Garden Maintenance and Watering work for Month AUG-2023. | 100 |  | 101949 | 2023-09-20 | 8800 | 2023-10-30 15:49 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-09-18 15:51 | Charges for Garden Maintenance and Watering work for Month JULY-2023. | 100 |  | 101949 | 2023-09-20 | 8800 | 2023-10-30 15:49 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-04-12 | Charges for Garden Maintenance and Watering work for Month MAR-2023. | 100 |  | 99135 | 2023-04-12 | 8800 | 2023-05-04 14:17 | -4400 | SITARAM GANGADHAR AUTI
Male Coolie | N/C | N/C | PRAKASH CONTRACTOR | 637 | 2023-03-14 | P.L. Deshpande Garden Maintenance work | 8 | 550 | 0 | 4400 | 0 | 2023-04-12 | Charges for Garden Maintenance and Watering work for Month FEB-2023. | 100 |  | 99135 | 2023-04-12 | 8800 | 2023-05-04 14:17 | -4400 | SITARAM GANGADHAR AUTI
Pile Concreting Work | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 235.25 | 200 | 0 | 47050 | 8469 | 2024-03-14 14:48 | Charges for Concreting work for Piling including all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -595050 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 5.27 | 2400 | 0 | 12648 | 2276.64 | 2024-03-15 15:05 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -629452 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 42.73 | 2400 | 0 | 102552 | 18459.36 | 2024-03-14 14:48 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -539548 | MASKE PILE FOUNDATION
Reinforcement for Piling-BC | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 235.25 | 200 | 0 | 47050 | 8469 | 2024-03-14 14:48 | Charges for Reinforcement work for Piling. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -595050 | MASKE PILE FOUNDATION
Mobilisation - DEn | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 1 | 100000 | 0 | 100000 | 18000 | 2024-03-14 14:48 | Charges for One Time Transportation including crane for Club House piling work. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -542100 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 15.48 | 1600 | 0 | 24768 | 4458.24 | 2024-03-15 15:05 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through all strata excluding weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -617332 | MASKE PILE FOUNDATION
Piling Work 500mm Dia. - ULT | N/C | N/C | MASKE PILE FOUNDATION | 665 | 2023-04-12 | Club House-Pile Steel Work | 192.52 | 1600 | 0 | 308032 | 55445.76 | 2024-03-14 14:48 | Charges for 500mm dia Boring with Hydraulic Rotary Rig through all strata excluding weathered/ Hard Strata with all equipment,labour,tools,tackle etc. | 100 |  | 106059 | 2024-03-15 | 642100 | 2024-03-20 12:36 | -334068 | MASKE PILE FOUNDATION
Granular Sub Base (M) | N/C | N/C | AMAN ASSOCIATES | 751 | 2023-08-03 | F-Bldg Side Road Work -PQC Road | 2760.9965 | 37.33 | 0 | 103067.9993 | 18552.24 | 2023-11-02 | Material Supply Charges for Granular Sub base of 250mm for Road work near F Building. | 100 |  | 103210 | 2023-11-02 | 129130 | 1900-01-01 | -26062.0007 | AMAN ASSOCIATES
Wet Mix Macadam (M) | N/C | N/C | AMAN ASSOCIATES | 751 | 2023-08-03 | F-Bldg Side Road Work -PQC Road | 1201.0138 | 21.7 | 0 | 26061.9995 | 4691.16 | 2023-11-02 | Material Supply Charges for Wet Mix Macadam of 150mm for Road work near F Building. | 100 |  | 103210 | 2023-11-02 | 129130 | 1900-01-01 | -103068.0005 | AMAN ASSOCIATES
Wet Mix Macadam (L) | N/C | N/C | VIRAJ ENTERPRISES | 805 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 5468 | 4.5 | 0 | 24606 | 4429.08 | 2023-12-02 17:37 | Labour Charges for Wet Mix Macadam of 150mm for Road work near F Building | 100 |  | 103608 | 2023-12-04 | 161184.35 | 2024-01-16 15:27 | -136578.35 | VIRAJ ENTERPRISES
Dry Lean Concrete (L) | N/C | N/C | VIRAJ ENTERPRISES | 805 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 5468 | 5.7 | 0 | 31167.6 | 5610.16 | 2023-12-02 17:37 | Labour Charges for Dry Lean Concrete work of 100mm for Road work near F Building. | 100 |  | 103608 | 2023-12-04 | 161184.35 | 2024-01-16 15:27 | -130016.75 | VIRAJ ENTERPRISES
Pavement Quality Concrete (L) | N/C | N/C | VIRAJ ENTERPRISES | 805 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 4053 | 18.75 | 0 | 75993.75 | 13678.88 | 2023-12-02 17:37 | Labour Charges for Pavement Quality Concrete work of 200mm for Road work near F Building. | 100 |  | 103608 | 2023-12-04 | 161184.35 | 2024-01-16 15:27 | -85190.6 | VIRAJ ENTERPRISES
Rolling,Compaction,Levelling | N/C | N/C | VIRAJ ENTERPRISES | 805 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 2558 | 4 | 0 | 10232 | 1841.76 | 2023-12-02 17:37 | Labour Charges for Rolling,Compaction and levelling work for road work near F Building. | 100 |  | 103608 | 2023-12-04 | 161184.35 | 2024-01-16 15:27 | -150952.35 | VIRAJ ENTERPRISES
GSB 1st Layer (L) | N/C | N/C | VIRAJ ENTERPRISES | 805 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 2558 | 3.75 | 0 | 9592.5 | 1726.66 | 2023-12-02 17:37 | Labour Charges for 1st Layer of Granular Sub base of 125mm for Road work near F Building. | 100 |  | 103608 | 2023-12-04 | 161184.35 | 2024-01-16 15:27 | -151591.85 | VIRAJ ENTERPRISES
GSB 2nd Layer (L) | N/C | N/C | VIRAJ ENTERPRISES | 805 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 2558 | 3.75 | 0 | 9592.5 | 1726.66 | 2023-12-02 17:37 | Labour Charges for 2nd Layer of Granular Sub base of 125mm for Road work near F Building. | 100 |  | 103608 | 2023-12-04 | 161184.35 | 2024-01-16 15:27 | -151591.85 | VIRAJ ENTERPRISES
Granular Sub Base (M) | N/C | N/C | VIRAJ ENTERPRISES | 806 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 2558 | 42.5 | 0 | 108715 | 19568.7 | 2023-12-02 17:37 | Material Supply Charges for Granular Sub base of 250mm for Road work near F Building | 100 |  | 103610 | 2023-12-04 | 855396.65 | 2024-01-16 15:25 | -746681.65 | VIRAJ ENTERPRISES
Dry Lean Concrete (M) | N/C | N/C | VIRAJ ENTERPRISES | 806 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 5468 | 32.3 | 0 | 176616.4 | 31790.96 | 2023-12-02 17:37 | Material Supply Charges for Dry Lean Concrete work of 100mm for Road work near F Building. | 100 |  | 103610 | 2023-12-04 | 855396.65 | 2024-01-16 15:25 | -678780.25 | VIRAJ ENTERPRISES
Wet Mix Macadam (M) | N/C | N/C | VIRAJ ENTERPRISES | 806 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 5468 | 25.5 | 0 | 139434 | 25098.12 | 2023-12-02 17:37 | Material Supply Charges for Wet Mix Macadam of 150mm for Road work near F Building | 100 |  | 103610 | 2023-12-04 | 855396.65 | 2024-01-16 15:25 | -715962.65 | VIRAJ ENTERPRISES
M25 PQC (M) | N/C | N/C | VIRAJ ENTERPRISES | 806 | 2023-11-06 | F-Bldg Side Road Work -PQC Road | 4053 | 106.25 | 0 | 430631.25 | 77513.62 | 2023-12-02 17:37 | Material Supply Charges for M 25 Pavament Quality Concrete work for F Building side road | 100 |  | 103610 | 2023-12-04 | 855396.65 | 2024-01-16 15:25 | -424765.4 | VIRAJ ENTERPRISES
Old Shrub removing & shifting | N/C | N/C | SNEHA GARDEN DEVELOPERS | 813 | 2023-11-21 | Divider Plantation Work(Main+Inside Road | 1000 | 9 | 0 | 9000 | 1620 | 2024-02-29 | Labour charges for old Shrub Removing work, Dibbling soil & New plantation work including transportation for Altus Road Divider. | 100 |  | 105673 | 2024-03-04 | 9000 | 2024-03-23 12:15 | 0 | SNEHA GARDEN DEVELOPERS
Euphorbia Mili | N/C | N/C | SNEHA GARDEN DEVELOPERS | 813 | 2023-11-21 | Divider Plantation Work(Main+Inside Road | 1000 | 50 | 0 | 50000 | 9000 | 2024-01-09 | Charges for Iforbia Shrub Plantation Height upto 1.5 to 2 ft, Bag Size (9 x 11) for Ganga altus Road Divider. | 100 |  | 104540 | 2024-01-15 | 50000 | 2024-02-21 11:35 | 0 | SNEHA GARDEN DEVELOPERS
G.I. Sheet Removing - SOI | N/C | N/C | SURESH RANGNATH SHITOLE | 821 | 2023-11-24 | Removing of GI Sheet,Channels&Angle (Store&Steel Yard Area) | 1448 | 6 | 0 | 8688 | 0 | 2023-12-08 17:20 | Labour charges for GI Sheet Removing work with Frame including removing of Channel & Angle. | 100 |  | 103809 | 2023-12-11 | 8688 | 2023-12-25 15:42 | 0 | SURESH RANGNATH SHITOLE
G.I. Sheet Removing - SOI | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 1700 | 6 | 0 | 10200 | 0 | 2024-05-19 16:56 | Labour charges for GI Sheet Removing work including frame for Steel yard shifting, Store-2,8,9,10, Chemical godown,pump room, store near well,etc. | 100 |  | 107681 | 2024-05-20 | 20385 | 2024-07-15 14:59 | -10185 | SURESH RANGNATH SHITOLE
G.I. Sheet Fixing - BC | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 700 | 13 | 0 | 9100 | 0 | 2024-05-19 16:58 | Labour charges for GI sheet Fixing work with vertical channel fixing at loft intertnal including tapping screw for steel yard and store. | 100 |  | 107681 | 2024-05-20 | 20385 | 2024-07-15 14:59 | -11285 | SURESH RANGNATH SHITOLE
G.I. Sheet Fixing - BC | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 1094.36 | 13 | 0 | 14226.68 | 0 | 2023-12-08 17:23 | Labour charges for GI sheet Fixing work with vertical channel fixing at loft intertnal including tapping screw for steel yard and store. | 100 |  | 103811 | 2023-12-11 | 14226.68 | 2024-01-02 11:43 | 0 | SURESH RANGNATH SHITOLE
G.I. Sheet Fixing - BC | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 603.668 | 13 | 0 | 7847.684 | 0 | 2024-02-26 16:50 | Labour charges for GI sheet Fixing work with vertical channel fixing at loft intertnal including tapping screw for steel yard and store. | 100 |  | 105599 | 2024-02-26 | 23672.33 | 2024-03-29 15:10 | -15824.646 | SURESH RANGNATH SHITOLE
G.I. Sheet Removing - SOI | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 2637.4419 | 6 | 0 | 15824.6514 | 0 | 2024-02-26 16:44 | Labour charges for GI Sheet Removing work including frame for Steel yard shifting, Store-2,8,9,10, Chemical godown,pump room, store near well,etc. | 100 |  | 105599 | 2024-02-26 | 23672.33 | 2024-03-29 15:10 | -7847.6786 | SURESH RANGNATH SHITOLE
G.I. Sheet Removing - SOI | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 534.3672 | 6 | 0 | 3206.2032 | 0 | 2024-06-02 12:23 | Labour charges for GI Sheet Removing work including frame for Steel yard shifting, Store-2,8,9,10, Chemical godown,pump room, store near well,etc. | 100 |  | 107941 | 2024-06-03 | 8221.29 | 2024-07-05 11:42 | -5015.0868 | SURESH RANGNATH SHITOLE
G.I. Sheet Fixing - BC | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 385.776 | 13 | 0 | 5015.088 | 0 | 2024-06-02 12:30 | Labour charges for GI sheet Fixing work with vertical channel fixing at loft intertnal including tapping screw for steel yard and store. | 100 |  | 107941 | 2024-06-03 | 8221.29 | 2024-07-05 11:42 | -3206.202 | SURESH RANGNATH SHITOLE
G.I. Sheet Removing - SOI | N/C | N/C | SURESH RANGNATH SHITOLE | 822 | 2023-11-24 | Removing & fixing of GI Sheet (Steel Yard & Store) | 200.57 | 6 | 0 | 1203.42 | 0 | 2024-02-02 15:36 | Labour charges for GI Sheet Removing work including frame for Steel yard shifting, Store-2,8,9,10, Chemical godown,pump room, store near well,etc. | 100 |  | 105008 | 2024-02-05 | 2277.42 | 1900-01-01 | -1074 | SURESH RANGNATH SHITOLE
Excavation By Bucket (Shifting Inside) | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | F-Ent.Gate-Excavation & Backfilling | 175.032 | 60 | 0 | 10501.92 | 0 | 2023-12-21 18:29 | Charges for Excavation work by Bucket & shifting it inside for Main Gate Footing near F-Bldg. | 100 |  | 104100 | 2023-12-25 | 32424.96 | 2024-01-02 11:44 | -21923.04 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | F-Ent.Gate-Excavation & Backfilling | 175.032 | 20 | 0 | 3500.64 | 0 | 2023-12-21 18:29 | Charges for Spreading & Levelling work for Main Gate Footing near F-Bldg. | 100 |  | 104100 | 2023-12-25 | 32424.96 | 2024-01-02 11:44 | -28924.32 | SHIVAM ENTERPRISES
Excavation By Bucket (Shifting Inside) | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | D&E-Ent.Gate-Excavation & Backfilling | 109.824 | 60 | 0 | 6589.44 | 0 | 2023-12-21 18:29 | Charges for Excavation work by Bucket & shifting it inside for Main Gate Footing near D-Bldg. | 100 |  | 104100 | 2023-12-25 | 32424.96 | 2024-01-02 11:44 | -25835.52 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | F-Ent.Gate-Excavation & Backfilling | 160.608 | 60 | 0 | 9636.48 | 0 | 2023-12-21 18:29 | Charges for Backfilling work for Main Gate Footing near F-Bldg. | 100 |  | 104100 | 2023-12-25 | 32424.96 | 2024-01-02 11:44 | -22788.48 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | D&E-Ent.Gate-Excavation & Backfilling | 109.824 | 20 | 0 | 2196.48 | 0 | 2023-12-21 18:29 | Charges for Spreading & Levelling work for Main Gate Footing near F-Bldg. | 100 |  | 104100 | 2023-12-25 | 32424.96 | 2024-01-02 11:44 | -30228.48 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | Excavation & Backfilling Work-East Side Compound Wall | 587.895 | 60 | 0 | 35273.7 | 0 | 2024-07-15 | Charges for Backfilling of East Side Compound wall . | 100 |  | 109110 | 2024-07-15 | 35273.7 | 2024-08-07 11:49 | 0 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | D,E&F Bldg.-Road Excavation Work | 1711.29 | 20 | 0 | 34225.8 | 0 | 2024-02-11 16:00 | Charges for Spreading & Levelling work | 100 |  | 105255 | 2024-02-12 | 142935.72 | 2024-03-20 15:55 | -108709.92 | SHIVAM ENTERPRISES
Excavation Work | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | D,E&F Bldg.-Road Excavation Work | 1711.29 | 60 | 0 | 102677.4 | 0 | 2024-02-11 16:00 | Charges for D, E & F Bldg Road Excavation work by Bucket & Shifting it inside. | 100 |  | 105255 | 2024-02-12 | 142935.72 | 2024-03-20 15:55 | -40258.32 | SHIVAM ENTERPRISES
Backfilling | N/C | N/C | SHIVAM ENTERPRISES | 828 | 2023-11-29 | D&E-Ent.Gate-Excavation & Backfilling | 100.542 | 60 | 0 | 6032.52 | 0 | 2024-02-11 16:00 | Charges for Backfilling work for Main Gate Footing near D-Bldg. | 100 |  | 105255 | 2024-02-12 | 142935.72 | 2024-03-20 15:55 | -136903.2 | SHIVAM ENTERPRISES
Painting work (M+L) -BC | N/C | N/C | VEER BHADRA ENTERPRISES | 850 | 2023-12-12 | Altus& Arcadia-Divider-Paint Work | 2028.81 | 10 | 0 | 20288.1 | 3651.86 | 2024-01-08 | Material supply & Labour charges for Painting work includes 1 Coat Primer and 2 Coat Paint for Divider Kerbs D.P Road infront of site. | 100 |  | 104505 | 2024-01-08 | 20288.1 | 2024-02-09 11:07 | 0 | VEER BHADRA ENTERPRISES
RCC Work - DCH | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work D& E-Entrance Gate RCC Labour | 0.6 | 300000 | 0 | 72000 | 12960 | 2024-02-03 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 105066 | 2024-02-05 | 144000 | 2024-03-02 12:25 | -72000 | ROHIT CONSTRUCTION
RCC Work - DEn | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work F-Entrance Gate RCC Labour | 0.6 | 300000 | 0 | 72000 | 12960 | 2024-02-03 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 105066 | 2024-02-05 | 144000 | 2024-03-02 12:25 | -72000 | ROHIT CONSTRUCTION
RCC Work - DCH | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work D& E-Entrance Gate RCC Labour | 1 | 300000 | 0 | 180000 | 32400 | 2024-04-08 | After Completion of all RCC Work Above Slab-Column, Beam,Elevation including shuttering,Deshuttering,Reinforcement & Concreting. | 60 |  | 106714 | 2024-04-08 | 324000 | 2024-04-25 11:25 | -144000 | ROHIT CONSTRUCTION
RCC Work - DEn | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work F-Entrance Gate RCC Labour | 0.8 | 300000 | 0 | 144000 | 25920 | 2024-04-08 | After Completion of all RCC Work Above Slab-Column, Beam,Elevation including shuttering,Deshuttering,Reinforcement & Concreting. | 60 |  | 106714 | 2024-04-08 | 324000 | 2024-04-25 11:25 | -180000 | ROHIT CONSTRUCTION
RCC Work - DEn | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work F-Entrance Gate RCC Labour | 0.4 | 300000 | 0 | 48000 | 8640 | 2024-01-23 16:28 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 104851 | 2024-01-29 | 96000 | 2024-03-07 11:22 | -48000 | ROHIT CONSTRUCTION
RCC Work - DCH | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work D& E-Entrance Gate RCC Labour | 0.4 | 300000 | 0 | 48000 | 8640 | 2024-01-23 16:28 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 104851 | 2024-01-29 | 96000 | 2024-03-07 11:22 | -48000 | ROHIT CONSTRUCTION
Rebaring work 16mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | D&F Bldg. Entrance Gate Rebaring Work | 2 | 500 | 0 | 1000 | 180 | 2024-07-22 11:44 | Labour charges for 16mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D & F-Entrance Gate | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -104235 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 896 | 2023-12-29 | D&F Bldg. Entrance Gate Rebaring Work | 18 | 260 | 0 | 4680 | 842.4 | 2024-07-22 11:44 | Labour charges for 12mm Dia. Bar Rebarring work with 200mm Depth using Hilti RE-500 for D & F-Entrance Gate | 100 |  | 109441 | 2024-07-30 | 105235 | 1900-01-01 | -100555 | AVCON TECHNICS PVT LTD
RCC Work - Mkt | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-Retaining Wall -RCC-East Side Compound Wall | 495.144 | 210 | 0 | 103980.24 | 0 | 2024-03-01 19:02 | Labour charges for RCC Work for Retaining wall (400 mm thick) including Shuttering, Reinforcement & Concreting work for East side Compound wall. | 100 |  | 105725 | 2024-03-04 | 229430.71 | 2024-03-18 12:07 | -125450.47 | VIJAY MOHITE
Excavation Manually | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Excavation & Backfilling Work-East Side Compound Wall | 62.976 | 625 | 0 | 39360 | 0 | 2024-03-01 19:02 | Labour charges for Manual Excavation work for Compound wall Footing & Retaining wall to East side Compound wall. | 100 |  | 105725 | 2024-03-04 | 229430.71 | 2024-03-18 12:07 | -190070.71 | VIJAY MOHITE
PCC Work | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-PCC- Work-East Side Compound Wall | 871.884 | 8 | 0 | 6975.072 | 0 | 2024-03-01 19:02 | Labour charges for PCC Work for Raft for East side Compound wall RCC Work. | 100 |  | 105725 | 2024-03-04 | 229430.71 | 2024-03-18 12:07 | -222455.638 | VIJAY MOHITE
RCC Work - Mkt | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-Raft-RCC-East Side Compound Wall | 753.48 | 105 | 0 | 79115.4 | 0 | 2024-03-01 19:02 | Labour charges for RCC Work for Raft including Shuttering, Reinforcement & Concreting work for East side Compound wall. | 100 |  | 105725 | 2024-03-04 | 229430.71 | 2024-03-18 12:07 | -150315.31 | VIJAY MOHITE
PCC Work | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-PCC- Work-East Side Compound Wall | 348.75 | 8 | 0 | 2790 | 0 | 2024-06-17 17:45 | Labour charges for PCC Work for Raft for East side Compound wall RCC Work. | 100 |  | 108436 | 2024-06-17 | 302432.99 | 2024-07-05 11:37 | -299642.99 | VIJAY MOHITE
RCC Work - Mkt | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-Raft-RCC-East Side Compound Wall | 296.0108 | 105 | 0 | 31081.134 | 0 | 2024-06-17 17:50 | Labour charges for RCC Work for Raft including Shuttering, Reinforcement & Concreting work for East side Compound wall. | 100 |  | 108436 | 2024-06-17 | 302432.99 | 2024-07-05 11:37 | -271351.856 | VIJAY MOHITE
Excavation Manually | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Excavation & Backfilling Work-East Side Compound Wall | 429.0202 | 625 | 0 | 268137.625 | 0 | 2024-04-29 11:55 | Labour charges for Manual Excavation work for Compound wall Footing & Retaining wall to East side Compound wall. | 100 |  | 107216 | 2024-04-30 | 268137.63 | 2024-05-28 19:08 | -0.005 | VIJAY MOHITE
RCC Work - Mkt | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-Retaining Wall -RCC-East Side Compound Wall | 629.586 | 210 | 0 | 132213.06 | 0 | 2024-06-17 17:58 | Labour charges for RCC Work for Retaining wall (400 mm thick) including Shuttering, Reinforcement & Concreting work for East side Compound wall. | 100 |  | 108436 | 2024-06-17 | 302432.99 | 2024-07-05 11:37 | -170219.93 | VIJAY MOHITE
RCC Work - Mkt | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Altus-Retaining Wall -RCC-East Side Compound Wall | 649.28 | 210 | 0 | 136348.8 | 0 | 2024-06-17 17:54 | Labour charges for RCC Work for Retaining wall (300 mm thick) including Shuttering, Reinforcement & Concreting work for East side Compound wall. | 100 |  | 108436 | 2024-06-17 | 302432.99 | 2024-07-05 11:37 | -166084.19 | VIJAY MOHITE
Excavation Manually | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Excavation & Backfilling Work-East Side Compound Wall | 42.5038 | 625 | 0 | 26564.875 | 0 | 2024-05-05 12:56 | Labour charges for Manual Excavation work for Compound wall Footing & Retaining wall to East side Compound wall. | 100 | JCB bill 02-02 to 22-04 | 107395 | 2024-05-07 | 26564.88 | 2024-05-28 19:01 | -0.005 | SHIVAM ENTERPRISES
Excavation Manually | N/C | N/C | VIJAY MOHITE | 903 | 2024-01-09 | Excavation & Backfilling Work-East Side Compound Wall | 139.02 | 575 | 0 | 79936.5 | 0 | 2024-07-23 19:06 | Labour charges for Manual Excavation work for compound wall Footing & Retaining wall to East side compound wall. | 100 |  | 109391 | 2024-07-29 | 79936.5 | 1900-01-01 | 0 | VIJAY MOHITE
Earthing Work (M) | N/C | N/C | ITORRENT INDUSTRIES PVT LTD | 939 | 2024-02-19 | Borewell Earthing Work | 75 | 1700 | 0 | 127500 | 22950 | 2024-06-25 16:42 | Material supply charges of GI Earthing 76mm x 3mtr with 50kg BFC Bag for Bore Drilling Earthing work. | 100 |  | 108628 | 2024-06-27 | 177300 | 2024-06-27 20:05 | -49800 | ITORRENT INDUSTRIES PVT LTD
Earthing Work (M) | N/C | N/C | ITORRENT INDUSTRIES PVT LTD | 939 | 2024-02-19 | Borewell Earthing Work | 6 | 2900 | 0 | 17400 | 3132 | 2024-06-25 16:42 | Material supply charges of Copper bonded Electrode 76mm x 3mtr with 50kg BFC Bag for Bore Drilling Earthing work. | 100 |  | 108628 | 2024-06-27 | 177300 | 2024-06-27 20:05 | -159900 | ITORRENT INDUSTRIES PVT LTD
Transport Charges | N/C | N/C | ITORRENT INDUSTRIES PVT LTD | 939 | 2024-02-19 | Borewell Earthing Work | 81 | 100 | 0 | 8100 | 1458 | 2024-06-25 16:43 | Transportation Charges for GI Earthing & Copper Bonded Electrode for Bore Drilling Earthing work including Loading,Unloading,shifting,wastage,Profit & all other compliance etc. | 100 |  | 108628 | 2024-06-27 | 177300 | 2024-06-27 20:05 | -169200 | ITORRENT INDUSTRIES PVT LTD
EPC Pit Cover (Green) (M) | N/C | N/C | ITORRENT INDUSTRIES PVT LTD | 939 | 2024-02-19 | Borewell Earthing Work | 81 | 300 | 0 | 24300 | 4374 | 2024-06-25 17:15 | Material supply charges of EPC Pit Cover (Green) for GI Earthing & Copper Bonded Electrode Bore Drilling Earthing work. | 100 |  | 108628 | 2024-06-27 | 177300 | 2024-06-27 20:05 | -153000 | ITORRENT INDUSTRIES PVT LTD
Earthing Work (L) | N/C | N/C | ITORRENT INDUSTRIES PVT LTD | 940 | 2024-02-19 | Borewell Earthing Work | 75 | 1700 | 0 | 127500 | 22950 | 2024-06-25 16:37 | Labour charges for GI Earthing work 76mm x 3mtr with 50 Kg BFC Bag including Bore Drilling, Installation, Loading,Unloading,shifting,wastage,Profit & all other compliance etc. | 100 |  | 108629 | 2024-06-27 | 137700 | 2024-07-05 11:29 | -10200 | ITORRENT INDUSTRIES PVT LTD
Earthing Work (L) | N/C | N/C | ITORRENT INDUSTRIES PVT LTD | 940 | 2024-02-19 | Borewell Earthing Work | 6 | 1700 | 0 | 10200 | 1836 | 2024-06-25 16:38 | Labour charges for Copper Bonded Electrode 76mm x 3mtr with 50 Kg BFC Bag including Bore Drilling, Installation, Loading,Unloading,shifting,wastage,Profit & all other compliance etc. | 100 |  | 108629 | 2024-06-27 | 137700 | 2024-07-05 11:29 | -127500 | ITORRENT INDUSTRIES PVT LTD
GI Earthing Patti 25x3 (M) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 961 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 54.31 | 101.2 | 0 | 5496.172 | 989.32 | 2024-07-29 17:32 | Material supply charges for providing of 25mm x 3mm GI Earthing patti for D, E & F Bldg Development work. | 100 |  | 109427 | 2024-07-29 | 39309.62 | 1900-01-01 | -33813.448 | ADITI POWER CARE AND ENTERPRISES
GI Earthing Patti 50x6 (M) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 961 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 334.125 | 101.2 | 0 | 33813.45 | 6086.42 | 2024-07-29 17:32 | Material supply charges for providing of 50mm x 6mm GI Earthing patti for D, E & F building Development work. | 100 |  | 109427 | 2024-07-29 | 39309.62 | 1900-01-01 | -5496.17 | ADITI POWER CARE AND ENTERPRISES
Earthing Patti 25x3 (L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 962 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 90.52 | 50 | 0 | 4526 | 814.68 | 2024-07-29 17:33 | Labour charges for Erection, testing& commissioning GI earthing Patti(25mmx 3mm) of approved makes confirming to IS 3043:1987. The strip shall run on floor/ ceiling/ walls, from the equipments to the nearest pit with necessary accessories. | 100 |  | 109429 | 2024-07-29 | 15218 | 1900-01-01 | -10692 | ADITI POWER CARE AND ENTERPRISES
GI Earthing Patti 50 x 6mm (L) | N/C | N/C | ADITI POWER CARE AND ENTERPRISES | 962 | 2024-04-09 | D,E, F & Development-Earthing Patti Work | 133.65 | 80 | 0 | 10692 | 1924.56 | 2024-07-29 17:33 | Labour charges for Erection, testing& commissioning GI earthing Patti(50mmx 6mm) of approved makes confirming to IS 3043:1987. The strip shall run on floor/ ceiling/ walls, from the equipments to the nearest pit with necessary accessories. | 100 |  | 109429 | 2024-07-29 | 15218 | 1900-01-01 | -4526 | ADITI POWER CARE AND ENTERPRISES