## Work_Completion_Browse638587289
Work Completion Browse
Project : GANGA ALTUS
Labour : Floor Guard Removing & Acid Wash
From Date : 08/08/2024 To date: 08/08/2024
Page 1 of 1
Total Records: 34 Records 1 to 34
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1701-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1403-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1501-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1503-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1504-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-2204-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1703-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1704-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | PAPPU BAGELA | 487 | 2022-07-15 | D-1301-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | UBALE TRANSPORTS AND WATER SUPPLIERS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1108-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1707-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1105-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1205-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1708-2BHK Flooring & Tiling Work | 143.59 | 2 | 0 | 287.18 | 51.7 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1506-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1107-2BHK Vitrified Flooring Work | 509.56 | 2 | 0 | 1019.12 | 183.44 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Flooring & Tiling Work | 166.84 | 2 | 0 | 333.68 | 60.06 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS
Floor Guard Removing & Acid Wash | N/C | N/C | R.M.Marbles | 488 | 2022-07-15 | D-1505-3BHK Vitrified Flooring Work | 669.46 | 2 | 0 | 1338.92 | 241 | 2024-08-08 | Labour Charges for- Floor Guard removing & Acid wash work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MARSH HOUSEKEEPING SOLUTIONS