## Work_Completion_Browse638588043
Work Completion Browse
Project : GANGA ARCADIA - A BUILDING
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 59 Records 1 to 59
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
JCB Charges | N/C | N/C | DRAUPADA EARTHMOVERS | 10 | 2021-07-28 | JCB Work on site | 18 | 800 | 0 | 14400 | 2592 | 2021-08-19 | JCB Bucket total hours for Excavation, Plot Levelling Work, Demolishing Work. | 100 |  | 91253 | 2021-08-19 | 14400 | 2021-08-23 14:46 | 0 | DRAUPADA EARTHMOVERS
Department Labour-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 15 | 2021-12-29 | Barrication Work (L) | 35 | 600 | 0 | 21000 | 3780 | 2022-02-19 | VNE Infra Barrication Work. | 100 |  | 93540 | 2022-02-21 | 21000 | 1900-01-01 | 0 | VNE INFRA PROJECTS P LTD
Department Labour-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 15 | 2021-12-29 | Barrication Work (L) | 20 | 600 | 0 | 12000 | 0 | 2022-09-21 | Ritu Enterprises Barrication Work. | 100 |  | 96320 | 2022-09-22 | 12000 | 2022-10-12 12:01 | 0 | KANU KALIPADA BALA
Department Labour-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 15 | 2021-12-29 | Barrication Work (L) | 1 | 20000 | 0 | 20000 | 3600 | 2022-02-19 | R.T.S Steel Barrication Work. | 100 |  | 96161 | 2022-09-08 | 20000 | 2022-09-15 17:13 | 0 | R.T.S. STEEL SERVICES
Fabrication Work | N/C | N/C | R.T.S. STEEL SERVICES | 18 | 2022-01-29 | Fabrication Work for site barrication | 800 | 10 | 0 | 8000 | 1440 | 2022-02-19 | Labour Charges for- Fabrication Work for Site Barrication | 100 |  | 96162 | 2022-09-08 | 8000 | 2022-09-15 17:13 | 0 | R.T.S. STEEL SERVICES
Labour Lumpsum - SOS | N/C | N/C | VIKAS GARADE | 19 | 2022-02-14 | Compound wall-video shooting | 1 | 10000 | 0 | 10000 | 0 | 2022-10-21 | A Building Video Shooting 4 Days. | 100 |  | 96845 | 2022-10-22 | 10000 | 2022-11-16 11:40 | 0 | VIKAS GARADE
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 1500 | 0 | 1500 | 270 | 2023-06-28 | Soil Analysis Test for the Month of MAY-2023 (4 x 1500) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -11000 | EHS Matrix Private Limited
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 1500 | 0 | 1500 | 270 | 2023-12-01 | Soil Analysis Test for the Month of NOV-2023 (4 x 1500) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -11100 | EHS Matrix Private Limited
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 8 | 1500 | 0 | 3000 | 540 | 2024-06-11 | Soil Analysis Test for the Month of MAY-2024 (4 x 1500) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -11100 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 20 | 100 | 0 | 500 | 90 | 2023-06-28 | Noise Test Day for the Month of MAY-2023 (10 x 125) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -12000 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 20 | 100 | 0 | 500 | 90 | 2023-12-01 | Noise Test Day for the Month of NOV-2023 (10 x 125) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -12100 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 20 | 100 | 0 | 500 | 90 | 2024-06-11 | Noise Test Day for the Month of MAY-2024 (10 x 125) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -13600 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 20 | 100 | 0 | 500 | 90 | 2023-06-28 | Noise Test Night for the Month of MAY-2023 (10 x 125) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -12000 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 20 | 100 | 0 | 500 | 90 | 2023-12-01 | Noise Test Night for the Month of NOV-2023 (10 x 125) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -12100 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 20 | 100 | 0 | 500 | 90 | 2024-06-11 | Noise Test Night for the Month of MAY-2024 (10 x 125) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -13600 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 16 | 1500 | 0 | 6000 | 1080 | 2023-06-28 | Ambient Air Test for the Month of MAY-2023 (5 x 1500) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -6500 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 16 | 1500 | 0 | 6000 | 1080 | 2023-12-01 | Ambient Air Test for the Month of NOV-2023 (5 x 1500) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -6600 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 16 | 1500 | 0 | 6000 | 1080 | 2024-06-11 | Ambient Air Test for the Month of MAY-2024 (5 x 1500) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -8100 | EHS Matrix Private Limited
Sewage Water Analysis | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 1200 | 0 | 1200 | 216 | 2023-06-28 | Untreated Effluent Sample for STP for the Month of MAY-2023 (2 x 1000) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -11300 | EHS Matrix Private Limited
Sewage Water Analysis | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 1200 | 0 | 1200 | 216 | 2023-12-01 | Untreated Effluent Sample for STP for the Month of NOV-2023 (2 x 1000) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -11400 | EHS Matrix Private Limited
Sewage Water Analysis | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 1200 | 0 | 1200 | 216 | 2024-06-11 | Untreated Effluent Sample for STP for the Month of MAY-2024 (2 x 1000) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -12900 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 8 | 900 | 0 | 1800 | 324 | 2023-06-28 | DG Stack Monitoring Report for the Month of MAY-2023 (5 x 900) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -10700 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 900 | 0 | 900 | 162 | 2023-12-01 | DG Stack Monitoring Report for the Month of NOV-2023 (5 x 900) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -11700 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 900 | 0 | 900 | 162 | 2024-06-11 | DG Stack Monitoring Report for the Month of MAY-2024 (5 x 900) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -13200 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 4 | 1000 | 0 | 1000 | 180 | 2023-06-28 | Drinking water for the Month of MAY-2023 (6 x 1000) | 25 |  | 100334 | 2023-06-28 | 12500 | 2023-07-11 14:12 | -11500 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 8 | 1000 | 0 | 2000 | 360 | 2023-12-01 | Drinking water for the Month of NOV-2023 (6 x 1000) | 25 |  | 103548 | 2023-12-01 | 12600 | 2023-12-16 17:31 | -10600 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 28 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | 8 | 1000 | 0 | 2000 | 360 | 2024-06-11 | Drinking water for the Month of MAY-2024 (6 x 1000) | 25 |  | 108305 | 2024-06-11 | 14100 | 2024-06-27 18:27 | -12100 | EHS Matrix Private Limited
Miscellaneous Expenses | N/C | N/C | PUNDLIK P MAHAJAN | 3 | 2021-03-26 | Misc Expenses | 0.8239 | 50000 | 0 | 41195 | 0 | 2021-04-30 | A Bldg Miscellaneous work | 100 |  | 90936 | 2021-07-21 | 50000 | 2021-09-24 18:48 | -8805 | PUNDLIK P MAHAJAN
Miscellaneous Expenses | N/C | N/C | PUNDLIK P MAHAJAN | 3 | 2021-03-26 | Misc Expenses | 0.146 | 50000 | 0 | 7300 | 0 | 2021-05-17 | A Bldg Miscellaneous work | 100 |  | 90936 | 2021-07-21 | 50000 | 2021-09-24 18:48 | -42700 | PUNDLIK P MAHAJAN
Miscellaneous Expenses | N/C | N/C | PUNDLIK P MAHAJAN | 3 | 2021-03-26 | Misc Expenses | 0.0301 | 50000 | 0 | 1505 | 0 | 2021-06-29 | A Bldg Miscellaneous work | 100 |  | 90936 | 2021-07-21 | 50000 | 2021-09-24 18:48 | -48495 | PUNDLIK P MAHAJAN
Fabrication work (L) | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | MS Box GI barrication work | 1638.966 | 17 | 0 | 27862.422 | 5015.24 | 2021-06-08 | Fabrication Work for fixing of MS Angle (50 x 5,25mm Bar & bottom 8mm bar) | 100 |  | 90484 | 2021-06-09 | 43716.27 | 2021-06-24 16:11 | -15853.848 | GURUDATTA KRUPA ENTERPRISES
Fabrication work (L) | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | MS Box GI barrication work | 298.584 | 22 | 0 | 6568.848 | 1182.4 | 2021-06-08 | Fabrication work for fixing of Sqaure Pipe (40 x 60) | 100 |  | 90484 | 2021-06-09 | 43716.27 | 2021-06-24 16:11 | -37147.422 | GURUDATTA KRUPA ENTERPRISES
GI Sheet Fixing | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | MS Box GI barrication work | 1682 | 5 | 0 | 8410 | 1513.8 | 2021-06-08 | GI Sheet Fixing | 100 |  | 90484 | 2021-06-09 | 43716.27 | 2021-06-24 16:11 | -35306.27 | GURUDATTA KRUPA ENTERPRISES
Tapping Screw- Den | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | MS Box GI barrication work | 350 | 2.5 | 0 | 875 | 157.5 | 2021-06-08 | Material Supply for Tapping Screw | 100 |  | 90484 | 2021-06-09 | 43716.27 | 2021-06-24 16:11 | -42841.27 | GURUDATTA KRUPA ENTERPRISES
GI Sheet Fixing (L) | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | GI Sheet Removing & fixing Work-Retaining Wall Side | 300 | 5 | 0 | 1500 | 270 | 2024-04-26 15:13 | Labour charges for GI Sheet fixing for Barrication work between Arcadia A Bldg & B-bldg side near Retaining wall. | 100 |  | 107205 | 2024-04-30 | 4306.05 | 1900-01-01 | -2806.05 | GURUDATTA KRUPA ENTERPRISES
G.I. Sheet Removing - SOI | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | GI Sheet Removing & fixing Work-Retaining Wall Side | 300 | 3 | 0 | 900 | 162 | 2024-04-26 15:13 | Labour charges for GI Sheet Removing for Barrication work between Arcadia A Bldg & B-bldg side near Retaining wall. | 100 |  | 107205 | 2024-04-30 | 4306.05 | 1900-01-01 | -3406.05 | GURUDATTA KRUPA ENTERPRISES
MS Angle Fixing | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | GI Sheet Removing & fixing Work-Retaining Wall Side | 84.99 | 15 | 0 | 1274.85 | 229.48 | 2024-04-26 15:13 | Labour charges for fixing MS Angle (50 x 50x 5mm) for Barrication work between Arcadia A Bldg & B-bldg side near Retaining wall. | 100 |  | 107205 | 2024-04-30 | 4306.05 | 1900-01-01 | -3031.2 | GURUDATTA KRUPA ENTERPRISES
MS Square Pipe (L) | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | GI Sheet Removing & fixing Work-Retaining Wall Side | 42.08 | 15 | 0 | 631.2 | 113.62 | 2024-04-26 15:13 | Labour charges for fixing MS Square pipe(50 x 50 x 5mm) for Barrication work between Arcadia A Bldg & B-bldg side near Retaining wall. | 100 |  | 107205 | 2024-04-30 | 4306.05 | 1900-01-01 | -3674.85 | GURUDATTA KRUPA ENTERPRISES
Frame work | N/C | N/C | GURUDATTA KRUPA ENTERPRISES | 5 | 2021-05-03 | Old Material cutting & Frame work | 1200 | 10 | 0 | 12000 | 2160 | 2021-12-25 | Labour Charges for MS Frame Making with old material available at site for Barrication & Flex work | 100 |  | 92858 | 2021-12-27 | 12000 | 1900-01-01 | 0 | GURUDATTA KRUPA ENTERPRISES
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.3978 | 45000 | -1 | 17901 | 0 | 2024-02-21 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JAN 2024 170012942535 | 105447 | 2024-02-21 | 17900 | 2024-02-21 11:16 | 1 | MSEDCL01170012942535
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.3704 | 45000 | 2 | 16668 | 0 | 2024-03-13 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF MARCH 2024 | 106045 | 2024-03-13 | 16670 | 2024-03-13 17:49 | -2 | MSEDCL01170012942535
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.3876 | 45000 | -2 | 17442 | 0 | 2024-04-11 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF MARCH 2024 | 106754 | 2024-04-11 | 17440 | 2024-04-11 16:44 | 2 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.2582 | 45000 | 1 | 11619 | 0 | 2024-06-10 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 108262 | 2024-06-10 | 11620 | 2024-06-10 18:21 | -1 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.7044 | 45000 | 2 | 31698 | 0 | 2024-07-12 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JUNE 2024 | 108994 | 2024-07-12 | 31700 | 2024-07-12 10:56 | -2 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.0118 | 45000 | -1 | 531 | 0 | 2024-07-23 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JUNE 2024 | 109292 | 2024-07-23 | 530 | 2024-07-23 15:08 | 1 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.1256 | 45000 | -2 | 5652 | 0 | 2024-07-23 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JULY 2024 | 109298 | 2024-07-23 | 5650 | 2024-07-23 18:40 | 2 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.0098 | 45000 | -1 | 441 | 0 | 2024-07-23 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JULY 2024 | 109299 | 2024-07-23 | 440 | 2024-07-23 18:40 | 1 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.0098 | 45000 | -1 | 441 | 0 | 2024-07-23 | Charges for Electricity Bills for Year 2023-24 | 100 | FOR THE MONTH OF JULY 2024 | 109300 | 2024-07-23 | 440 | 2024-07-23 18:40 | 1 | MSEDCL
GI Sheet Fixing (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 360 | 5 | 0 | 1800 | 0 | 2024-07-26 13:37 | Labour charges for Fixing of GI Sheet for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -8467.2 | SURESH RANGNATH SHITOLE
MS Angle 50 x 50 x 5mm | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 126.8 | 12 | 0 | 1521.6 | 0 | 2024-07-26 13:37 | Labour charges for Fixing of MS Angle 50x50x5mm for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -8745.6 | SURESH RANGNATH SHITOLE
M.S.Channel (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 204 | 12 | 0 | 2448 | 0 | 2024-07-26 13:37 | Labour charges for Fixing of MS C Channel 100mm for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -7819.2 | SURESH RANGNATH SHITOLE
MS Pipe 40 x 40 x 2mm (L) | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 146.9 | 12 | 0 | 1762.8 | 0 | 2024-07-26 13:37 | Labour charges for Fixing of MS Square Pipe 40x40x2mm for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -8504.4 | SURESH RANGNATH SHITOLE
GI Sheet Removing - DCW | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 300 | 2.5 | 0 | 750 | 0 | 2024-07-26 13:37 | Labour charges for GI Sheet Removing work for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -9517.2 | SURESH RANGNATH SHITOLE
Channel removing- SOSB | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 204 | 6 | 0 | 1224 | 0 | 2024-07-26 13:37 | Labour charges for MS Channel Removing work for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -9043.2 | SURESH RANGNATH SHITOLE
MS Angle Removing | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | Fabrication Work for Partition between A&B Bldg. | 126.8 | 6 | 0 | 760.8 | 0 | 2024-07-26 13:37 | Labour charges for MS Angle Removing work for Partition of A & B-Bldg. | 100 |  | 109373 | 2024-07-29 | 10267.2 | 1900-01-01 | -9506.4 | SURESH RANGNATH SHITOLE
Channel removing- SOSB | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | GI Sheet Removing & fixing Work-Retaining Wall Side | 58.2 | 6 | 0 | 349.2 | 0 | 2024-02-12 14:56 | Labour charges MS Channel (100x75x75) Removing work for A-Bldg Retaining wall side. | 100 |  | 106958 | 2024-04-19 | 12050.4 | 2024-05-06 12:26 | -11701.2 | SURESH RANGNATH SHITOLE
MS Channel Fixing BCo | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | GI Sheet Removing & fixing Work-Retaining Wall Side | 173.6 | 12 | 0 | 2083.2 | 0 | 2024-02-12 14:56 | Labour charges for MS Channel (100x75x75) Fixing work for A-Bldg Retaining wall side. | 100 |  | 106958 | 2024-04-19 | 12050.4 | 2024-05-06 12:26 | -9967.2 | SURESH RANGNATH SHITOLE
MS Angle Fixing | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | GI Sheet Removing & fixing Work-Retaining Wall Side | 541.5 | 12 | 0 | 6498 | 0 | 2024-02-12 14:56 | Labour charges for MS Angle (75x75x5mm) Fixing work for A-Bldg Retaining wall side. | 100 |  | 106958 | 2024-04-19 | 12050.4 | 2024-05-06 12:26 | -5552.4 | SURESH RANGNATH SHITOLE
G.I. Sheet Removing - SOI | N/C | N/C | SURESH RANGNATH SHITOLE | 67 | 2024-01-30 | GI Sheet Removing & fixing Work-Retaining Wall Side | 1040 | 3 | 0 | 3120 | 0 | 2024-02-12 14:56 | Labour charges for GI Sheet Remving work for A-Bldg Retaining wall side. | 100 |  | 106958 | 2024-04-19 | 12050.4 | 2024-05-06 12:26 | -8930.4 | SURESH RANGNATH SHITOLE