## Work_Completion_Browse638588044
Work Completion Browse
Project : GANGA ARCADIA - A BUILDING
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 20 Records 1 to 20
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Visiting Charges-AIE | N/C | N/C | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | 11 | 2021-10-22 | Vastu Consultancy Visit Charges | 1 | 25423.73 | 0 | 25423.73 | 4576.28 | 2021-10-28 | Vastu Consultancy Visiting Charges | 100 |  | 92257 | 2021-10-28 | 25423.73 | 2021-10-29 18:39 | 0 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 21 | 2022-06-03 | Liaisoning Consultancy Professional fees for liaisoning | 148600 | 3 | 0 | 22290 | 0 | 2022-06-29 | Issue of Appointment letter | 5 |  | 95281 | 2022-06-29 | 156034 | 2022-07-30 19:26 | -133744 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 21 | 2022-06-03 | Liaisoning Consultancy Professional fees for liaisoning | 148604.4444 | 3 | 0 | 66872 | 0 | 2022-06-29 | Submission of Drawing for Sanction | 15 |  | 95281 | 2022-06-29 | 156034 | 2022-07-30 19:26 | -89162 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 21 | 2022-06-03 | Liaisoning Consultancy Professional fees for liaisoning | 148604.4444 | 3 | 0 | 66872 | 0 | 2022-06-29 | Project Sanction and Certified Copies | 15 |  | 95281 | 2022-06-29 | 156034 | 2022-07-30 19:26 | -89162 | AYAZ RAFIK SHAIKH
Liasoning Consultancy (Architectural) | N/C | N/C | AYAZ RAFIK SHAIKH | 21 | 2022-06-03 | Liaisoning Consultancy Professional fees for liaisoning | 74300 | 3 | 0 | 22290 | 0 | 2024-05-14 | Set Back Approval and Plinth Checking | 10 |  | 107575 | 2024-05-14 | 22290 | 2024-05-14 15:27 | 0 | AYAZ RAFIK SHAIKH
Labour Lumsum | N/C | N/C | THREED SIGN | 27 | 2023-03-31 | 3D Rendering & Brochure Design Charges | 1 | 149000 | 0 | 44700 | 8046 | 2023-04-19 | During 1st Cut View | 30 |  | 99234 | 2023-04-19 | 75000 | 2023-04-24 11:08 | -30300 | THREED SIGN
Labour Lumsum | N/C | N/C | THREED SIGN | 27 | 2023-03-31 | 3D Rendering & Brochure Design Charges | 0.3389 | 149000 | 2.34 | 30297.66 | 5454 | 2023-04-19 | At time of approval of created content before final output | 60 |  | 99234 | 2023-04-19 | 75000 | 2023-04-24 11:08 | -44702.34 | THREED SIGN
Labour Lumsum | N/C | N/C | THREED SIGN | 27 | 2023-03-31 | 3D Rendering & Brochure Design Charges | 1 | 149000 | 0 | 14900 | 2682 | 2023-06-20 | At the time of Delivery | 10 |  | 100216 | 2023-06-20 | 74000 | 2023-07-11 12:50 | -59100 | THREED SIGN
Labour Lumsum | N/C | N/C | THREED SIGN | 27 | 2023-03-31 | 3D Rendering & Brochure Design Charges | 0.6611 | 149000 | -2.34 | 59102.34 | 10638 | 2023-06-20 | At time of approval of created content before final output | 60 |  | 100216 | 2023-06-20 | 74000 | 2023-07-11 12:50 | -14897.66 | THREED SIGN
Professional Fees. | N/C | N/C | ZOPATE ELECTRICAL CONSULTANTS PVT LTD | 32 | 2023-08-09 | Professional Consultancy for Electrical Work | 1 | 100000 | 0 | 25000 | 4500 | 2023-08-24 | Advance Along with Work Order | 25 |  | 101422 | 2023-08-24 | 50000 | 2023-09-04 11:57 | -25000 | ZOPATE ELECTRICAL CONSULTANTS PVT LTD
Professional Fees. | N/C | N/C | ZOPATE ELECTRICAL CONSULTANTS PVT LTD | 32 | 2023-08-09 | Professional Consultancy for Electrical Work | 1 | 100000 | 0 | 25000 | 4500 | 2023-08-24 | After Submission of Basic Env. Data | 25 |  | 101422 | 2023-08-24 | 50000 | 2023-09-04 11:57 | -25000 | ZOPATE ELECTRICAL CONSULTANTS PVT LTD
Professional Fees. | N/C | N/C | ZOPATE ELECTRICAL CONSULTANTS PVT LTD | 32 | 2023-08-09 | Professional Consultancy for Electrical Work | 1 | 100000 | 0 | 25000 | 4500 | 2023-10-17 | After Submission of Final Env. Data | 25 |  | 102721 | 2023-10-17 | 50000 | 2023-10-18 11:40 | -25000 | ZOPATE ELECTRICAL CONSULTANTS PVT LTD
Professional Fees. | N/C | N/C | ZOPATE ELECTRICAL CONSULTANTS PVT LTD | 32 | 2023-08-09 | Professional Consultancy for Electrical Work | 1 | 100000 | 0 | 25000 | 4500 | 2023-10-17 | After Attending the EC Meeting | 25 |  | 102721 | 2023-10-17 | 50000 | 2023-10-18 11:40 | -25000 | ZOPATE ELECTRICAL CONSULTANTS PVT LTD
Plumbing Consultancy - | N/C | N/C | URJAL CONSULTANT PRIVATE LIMITED | 33 | 2023-08-12 | Professional Consultancy for Plumbing Work | 174636 | 2 | 0 | 69854.4 | 12573.8 | 2023-10-17 | Advance Along With Work Order | 20 |  | 102723 | 2023-10-17 | 69854.4 | 2023-10-18 11:46 | 0 | URJAL CONSULTANT PRIVATE LIMITED
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 49 | 2023-10-11 | A Bldg RCC Consultancy | 116180.043 | 5.75 | 0 | 66803.5247 | 12024.64 | 2023-10-17 | Advance / on signing of Agreement. | 10 |  | 102727 | 2023-10-17 | 202170.04 | 2023-10-18 11:44 | -135366.5153 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 49 | 2023-10-11 | A Bldg RCC Consultancy | 116180.043 | 5.75 | 0 | 66803.5247 | 12024.64 | 2023-10-17 | On Completion of Concept design stage (Cloumn, Beam, Slab framing plan and DBR) | 10 |  | 102727 | 2023-10-17 | 202170.04 | 2023-10-18 11:44 | -135366.5153 | G.A.BHILARE CONSULTANTS PVT LTD
RCC Consultancy | N/C | N/C | G.A.BHILARE CONSULTANTS PVT LTD | 49 | 2023-10-11 | A Bldg RCC Consultancy | 59620 | 5.75 | 0 | 68563 | 12341.34 | 2023-10-17 | On issue of Foundation drawing. | 20 |  | 102727 | 2023-10-17 | 202170.04 | 2023-10-18 11:44 | -133607.04 | G.A.BHILARE CONSULTANTS PVT LTD
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 76 | 2024-03-13 | Contract Labour act Registration & Compliance | 20 | 350 | 0 | 7000 | 1260 | 2024-04-08 | BOCW Registration under contract Labour Act Registration from 1st March 2024 to 31st December 2025. | 100 |  | 106666 | 2024-04-08 | 7000 | 2024-04-09 14:57 | 0 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration &Compliance. | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 76 | 2024-03-13 | Contract Labour act Registration & Compliance | 15 | 350 | 0 | 5250 | 945 | 2024-04-08 | BOCW Registration under contract Labour Act Registration from 1st March 2024 to 31st December 2025. | 100 |  | 106668 | 2024-04-08 | 5500 | 2024-04-09 14:58 | -250 | NIKISHA CONSULTANCY SERVICES
B.O.C.W. Act Registration | N/C | N/C | NIKISHA CONSULTANCY SERVICES | 76 | 2024-03-13 | Contract Labour act Registration & Compliance | 1 | 250 | 0 | 250 | 45 | 2024-04-08 | Charges for B.O.C.W Act Registration | 100 |  | 106668 | 2024-04-08 | 5500 | 2024-04-09 14:58 | -5250 | NIKISHA CONSULTANCY SERVICES