## Work_Completion_Browse638588046
Work Completion Browse
Project : GANGA ARCADIA - A BUILDING
From Date : 01/01/2000 To date: 01/01/2000
Page 1 of 1
Total Records: 17 Records 1 to 17
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
12" Dia Derex Pipe line | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 2 | 2021-03-22 | Drainage Line Work (Temporary) | 120 | 12 | 0 | 1440 | 259.2 | 2021-06-09 | 12" Dia Derex Pipe Line for B Bldg Drainage line | 100 |  | 90483 | 2021-06-09 | 3440 | 2021-09-03 18:35 | -2000 | SHINDE PLUMBING CONTRACTOR
Chamber 24" x 36" (3ft Ht) - UTI | N/C | N/C | SHINDE PLUMBING CONTRACTOR | 2 | 2021-03-22 | Drainage Line Work (Temporary) | 2 | 1000 | 0 | 2000 | 360 | 2021-06-09 | 24" x 36" Chamber Work for PCC,BBM Plaster cover fixing work | 100 |  | 90483 | 2021-06-09 | 3440 | 2021-09-03 18:35 | -1440 | SHINDE PLUMBING CONTRACTOR
H.T. & L.T. Line Shifting- UTI | N/C | N/C | ARYA CONSULTANCY | 73 | 2024-02-22 | A-Electrical Work-HT & LT line shifting | 1 | 100000 | 0 | 20000 | 3600 | 2024-05-09 | File Submission | 20 |  | 107446 | 2024-05-09 | 50000 | 2024-05-15 14:43 | -30000 | ARYA CONSULTANCY
H.T. & L.T. Line Shifting- UTI | N/C | N/C | ARYA CONSULTANCY | 73 | 2024-02-22 | A-Electrical Work-HT & LT line shifting | 1 | 100000 | 0 | 20000 | 3600 | 2024-05-09 | Site Visit | 20 |  | 107446 | 2024-05-09 | 50000 | 2024-05-15 14:43 | -30000 | ARYA CONSULTANCY
H.T. & L.T. Line Shifting- UTI | N/C | N/C | ARYA CONSULTANCY | 73 | 2024-02-22 | A-Electrical Work-HT & LT line shifting | 1 | 100000 | 0 | 10000 | 1800 | 2024-05-09 | Estimate | 10 |  | 107446 | 2024-05-09 | 50000 | 2024-05-15 14:43 | -40000 | ARYA CONSULTANCY
OWC Inst. Test & Commissioning | N/C | N/C | DEFIANT RENEWABLES PRIVATE LIMITED | 75 | 2024-03-04 | OWC System | 1 | 812000 | 0 | 568400 | 68208 | 2024-05-10 | Against Material Delivery at Site | 70 |  | 108621 | 2024-06-27 | 568400 | 2024-06-27 18:33 | 0 | DEFIANT RENEWABLES PRIVATE LIMITED
UGWT Labour | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | UGWT- RCC Work (L) | 267772 | 4.25 | 0 | 284507.75 | 51211.4 | 2024-07-06 15:34 | Upto Raft all Work including | 25 |  | 108864 | 2024-07-08 | 674818.15 | 2024-08-05 13:30 | -390310.4 | ROHIT CONSTRUCTION
UGWT Labour | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | UGWT- RCC Work (L) | 133886 | 4.25 | 0 | 199155.425 | 35847.98 | 2024-07-19 19:19 | RCC Work for all Pardi work | 35 |  | 109265 | 2024-07-22 | 589575.68 | 2024-08-05 13:23 | -390420.255 | ROHIT CONSTRUCTION
PCC - SO | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | Pump Room - RCC Work (L) | 660 | 8 | 0 | 5280 | 950.4 | 2024-07-06 15:21 | Labour charges for PCC Work for STP & UGWT Pumproom including shuttering & Concreting work. | 100 |  | 108864 | 2024-07-08 | 674818.15 | 2024-08-05 13:30 | -669538.15 | ROHIT CONSTRUCTION
PCC - SO | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | Pump Room - RCC Work (L) | 660 | 8 | 0 | 5280 | 950.4 | 2024-07-19 19:35 | Labour charges for PCC Work for STP & UGWT Pumproom including shuttering & Concreting work. | 100 |  | 109265 | 2024-07-22 | 589575.68 | 2024-08-05 13:23 | -584295.68 | ROHIT CONSTRUCTION
RCC Raft - DCW | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | Pump Room - RCC Work (L) | 660 | 85 | 0 | 56100 | 10098 | 2024-07-06 15:21 | Labour charges for RCC Work for Raft at STP & UGWT Pumproom including Shuttering, Reinforcement & Concreting work. | 100 |  | 108864 | 2024-07-08 | 674818.15 | 2024-08-05 13:30 | -618718.15 | ROHIT CONSTRUCTION
RCC Raft - DCW | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | Pump Room - RCC Work (L) | 661.2924 | 85 | 0 | 56209.854 | 10117.78 | 2024-07-19 19:37 | Labour charges for RCC Work for Raft at STP & UGWT Pumproom including Shuttering, Reinforcement & Concreting work. | 100 |  | 109265 | 2024-07-22 | 589575.68 | 2024-08-05 13:23 | -533365.826 | ROHIT CONSTRUCTION
RCC Work STP | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | STP-170KLD-RCC Work (L) | 221129.68 | 4.25 | 0 | 234950.285 | 42291.06 | 2024-06-13 | Upto Raft all work including | 25 |  | 108323 | 2024-06-14 | 234950.29 | 2024-06-26 11:32 | -0.005 | ROHIT CONSTRUCTION
RCC Work STP | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | STP-170KLD-RCC Work (L) | 221129.68 | 4.25 | 0 | 328930.399 | 59207.48 | 2024-07-06 14:39 | RCC Work for all Pardi work | 35 |  | 108864 | 2024-07-08 | 674818.15 | 2024-08-05 13:30 | -345887.751 | ROHIT CONSTRUCTION
RCC Work STP | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | STP-170KLD-RCC Work (L) | 221129.68 | 4.25 | 0 | 328930.399 | 59207.48 | 2024-07-19 19:08 | RCC Work for Top Slab | 35 |  | 109265 | 2024-07-22 | 589575.68 | 2024-08-05 13:23 | -260645.281 | ROHIT CONSTRUCTION
Membrane Horizontal Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 86 | 2024-06-01 | A-STP-170KLD,UGWT,Pumproom-External Waterproofing Work | 2791 | 13 | 0 | 36283 | 6530.94 | 2024-06-08 | Labour charges for STP,UGWT & Pumproom Horizontal Waterproofing,Cleaning 120GSM fleeces as cushion on entire pcc area 250 GSM Rigidex-F Membrane over fleece just 300mm,make Rigidex-F Membrane joint waterproof,etc | 100 |  | 108149 | 2024-06-10 | 36283 | 2024-06-24 12:32 | 0 | AQUARIUS WATERPROOFING
Membrane Horizontal Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 87 | 2024-06-01 | A-STP-170KLD,UGWT,Pumproom-External Waterproofing Work | 2791 | 34 | 0 | 94894 | 17080.92 | 2024-06-08 | Material supply charges of Horizontal Membrane Waterproofing work for STP,UGWT & Pumproom with Rigidex-F Membrane. | 100 |  | 108150 | 2024-06-10 | 94894 | 2024-06-24 12:32 | 0 | AQUARIUS WATERPROOFING