## Work_Completion_Browse638593239
Work Completion Browse
Project : GANGA ALTUS
Contractor : VIJAY MOHITE
Executed By : VIJAY MOHITE
From Date : 18/03/2023 To date: 18/03/2023
Page 1 of 1
Total Records: 7 Records 1 to 7
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 653.72 | 290 | 0 | 189578.8 | 0 | 2023-10-20 15:06 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 |  | 102866 | 2023-10-20 | 201003.8 | 2023-11-01 14:27 | -11425 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 114.25 | 100 | 0 | 11425 | 0 | 2023-10-20 15:06 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 102866 | 2023-10-20 | 201003.8 | 2023-11-01 14:27 | -189578.8 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 408.57 | 100 | 0 | 40857 | 0 | 2024-06-16 12:33 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -123486.75 | VIJAY MOHITE
RCC Substructure Labour (B-up area)- BC | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 539.47 | 100 | 0 | 53947 | 0 | 2023-09-13 | Labour charges for RCC Work for Substructure including PCC Below Footing,soling,Footing RCC Work,pile breaking,pile cap casting,plinth beam,plinth filling, PCC at plinth with steel work for Transformer room. | 100 |  | 101847 | 2023-09-15 | 53947 | 1900-01-01 | 0 | VIJAY MOHITE
Pile Breaking -DCW | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 10 | 500 | 0 | 5000 | 0 | 2024-06-16 12:27 | Labour charges for Pile Breaking Work for Transformer Room. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -159343.75 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 817.15 | 145 | 0 | 118486.75 | 0 | 2024-06-16 12:27 | Labour charges for RCC Work for Superstructure due to increase in height more than 5 Meter. | 100 |  | 108392 | 2024-06-17 | 164343.75 | 2024-06-26 11:41 | -45857 | VIJAY MOHITE
RCC Superstructure (B-up area) | N/C | N/C | VIJAY MOHITE | 638 | 2023-03-18 | Transformer Room-RCC Work (L) | 219.7855 | 290 | 0 | 63737.795 | 0 | 2024-06-17 20:05 | Labour charges for RCC Work for Super-structure including columns above plinth beam, Beams and slabs for Transformer Room. | 100 | Final Bill For Remaining 20% | 108503 | 2024-06-24 | 63737.8 | 2024-07-05 11:37 | -0.005 | VIJAY MOHITE