## Work_Completion_Browse638596684
Work Completion Browse
Project : GANGA ALTUS
Executed By : SHUBHAM SURENDRA BAHADUR SINGH
From Date : 18/08/2024 To date: 18/08/2024
Page 1 of 1
Total Records: 48 Records 1 to 48
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-001-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-002-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-003-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-004-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-005-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-006-3BHK Internal Painting Work | 1809 | 0.75 | 0 | 1356.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-007-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Wall | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-008-2BHK Internal Painting Work | 1337 | 0.75 | 0 | 1002.75 | 0 | 2024-08-19 | Labour Charges for- Water Base Primer for Wall.All Equipments, tools & transportation of all raw material from store to site to be in contractors scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-001-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-002-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-003-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-004-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-005-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-006-3BHK Internal Painting Work | 1809 | 1 | 0 | 1809 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-007-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Wall Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-008-2BHK Internal Painting Work | 1337 | 1 | 0 | 1337 | 0 | 2024-08-19 | Labour Charges for- 1st Coat of OBD Paint for Wall. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-001-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-002-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-003-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-004-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-005-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-006-3BHK Internal Painting Work | 748 | 0.75 | 0 | 561 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-007-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
Primer Water Base- Ceiling | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-008-2BHK Internal Painting Work | 556 | 0.75 | 0 | 417 | 0 | 2024-08-19 | Labour Charges for- Water base primer for Ceiling Paint. Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-001-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-002-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-003-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-004-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-005-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-006-3BHK Internal Painting Work | 748 | 1 | 0 | 748 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-007-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
1st Coat Ceiling Paint | N/C | N/C | YUGESH KUMAR | 371 | 2022-02-05 | D-008-2BHK Internal Painting Work | 556 | 1 | 0 | 556 | 0 | 2024-08-19 | Labour Charges for- 1st Coat OBD Paint for Ceiling.Tools,Equipments and transportation of all raw material form store to site to be in contractor scope. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 1812 | 1 | 0 | 1812 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Wall Putty - | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 1353 | 1 | 0 | 1353 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Putty for wall. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-001-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-002-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-003-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-004-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-005-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-006-3BHK Putty Work (L) | 770 | 1 | 0 | 770 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-007-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH
2nd Coat Ceiling Putty | N/C | N/C | YUGESH KUMAR | 386 | 2022-02-21 | D-008-2BHK Putty Work (L) | 577 | 1 | 0 | 577 | 0 | 2024-08-19 | Labour Charges for- 2nd Coat Ceiling putty. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHUBHAM SURENDRA BAHADUR SINGH