## Work_Completion_Browse638598388
Work Completion Browse
Project : GANGA ASMI
From Date : 01/06/2024 To date: 01/06/2024
Page 1 of 1
Total Records: 126 Records 1 to 126
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Liasoning Consultancy (Architectural) | N/C | N/C | KIMAYA ASSOCIATES | 132 | 2021-05-31 | Wing-1(Podium To 28th Fl) Liasoning Architect Consultancy - | 304898.26 | 4 | 0 | 121959.304 | 21952.68 | 2024-06-29 | Setback approval & Plinth checking | 10 |  | 108643 | 2024-06-29 | 121959.3 | 1900-01-01 | 0.004 | KIMAYA ASSOCIATES
Liasoning Consultancy (Architectural) | N/C | N/C | KIMAYA ASSOCIATES | 132 | 2021-05-31 | A Building Liasoning Architect Consultancy | 46897.46 | 4 | 0 | 18758.984 | 3376.62 | 2024-06-29 | Setback approval & Plinth checking | 10 |  | 108644 | 2024-06-29 | 18758.98 | 1900-01-01 | 0.004 | KIMAYA ASSOCIATES
Liasoning Consultancy (Architectural) | N/C | N/C | KIMAYA ASSOCIATES | 132 | 2021-05-31 | Parking - Liasoning Architect Consultancy | 329612.73 | 4 | 0 | 65922.546 | 11866.06 | 2024-06-29 | Issue of Appointment Letter | 5 |  | 108642 | 2024-06-29 | 65922.55 | 1900-01-01 | -0.004 | KIMAYA ASSOCIATES
RCC Consultancy | N/C | N/C | JW CONSULTANTS LLP | 156 | 2021-08-30 | Wing-1 RCC Consultancy | 38095.2381 | 7.5 | 0 | 100000 | 18000 | 2024-06-29 | During Construction stage on pro-rata basis. | 35 |  | 108645 | 2024-06-29 | 1699749 | 1900-01-01 | -1599749 | JW CONSULTANTS LLP
RCC Consultancy | N/C | N/C | JW CONSULTANTS LLP | 156 | 2021-08-30 | Wing-2 RCC Consultancy | 167476.1905 | 7.5 | 0 | 439625.0001 | 79132.5 | 2024-06-29 | During Construction stage on pro-rata basis. | 35 |  | 108645 | 2024-06-29 | 1699749 | 1900-01-01 | -1260123.9999 | JW CONSULTANTS LLP
RCC Consultancy | N/C | N/C | JW CONSULTANTS LLP | 156 | 2021-08-30 | Wing-3 RCC Consultancy | 14596.4444 | 7.5 | 0 | 32841.9999 | 5911.56 | 2024-06-29 | On completion of working drawings on pro-rata basis. | 30 |  | 108645 | 2024-06-29 | 1699749 | 1900-01-01 | -1666907.0001 | JW CONSULTANTS LLP
RCC Consultancy | N/C | N/C | JW CONSULTANTS LLP | 156 | 2021-08-30 | Wing-3 RCC Consultancy | 146155.0476 | 7.5 | 0 | 383657 | 69058.26 | 2024-06-29 | During Construction stage on pro-rata basis. | 35 |  | 108645 | 2024-06-29 | 1699749 | 1900-01-01 | -1316092 | JW CONSULTANTS LLP
RCC Consultancy | N/C | N/C | JW CONSULTANTS LLP | 156 | 2021-08-30 | Wing-1,2,3 Parking RCC Consultancy | 112333.3333 | 7.5 | 0 | 252749.9999 | 45495 | 2024-06-29 | On completion of working drawings on pro-rata basis. | 30 |  | 108645 | 2024-06-29 | 1699749 | 1900-01-01 | -1446999.0001 | JW CONSULTANTS LLP
RCC Consultancy | N/C | N/C | JW CONSULTANTS LLP | 156 | 2021-08-30 | Wing-1,2,3 Parking RCC Consultancy | 187000 | 7.5 | 0 | 490875 | 88357.5 | 2024-06-29 | During Construction stage on pro-rata basis. | 35 |  | 108645 | 2024-06-29 | 1699749 | 1900-01-01 | -1208874 | JW CONSULTANTS LLP
Fogging work-SO | N/C | N/C | S.R.Enterprises | 166 | 2021-09-16 | Sales Office,Lab Camp,Site Office area-Fogging Work | 1 | 8000 | 0 | 8000 | 1440 | 2024-06-03 | Sales office area, Labour camp, Site office Pest control & Fogging work (8 times in month) for the Month of MAY-2024. | 100 |  | 108017 | 2024-06-04 | 8000 | 2024-06-24 12:04 | 0 | S.R.Enterprises
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 174 | 2021-10-22 | Site Infra Soil Test-Site Visit Wing-1,2,3 | 4 | 7500 | 0 | 15000 | 2700 | 2024-06-29 | Advance along with work order | 50 |  | 108652 | 2024-07-01 | 37500 | 1900-01-01 | -22500 | GLOBAL GEOTECHNICS
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 174 | 2021-10-22 | Site Infra Soil Test-Site Visit Wing-1,2,3 | 4 | 7500 | 0 | 15000 | 2700 | 2024-06-29 | On submission of Report | 50 |  | 108652 | 2024-07-01 | 37500 | 1900-01-01 | -22500 | GLOBAL GEOTECHNICS
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 174 | 2021-10-22 | Site Infra Soil Test-Site Visit Wing-1,2,3 | 2 | 7500 | 0 | 7500 | 1350 | 2024-06-29 | On submission of Report | 50 |  | 108652 | 2024-07-01 | 37500 | 1900-01-01 | -30000 | GLOBAL GEOTECHNICS
Department Labour - Day | N/C | N/C | SWAMI GOLAPPA | 222 | 2022-02-08 | Goel House Monthly Department Labour | 20 | 600 | 0 | 12000 | 0 | 2024-06-17 13:07 | Labour Charges for Department work for the month of MAY-2024 ( 1 MC + Rent & Transportation included) | 100 |  | 108401 | 2024-06-17 | 12000 | 2024-06-24 12:07 | 0 | SWAMI GOLAPPA
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.822 | 100000 | 0 | 8220 | 1479.6 | 2024-06-08 | Testing and Certification of construction material and structure test. | 10 |  | 108154 | 2024-06-10 | 8220 | 2024-06-26 17:16 | 0 | OM ENGINEERING & SCIENTIFIC EQUIPMENTS
Rent for Tent | N/C | N/C | B.S. KATURE | 30 | 2020-07-20 | Sales Office&Show Flats -Rent for Mandap | 1 | 100000 | 0 | 100000 | 18000 | 2024-06-03 | Rent for Sales office Mandap for the month of MAY-2024 | 100 |  | 108018 | 2024-06-04 | 100000 | 2024-06-24 12:06 | 0 | B.S. KATURE
Rebaring work 8mm dia.- DTR | N/C | N/C | AVCON TECHNICS PVT LTD | 312 | 2022-05-31 | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | 73 | 150 | 0 | 10950 | 1971 | 2024-06-17 | Charges for Providing and fixing 8mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 150mm depth placing the dowel in position and effectively grouting the hole with approved brand of chemical etc. complete. | 100 |  | 108421 | 2024-06-17 | 26390 | 2024-07-15 15:06 | -15440 | AVCON TECHNICS PVT LTD
Rebarring work 10mm dia- BC | N/C | N/C | AVCON TECHNICS PVT LTD | 312 | 2022-05-31 | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | 1 | 200 | 0 | 200 | 36 | 2024-06-17 | Charges for Providing and fixing 10mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 200mm depth placing the dowel in position and effectively grouting the hole with approved brand of chemical etc. complete. | 100 |  | 108421 | 2024-06-17 | 26390 | 2024-07-15 15:06 | -26190 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 312 | 2022-05-31 | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | 11 | 260 | 0 | 2860 | 514.8 | 2024-06-17 | Charges for Providing and fixing 12mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 200mm depth placing the dowel in position and effectively grouting the hole with approved brand of chemical etc. complete. | 100 |  | 108421 | 2024-06-17 | 26390 | 2024-07-15 15:06 | -23530 | AVCON TECHNICS PVT LTD
Rebaring work 16mm dia.- DTR | N/C | N/C | AVCON TECHNICS PVT LTD | 312 | 2022-05-31 | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | 21 | 500 | 0 | 10500 | 1890 | 2024-06-17 | Charges for Providing and fixing 16mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 200mm depth placing the dowel in position and effectively grouting the hole with approved brand of chemical etc. complete. | 100 |  | 108421 | 2024-06-17 | 26390 | 2024-07-15 15:06 | -15890 | AVCON TECHNICS PVT LTD
Rebaring work 20mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 312 | 2022-05-31 | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | 2 | 940 | 0 | 1880 | 338.4 | 2024-06-17 | Charges for Providing and fixing 20mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 200mm depth placing the dowel in position and effectively grouting the hole with approved brand of chemical etc. complete. | 100 |  | 108421 | 2024-06-17 | 26390 | 2024-07-15 15:06 | -24510 | AVCON TECHNICS PVT LTD
Garbage Collection UGC | N/C | N/C | VIKAS GARADE | 315 | 2022-06-06 | Site Infra Misc Work | 1 | 1000 | 0 | 1000 | 0 | 2024-06-03 | Labour charges for Collection of Garbage from sales office & Labour camp 1,2 & 3 for month of MAY-2024 | 100 |  | 108024 | 2024-06-04 | 2000 | 2024-06-24 12:08 | -1000 | VIKAS GARADE
Maintanance Work - SMS | N/C | N/C | VIKAS GARADE | 315 | 2022-06-06 | Site Infra Misc Work | 1 | 1000 | 0 | 1000 | 0 | 2024-06-03 | MSEB Maintenance for month of MAY-2024 | 100 |  | 108024 | 2024-06-04 | 2000 | 2024-06-24 12:08 | -1000 | VIKAS GARADE
Security Services. | N/C | N/C | SHREE GANESH SECURITY SERVICES | 333 | 2022-07-09 | H.O. Admin Security Services | 0.1485 | 140873 | 5.36 | 20919.6405 | 3766.5 | 2024-06-07 | Security services for the month of MAY-2024 | 100 |  | 108075 | 2024-06-07 | 20925 | 2024-06-07 11:19 | -5.3595 | SHREE GANESH SECURITY SERVICES
Site Expenses -SO | N/C | N/C | VIKAS GARADE | 38 | 2020-09-24 | Site Expenses | 1 | 10000 | 0 | 10000 | 0 | 2024-06-03 | Petty Cash expenses for the month of MAY-2024 | 100 |  | 108015 | 2024-06-04 | 10000 | 2024-06-24 12:08 | 0 | VIKAS GARADE
Architectural Consultancy | N/C | N/C | SPACE DESIGNERS SYNDICATE | 394 | 2023-01-20 | Phase-A Wing-2 Architectural Consultancy | 40000.136 | 19 | 0 | 200000 | 36000 | 2024-06-01 | PREPARATION OF WORKING DRAWING | 26.3157 |  | 107881 | 2024-06-01 | 200000 | 2024-06-03 12:37 | -2.312e-06 | SPACE DESIGNERS SYNDICATE
Professional Fees | N/C | N/C | TALENTAX RENAISSANCE PRIVATE LIMITED | 399 | 2023-01-25 | GST Consultancy | 1 | 2000 | 0 | 2000 | 360 | 2024-06-28 | Professional Fees towards GST Related Service for the month of MAY-2024 | 100 |  | 108634 | 2024-06-28 | 2000 | 2024-06-28 16:14 | 0 | TALENTAX RENAISSANCE PRIVATE LIMITED
Rent Charges | N/C | N/C | JAIPRAKASH RAMRATAN BAJAARI | 402 | 2023-02-01 | H.O. Admin Rental Charges | 12 | 166668 | 0 | 166667.3333 | 0 | 2024-06-03 | JUNE-2024 | 8.3333 |  | 107958 | 2024-06-03 | 166667.33 | 2024-06-03 15:51 | 0.003328 | JAIPRAKASH RAMRATAN BAJAARI
Septic Tank Cleaning services | N/C | N/C | KAM FOUNDATION | 403 | 2023-02-01 | Site Infra Septic Tank Cleaning | 6 | 1500 | 0 | 9000 | 1620 | 2024-06-03 | Charges for Sales office and labour camp Septic tank Cleaning (Sludge removing) Evacuation work.4 Times in a year from JAN-2024 to DEC-2024. | 100 |  | 108016 | 2024-06-04 | 9000 | 2024-07-05 12:03 | 0 | KAM FOUNDATION
Marketing Operating Expenses | N/C | N/C | SUMIT SATISHCHANDRA SHARMA | 406 | 2023-02-09 | Marketing Expenses | 4.767 | 10000 | 0 | 3177.6822 | 0 | 2024-06-05 | MAY 2024 | 6.666 |  | 108152 | 2024-06-10 | 3177.68 | 2024-06-15 11:31 | 0.0022 | SUMIT SATISHCHANDRA SHARMA
Marketing Operating Expenses | N/C | N/C | SUMIT SATISHCHANDRA SHARMA | 406 | 2023-02-09 | Marketing Expenses | 6.024 | 10000 | 0 | 4015.5984 | 0 | 2024-06-17 | JUNE 2024 | 6.666 |  | 108420 | 2024-06-17 | 4015.6 | 2024-06-26 18:40 | -0.0016 | SUMIT SATISHCHANDRA SHARMA
UGWT Labour | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 614491.5 | 2.25 | 0 | 483912.0563 | 87104.18 | 2024-06-14 | RCC Work for all Pardi work | 35 |  | 108347 | 2024-06-15 | 483912.06 | 2024-06-15 17:58 | -0.00375 | PURVA CONSTRUCTION
Reinforcement Work-Mkt | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 10000 | 8 | 0 | 80000 | 14400 | 2024-06-14 | Labour Charges for UGWT Pumproom reinforcement work. | 100 |  | 108356 | 2024-06-17 | 600706.4 | 2024-07-12 15:25 | -520706.4 | PURVA CONSTRUCTION
Shuttering Work-Mkt | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 783.6 | 550 | 0 | 430980 | 77576.4 | 2024-06-14 | Labour Charges for UGWT Pumproom Shuttering work. | 100 |  | 108356 | 2024-06-17 | 600706.4 | 2024-07-12 15:25 | -169726.4 | PURVA CONSTRUCTION
Concrete Work - UTI | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Work (L) | 203.904 | 350 | 0 | 71366.4 | 12845.96 | 2024-06-14 | Labour Charges for UGWT Pumproom Concrete work. | 100 |  | 108356 | 2024-06-17 | 600706.4 | 2024-07-12 15:25 | -529340 | PURVA CONSTRUCTION
Rate Diff.Plum Concrete | N/C | N/C | PURVA CONSTRUCTION | 415 | 2023-02-21 | UGWT RCC Plum Concrete Above Raft (C60-R40) | 183.6 | 100 | 0 | 18360 | 3304.8 | 2024-06-14 | Rate Differnace Charges for Plum Concrete work above UGWT Raft | 100 |  | 108356 | 2024-06-17 | 600706.4 | 2024-07-12 15:25 | -582346.4 | PURVA CONSTRUCTION
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 421 | 2023-02-23 | Head Office Expenses | 12 | 32500 | 0 | 32499.87 | 5849.98 | 2024-06-27 | APR-2024 | 8.3333 |  | 108612 | 2024-06-27 | 32499.87 | 2024-06-29 18:02 | 0 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 421 | 2023-02-23 | Head Office Expenses | 11.8062 | 32500 | 0 | 31974.9971 | 5755.5 | 2024-06-27 | MAY-2024 | 8.3333 |  | 108613 | 2024-06-27 | 31975 | 2024-06-29 18:03 | -0.0029005 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 422 | 2023-02-23 | Head Office Housekeeping | 12 | 4500 | 0 | 4499.982 | 810 | 2024-06-27 | APR-2024 | 8.3333 |  | 108614 | 2024-06-27 | 4499.98 | 2024-06-29 18:02 | 0.002 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 422 | 2023-02-23 | Head Office Housekeeping | 12 | 4500 | 0 | 4499.982 | 810 | 2024-06-27 | MAY-2024 | 8.3333 |  | 108615 | 2024-06-27 | 4499.98 | 2024-06-29 18:03 | 0.002 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Company Secretary charges | N/C | N/C | ASB AND ASSOCIATES | 466 | 2023-04-04 | Company Secretary | 1 | 183333.334 | 0 | 183333.334 | 33000 | 2024-06-03 | Charges for Company Secretary for the month of MAY-2024 | 100 |  | 108008 | 2024-06-03 | 183333.33 | 2024-06-03 18:46 | 0.004 | ASB AND ASSOCIATES
Garden Maintenance | N/C | N/C | SITARAM GANGADHAR AUTI | 477 | 2023-04-14 | Garden Work | 1 | 20000 | 0 | 20000 | 0 | 2024-06-03 | Charges for Garden and all plants/trees Maintenance including cutting,trimming,watering,cleaning of all area for month MAY-2024. | 100 |  | 108020 | 2024-06-04 | 20000 | 2024-06-15 11:31 | 0 | SITARAM GANGADHAR AUTI
Professional Fees | N/C | N/C | SUNITA S MISHRA | 487 | 2023-05-01 | Professional Fees | 1 | 500000 | 0 | 500000 | 90000 | 2024-06-01 | Professioanl Consultancy Charges for the month of MAY-2024. | 100 |  | 107879 | 2024-06-01 | 500000 | 2024-06-01 11:07 | 0 | SUNITA S MISHRA
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 8 | 1500 | 0 | 3000 | 540 | 2024-06-11 | Soil Analysis Test for Month of MAY-2024 (4 x1500) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -9200 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 12 | 100 | 0 | 300 | 54 | 2024-06-11 | Noise Test Day for Month of MAY-2024 (10 x125) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -11900 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 12 | 100 | 0 | 300 | 54 | 2024-06-11 | Noise Test Night for Month of MAY-2024 (10 x125) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -11900 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 12 | 1500 | 0 | 4500 | 810 | 2024-06-11 | Ambient Air Test for Month of MAY-2024 (5 x1500) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -7700 | EHS Matrix Private Limited
Sewage Water Analysis | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 4 | 1200 | 0 | 1200 | 216 | 2024-06-11 | Untreated Effluent for STP for Month of MAY-2024 (2 x1000) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -11000 | EHS Matrix Private Limited
Stack Monitoring Report SOS | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 4 | 900 | 0 | 900 | 162 | 2024-06-11 | DG Stack Monitoring Report for Month of MAY-2024 (5 x900) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -11300 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 501 | 2023-05-24 | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | 8 | 1000 | 0 | 2000 | 360 | 2024-06-11 | Drinking water for the Month of MAY-2024 (6 x 1000) | 25 |  | 108301 | 2024-06-11 | 12200 | 2024-06-27 18:38 | -10200 | EHS Matrix Private Limited
RCC Superstructure (B-up area) | N/C | N/C | KSHITEEJ ENTERPRISES | 508 | 2023-05-30 | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | 5351.855 | 195.232 | 0 | 1044853.3554 | 188073.6 | 2024-06-26 | Charges for- P5 Level 4th Slab Shuttering, Reinforcement Concreting work for Slab,Beam, Staricase & All Shearwalls. | 100 |  | 108896 | 2024-07-08 | 1044853.36 | 2024-07-15 11:02 | -0.00464 | VINAYAKA ASSOCIATE
Legal Consultancy | N/C | N/C | UMESH SHANTARAM VASTE | 510 | 2023-06-06 | Legal Consultancy | 1 | 35000 | 0 | 35000 | 6300 | 2024-06-04 | Professional Consultancy Charges for the month of MAY-2024 | 100 |  | 108046 | 2024-06-04 | 35000 | 2024-06-04 12:36 | 0 | UMESH SHANTARAM VASTE
Soil Analysis Test- SOS | N/C | N/C | EHS Matrix Private Limited | 525 | 2023-07-07 | Morwadi Air, Noise, Water, Soil Test Report | 8 | 1500 | 0 | 3000 | 540 | 2024-06-11 | Soil Analysis Test for month of MAY-2024 (4 x 1500) | 25 |  | 108304 | 2024-06-11 | 7400 | 2024-06-27 18:38 | -4400 | EHS Matrix Private Limited
NOise Test Day SOS | N/C | N/C | EHS Matrix Private Limited | 525 | 2023-07-07 | Morwadi Air, Noise, Water, Soil Test Report | 8 | 100 | 0 | 200 | 36 | 2024-06-11 | Noise Test day for month of MAY-2024 (10 x 100) | 25 |  | 108304 | 2024-06-11 | 7400 | 2024-06-27 18:38 | -7200 | EHS Matrix Private Limited
Noise Test Night SOS | N/C | N/C | EHS Matrix Private Limited | 525 | 2023-07-07 | Morwadi Air, Noise, Water, Soil Test Report | 8 | 100 | 0 | 200 | 36 | 2024-06-11 | Noise Test Night for month of MAY-2024 (10 x 100) | 25 |  | 108304 | 2024-06-11 | 7400 | 2024-06-27 18:38 | -7200 | EHS Matrix Private Limited
Air Test SOS | N/C | N/C | EHS Matrix Private Limited | 525 | 2023-07-07 | Morwadi Air, Noise, Water, Soil Test Report | 8 | 1500 | 0 | 3000 | 540 | 2024-06-11 | Ambient Air Test for Month of MAY-2024 (5 x 1500) | 25 |  | 108304 | 2024-06-11 | 7400 | 2024-06-27 18:38 | -4400 | EHS Matrix Private Limited
Water Testing report - SOS | N/C | N/C | EHS Matrix Private Limited | 525 | 2023-07-07 | Morwadi Air, Noise, Water, Soil Test Report | 4 | 1000 | 0 | 1000 | 180 | 2024-06-11 | Drinking Water for Month of MAY-2024 (12 x 1000) | 25 |  | 108304 | 2024-06-11 | 7400 | 2024-06-27 18:38 | -6400 | EHS Matrix Private Limited
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 555 | 2023-08-26 | Wing 1 1st Floor Rebaring Work | 72 | 125 | 0 | 9000 | 1620 | 2024-06-06 | Charges for Providing and fixing 12mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 150mm depth,. placing the dowel in position and effectively grouting the hole with Hilti RE 100 chemical etc Complete. | 100 |  | 108153 | 2024-06-10 | 21000 | 2024-07-11 10:55 | -12000 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 555 | 2023-08-26 | Wing 1 2nd Floor Rebaring Work | 40 | 125 | 0 | 5000 | 900 | 2024-06-06 | Charges for Providing and fixing 12mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 150mm depth,. placing the dowel in position and effectively grouting the hole with Hilti RE 100 chemical etc Complete. | 100 |  | 108153 | 2024-06-10 | 21000 | 2024-07-11 10:55 | -16000 | AVCON TECHNICS PVT LTD
Rebaring work 12mm- cc | N/C | N/C | AVCON TECHNICS PVT LTD | 555 | 2023-08-26 | Wing 1 Podium Floor Rebaring Work | 56 | 125 | 0 | 7000 | 1260 | 2024-06-06 | Charges for Providing and fixing 12mm Dia Steel anchor dowel in hard concrete including drilling hole of upto 150mm depth,. placing the dowel in position and effectively grouting the hole with Hilti RE 100 chemical etc Complete. | 100 |  | 108153 | 2024-06-10 | 21000 | 2024-07-11 10:55 | -14000 | AVCON TECHNICS PVT LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VINAYAKA ASSOCIATE | 575 | 2023-10-07 | 8th Slab RCC slab,beam,ST,Shear wall | 154.83 | 155 | 0 | 23998.65 | 0 | 2024-06-10 | Labour charges for Aluform Shuttering/ Reinforcement/ Concreting for Slab, Beam, Staircase and all shear walls. | 100 |  | 108156 | 2024-06-10 | 23998.65 | 2024-06-27 15:51 | 0 | PRASNA PLUMBING SERVICE
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VINAYAKA ASSOCIATE | 575 | 2023-10-07 | 10th Slab RCC slab,beam,ST,Shear wall | 82.58 | 155 | 0 | 12799.9 | 0 | 2024-06-28 | Labour charges for Aluform Shuttering/ Reinforcement/ Concreting for Slab, Beam, Staircase and all shear walls. | 100 |  | 108651 | 2024-07-01 | 12799.9 | 1900-01-01 | 0 | PRASNA PLUMBING SERVICE
Door Fixing (L) | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 2 | 1800 | 0 | 3600 | 648 | 2024-06-17 12:36 | Charges for Meeting room no 4 toilet and out house kitchen door motorised lock with handle changing work and fixing work | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -15450 | LAXMI FURNITURE
Mirror Fixing | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 3 | 1800 | 0 | 5400 | 972 | 2024-06-17 12:36 | Charges for Mirror removing and refixing work for bedroom no 5 and 6 of Goel House. | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -13650 | LAXMI FURNITURE
Door Closer Fixing Work -BCo | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 2 | 1400 | 0 | 2800 | 504 | 2024-06-17 12:36 | Charges for Bedroom no 6 and Kitchen side passage door closer fixing work | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -16250 | LAXMI FURNITURE
Door Repairing Work | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 1 | 1000 | 0 | 1000 | 180 | 2024-06-17 12:36 | Charges for Bedroom no 1 door repairing work. | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -18050 | LAXMI FURNITURE
Channel Fixing - SOS | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 1 | 750 | 0 | 750 | 135 | 2024-06-17 12:36 | Charges for Bedroom no 2 TV Drawer Channel refixing work. | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -18300 | LAXMI FURNITURE
Door Repairing Work | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 1 | 500 | 0 | 500 | 90 | 2024-06-17 12:36 | Charges for Bedroom no 5 door repairing work | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -18550 | LAXMI FURNITURE
Wall Panelling Work | N/C | N/C | LAXMI FURNITURE | 599 | 2023-10-27 | Goel House Carpentary Work | 1 | 5000 | 0 | 5000 | 900 | 2024-06-17 12:36 | Charges for Living room wall panelling removing and refixing work with veneer finish due to termites. | 100 |  | 108611 | 2024-06-26 | 19050 | 2024-06-27 15:15 | -14050 | LAXMI FURNITURE
Cleaning Work - SO | N/C | N/C | AQUA CLEAN | 618 | 2023-11-17 | Labour Camp Water Tank Cleaning | 1 | 3000 | 0 | 3000 | 0 | 2024-06-03 | Charges for Drinking Water Tank cleaning work for Labour camp for month MAY-2024 | 100 |  | 108019 | 2024-06-04 | 3000 | 1900-01-01 | 0 | AQUA CLEAN
Housekeeping-SMS | N/C | N/C | KARAN JAGRAM BALMIKI | 619 | 2023-11-18 | Site Expenses Curing & House Keeping | 1 | 25000 | 0 | 25000 | 0 | 2024-06-03 | Charges for all Labour Camp Cleaning & Housekeeping work for Month MAY-2024. | 100 |  | 108022 | 2024-06-04 | 25000 | 2024-06-15 11:32 | 0 | KARAN JAGRAM BALMIKI
Website Maintainence - | N/C | N/C | WORLD WEB SOLUTIONS | 648 | 2023-12-08 | ONLINE / DIGITAL Social / Digital Activity | 12 | 90000 | 0 | 89999.64 | 16199.94 | 2024-06-10 | 2) MAY 2024 | 8.3333 | WEBSITE MAINTANCE AND DEVELOPMNET CHAREGES OF GGG + RR FOR THE MONTH OF MAY 2024 | 108263 | 2024-06-10 | 89999.64 | 2024-06-15 16:04 | 0 | WORLD WEB SOLUTIONS
Vehical Service & Repair | N/C | N/C | NITIN D PARDESHI | 651 | 2023-12-09 | Vehicle Fuel, Maintenance & Insurance | 0.6552 | 25000 | 1 | 16380 | 0 | 2024-06-10 | Charges for Vehicle Service & Repairing work for Year 2023-24 | 100 |  | 108162 | 2024-06-10 | 16381 | 2024-06-10 18:20 | -1 | MAKS AUTOMOTIVE PVT LTD
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 652 | 2023-12-09 | Goel House Electricity expenses | 0.0839 | 75000 | -2.5 | 6292.5 | 0 | 2024-06-07 | Charges for Electricity Bills for Goel House for Year 2023-24 | 100 |  | 108089 | 2024-06-07 | 6290 | 2024-06-10 11:57 | 2.5 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 652 | 2023-12-09 | Goel House Electricity expenses | 0.2067 | 75000 | -2.5 | 15502.5 | 0 | 2024-06-10 | Charges for Electricity Bills for Goel House for Year 2023-24 | 100 |  | 108265 | 2024-06-10 | 15500 | 2024-06-10 18:21 | 2.5 | MSEDCL
Membrane Vertical Waterproofing (L) | N/C | N/C | AQUARIUS WATERPROOFING | 653 | 2023-12-09 | UGWT Waterproofing Membrane W/P (Vertical) | 3613.3155 | 15 | 0 | 54199.7325 | 9755.96 | 2024-06-24 | Labour charges for waterproofing for UGWT Vertical retaining wall with remove all binding wire & nails from wall,cleaning,open all cold joint in V shape,honeycomb & Tie rod repairing treat by perma polycare+SBR Bond.Apply Neoproof RC 202+50 GSM coating | 100 |  | 108595 | 2024-06-24 | 54199.73 | 1900-01-01 | 0.0025 | AQUARIUS WATERPROOFING
Rental Charges. | N/C | N/C | NITIN D PARDESHI | 675 | 2023-12-19 | Photocopy-Xerox Machine Rental Charges. | 6.1002 | 15000 | 0.06 | 7624.945 | 1372.5 | 2024-06-07 | Rental Charges for MAY 2024 | 8.333 |  | 108093 | 2024-06-07 | 7625 | 2024-06-10 11:57 | -0.05501 | CANAN ENTERPRISES
Insurance Renewal | N/C | N/C | NITIN D PARDESHI | 676 | 2023-12-19 | Vehicle Fuel, Maintenance & Insurance | 0.2459 | 50000 | -1 | 12295 | 0 | 2024-06-13 | Charges for Vehicle Insurance from DEC-2023 to NOV-2024 | 100 |  | 108317 | 2024-06-13 | 12294 | 2024-06-13 17:49 | 1 | ICICI LOMBARD GIC LTD
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 677 | 2023-12-19 | Site Electricity expenses | 1.3175 | 350000 | -5 | 461125 | 0 | 2024-06-10 | Charges for Electricity Bills from DEC-2023 to NOV-2024 | 100 |  | 108264 | 2024-06-10 | 461120 | 2024-06-10 18:21 | 5 | MSEDCL
Tea Expenses-SO | N/C | N/C | ANIL SHRIHARI MEDHAKE | 685 | 2023-12-30 | Site Expenses | 0.8417 | 9000 | 0 | 7575.3 | 0 | 2024-06-28 | Tea Expenses for the month of APRIL-2024 | 100 |  | 108654 | 2024-07-01 | 7575.3 | 2024-07-26 12:34 | 0 | ANIL SHRIHARI MEDHAKE
Tea Expenses-SO | N/C | N/C | ANIL SHRIHARI MEDHAKE | 685 | 2023-12-30 | Site Expenses | 0.9573 | 9000 | 0 | 8615.7 | 0 | 2024-06-28 | Tea Expenses for the month of MAY-2024 | 100 |  | 108653 | 2024-07-01 | 8615.7 | 2024-07-26 12:34 | 0 | VIKAS GARADE
Housekeeping (M) | N/C | N/C | VIKAS GARADE | 698 | 2024-01-18 | Sales office & Sample flat Housekeeping Material | 1 | 2000 | 0 | 2000 | 0 | 2024-06-03 | Charges for Housekeeping material for the month of MAY-2024 | 100 |  | 108021 | 2024-06-04 | 2000 | 2024-06-15 11:40 | 0 | VIKAS GARADE
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 707 | 2024-02-03 | DG Set 125kva DG set servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-06-11 | APR-2024 | 8.33 |  | 108354 | 2024-06-17 | 2758.89 | 2024-07-15 11:02 | -1839.258 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 707 | 2024-02-03 | DG Set 125kva DG set servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-06-11 | MAY-2024 | 8.33 |  | 108354 | 2024-06-17 | 2758.89 | 2024-07-15 11:02 | -1839.258 | MEGAPOWER SOLUTION PVT LTD
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 707 | 2024-02-03 | DG Set 125kva DG set servicing kit | 12 | 920 | 0 | 919.632 | 165.54 | 2024-06-11 | JUN-2024 | 8.33 |  | 108354 | 2024-06-17 | 2758.89 | 2024-07-15 11:02 | -1839.258 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 708 | 2024-02-03 | DG Set 125kva DG set servicing kit | 1 | 11132 | 0 | 11132 | 2003.76 | 2024-06-11 | Material Supply Charges for B-Check Servicing kit (Lubricant Oil-10 Ltr, Coolant-01 Ltr, Distill Water-01 Ltr, Oil Filter-01 Nos) for 125kva DG Set Servicing work. | 100 |  | 108355 | 2024-06-17 | 16272.04 | 2024-07-05 12:03 | -5140.04 | MEGAPOWER SOLUTION PVT LTD
Air Filter element | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 708 | 2024-02-03 | DG Set 125kva DG set servicing kit | 1 | 4404.04 | 0 | 4404.04 | 792.72 | 2024-06-11 | Material Supply charges for Air Filter Element 125kva DG Set Servicing work. | 100 |  | 108355 | 2024-06-17 | 16272.04 | 2024-07-05 12:03 | -11868 | MEGAPOWER SOLUTION PVT LTD
Material Supply Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 708 | 2024-02-03 | DG Set 125kva DG set servicing kit | 1 | 736 | 0 | 736 | 132.48 | 2024-06-11 | Material delivery charges for 125kva DG Set Servicing work. | 100 |  | 108355 | 2024-06-17 | 16272.04 | 2024-07-05 12:03 | -15536.04 | MEGAPOWER SOLUTION PVT LTD
Waterproofing Work-cc- | N/C | N/C | ARTI ENTERPRISES | 729 | 2024-03-18 | Building B1 Waterproofing Work | 420 | 35 | 0 | 14700 | 2646 | 2024-06-17 12:49 | Charges for repairs to stop water leakage by non destructive method for Parapet wall. | 100 |  | 108400 | 2024-06-17 | 66225 | 1900-01-01 | -51525 | ARTI ENTERPRISES
Waterproofing wok (L)-BC | N/C | N/C | ARTI ENTERPRISES | 729 | 2024-03-18 | Building B1 Waterproofing Work | 340 | 85 | 0 | 28900 | 5202 | 2024-06-17 12:49 | Charges for repairs to stop water leakage by non destructive method for Left Side bedroom floor. | 100 |  | 108400 | 2024-06-17 | 66225 | 1900-01-01 | -37325 | ARTI ENTERPRISES
Waterproofing wok (L)-BC | N/C | N/C | ARTI ENTERPRISES | 729 | 2024-03-18 | Building B1 Waterproofing Work | 100 | 85 | 0 | 8500 | 1530 | 2024-06-17 12:49 | Charges for repairs to stop water leakage by non destructive method for Studio offset. | 100 |  | 108400 | 2024-06-17 | 66225 | 1900-01-01 | -57725 | ARTI ENTERPRISES
Waterproofing MKT | N/C | N/C | ARTI ENTERPRISES | 729 | 2024-03-18 | Building B1 Waterproofing Work | 77 | 75 | 0 | 5775 | 1039.5 | 2024-06-17 12:49 | Charges for repairs to stop water leakage by non destructive method for Window Border. | 100 |  | 108400 | 2024-06-17 | 66225 | 1900-01-01 | -60450 | ARTI ENTERPRISES
Waterproofing MKT | N/C | N/C | ARTI ENTERPRISES | 729 | 2024-03-18 | Building B1 Waterproofing Work | 18 | 75 | 0 | 1350 | 243 | 2024-06-17 12:49 | Charges for repairs to stop water leakage by non destructive method for Staircase window. | 100 |  | 108400 | 2024-06-17 | 66225 | 1900-01-01 | -64875 | ARTI ENTERPRISES
Waterproofing work. | N/C | N/C | ARTI ENTERPRISES | 729 | 2024-03-18 | Building B1 Waterproofing Work | 1 | 7000 | 0 | 7000 | 1260 | 2024-06-17 12:49 | Charges for repairs to stop water leakage by non destructive method for Toilet.Including Fault finding,repairs,pressure grouting with waterproofing compound and sealing of floor and wall joints with waterproofing compound. | 100 |  | 108400 | 2024-06-17 | 66225 | 1900-01-01 | -59225 | ARTI ENTERPRISES
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | RED TREE DESIGN STUDIO PRIVATE LIMITED | 734 | 2024-04-02 | ONLINE / DIGITAL Social / Digital Activity | 12 | 300000 | 0 | 299999.88 | 53999.98 | 2024-06-06 | 2) MONTH OF MAY 2024 | 8.3333 | GOEL GANGA GROUP + REAL RICH - ONLINE SOCIAL + DIGITAL MEDIA MONTHLY BASIS RETAINERSHIP CHARGES AS ON MAY 2024 @ 3,00,000/- + TAX | 108074 | 2024-06-06 | 299999.88 | 2024-06-12 15:08 | 0 | RED TREE DESIGN STUDIO PRIVATE LIMITED
Department Labour - DEn | N/C | N/C | PRASNA PLUMBING SERVICE | 736 | 2024-04-10 | New Lab Camp domestic drinking tank plumbing work | 5 | 1000 | 0 | 5000 | 0 | 2024-06-01 14:25 | Department Plumber Charges for GI Material fittings plumbing work for drinking and domestic tank new labour camp. | 100 |  | 107900 | 2024-06-03 | 8000 | 2024-06-24 12:09 | -3000 | PRASNA PLUMBING SERVICE
Department Labour - DER | N/C | N/C | PRASNA PLUMBING SERVICE | 736 | 2024-04-10 | New Lab Camp domestic drinking tank plumbing work | 5 | 600 | 0 | 3000 | 0 | 2024-06-01 14:25 | Department Helper Charges for plumbing work for drinking and domestic tank new labour camp. | 100 |  | 107900 | 2024-06-03 | 8000 | 2024-06-24 12:09 | -5000 | PRASNA PLUMBING SERVICE
Breaking Work - Dld | N/C | N/C | BASAV ENTERPRISES | 738 | 2024-04-10 | New Labour Camp | 1 | 5000 | 0 | 5000 | 0 | 2024-06-26 | Charges for New Labour camp waste Concrete breaking work . | 100 |  | 108650 | 2024-07-01 | 5000 | 1900-01-01 | 0 | BASAV ENTERPRISES
False Ceiling (m+l) -BC | N/C | N/C | N A DECORATORS | 739 | 2024-04-12 | Maya Satellite False Ceiling work | 152.25 | 125 | 0 | 19031.25 | 3425.62 | 2024-06-03 18:02 | Material & Labour charges for Fixing of Gypsum Board False ceiling work. | 100 |  | 107998 | 2024-06-03 | 21531.25 | 1900-01-01 | -2500 | N A DECORATORS
Gala Cutting | N/C | N/C | N A DECORATORS | 739 | 2024-04-12 | Maya Satellite False Ceiling work | 5 | 100 | 0 | 500 | 90 | 2024-06-03 18:02 | Labour charges for Light Gala Cutting work | 100 |  | 107998 | 2024-06-03 | 21531.25 | 1900-01-01 | -21031.25 | N A DECORATORS
Rabbit Shifting lumpsum- BRE | N/C | N/C | N A DECORATORS | 739 | 2024-04-12 | Maya Satellite False Ceiling work | 1 | 2000 | 0 | 2000 | 360 | 2024-06-03 18:02 | Charges for Rabbit shifting work for False ceiling work. | 100 |  | 107998 | 2024-06-03 | 21531.25 | 1900-01-01 | -19531.25 | N A DECORATORS
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | ANIMOTIONSZ | 746 | 2024-04-22 | ONLINE / DIGITAL Social / Digital Activity | 3 | 15000 | 0 | 14999.985 | 2700 | 2024-06-06 | 2) MAY 2024 | 33.3333 | GANGA ASMI - MANAGING THE CAMPAIGN FOR INCREASING THR ROI + CREATION OF ADS+ LANDING PAGE + FACEBOOK PAID CAMPAING = MONITORING CHARGES 15,000/- RS PER MONTH + TAX AS MAY 2024 | 108071 | 2024-06-06 | 14999.99 | 2024-06-15 16:05 | -0.005 | ANIMOTIONSZ
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | ANIMOTIONSZ | 747 | 2024-04-22 | ONLINE / DIGITAL Social / Digital Activity | 3 | 7500 | 0 | 7499.9925 | 1350 | 2024-06-06 | 2) MAY 2024 | 33.3333 | WTC NAGPUR - MANAGING THE CAMPAIGN FOR INCREASING THR ROI + CREATION OF ADS+ LANDING PAGE + FACEBOOK PAID CAMPAING = MONITORING CHARGES 15,000/- RS PER MONTH + TAX AS MAY 2024 | 108070 | 2024-06-06 | 7499.99 | 2024-06-15 16:05 | 0.0025 | ANIMOTIONSZ
Bobcat Hiring Charges | N/C | N/C | ATHARVA ENTERPRISES (Swati Ranade) | 767 | 2024-05-09 | Non Tower Area Backfilling & Soling | 40 | 800 | 0 | 32000 | 5760 | 2024-06-25 | Bobcat Hiring Charges for Non tower area backfilling and solling work work. | 100 |  | 108648 | 2024-07-01 | 32000 | 1900-01-01 | 0 | ATHARVA ENTERPRISES (Swati Ranade)
Retainership for Digital Media - | N/C | N/C | GOOD OLD DELIGHT | 769 | 2024-05-09 | ONLINE / DIGITAL Social / Digital Activity | 12 | 40000 | 0 | 39999.84 | 7199.98 | 2024-06-06 | 2) MAY 2024 | 8.3333 | MONTHLY MARKETING / MARKETING SOCIAL / DIGITAL MONTHLY RETAINERSHIP CHARGES @ 40,000/- + TAX PER MONTH AS ON MAY 2024 | 108072 | 2024-06-06 | 39999.84 | 2024-06-12 15:09 | 0 | GOOD OLD DELIGHT
Travelling Allowance | N/C | N/C | VAISHNAVI MANGESH KADU | 776 | 2024-05-21 | Vaishnavi Kadu Travelling Expences | 0.101 | 3000 | 0 | 303 | 0 | 2024-06-05 | Travelling Allowance for the month of FEB-2024 | 100 |  | 108065 | 2024-06-05 | 1494 | 2024-06-15 16:34 | -1191 | VAISHNAVI MANGESH KADU
Travelling Allowance | N/C | N/C | VAISHNAVI MANGESH KADU | 776 | 2024-05-21 | Vaishnavi Kadu Travelling Expences | 0.1013 | 3000 | 0.1 | 303.9 | 0 | 2024-06-05 | Travelling Allowance for the month of MAR-2024 | 100 |  | 108065 | 2024-06-05 | 1494 | 2024-06-15 16:34 | -1190.1 | VAISHNAVI MANGESH KADU
Travelling Allowance | N/C | N/C | VAISHNAVI MANGESH KADU | 776 | 2024-05-21 | Vaishnavi Kadu Travelling Expences | 0.2957 | 3000 | -0.1 | 887.1 | 0 | 2024-06-05 | Travelling Allowance for the month of APR-2024 | 100 |  | 108065 | 2024-06-05 | 1494 | 2024-06-15 16:34 | -606.9 | VAISHNAVI MANGESH KADU
MS Plate 71 x 72 x 4mm | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 71 | 73 | 0 | 5183 | 0 | 2024-06-08 | Material supply Charges for MS Plate (71 x 72 x 4mm) fixing for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -38182 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
MS Plate 97 x 72 x 4mm | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 120 | 87 | 0 | 10440 | 0 | 2024-06-08 | Material supply Charges for MS Plate (97 x 72 x 4mm) fixing for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -32925 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
MS Plate 132 x 72 x 4mm | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 36 | 120 | 0 | 4320 | 0 | 2024-06-08 | Material supply Charges for MS Plate (132 x 72 x 4mm) fixing for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -39045 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
MS Plate 206 x 72 x 4mm | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 44 | 175 | 0 | 7700 | 0 | 2024-06-08 | Material supply Charges for MS Plate (206 x 72 x 4mm) fixing for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -35665 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
MS Plate 231 x 76 x 4mm | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 26 | 197 | 0 | 5122 | 0 | 2024-06-08 | Material supply Charges for MS Plate (231 x 76 x 4mm) fixing for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -38243 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
MS Plate 132 x 210 x 4mm | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 23 | 250 | 0 | 5750 | 0 | 2024-06-08 | Material supply Charges for MS Plate (132 x 210 x 4mm) fixing for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -37615 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Hardware Material | N/C | N/C | LAXMI ELECTRICALS (Prop.Mayur Raskar) | 781 | 2024-05-24 | Wing 1-8th Slab (2nd Floor) Wing 1 8th slab MS Plates | 1 | 4850 | 0 | 4850 | 0 | 2024-06-08 | Material Supply charges for Hardware Nut Bolt for 8th Slab Wing-01 | 100 |  | 108468 | 2024-06-19 | 43365 | 2024-06-26 11:29 | -38515 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Kamakhya Yantra (Large) | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 1 | 1636.25 | 0 | 1636.25 | 294.52 | 2024-06-15 | Charges for Kamakhya Yantra for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -230195.75 | VASTURAVIRAJ VASTU SERVICES PVT LTD
PT (Large) | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 1 | 1636.25 | 0 | 1636.25 | 294.52 | 2024-06-15 | Charges for PT (Large) for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -230195.75 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Shiv yantra | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 1 | 1636.25 | 0 | 1636.25 | 294.52 | 2024-06-15 | Charges for Shiv Yantra for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -230195.75 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Mandal Remedy | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 1 | 135000 | 0 | 135000 | 351 | 2024-06-15 | Charges for Mandal Remedy (Brama, Aryama, Pruthvidhar Viswaswan Mitra Savita, Anil) for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -96832 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Vasturaviraj Pyramid Lapiz WB - No. | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 8 | 1028.5 | 0 | 8228 | 1481.04 | 2024-06-15 | Charges for Vasturaviraj Pyramid Lapiz WB for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -223604 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Vasturaviraj Pyramid Yellow WB - No. | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 12 | 1028.5 | 0 | 12342 | 2221.56 | 2024-06-15 | Charges for Vasturaviraj Pyramid Yellow WB for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -219490 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Vasturaviraj Pyramid Clear Quartz WB - No. | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 12 | 1028.5 | 0 | 12342 | 2221.56 | 2024-06-15 | Charges for Vasturaviraj Pyramid Clear Quartz WB for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -219490 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Vasturaviraj Pyramid (with crystal) | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 225 | 255 | 0 | 57375 | 10327.5 | 2024-06-15 | Charges for Vasturaviraj Pyramid (with crystal) for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -174457 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Surya (L) | N/C | N/C | VASTURAVIRAJ VASTU SERVICES PVT LTD | 791 | 2024-06-14 | Vastu Remedy Material | 1 | 1636.25 | 0 | 1636.25 | 294.52 | 2024-06-15 | Charges for Surya (L) for Vastu purpose. | 100 |  | 108448 | 2024-06-18 | 231832 | 2024-06-19 14:38 | -230195.75 | VASTURAVIRAJ VASTU SERVICES PVT LTD
Tractor Trips-BRE | N/C | N/C | UMESH SHIVAPPA | 792 | 2024-06-14 | Non Tower Area Tractor For Material Shifting | 159 | 300 | 0 | 47700 | 0 | 2024-06-25 | Tractor trips Charges for internal material shifting and backfilling work for non tower area. | 100 |  | 108624 | 2024-06-27 | 47700 | 1900-01-01 | 0 | UMESH SHIVAPPA
Rental Charges - So | N/C | N/C | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | 84 | 2021-02-26 | Sales Office - AC Rental charges | 1 | 60000 | 0 | 60000 | 10800 | 2024-06-03 | AC Rental Charges for the Month of MAY-2024 | 100 |  | 108762 | 2024-07-02 | 60000 | 2024-07-05 12:03 | 0 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD