## Work_Completion_Browse638598410
Work Completion Browse
Project : GANGA ALTUS
Contractor : VNE INFRA PROJECTS P LTD
From Date : 01/07/2019 To date: 01/07/2019
Page 1 of 1
Total Records: 469 Records 1 to 469
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Dressing, Levelling & Cleaning | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking Dressing Levelling &Cleaning | 15464.66 | 5.41 | 0 | 83663.8106 | 15065.06 | 2021-01-21 | E Bldg Substructure Work- Dressing,Levelling & Cleaning | 100 |  | 88779 | 2021-01-23 | 412274.6 | 2021-01-27 18:17 | -328610.7894 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking Footing & Column | 7823.33 | 32 | 0 | 250346.56 | 45062.38 | 2021-01-21 | E Bldg Substructure Work Footing & Column | 100 |  | 88779 | 2021-01-23 | 412274.6 | 2021-01-27 18:17 | -161928.04 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking Footing & Column | 7823.33 | 32 | 0 | 250346.56 | 45062.38 | 2021-04-14 | E Bldg Substructure Work Footing & Column | 100 |  | 89901 | 2021-04-19 | 250346.56 | 2021-04-20 14:58 | 0 | VNE INFRA PROJECTS P LTD
PCC | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking PCC Work | 7823.33 | 10 | 0 | 78233.3 | 14082 | 2021-01-21 | E Bldg Substructure Work PCC Work | 100 |  | 88779 | 2021-01-23 | 412274.6 | 2021-01-27 18:17 | -334041.3 | VNE INFRA PROJECTS P LTD
PCC | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking PCC Work | 7823.3 | 10 | 0 | 78233 | 14081.94 | 2021-07-23 | E Bldg Substructure Work PCC Work | 100 |  | 90971 | 2021-07-24 | 482693 | 2021-07-30 13:25 | -404460 | VNE INFRA PROJECTS P LTD
RCC Beam | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Bldg Parking RCC Beam | 15646.66 | 15 | 0 | 234699.9 | 42245.98 | 2021-03-23 | E Bldg Substructure Work RCC Beam | 100 |  | 89477 | 2021-03-24 | 234699.9 | 2021-03-26 16:19 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2889 | 140 | 0 | 404460 | 72802.8 | 2021-07-23 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 90971 | 2021-07-24 | 482693 | 2021-07-30 13:25 | -78233 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2111 | 140 | 0 | 295540 | 53197.2 | 2021-09-04 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91429 | 2021-09-04 | 463540 | 2021-09-07 16:52 | -168000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1665 | 140 | 0 | 233100 | 41958 | 2021-11-02 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92330 | 2021-11-03 | 233100 | 2021-12-04 12:24 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1200 | 140 | 0 | 168000 | 30240 | 2021-09-04 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91429 | 2021-09-04 | 463540 | 2021-09-07 16:52 | -295540 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4121 | 140 | 0 | 576940 | 103849.2 | 2021-09-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91732 | 2021-09-29 | 842940 | 2021-10-07 17:08 | -266000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3184 | 140 | 0 | 445760 | 80236.8 | 2021-10-12 17:12 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92012 | 2021-10-12 | 1190740.6 | 2021-10-16 13:26 | -744980.6 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2141.37 | 140 | 0 | 299791.8 | 53962.52 | 2021-11-02 10:43 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92307 | 2021-11-02 | 299791.8 | 2021-11-23 15:45 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1665 | 155 | 0 | 258075 | 46453.5 | 2021-11-30 09:51 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92755 | 2021-12-17 | 1083450 | 2021-12-17 12:23 | -825375 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 155 | 0 | 775000 | 139500 | 2021-12-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92881 | 2021-12-29 | 1187610 | 2022-01-06 15:03 | -412610 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5325 | 155 | 0 | 825375 | 148567.5 | 2021-11-30 09:51 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92755 | 2021-12-17 | 1083450 | 2021-12-17 12:23 | -258075 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2662.5 | 155 | 0 | 412687.5 | 74283.76 | 2021-11-22 12:54 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92427 | 2021-11-23 | 1237544.8 | 2021-12-04 12:26 | -824857.3 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2662 | 155 | 0 | 412610 | 74269.8 | 2021-12-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92881 | 2021-12-29 | 1187610 | 2022-01-06 15:03 | -775000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 165 | 0 | 825000 | 148500 | 2022-01-25 17:03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93223 | 2022-01-27 | 1967012.85 | 2022-02-09 14:33 | -1142012.85 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1600 | 165 | 0 | 264000 | 47520 | 2022-01-25 17:03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforment,Centering and Shuttering,Concreting,Strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93223 | 2022-01-27 | 1967012.85 | 2022-02-09 14:33 | -1703012.85 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1900 | 140 | 0 | 266000 | 47880 | 2021-09-28 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91732 | 2021-09-29 | 842940 | 2021-10-07 17:08 | -576940 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5321.29 | 140 | 0 | 744980.6 | 134096.5 | 2021-10-12 17:12 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92012 | 2021-10-12 | 1190740.6 | 2021-10-16 13:26 | -445760 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5321.66 | 155 | 0 | 824857.3 | 148474.32 | 2021-11-22 12:54 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92427 | 2021-11-23 | 1237544.8 | 2021-12-04 12:26 | -412687.5 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5321.29 | 165 | 0 | 878012.85 | 158042.32 | 2022-01-25 17:03 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93223 | 2022-01-27 | 1967012.85 | 2022-02-09 14:33 | -1089000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Podium Floor-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC W | 6626.32 | 255.45 | 0 | 1692693.444 | 304684.82 | 2022-03-17 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 94258 | 2022-04-08 | 1692693.44 | 2022-04-15 10:51 | 0.004 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12227 | 10 | 0 | 122270 | 22008.6 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571829 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12225 | 10 | 0 | 122250 | 22005 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -571849 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 112 | 2020-10-29 | E-Podium Floor-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC W | 8282.9 | 10 | 0 | 82829 | 14909.22 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95991 | 2022-08-25 | 694099 | 2022-08-27 13:01 | -611270 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 1787 | 145 | 0 | 259115 | 46640.7 | 2021-05-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 90342 | 2021-05-27 | 259115 | 2021-06-01 10:42 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 2130 | 145 | 0 | 308850 | 55593 | 2021-08-23 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91711 | 2021-09-29 | 308850 | 2021-09-29 13:09 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 4060 | 145 | 0 | 588700 | 105966 | 2022-01-11 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93095 | 2022-01-12 | 588700 | 2022-01-28 12:55 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 1787 | 145 | 0 | 259115 | 46640.7 | 2021-07-23 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 91030 | 2021-07-30 | 259115 | 2021-09-20 16:42 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 5386 | 145 | 0 | 780970 | 140574.6 | 2022-02-09 15:21 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 93411 | 2022-02-10 | 780970 | 2022-02-23 17:55 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 750 | 145 | 0 | 108750 | 19575 | 2022-08-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -771289.22 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 1787 | 155 | 0 | 276985 | 49857.3 | 2021-11-22 12:56 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 92428 | 2021-11-23 | 276985 | 2021-12-04 12:25 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 4591 | 155 | 0 | 711605 | 128088.9 | 2022-03-17 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 94255 | 2022-04-08 | 711605 | 2022-04-15 10:50 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 822 | 155 | 0 | 127410 | 22933.8 | 2022-08-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -752629.22 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 6360.729 | 155 | 0 | 985912.995 | 177464.34 | 2022-05-11 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 94756 | 2022-05-11 | 985913 | 2022-05-21 11:12 | -0.005 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 1589.7032 | 155 | 0 | 246403.996 | 44352.72 | 2022-08-25 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -633635.224 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 6360 | 205 | 0 | 1303800 | 234684 | 2022-06-06 | RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 95003 | 2022-06-06 | 1303800 | 2022-06-20 16:23 | 0 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between LG-1st Slab RCC Slab,Beam,Shear Wall,Stair | 7950 | 10 | 0 | 79500 | 14310 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800539.22 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair | 7950 | 10 | 0 | 79500 | 14310 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800539.22 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair | 7949.174 | 10 | 0 | 79491.74 | 14308.52 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800547.48 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P3-4th Slab RCC Slab,Beam,Shear Wall,Stair | 7949.174 | 10 | 0 | 79491.74 | 14308.52 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800547.48 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between P5-5th Slab RCC Slab,Beam,Shear Wall,Stair | 7949.174 | 10 | 0 | 79491.74 | 14308.52 | 2022-08-25 | Schedule for RCC Work | 100 |  | 95990 | 2022-08-25 | 880039.22 | 2022-08-27 13:02 | -800547.48 | VNE INFRA PROJECTS P LTD
Dressing, Levelling & Cleaning | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between Parking Dressing Levelling &Cleaning | 10509.22 | 4 | 0 | 42036.88 | 7566.64 | 2020-11-05 | Substructure Work-Dressing,Levelling & Cleaning | 100 |  | 88071 | 2020-11-06 | 336295.04 | 2020-11-09 18:41 | -294258.16 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 113 | 2020-10-29 | D&E-Bldg Between Parking Footing & Column | 10509.22 | 28 | 0 | 294258.16 | 52966.46 | 2020-11-05 | Substructure Work Footing & Column | 100 |  | 88071 | 2020-11-06 | 336295.04 | 2020-11-09 18:41 | -42036.88 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 5 | 80000 | 0 | 80000 | 14400 | 2020-12-28 | RMC Operator & Male Coolie for the month DEC - 2020 | 20 |  | 88506 | 2020-12-29 | 80000 | 2021-01-21 15:15 | 0 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 5 | 80000 | 0 | 80000 | 14400 | 2021-02-11 | RMC Operator & Male Coolie for the month JAN - 2020 | 20 |  | 88987 | 2021-02-11 | 80000 | 2021-02-12 11:19 | 0 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 5 | 80000 | 0 | 80000 | 14400 | 2021-05-18 | RMC Operator & Male Coolie for the month FEB - 2020 | 20 |  | 90268 | 2021-05-18 | 160000 | 2021-06-08 16:04 | -80000 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 5 | 80000 | 0 | 80000 | 14400 | 2021-05-18 | RMC Operator & Male Coolie for the month MAR - 2020 | 20 |  | 90268 | 2021-05-18 | 160000 | 2021-06-08 16:04 | -80000 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 1 | 80000 | 0 | 80000 | 14400 | 2021-09-24 | RMC Pump Operating Work APR-2021 (Operator & Helper) | 100 |  | 91656 | 2021-09-25 | 240000 | 2021-10-07 17:05 | -160000 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 1 | 80000 | 0 | 80000 | 14400 | 2021-09-24 | RMC Pump Operating Work MAY-2021 (Operator & Helper) | 100 |  | 91656 | 2021-09-25 | 240000 | 2021-10-07 17:05 | -160000 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 1 | 80000 | 0 | 80000 | 14400 | 2021-09-25 11:17 | RMC Pump Operating Work JUNE-2021 (Operator & Helper) | 100 |  | 91656 | 2021-09-25 | 240000 | 2021-10-07 17:05 | -160000 | VNE INFRA PROJECTS P LTD
RMC Pump Operator | N/C | N/C | VNE INFRA PROJECTS P LTD | 119 | 2020-11-27 | RMC Pump Operate | 1 | 80000 | 0 | 80000 | 14400 | 2021-09-15 | RMC Pump Operating Work JULY-2021 (Operator & Helper) | 100 |  | 91560 | 2021-09-16 | 80000 | 2021-10-07 17:09 | 0 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall PCC Work (L) | 7 | 250 | 0 | 1750 | 315 | 2020-12-28 | D Building Parking Area Retaining wall PCC Work for Raft with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting & unloading of material from store to required place in Contractor scope | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -511497 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall PCC Work (L) | 9.16 | 400 | 0 | 3664 | 659.52 | 2020-12-28 | D Bldg Parking Area Retaining wall Shuttering work for PCC Raft | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -509583 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 110.292 | 250 | 0 | 27573 | 4963.14 | 2020-12-28 | D Bldg Parking Area RCC work for Retaining wall of specified grade of concrete including all Reinforcement, shuttering (bothside), strutting, propping, concreting with compaction and removal of form etc completed as per drawing. | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -485674 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 890.62 | 450 | 0 | 400779 | 72140.22 | 2020-12-28 | D Bldg Parking Area Shuttering work for Retaining wall | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -112468 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 11.5 | 450 | 0 | 5175 | 931.5 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For Individual labour Registration Bill No-O-00043, dated-02/03/2021 | 89552 | 2021-03-29 | 5175 | 2021-03-30 13:03 | 0 | VISION MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 6.6667 | 450 | -0.02 | 3000.015 | 540 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For BOCW Act Registration Bill No-O-00042, dated-02/03/2021 | 89553 | 2021-03-29 | 3000 | 2021-03-30 13:03 | 0.015 | VISION MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 18.5 | 450 | 0 | 8325 | 0 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For Individual labour Registration Bill No-O-00040, dated-02/03/2021 | 89554 | 2021-03-29 | 8325 | 2021-03-30 13:03 | 0 | VISION MANAGEMENT SERVICES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 21.1111 | 450 | 0 | 9499.995 | 1710 | 2021-03-27 | D Bldg Parking Area Shuttering work for Retaining wall | 100 | For BOCW Act Registration Bill No-O-00039, dated-02/03/2021 | 89555 | 2021-03-29 | 9500 | 2021-03-30 13:04 | -0.005 | VISION MANAGEMENT SERVICES
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Retaining Wall Work (L) | 6726 | 7.5 | 0 | 50445 | 9080.1 | 2020-12-28 | D Bldg Parking Area Reinforcement Work for Retaining wall for Fixing reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBSdrawing | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -462802 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Ret Wall Raft Work(L) | 21 | 250 | 0 | 5250 | 945 | 2020-12-28 | D Bldg Parking Area RCC work for Raft of specified grade of concrete including compaction by vibrator, with proper line level and roughening them if special finish is to be provided.Loading, shifting & unloading of material in Contractor Scope | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -507997 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Ret Wall Raft Work(L) | 30.74 | 400 | 0 | 12296 | 2213.28 | 2020-12-28 | D Bldg Parking Area Shuttering Work for Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -500951 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 129 | 2020-12-21 | D-Bldg Parking Ret Wall Raft Work(L) | 1532 | 7.5 | 0 | 11490 | 2068.2 | 2020-12-28 | D Bldg Parking Area Reinforcement work Fixing reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 88507 | 2020-12-29 | 513247 | 2020-12-30 14:25 | -501757 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall PCC For Retaining Wall Raft(L) | 2.84 | 250 | 0 | 710 | 127.8 | 2021-04-19 | E Bldg Parking Area Retaining wall PCC Work for Raft with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting & unloading of material from store to required place in Contractor scope. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -232394.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall PCC For Retaining Wall Raft(L) | 3.24 | 400 | 0 | 1296 | 233.28 | 2021-04-19 | E Bldg Parking Area Retaining wall Shuttering work for Raft with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -231808.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Raft for Retaining Wall (L) | 9.4 | 250 | 0 | 2350 | 423 | 2021-04-19 | E Bldg Parking Area Retaining wall RCC work for Raft with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading, shifting & unloading of material from store to required place in contractor scope | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230754.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Raft for Retaining Wall (L) | 12.96 | 400 | 0 | 5184 | 933.12 | 2021-04-19 | E Bldg Parking Area Retaining wall Shuttering work for RCC Raft with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -227920.5 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Raft for Retaining Wall (L) | 349.3333 | 7.5 | 0 | 2619.9997 | 471.6 | 2021-04-19 | E Bldg Parking Area Retaining wall Reinforcement work for Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230484.5003 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 1657.4667 | 7.5 | 0 | 12431.0002 | 2237.58 | 2021-04-19 | E Bldg Parking Area Retaining wall Reinforcement work for Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -220673.4997 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 781.0667 | 7.5 | 0 | 5858.0003 | 1054.44 | 2021-07-23 | E Bldg Parking Area Retaining wall Reinforcement work for Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 90973 | 2021-07-24 | 74406 | 2021-07-30 13:25 | -68547.9998 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 29.54 | 250 | 0 | 7385 | 1329.3 | 2021-04-19 | E Bldg Parking Area RCC Retaining wall of specified grade of concrete including compaction by vibrator,with proper line level and roughening them if special finish is to be provided Loading,shifting & unloading of material in Contractor scope. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -225719.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 17.8 | 250 | 0 | 4450 | 801 | 2021-07-23 | E Bldg Parking Area RCC Retaining wall of specified grade of concrete including compaction by vibrator,with proper line level and roughening them if special finish is to be provided Loading,shifting & unloading of material in Contractor scope. | 100 |  | 90973 | 2021-07-24 | 74406 | 2021-07-30 13:25 | -69956 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 236.3 | 450 | 0 | 106335 | 19140.3 | 2021-04-19 | E Bldg Parking Area Retaining wall Shuttering work for Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -126769.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | E-Bldg Parking Retaining Wall Work (L) | 142.44 | 450 | 0 | 64098 | 11537.64 | 2021-07-23 | E Bldg Parking Area Retaining wall Shuttering work for Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 90973 | 2021-07-24 | 74406 | 2021-07-30 13:25 | -10308 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall PCC (L) | 3.7 | 250 | 0 | 925 | 166.5 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Concrete work with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading,shifting & unloading of material from store to required place to be done by contractor | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -232179.5 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall Raft (L) | 9.97 | 250 | 0 | 2492.5 | 448.66 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Concrete work with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading,shifting & unloading of material from store to required place to be done by contractor | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230612 | VNE INFRA PROJECTS P LTD
Concreting Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall RCC (L) | 19.56 | 250 | 0 | 4890 | 880.2 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Concrete work with proper shuttering, concreting with compaction, line level etc. complete as per drawing. Loading,shifting & unloading of material from store to required place to be done by contractor | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -228214.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall PCC (L) | 4.31 | 400 | 0 | 1724 | 310.32 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Shuttering work with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -231380.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall Raft (L) | 13.75 | 400 | 0 | 5500 | 990 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Shuttering work with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -227604.5 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall RCC (L) | 156.46 | 450 | 0 | 70407 | 12673.26 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Shuttering work with Providing & Fixing shuttering in position with proper support, Line & Level, Oiling the surface for proper finish and removal of form etc complete as per drawing. | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -162697.5 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall Raft (L) | 358 | 7.5 | 0 | 2685 | 483.3 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Reinforcement work with Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -230419.5 | VNE INFRA PROJECTS P LTD
Reinforcement Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 130 | 2020-12-22 | Between D&E-Bldg Retaining Wall RCC (L) | 822.6667 | 7.5 | 0 | 6170.0003 | 1110.6 | 2021-04-19 | D & E Bldg Between Parking Area Retaining wall Reinforcement work with Fixing in position reinforcement of various diameters for construction of Raft Foundation including Cutting & Bending as per BBS drawing | 100 |  | 89900 | 2021-04-19 | 233104.5 | 2021-04-20 14:58 | -226934.4997 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Shops pardi RCC work (L) | 421 | 450 | 0 | 189450 | 34101 | 2021-05-18 | D Bldg Shop Pardi Shuttering Work | 100 |  | 94807 | 2022-05-18 | 201499.5 | 2022-05-27 11:15 | -12049.5 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Shops pardi RCC work (L) | 21.74 | 300 | 0 | 6522 | 1173.96 | 2021-05-18 | D Bldg Shop Pardi Concreting Work (M 25) | 100 |  | 94807 | 2022-05-18 | 201499.5 | 2022-05-27 11:15 | -194977.5 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Shops pardi RCC work (L) | 737 | 7.5 | 0 | 5527.5 | 994.96 | 2021-05-18 | D Bldg Shop Pardi Reinforcement Work | 100 |  | 94807 | 2022-05-18 | 201499.5 | 2022-05-27 11:15 | -195972 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | E-Bldg Shops RCC Work | 22.55 | 300 | 0 | 6765 | 1217.7 | 2021-10-09 | E-Building Shop Pardi Cocreting work (M 50). | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -397077 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | E-Bldg Shops RCC Work | 620 | 7.5 | 0 | 4650 | 837 | 2021-10-09 | E-Building Shop Pardi Reinforcement work (Fe 500). | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -399192 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | E-Bldg Shops RCC Work | 442.38 | 450 | 0 | 199071 | 35832.78 | 2021-10-09 | E-Building Shop Pardi Shuttering work. | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -204771 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | D&E Podium Shops RCC Work | 407 | 450 | 0 | 183150 | 32967 | 2021-10-09 | D & E Building Podium Shop Pardi Shuttering work. | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -220692 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | D&E Podium Shops RCC Work | 534 | 7.5 | 0 | 4005 | 720.9 | 2021-10-09 | D & E Building Podium Shop Pardi Reinforcement work (Fe 500). | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -399837 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | D&E Podium Shops RCC Work | 20.67 | 300 | 0 | 6201 | 1116.18 | 2021-10-09 | D & E Building Podium Shop Pardi Concrete work. | 100 |  | 91992 | 2021-10-12 | 403842 | 2021-10-26 16:11 | -397641 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P1-Fl RCC Parapet Wall (L) | 47.22 | 8 | 0 | 377.76 | 68 | 2022-10-04 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48838.02 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P2-Fl RCC Parapet Wall (L) | 47.22 | 8 | 0 | 377.76 | 68 | 2022-10-04 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48838.02 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P3-Fl RCC Parapet Wall (L) | 47.22 | 8 | 0 | 377.76 | 68 | 2022-10-04 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48838.02 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P1-Fl RCC Parapet Wall (L) | 31.125 | 500 | 0 | 15562.5 | 2801.26 | 2022-10-04 | Labour charges for Shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -33653.28 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P2-Fl RCC Parapet Wall (L) | 31.125 | 500 | 0 | 15562.5 | 2801.26 | 2022-10-04 | Labour charges for Shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -33653.28 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P3-Fl RCC Parapet Wall (L) | 31.125 | 500 | 0 | 15562.5 | 2801.26 | 2022-10-04 | Labour charges for Shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -33653.28 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P1-Fl RCC Parapet Wall (L) | 1.55 | 300 | 0 | 465 | 83.7 | 2022-10-04 | Labour charges for Concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48750.78 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P2-Fl RCC Parapet Wall (L) | 1.55 | 300 | 0 | 465 | 83.7 | 2022-10-04 | Labour charges for Concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48750.78 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 197 | 2021-05-07 | Podium Betn D&E P3-Fl RCC Parapet Wall (L) | 1.55 | 300 | 0 | 465 | 83.7 | 2022-10-04 | Labour charges for Concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D & E-Building. | 100 |  | 96556 | 2022-10-05 | 49215.78 | 2022-10-15 11:34 | -48750.78 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-08-23 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91297 | 2021-08-24 | 501960 | 2021-09-03 17:16 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 4231.92 | 120 | 0 | 507830.4 | 91409.48 | 2021-09-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91572 | 2021-09-18 | 507830.4 | 2021-09-20 16:40 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-10-09 14:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91993 | 2021-10-12 | 1003920 | 2021-10-16 13:27 | -501960 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-11-02 11:30 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92323 | 2021-11-02 | 803136 | 2021-12-04 12:21 | -301176 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92624 | 2021-12-07 | 903528 | 2021-12-11 12:29 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 418.3 | 120 | 0 | 50196 | 9035.28 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2950876.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-08 16:34 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92654 | 2021-12-09 | 903528 | 2021-12-23 17:53 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 130.78 | 120 | 0 | 15693.6 | 2824.84 | 2022-08-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95827 | 2022-08-08 | 15693.6 | 2022-08-27 12:59 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-09-04 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91430 | 2021-09-04 | 501960 | 2021-09-07 16:52 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 4231.92 | 120 | 0 | 507830.4 | 91409.48 | 2021-09-24 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91655 | 2021-09-25 | 507830.4 | 2021-10-07 17:04 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 4183 | 120 | 0 | 501960 | 90352.8 | 2021-10-09 14:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 91993 | 2021-10-12 | 1003920 | 2021-10-16 13:27 | -501960 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 2509.8 | 120 | 0 | 301176 | 54211.68 | 2021-11-02 11:30 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92323 | 2021-11-02 | 803136 | 2021-12-04 12:21 | -501960 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 147.95 | 120 | 0 | 17754 | 3195.72 | 2022-02-07 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Horizontal Safety net fixing Work | 93383 | 2022-02-08 | 17754 | 2022-02-24 14:42 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 686 | 120 | 0 | 82320 | 14817.6 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -325156 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 402.5 | 120 | 0 | 48300 | 0 | 2023-07-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100859 | 2023-07-26 | 48300 | 2023-07-27 11:44 | 0 | PAWAR SHIVAPPA TARANAIK
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 436.75 | 120 | 0 | 52410 | 9433.8 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2948662.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92624 | 2021-12-07 | 903528 | 2021-12-11 12:29 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 418.3 | 120 | 0 | 50196 | 9035.28 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2950876.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 3764.7 | 120 | 0 | 451764 | 81317.52 | 2021-12-08 16:34 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92654 | 2021-12-09 | 903528 | 2021-12-23 17:53 | -451764 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 183.3333 | 120 | 0 | 21999.996 | 3960 | 2022-07-02 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95360 | 2022-07-04 | 22000 | 2022-07-14 11:43 | -0.004 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 234.9667 | 120 | 0 | 28196.004 | 5075.28 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2972876.356 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 2540.92 | 130 | 0 | 330319.6 | 59457.52 | 2021-12-30 17:57 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92919 | 2021-12-31 | 880469.2 | 2022-01-06 15:04 | -550149.6 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 169.2308 | 130 | 0 | 22000.004 | 3960 | 2022-08-04 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Safety net Fixing ( Flat no -1306,1307,1308,1301) Vertical safety net joint Below Brecket. | 95780 | 2022-08-04 | 22000 | 2022-08-16 11:41 | 0.004 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 753 | 130 | 0 | 97890 | 17620.2 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -309586 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 768.7692 | 130 | 0 | 99939.996 | 17989.2 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2901132.364 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-01-11 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93096 | 2022-01-12 | 870064 | 2022-01-28 12:55 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 836.6 | 130 | 0 | 108758 | 19576.44 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -298718 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 3764.7 | 130 | 0 | 489411 | 88093.98 | 2022-01-25 16:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93222 | 2022-01-27 | 978822 | 2022-01-28 17:45 | -489411 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-02-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93787 | 2022-03-11 | 870064 | 2022-03-11 15:52 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 836.6 | 130 | 0 | 108758 | 19576.44 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -298718 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-03-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94393 | 2022-04-14 | 870064 | 2022-04-22 13:04 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398656.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 3385.536 | 130 | 0 | 440119.68 | 79221.54 | 2022-05-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94816 | 2022-05-20 | 880239.36 | 2022-06-20 16:24 | -440119.68 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398020.96 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946057.4 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 4231.92 | 130 | 0 | 550149.6 | 99026.92 | 2021-12-30 17:57 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 92919 | 2021-12-31 | 880469.2 | 2022-01-06 15:04 | -330319.6 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-01-11 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93096 | 2022-01-12 | 870064 | 2022-01-28 12:55 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 75 | 130 | 0 | 9750 | 1755 | 2022-12-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97513 | 2022-12-26 | 407476 | 2023-01-24 19:58 | -397726 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 761.6 | 130 | 0 | 99008 | 17821.44 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2902064.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 3764.7 | 130 | 0 | 489411 | 88093.98 | 2022-01-25 16:28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93222 | 2022-01-27 | 978822 | 2022-01-28 17:45 | -489411 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-02-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 93787 | 2022-03-11 | 870064 | 2022-03-11 15:52 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 836.6 | 130 | 0 | 108758 | 19576.44 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2892314.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 3346.4 | 130 | 0 | 435032 | 78305.76 | 2022-03-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94393 | 2022-04-14 | 870064 | 2022-04-22 13:04 | -435032 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398656.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 418.3 | 130 | 0 | 54379 | 9788.22 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946693.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 3385.536 | 130 | 0 | 440119.68 | 79221.54 | 2022-05-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 94816 | 2022-05-20 | 880239.36 | 2022-06-20 16:24 | -440119.68 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -398020.96 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 423.192 | 130 | 0 | 55014.96 | 9902.7 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2946057.4 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 74429.28 | 2022-06-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95529 | 2022-07-16 | 936992 | 2022-07-22 11:41 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 101.682 | 140 | 0 | 14235.48 | 2562.38 | 2023-08-30 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | SAFETY NET REMOVING WORK | 101522 | 2023-08-30 | 14235.48 | 2023-09-12 12:52 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 316.618 | 140 | 0 | 44326.52 | 7978.78 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2956745.84 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-07-22 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95627 | 2022-07-23 | 936992 | 2022-08-04 10:36 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2942510.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-08-16 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95925 | 2022-08-19 | 1053808 | 2022-08-24 11:17 | -585312 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 247.8286 | 140 | 0 | 34696.004 | 6245.28 | 2023-01-16 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Debit for vertical safety net fixing & removing (for 14th floor) | 97809 | 2023-01-16 | 34696 | 2023-01-31 11:59 | 0.004 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-10-09 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% Bill Released against Internal Handover | 102481 | 2023-10-10 | 257749 | 1900-01-01 | -199187 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 170.4714 | 140 | 0 | 23865.996 | 4295.88 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2977206.364 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 1045.75 | 140 | 0 | 146405 | 26352.9 | 2022-08-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95992 | 2022-08-25 | 146405 | 2022-08-27 13:01 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 2509.8 | 140 | 0 | 351372 | 63246.96 | 2022-09-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96202 | 2022-09-10 | 351372 | 2022-09-15 16:40 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 198.29 | 140 | 0 | 27760.6 | 4996.9 | 2023-01-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Debit for horrizontal safety net fixing work | 97935 | 2023-01-25 | 27760.6 | 2023-02-27 15:41 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-10-09 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% Bill Released against Internal Handover | 102481 | 2023-10-10 | 257749 | 1900-01-01 | -199187 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 10.86 | 140 | 0 | 1520.4 | 273.68 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2999551.96 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 4183 | 140 | 0 | 585620 | 105411.6 | 2022-10-20 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96827 | 2022-10-20 | 819840 | 2022-11-08 10:41 | -234220 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-12-09 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97320 | 2022-12-10 | 468496 | 2022-12-24 10:48 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 500 | 140 | 0 | 70000 | 12600 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -676506 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 336.6 | 140 | 0 | 47124 | 8482.32 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2953948.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-06-25 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95529 | 2022-07-16 | 936992 | 2022-07-22 11:41 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 25.5 | 140 | 0 | 3570 | 642.6 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2997502.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 392.8 | 140 | 0 | 54992 | 9898.56 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2989418.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2022-07-22 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95627 | 2022-07-23 | 936992 | 2022-08-04 10:36 | -468496 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | 10% bill released against internal handing over work | 98415 | 2023-03-01 | 453035.92 | 2023-03-14 18:27 | -394473.92 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 418.3 | 140 | 0 | 58562 | 10541.16 | 2024-02-03 15:14 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2942510.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 2509.8 | 140 | 0 | 351372 | 63246.96 | 2022-08-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95925 | 2022-08-19 | 1053808 | 2022-08-24 11:17 | -702436 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 1671 | 140 | 0 | 233940 | 42109.2 | 2022-08-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 95925 | 2022-08-19 | 1053808 | 2022-08-24 11:17 | -819868 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 3346 | 140 | 0 | 468440 | 84319.2 | 2022-09-19 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96297 | 2022-09-20 | 468440 | 2022-10-04 12:00 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 128.5 | 140 | 0 | 17990 | 3238.2 | 2024-02-03 15:29 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2983082.36 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 708.5 | 140 | 0 | 99190 | 17854.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2945220.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 3346.4 | 140 | 0 | 468496 | 84329.28 | 2023-01-03 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 97618 | 2023-01-04 | 468496 | 2023-01-23 18:34 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 369 | 140 | 0 | 51660 | 9298.8 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -694846 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 71.4286 | 140 | 0 | 10000.004 | 0 | 2023-08-12 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 101223 | 2023-08-12 | 10000 | 2023-08-12 14:26 | 0.004 | PAWAR SHIVAPPA TARANAIK
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 396.1714 | 140 | 0 | 55463.996 | 9983.52 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2988946.214 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 1673 | 140 | 0 | 234220 | 42159.6 | 2022-10-20 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 96827 | 2022-10-20 | 819840 | 2022-11-08 10:41 | -585620 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 877.7571 | 140 | 0.01 | 122885.994 | 22119.48 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | for Internal handing over | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -623620.006 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 1632.2429 | 140 | 0 | 228514.006 | 41132.52 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2815896.204 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-01-28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98204 | 2023-02-15 | 501960 | 2023-02-20 15:36 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2023-08-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 101491 | 2023-08-28 | 250980 | 2023-09-12 12:51 | -125490 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-03-01 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98416 | 2023-03-01 | 501960 | 2023-03-14 18:27 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2023-08-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 101491 | 2023-08-28 | 250980 | 2023-09-12 12:51 | -125490 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-06 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99004 | 2023-04-06 | 501960 | 2023-04-11 17:44 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-12 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99129 | 2023-04-12 | 501960 | 2023-04-13 12:05 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 203.364 | 150 | 0 | 30504.6 | 5490.82 | 2023-08-26 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Safety net fixing work on 22nd floor(28th slab) | 101492 | 2023-08-28 | 30504.6 | 2023-09-12 12:50 | 0 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-06-08 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | For Part 1 | 99998 | 2023-06-08 | 746506 | 2023-06-21 14:54 | -244546 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-07-17 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100732 | 2023-07-17 | 501960 | 2023-07-29 10:57 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 1200 | 150 | 0 | 180000 | 32400 | 2023-02-15 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98203 | 2023-02-15 | 180000 | 2023-02-24 11:38 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 2146.4 | 150 | 0 | 321960 | 57952.8 | 2023-02-15 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98205 | 2023-02-15 | 321960 | 2023-02-24 11:37 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-03-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 98615 | 2023-03-11 | 501960 | 2023-03-29 11:34 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-10 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99083 | 2023-04-10 | 501960 | 2023-04-11 17:44 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-04-13 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99157 | 2023-04-13 | 501960 | 2023-04-14 11:50 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-06-23 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100259 | 2023-06-23 | 501960 | 2023-06-27 14:21 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 3346.4 | 150 | 0 | 501960 | 90352.8 | 2023-07-28 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 100893 | 2023-07-29 | 501960 | 2023-08-24 10:17 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 836.6 | 150 | 0 | 125490 | 22588.2 | 2024-06-20 18:56 | Labour Charges For Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2918920.21 | VNE INFRA PROJECTS P LTD
RCC Work -Dld | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace LMR OHWT | 0.75 | 1678594 | 0 | 1258945.5 | 226610.2 | 2024-02-03 15:00 | Top Terrace LMR OHWT RCC Work | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -1742126.86 | VNE INFRA PROJECTS P LTD
RCC Work -Dld | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace LMR OHWT | 0.029 | 1678594 | 0 | 48679.226 | 0 | 2024-04-12 16:52 | Top Terrace LMR OHWT RCC Work | 100 | OHWT REINFORCEMENT WORK | 106899 | 2024-04-15 | 48679.23 | 2024-06-10 11:28 | -0.004 | MOURYA AWADHESH KUMAR
RCC Work -Dld | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace LMR OHWT | 0.1192 | 1678594 | 0 | 200088.4048 | 36015.92 | 2024-04-12 17:05 | Top Terrace LMR OHWT RCC Work | 100 |  | 106898 | 2024-04-15 | 200088.4 | 1900-01-01 | 0.0048 | VNE INFRA PROJECTS P LTD
Sorting & Shifting Work | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Sorting & Shifting mockup,checking & rework(1st Floor) | 8366 | 75 | 0 | 627450 | 112941 | 2021-09-04 | Sorting And Shifting Mockup , Checking & Rework (1St Floor) | 100 |  | 91435 | 2021-09-06 | 627450 | 2021-09-07 17:26 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | 1875 | 75 | 0 | 140625 | 25312.5 | 2023-10-09 | Top Terrace LMR OHWT Parapet Wall Pergola And Elevation | 100 |  | 102481 | 2023-10-10 | 257749 | 1900-01-01 | -117124 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | 5625 | 75 | 0 | 421875 | 75937.5 | 2024-02-03 15:00 | Top Terrace LMR OHWT Parapet Wall Pergola And Elevation | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2579197.36 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 8366 | 10 | 0 | 83660 | 15058.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2960750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 8031.84 | 10 | 0 | 80318.4 | 14457.32 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2964091.81 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 168 | 10 | 0 | 1680 | 0 | 2024-06-10 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108270 | 2024-06-10 | 3360 | 1900-01-01 | -1680 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 7766 | 10 | 0 | 77660 | 13978.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2966750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 168 | 10 | 0 | 1680 | 0 | 2024-06-10 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108270 | 2024-06-10 | 3360 | 1900-01-01 | -1680 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 7766 | 10 | 0 | 77660 | 13978.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2966750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 7563.84 | 10 | 0 | 75638.4 | 13614.92 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2968771.81 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 7563.84 | 10 | 0 | 75638.4 | 13614.92 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2968771.81 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 468 | 10 | 0 | 4680 | 0 | 2024-05-19 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -35485 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 7466 | 10 | 0 | 74660 | 13438.8 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2969750.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 7934 | 10 | 0 | 79340 | 14281.2 | 2024-06-20 18:56 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -2965070.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 1321.5 | 10 | 0 | 13215 | 2378.7 | 2024-06-20 19:27 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -3031195.21 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 432 | 10 | 0 | 4320 | 0 | 2024-05-05 | Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall | 100 |  | 107386 | 2024-05-07 | 99360 | 2024-06-03 14:02 | -95040 | SALAM ENTERPRISES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-31st Slab RCC Built-up Area (L) | 3475 | 190.642 | 0 | 662480.95 | 119246.58 | 2023-08-31 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab, Beam, Staircase & All Shear walls. | 100 |  | 101541 | 2023-09-01 | 662480.95 | 2023-09-12 12:51 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-31st Slab RCC Built-up Area (L) | 188.1013 | 190.642 | -0.01 | 35860.008 | 6454.8 | 2024-06-20 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab, Beam, Staircase & All Shear walls. | 100 |  | 108477 | 2024-06-20 | 3044410.21 | 2024-06-24 12:12 | -3008550.202 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-31st Slab RCC Built-up Area (L) | 3346.4 | 190.642 | 0 | 637964.3888 | 114833.6 | 2023-09-15 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab, Beam, Staircase & All Shear walls. | 100 |  | 101897 | 2023-09-15 | 637964.39 | 2023-09-20 12:01 | -0.0012 | VNE INFRA PROJECTS P LTD
Lintel Casting work | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | Lintel casting for 3 BHK Flats (Stilt to 5th Floor) | 12 | 500 | 0 | 6000 | 1080 | 2023-10-11 | Labour charges for Lintel Binding, Shuttering and Concrete casting work for D-Bldg 3 BHK Flats from Stilt Floor to 5th Floor. | 100 |  | 102540 | 2023-10-12 | 6000 | 1900-01-01 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-7th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-8th Slab RCC Built-up Area (L) | 313.83 | 120 | 0 | 37659.6 | 6778.72 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -742480.38 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-9th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-10th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-11th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-12th Slab RCC Built-up Area (L) | 325.19 | 120 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-13th Slab RCC Built-up Area (L) | 313.83 | 130 | 0 | 40797.9 | 7343.62 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -739342.08 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-14th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-15th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-16th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-17th Slab RCC Built-up Area (L) | 325.19 | 130 | 0 | 42274.7 | 7609.44 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -737865.28 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 100 | 130 | 0 | 13000 | 2340 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -767139.98 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-18th Slab RCC Built-up Area (L) | 213.83 | 130 | 0 | 27797.9 | 5003.62 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2973274.46 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 325.19 | 140 | 0 | 45526.6 | 8194.78 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -734613.38 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-20th Slab RCC Built-up Area (L) | 325.19 | 140 | 0 | 45526.6 | 8194.78 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -734613.38 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 260.152 | 140 | 0 | 36421.28 | 6555.84 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -743718.7 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-21st Slab RCC Built-up Area (L) | 65.038 | 140 | 0 | 9105.32 | 1638.96 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991967.04 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 260.152 | 140 | 0 | 36421.28 | 6555.84 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -743718.7 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-22nd Slab RCC Built-up Area (L) | 65.038 | 140 | 0 | 9105.32 | 1638.96 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991967.04 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 329.336 | 140 | 0 | 46107.04 | 8299.26 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -734032.94 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-23rd Slab RCC Built-up Area (L) | 82.334 | 140 | 0 | 11526.76 | 2074.82 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2989545.6 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 260.152 | 140 | 0 | 36421.28 | 6555.84 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -743718.7 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-24th Slab RCC Built-up Area (L) | 65.038 | 140 | 0 | 9105.32 | 1638.96 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991967.04 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 260.152 | 150 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-25th Slab RCC Built-up Area (L) | 65.038 | 150 | 0 | 9755.7 | 1756.02 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991316.66 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 260.152 | 150 | 0 | 39022.8 | 7024.1 | 2023-04-05 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 99084 | 2023-04-10 | 780139.98 | 2023-04-13 12:04 | -741117.18 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-26th Slab RCC Built-up Area (L) | 65.038 | 150 | 0 | 9755.7 | 1756.02 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2991316.66 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-27th Slab RCC Built-up Area (L) | 325.19 | 150 | 0 | 48778.5 | 8780.14 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2952293.86 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 305.0467 | 150 | 0 | 45757.005 | 8236.26 | 2023-05-18 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 | Debit for horizontal safety net removing work on 9th Floor and fixing work on 19th floor | 99700 | 2023-05-18 | 45757.01 | 2023-06-15 13:02 | -0.005 | GREEN SAFETY SOLUTIONS
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-28th Slab RCC Built-up Area (L) | 106.6233 | 150 | 0 | 15993.495 | 2878.84 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2985078.865 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-29th Slab RCC Built-up Area (L) | 325.19 | 150 | 0 | 48778.5 | 8780.14 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2952293.86 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-30th Slab RCC Built-up Area (L) | 325.19 | 150 | 0 | 48778.5 | 8780.14 | 2024-02-03 15:06 | Quantity Differance Charges For D Buidling area Aluform Shuttering /Rainforement/Concreting For Slab,Beam,Staircase & All Shearwalls | 100 |  | 105125 | 2024-02-06 | 3001072.36 | 2024-02-08 11:21 | -2952293.86 | VNE INFRA PROJECTS P LTD
Schedule & Quality | N/C | N/C | VNE INFRA PROJECTS P LTD | 198 | 2021-05-14 | D-19th Slab RCC Built-up Area (L) | 272.5 | 10 | 0 | 2725 | 0 | 2024-05-19 | Quantity Differance Charges for Scheduling And Quality For Aluform Shuttering / Rainforcement/Concreting For Slab,Beam,Staircase & All Shearwall. | 100 |  | 107666 | 2024-05-20 | 40165 | 2024-06-10 11:26 | -37440 | SALAM ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 3519.0667 | 7.5 | 0 | 26393.0003 | 4750.74 | 2022-10-08 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 96627 | 2022-10-10 | 143386 | 2022-10-17 10:35 | -116992.9998 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 12481.0667 | 7.5 | 0 | 93608.0002 | 16849.44 | 2023-01-02 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 97592 | 2023-01-03 | 345226 | 2023-01-23 18:38 | -251617.9997 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 15500 | 7.5 | 0 | 116250 | 20925 | 2023-04-18 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99232 | 2023-04-19 | 419250 | 2023-04-24 10:50 | -303000 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 6862.2667 | 7.5 | 0 | 51467.0002 | 9264.06 | 2023-05-04 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99418 | 2023-05-04 | 403150 | 2023-05-16 12:29 | -351682.9998 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 3385.0667 | 7.5 | 0 | 25388.0003 | 4569.84 | 2023-10-02 | UGWT Reinforcement Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 102186 | 2023-10-03 | 115388 | 2023-10-17 12:48 | -89999.9998 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 65.03 | 300 | 0 | 19509 | 3511.62 | 2022-10-08 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 96627 | 2022-10-10 | 143386 | 2022-10-17 10:35 | -123877 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 99 | 300 | 0 | 29700 | 5346 | 2023-01-02 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 97592 | 2023-01-03 | 345226 | 2023-01-23 18:38 | -315526 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 260 | 300 | 0 | 78000 | 14040 | 2023-04-18 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99232 | 2023-04-19 | 419250 | 2023-04-24 10:50 | -341250 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 82.6 | 300 | 0 | 24780 | 4460.4 | 2023-05-04 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99418 | 2023-05-04 | 403150 | 2023-05-16 12:29 | -378370 | RITU ENTERPRISES
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 45 | 300 | 0 | 13500 | 2430 | 2023-10-02 | UGWT Concreting Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 102186 | 2023-10-03 | 115388 | 2023-10-17 12:48 | -101888 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 216.6311 | 450 | 0 | 97483.995 | 17547.12 | 2022-10-08 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 96627 | 2022-10-10 | 143386 | 2022-10-17 10:35 | -45902.005 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 493.1511 | 450 | 0 | 221917.995 | 39945.24 | 2023-01-02 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 97592 | 2023-01-03 | 345226 | 2023-01-23 18:38 | -123308.005 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 500 | 450 | 0 | 225000 | 40500 | 2023-04-18 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99232 | 2023-04-19 | 419250 | 2023-04-24 10:50 | -194250 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 726.4511 | 450 | 0 | 326902.995 | 58842.54 | 2023-05-04 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 99418 | 2023-05-04 | 403150 | 2023-05-16 12:29 | -76247.005 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D&E Bldg -UGWT RCC Work (L) | 170 | 450 | 0 | 76500 | 13770 | 2023-10-02 | UGWT Shuttering Work for (PCC,Footing,Column,RCC Raft Box,Raft Slab,RCC Pardi,Top Slab,Top Beam & Staircase) | 100 |  | 102186 | 2023-10-03 | 115388 | 2023-10-17 12:48 | -38888 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-8th Refuge slab rcc work with scaffolding. | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2022-05-09 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 94732 | 2022-05-09 | 67640.32 | 2022-08-17 15:12 | -33820.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-13th Refuge slab rcc work with scaffolding. | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2022-05-09 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 94732 | 2022-05-09 | 67640.32 | 2022-08-17 15:12 | -33820.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-18th Refuge slab rcc work with scaffolding. - 96.08 Sq. | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2022-06-29 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 95284 | 2022-06-29 | 33820.16 | 2022-08-17 15:12 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-23rd Refuge slab rcc work with scaffolding | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2023-08-01 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 100933 | 2023-08-01 | 67640.32 | 2023-08-09 12:17 | -33820.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | D-28th Refuge slab rcc work with scaffolding | 96.08 | 352 | 0 | 33820.16 | 6087.62 | 2023-08-01 | Labour Charges for- Refuge Area RCC work with Scaffolding . | 100 |  | 100933 | 2023-08-01 | 67640.32 | 2023-08-09 12:17 | -33820.16 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg Shops Mezzanine Floor RCC Work (L) | 1205 | 92.5 | 0 | 111462.5 | 20063.26 | 2022-05-19 | Labour Charges for- E Building shops mezzanine floor RCC Slab & Beam work. | 100 |  | 94815 | 2022-05-20 | 111462.5 | 2022-06-20 16:24 | 0 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P1-Fl RCC Parapet Wall (L) | 68.09 | 8 | 0 | 544.72 | 98.04 | 2022-10-04 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73719.44 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P2-Fl RCC Parapet Wall (L) | 68.09 | 8 | 0 | 544.72 | 98.04 | 2022-10-04 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73719.44 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P3-Fl RCC Parapet Wall (L) | 68.09 | 8 | 0 | 544.72 | 98.04 | 2022-10-04 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73719.44 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P1-Fl RCC Parapet Wall (L) | 47.01 | 500 | 0 | 23505 | 4230.9 | 2022-10-04 | Labour charges for Shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -50759.16 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P2-Fl RCC Parapet Wall (L) | 47.01 | 500 | 0 | 23505 | 4230.9 | 2022-10-04 | Labour charges for Shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -50759.16 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P3-Fl RCC Parapet Wall (L) | 47.01 | 500 | 0 | 23505 | 4230.9 | 2022-10-04 | Labour charges for Shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -50759.16 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P1-Fl RCC Parapet Wall (L) | 2.35 | 300 | 0 | 705 | 126.9 | 2022-10-04 | Labour charges for Concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73559.16 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P2-Fl RCC Parapet Wall (L) | 2.35 | 300 | 0 | 705 | 126.9 | 2022-10-04 | Labour charges for Concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73559.16 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 225 | 2021-06-22 | E-Bldg P3-Fl RCC Parapet Wall (L) | 2.35 | 300 | 0 | 705 | 126.9 | 2022-10-04 | Labour charges for Concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) E-Building. | 100 |  | 96554 | 2022-10-05 | 74264.16 | 2022-10-15 11:31 | -73559.16 | VNE INFRA PROJECTS P LTD
Labour Lumpsum-cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | Well RCC Work | 1 | 250000 | 0 | 250000 | 45000 | 2021-10-12 16:54 | Construction of RCC Pardi for Well including Reinforcement, Shuttering & Concreting work - (L). | 100 |  | 92011 | 2021-10-12 | 250000 | 2021-10-16 13:31 | 0 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 144.45 | 8 | 0 | 1155.6 | 208 | 2022-10-06 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -156238.2 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 210.53 | 8 | 0 | 1684.24 | 303.16 | 2023-08-29 | Labour charges for Reinforcement work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -190178.48 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 144.45 | 8 | 0 | 1155.6 | 208 | 2022-10-06 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -156238.2 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 210.53 | 8 | 0 | 1684.24 | 303.16 | 2023-08-29 | Labour charges for Reinforcement work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -190178.48 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 144.45 | 8 | 0 | 1155.6 | 208 | 2022-10-06 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -156238.2 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 210.53 | 8 | 0 | 1684.24 | 303.16 | 2023-08-29 | Labour charges for Reinforcement work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -190178.48 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 99.63 | 500 | 0 | 49815 | 8966.7 | 2022-10-06 | Labour charges for shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -107578.8 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 124.54 | 500 | 0 | 62270 | 11208.6 | 2023-08-29 | Labour charges for shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -129592.72 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 10 | 500 | 0 | 5000 | 0 | 2023-08-31 | Labour charges for shuttering work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101534 | 2023-08-31 | 5000 | 2023-09-01 10:58 | 0 | PAWAR SHIVAPPA TARANAIK
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 99.63 | 500 | 0 | 49815 | 8966.7 | 2022-10-06 | Labour charges for shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -107578.8 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 124.54 | 500 | 0 | 62270 | 11208.6 | 2023-08-29 | Labour charges for shuttering work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -129592.72 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 99.63 | 500 | 0 | 49815 | 8966.7 | 2022-10-06 | Labour charges for shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -107578.8 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 124.54 | 500 | 0 | 62270 | 11208.6 | 2023-08-29 | Labour charges for shuttering work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101512 | 2023-08-30 | 191862.72 | 2023-09-12 12:52 | -129592.72 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 4.98 | 300 | 0 | 1494 | 268.92 | 2022-10-06 | Labour charges for concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -155899.8 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P1-Fl RCC Parapet Wall (L) | 6.227 | 300 | 0 | 1868.1 | 336.26 | 2023-08-30 | Labour charges for concreting work for P1 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101523 | 2023-08-30 | 5604.3 | 2023-09-12 12:51 | -3736.2 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 4.98 | 300 | 0 | 1494 | 268.92 | 2022-10-06 | Labour charges for concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -155899.8 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P2-Fl RCC Parapet Wall (L) | 6.227 | 300 | 0 | 1868.1 | 336.26 | 2023-08-30 | Labour charges for concreting work for P2 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101523 | 2023-08-30 | 5604.3 | 2023-09-12 12:51 | -3736.2 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 4.98 | 300 | 0 | 1494 | 268.92 | 2022-10-06 | Labour charges for concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 96572 | 2022-10-06 | 157393.8 | 2022-10-15 11:34 | -155899.8 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 263 | 2021-09-14 | D-Bldg P3-Fl RCC Parapet Wall (L) | 6.227 | 300 | 0 | 1868.1 | 336.26 | 2023-08-30 | Labour charges for concreting work for P3 Floor RCC Parapet Wall (Parking floor outer periphery) D-Building. | 100 |  | 101523 | 2023-08-30 | 5604.3 | 2023-09-12 12:51 | -3736.2 | VNE INFRA PROJECTS P LTD
PCC Work.- | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 1.7 | 300 | 0 | 510 | 91.8 | 2022-03-05 | PCC Work for Aminity Plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -107944 | VNE INFRA PROJECTS P LTD
PCC Work.- | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 4.0267 | 300 | -0.01 | 1208.01 | 217.44 | 2022-10-06 | PCC Work for Aminity Plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -191769.99 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 20.4 | 300 | 0 | 6120 | 1101.6 | 2022-03-05 | Concreting Work Amenity plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -102334 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 12 | 300 | 0 | 3600 | 0 | 2022-09-30 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96434 | 2022-09-30 | 69844 | 2022-10-17 18:45 | -66244 | KANU KALIPADA BALA
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 6.5 | 300 | 0 | 1950 | 351 | 2022-09-30 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96433 | 2022-09-30 | 30561 | 2022-10-17 18:52 | -28611 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 21.88 | 300 | 0 | 6564 | 1181.52 | 2022-10-06 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -186414 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 13.98 | 300 | 0 | 4194 | 754.92 | 2022-10-06 | Concreting Work Amenity plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -188784 | VNE INFRA PROJECTS P LTD
Concreting Work | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 16 | 300 | 0 | 4800 | 864 | 2023-01-27 | Concreting Work Amenity plot Compound Wall. | 100 |  | 102309 | 2023-10-05 | 19538 | 1900-01-01 | -14738 | RITU ENTERPRISES
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 1500 | 8 | 0 | 12000 | 2160 | 2022-03-05 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -96454 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 1393 | 8 | 0 | 11144 | 0 | 2022-09-30 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 96434 | 2022-09-30 | 69844 | 2022-10-17 18:45 | -58700 | KANU KALIPADA BALA
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 837 | 8 | 0 | 6696 | 1205.28 | 2022-09-30 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 96433 | 2022-09-30 | 30561 | 2022-10-17 18:52 | -23865 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 3181 | 8 | 0 | 25448 | 4580.64 | 2022-10-06 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -167530 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 370 | 8 | 0 | 2960 | 532.8 | 2023-01-27 | Reinforcement Work for Aminity Plot Compound wall. | 100 |  | 102309 | 2023-10-05 | 19538 | 1900-01-01 | -16578 | RITU ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 113 | 500 | 0 | 56500 | 10170 | 2022-03-05 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -51954 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 110.2 | 500 | 0 | 55100 | 0 | 2022-09-30 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 96434 | 2022-09-30 | 69844 | 2022-10-17 18:45 | -14744 | KANU KALIPADA BALA
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 298 | 500 | 0 | 149000 | 26820 | 2022-10-06 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -43978 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 23.556 | 500 | 0 | 11778 | 2120.04 | 2023-01-27 | Shuttering Work for Amenity Plot Compoung Wall. | 100 |  | 102309 | 2023-10-05 | 19538 | 1900-01-01 | -7760 | RITU ENTERPRISES
Plum Concrete | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 11.88 | 300 | 0 | 3564 | 641.52 | 2022-03-05 | Plum Concrete for Amenity Plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -104890 | VNE INFRA PROJECTS P LTD
Plum Concrete | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 21.88 | 300 | 0 | 6564 | 1181.52 | 2022-10-06 | Plum Concrete for Amenity Plot Compound Wall. | 100 |  | 96596 | 2022-10-07 | 192978 | 2022-10-17 18:53 | -186414 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 60 | 450 | 0 | 27000 | 4860 | 2022-03-05 | Plum Concrete Shuttering Work for Amenity Plot Compound wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -81454 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 48.7 | 450 | 0 | 21915 | 3944.7 | 2022-09-30 | Plum Concrete Shuttering Work for Amenity Plot Compound wall. | 100 |  | 96433 | 2022-09-30 | 30561 | 2022-10-17 18:52 | -8646 | VNE INFRA PROJECTS P LTD
Reinforcement- Ded | N/C | N/C | VNE INFRA PROJECTS P LTD | 326 | 2021-12-23 | RCC Work Compound wall RCC Work | 345 | 8 | 0 | 2760 | 496.8 | 2022-03-05 | Plum Concrete -Steel ( Shear Connector Steel) for Amenity Plot Compound Wall. | 100 |  | 94867 | 2022-05-27 | 108454 | 2022-06-15 12:05 | -105694 | VNE INFRA PROJECTS P LTD
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 352 | 2022-01-19 | Material Lift Raft Work at E-Bldg | 4 | 250 | 0 | 1000 | 180 | 2023-05-22 | Material Lift Raft Concrete Work | 100 |  | 99747 | 2023-05-23 | 5161 | 2023-06-10 10:36 | -4161 | KSHITEEJ ENTERPRISES
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 352 | 2022-01-19 | Material Lift Raft Work at E-Bldg | 224 | 8 | 0 | 1792 | 322.56 | 2023-05-22 | Material Lift Raft Reinforcement Work | 100 |  | 99747 | 2023-05-23 | 5161 | 2023-06-10 10:36 | -3369 | KSHITEEJ ENTERPRISES
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 352 | 2022-01-19 | Material Lift Raft Work at E-Bldg | 4.738 | 500 | 0 | 2369 | 426.42 | 2023-05-22 | E- Building Lift Shuttering Work. | 100 |  | 99747 | 2023-05-23 | 5161 | 2023-06-10 10:36 | -2792 | KSHITEEJ ENTERPRISES
Concrete Work - BCP | N/C | N/C | VNE INFRA PROJECTS P LTD | 353 | 2022-01-19 | Material Lift Raft Work at D-Bldg | 4 | 250 | 0 | 1000 | 180 | 2022-03-05 | Material LIift Raft Concrete Work | 100 |  | 94908 | 2022-05-30 | 10775.31 | 2022-05-30 17:24 | -9775.31 | VNE INFRA PROJECTS P LTD
Reinforcement work- cc | N/C | N/C | VNE INFRA PROJECTS P LTD | 353 | 2022-01-19 | Material Lift Raft Work at D-Bldg | 233.264 | 8 | 0 | 1866.112 | 335.9 | 2022-03-05 | Material Lift Reinforcement Work | 100 |  | 94908 | 2022-05-30 | 10775.31 | 2022-05-30 17:24 | -8909.198 | VNE INFRA PROJECTS P LTD
Shuttering Work-Dev | N/C | N/C | VNE INFRA PROJECTS P LTD | 353 | 2022-01-19 | Material Lift Raft Work at D-Bldg | 15.8184 | 500 | 0 | 7909.2 | 1423.66 | 2022-03-05 | D- Building Lift Shuttering Work. | 100 |  | 94908 | 2022-05-30 | 10775.31 | 2022-05-30 17:24 | -2866.11 | VNE INFRA PROJECTS P LTD
Labour Lumpsum - SOSI | N/C | N/C | VNE INFRA PROJECTS P LTD | 354 | 2022-01-19 | D&E-Bldg Foundation work for Canopy. | 40 | 800 | 0 | 32000 | 5760 | 2022-02-17 | Canopy Piller Foundation Making D&E Bldg Front | 100 |  | 94256 | 2022-04-08 | 32000 | 2022-04-13 19:15 | 0 | VNE INFRA PROJECTS P LTD
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-7th Slab RCC Buit-Up Area | 4345.59 | 120 | 0 | 521470.8 | 93864.74 | 2022-09-10 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96203 | 2022-09-10 | 1010350.24 | 2022-09-15 16:44 | -488879.44 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-8th Refuge Slab RCC Buit-Up Area | 614.4362 | 120 | 0 | 73732.344 | 13271.82 | 2022-10-04 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 | For Flat 103 | 96557 | 2022-10-05 | 73732.34 | 2022-10-15 11:52 | 0.004 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-8th Refuge Slab RCC Buit-Up Area | 3773.5667 | 120 | 0 | 452828.004 | 81509.04 | 2022-10-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96829 | 2022-10-20 | 768840 | 2022-11-08 10:45 | -316011.996 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-7th Slab RCC Buit-Up Area | 4345.6 | 120 | 0 | 521472 | 93864.96 | 2022-09-26 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96374 | 2022-09-27 | 684431 | 2022-10-04 11:59 | -162959 | HIGHRISE CONSTRUCTION COMPANY
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Bldg-8th Refuge Slab RCC Buit-Up Area | 2633.4333 | 120 | 0 | 316011.996 | 56882.16 | 2022-10-20 | Labour Charges for- Aluform Shuttering,Reinforement,Concreting for slab,beam,staircase & all Shear walls. | 100 |  | 96829 | 2022-10-20 | 768840 | 2022-11-08 10:45 | -452828.004 | HIGHRISE CONSTRUCTION COMPANY
Sorting & Shifting Work | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Shifting mockup,checking & rework - 8691.19 Sq.Ft | 6518.3925 | 75 | 0 | 488879.4375 | 87998.3 | 2022-09-10 | Charges for- Sorting & Shifting ,Mockup, Checking and Rework (1st Floor) | 100 |  | 96203 | 2022-09-10 | 1010350.24 | 2022-09-15 16:44 | -521470.8025 | HIGHRISE CONSTRUCTION COMPANY
Sorting & Shifting Work | No category | N/C | VNE INFRA PROJECTS P LTD | 529 | 2022-08-30 | E-Shifting mockup,checking & rework - 8691.19 Sq.Ft | 2172.7867 | 75 | 0 | 162959.0025 | 29332.62 | 2022-09-26 | Charges for- Sorting & Shifting ,Mockup, Checking and Rework (1st Floor) | 100 |  | 96374 | 2022-09-27 | 684431 | 2022-10-04 11:59 | -521471.9975 | HIGHRISE CONSTRUCTION COMPANY
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 297 | 140 | 0 | 41580 | 7484.4 | 2023-10-05 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 | Challan No 22 12 mm-50 Nos,16mm-1 Nos. Callan No- 138 12mm-89 Nos,16mm - 2 Nos. Ch No-131 - 12mm - 36 Nos. | 102321 | 2023-10-05 | 41580 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 456 | 140 | 0 | 63840 | 11491.2 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -189876.36 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 179.86 | 155 | 0 | 27878.3 | 5018.1 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -225838.06 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 179.86 | 155 | 0 | 27878.3 | 5018.1 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -225838.06 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 180.73 | 165 | 0 | 29820.45 | 5367.68 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -223895.91 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 633 | 2023-03-03 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 408.29 | 255.454 | 0 | 104299.3137 | 18773.88 | 2023-10-11 | Quantity Differance Charges for-Area of D Bldg RCC work for Column,Beam,Slab,Staircase,RCC pardi including all Reinforcement ,Centering and shuttering,Concreting,strutting,propping and removal of form,Hacking & cleaning etc | 100 |  | 102505 | 2023-10-11 | 253716.36 | 1900-01-01 | -149417.0463 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1429 | 140 | 0 | 200060 | 36010.8 | 2020-11-23 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 88216 | 2020-11-23 | 845041 | 2020-11-25 10:27 | -644981 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 238.5 | 140 | 0 | 33390 | 6010.2 | 2021-03-13 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 89350 | 2021-03-13 | 889241 | 2021-03-22 12:33 | -855851 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1400 | 140 | 0 | 196000 | 35280 | 2023-07-25 12:17 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 100835 | 2023-07-25 | 196000 | 2023-08-09 12:23 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1932 | 140 | 0 | 270480 | 48686.4 | 2023-08-07 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 101083 | 2023-08-08 | 270480 | 2023-08-14 14:32 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5325.37 | 140 | 0 | 745551.8 | 134199.32 | 2020-12-28 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 88505 | 2020-12-29 | 745551.8 | 2020-12-30 14:25 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 140 | 0 | 700000 | 126000 | 2021-01-16 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 88750 | 2021-01-16 | 700000 | 2021-01-19 15:25 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5325.37 | 140 | 0 | 745551.8 | 134199.32 | 2021-01-21 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 88778 | 2021-01-23 | 745551.8 | 2021-01-27 17:58 | 0 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 155 | 0 | 775000 | 139500 | 2021-02-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 88984 | 2021-02-11 | 1600432.35 | 2021-02-12 11:18 | -825432.35 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5000 | 155 | 0 | 775000 | 139500 | 2021-02-26 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 89100 | 2021-03-02 | 1600432.35 | 2021-03-04 10:16 | -825432.35 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5325.37 | 155 | 0 | 825432.35 | 148577.82 | 2021-02-26 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 89100 | 2021-03-02 | 1600432.35 | 2021-03-04 10:16 | -775000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 5325.37 | 155 | 0 | 825432.35 | 148577.82 | 2021-02-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 88984 | 2021-02-11 | 1600432.35 | 2021-02-12 11:18 | -775000 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1250 | 165 | 0 | 206250 | 37125 | 2021-04-17 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 89899 | 2021-04-19 | 425921.51 | 2021-04-20 14:58 | -219671.51 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1250 | 165 | 0 | 206250 | 37125 | 2021-05-08 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 90160 | 2021-05-08 | 425921.51 | 2021-05-12 17:23 | -219671.51 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2500 | 165 | 0 | 412500 | 74250 | 2021-05-18 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 90269 | 2021-05-18 | 851843.03 | 2021-05-19 10:19 | -439343.03 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1331.3425 | 165 | 0 | 219671.5125 | 39540.88 | 2021-04-17 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 89899 | 2021-04-19 | 425921.51 | 2021-04-20 14:58 | -206249.9975 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1331.3425 | 165 | 0 | 219671.5125 | 39540.88 | 2021-05-08 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 90160 | 2021-05-08 | 425921.51 | 2021-05-12 17:23 | -206249.9975 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2662.685 | 165 | 0 | 439343.025 | 79081.74 | 2021-05-18 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. | 100 |  | 90269 | 2021-05-18 | 851843.03 | 2021-05-19 10:19 | -412500.005 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 714.2821 | 140 | 0 | 99999.494 | 17999.9 | 2020-10-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 87683 | 2020-10-10 | 334699.39 | 2020-10-17 14:34 | -234699.896 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4607.0071 | 140 | 0.01 | 644980.994 | 116096.58 | 2020-11-23 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 88216 | 2020-11-23 | 845041 | 2020-11-25 10:27 | -200060.006 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1901.8929 | 140 | -0.01 | 266265.006 | 47927.7 | 2021-03-13 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 89350 | 2021-03-13 | 889241 | 2021-03-22 12:33 | -622975.994 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 104.9286 | 140 | 0 | 14690.004 | 2644.2 | 2023-07-27 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit For Rebaring for D Bldg 1st slab 12 mm Bars having Qunatity - 58 nos X 230 Rs = 13340 16 mm Bars having Qunatity - 3 nos X 450 Rs =1350 Rs ,total- 14690 Rs. | 100879 | 2023-07-28 | 14690 | 2023-08-30 11:56 | 0.004 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 208.2143 | 140 | 0 | 29150.002 | 5247 | 2023-08-08 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit for rebaring at 1st slab 12mm having Quantity-115 Nos.,16mm having Quantity 6 no. for tie beam | 101112 | 2023-08-08 | 29150 | 2023-09-12 12:48 | 0.002 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 437 | 140 | 0 | 61180 | 11012.4 | 2023-09-08 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit For Rebaring -12mm - 266 Nos, 230 Rs. each | 101747 | 2023-09-08 | 61180 | 1900-01-01 | 0 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1200 | 140 | 0 | 168000 | 30240 | 2023-09-13 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 101829 | 2023-09-13 | 168000 | 2023-09-20 12:00 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1400 | 140 | 0 | 196000 | 35280 | 2023-10-02 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 102187 | 2023-10-03 | 196000 | 2023-10-17 12:47 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 42.8571 | 140 | 0.01 | 5999.994 | 0 | 2023-11-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | for Slab Chipping at Joint | 103404 | 2023-11-09 | 12000 | 2023-12-19 10:47 | -6000.006 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 26.39 | 140 | 0 | 3694.6 | 665.02 | 2024-02-19 17:24 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -155365.35 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1901.8903 | 155 | 0 | 294792.9965 | 53062.74 | 2021-03-13 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 89350 | 2021-03-13 | 889241 | 2021-03-22 12:33 | -594448.0035 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2800 | 155 | 0 | 434000 | 78120 | 2023-11-02 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 103204 | 2023-11-02 | 434000 | 2023-11-23 11:38 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 38.7097 | 155 | 0 | 6000.0035 | 0 | 2023-11-09 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | for Slab Chipping at Joint | 103404 | 2023-11-09 | 12000 | 2023-12-19 10:47 | -5999.9965 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 580.69 | 155 | 0 | 90006.95 | 16201.26 | 2024-02-19 17:24 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -69053 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1901.8903 | 155 | 0 | 294792.9965 | 53062.74 | 2021-03-13 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 89350 | 2021-03-13 | 889241 | 2021-03-22 12:33 | -594448.0035 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1345 | 155 | 0 | 208475 | 37525.5 | 2023-12-04 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | =Total work done quantity in 4th ramp =1681 ,we have relesed 80 % Bill of that quantity | 103788 | 2023-12-11 | 208475 | 2023-12-16 17:30 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2074.3997 | 155 | 0 | 321531.9535 | 57875.76 | 2023-12-25 16:21 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 104182 | 2023-12-25 | 321531.95 | 2024-01-02 11:45 | 0.0035 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 2660.645 | 165 | 0 | 439006.425 | 79021.16 | 2023-10-11 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 102506 | 2023-10-11 | 439006.43 | 1900-01-01 | -0.005 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 15.2727 | 165 | 0 | 2519.9955 | 0 | 2023-10-11 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit for Shivappa Pawar (Housekeeping ) | 102547 | 2023-10-12 | 2520 | 2023-11-06 16:15 | -0.0045 | PAWAR SHIVAPPA TARANAIK
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1333.33 | 165 | 0 | 219999.45 | 39599.9 | 2024-01-21 12:30 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | D building podium 4th to 5th slab ramp | 104685 | 2024-01-22 | 219999.45 | 2024-02-19 15:20 | 0 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 36.37 | 165 | 0 | 6001.05 | 0 | 2024-02-02 17:58 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | 5th slab chipping work | 106051 | 2024-03-14 | 6001.05 | 2024-03-18 12:06 | 0 | PRAKASH SAHU
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1230.6667 | 165 | -0.01 | 203060.0055 | 36550.8 | 2024-02-03 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 | Debit for Rebaring (Challan No- 8,15,26,36,98) | 105063 | 2024-02-05 | 203060 | 2024-02-29 16:55 | 0.0055 | AVCON TECHNICS PVT LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 45 | 165 | 0 | 7425 | 1336.5 | 2024-02-19 17:24 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (D Bldg Surrounding Area | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -151634.95 | RITU ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4141.45 | 255.45 | 0 | 1057933.4025 | 190428.02 | 2021-07-03 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (Girder Slab) | 100 |  | 90763 | 2021-07-03 | 2057933.4 | 2021-07-05 12:25 | -999999.9975 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3914.6604 | 255.45 | 0 | 999999.9992 | 180000 | 2021-07-03 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (Girder Slab) | 100 |  | 90763 | 2021-07-03 | 2057933.4 | 2021-07-05 12:25 | -1057933.4008 | VNE INFRA PROJECTS P LTD
RCC Superstructure (B-up area) | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 226.7896 | 255.45 | 0 | 57933.4033 | 10428.02 | 2024-02-19 18:32 | RCC work for Column, Beam, Slab, Staircase, RCC Pardi including all Reinforcement, Centering and shuttering, Concreting, strutting, propping and removal of form, Hacking & cleaning etc. (Girder Slab) | 100 |  | 105552 | 2024-02-26 | 159059.95 | 2024-04-04 16:27 | -101126.5467 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12227 | 10 | 0 | 122270 | 22008.6 | 2021-03-17 | Schedule for RCC Work | 100 |  | 89374 | 2021-03-18 | 489080 | 2021-03-22 12:34 | -366810 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-UGF-1st Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1789.2 | 10 | 0 | 17892 | 3220.56 | 2023-07-27 | Schedule for RCC Work | 100 | Debit For D Building LG Floor drive way Dressing leveling & Trimixing Concreting Work Having Area 3578.55 Sq.ft X 5 Rs. = 17892 Rs. | 100878 | 2023-07-28 | 17892 | 2023-09-04 19:05 | 0 | JAI SAIRAM CONSTRUCTION
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12227 | 10 | 0 | 122270 | 22008.6 | 2021-03-17 | Schedule for RCC Work | 100 |  | 89374 | 2021-03-18 | 489080 | 2021-03-22 12:34 | -366810 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P1-2nd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12227 | 10 | 0 | 122270 | 22008.6 | 2021-03-17 | Schedule for RCC Work | 100 |  | 89374 | 2021-03-18 | 489080 | 2021-03-22 12:34 | -366810 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P2-3rd Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 12227 | 10 | 0 | 122270 | 22008.6 | 2021-03-17 | Schedule for RCC Work | 100 |  | 89374 | 2021-03-18 | 489080 | 2021-03-22 12:34 | -366810 | VNE INFRA PROJECTS P LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P3-4th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 3419.66 | 10 | 0 | 34196.6 | 6155.38 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -86753.4 | AVCON TECHNICS PVT LTD
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-5th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 15646.66 | 10 | 0 | 156466.6 | 28163.98 | 2024-07-20 18:32 | Schedule for RCC Work | 100 |  | 109264 | 2024-07-22 | 203575.4 | 2024-08-05 13:58 | -47108.8 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 4710.88 | 10 | 0 | 47108.8 | 8479.58 | 2024-07-20 18:32 | Schedule for RCC Work | 100 |  | 109264 | 2024-07-22 | 203575.4 | 2024-08-05 13:58 | -156466.6 | RITU ENTERPRISES
Schedule- BC | No category | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-P4-6th Slab RCC Slab,Beam,Shear Wall,Stair RCC Work | 1836.02 | 10 | 0 | 18360.2 | 3304.84 | 2024-07-21 12:05 | Schedule for RCC Work | 100 |  | 109246 | 2024-07-22 | 120950 | 1900-01-01 | -102589.8 | AVCON TECHNICS PVT LTD
Dressing, Levelling & Cleaning | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-Bldg Parking Dressing Levelling &Cleaning - 15646.66 Sq | 15464.66 | 5.41 | 0 | 83663.8106 | 15065.06 | 2020-09-21 | D Bldg Substructure Work- Dressing,Levelling & Cleaning | 100 |  | 87423 | 2020-09-22 | 975554.36 | 2020-09-28 15:11 | -891890.5494 | VNE INFRA PROJECTS P LTD
Footing & Column | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-Bldg Parking Footing & Column - 15646.66 Sq.Ft | 15646.66 | 32 | 0 | 500693.12 | 90124.76 | 2020-09-21 | D Bldg Substructure Work for Footing & Column | 100 |  | 87423 | 2020-09-22 | 975554.36 | 2020-09-28 15:11 | -474861.24 | VNE INFRA PROJECTS P LTD
PCC | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-Bldg Parking PCC Work - 15646.66 Sq.Ft | 15646.66 | 10 | 0 | 156466.6 | 28163.98 | 2020-09-21 | D Bldg Substructure Work for PCC Work | 100 |  | 87423 | 2020-09-22 | 975554.36 | 2020-09-28 15:11 | -819087.76 | VNE INFRA PROJECTS P LTD
RCC Beam | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-Bldg Parking RCC Beam - 15646.66 Sq.Ft | 15646.66 | 15 | 0 | 234699.9 | 42245.98 | 2020-09-21 | D Bldg Substructure Work for RCC Beam | 100 |  | 87423 | 2020-09-22 | 975554.36 | 2020-09-28 15:11 | -740854.46 | VNE INFRA PROJECTS P LTD
Soling & PCC | N/C | N/C | VNE INFRA PROJECTS P LTD | 68 | 2020-08-22 | D-Bldg Parking Soling & PCC - 15646.66 Sq.Ft | 15646.66 | 15 | 0 | 234699.9 | 42245.98 | 2020-10-09 | D Bldg Substructure Work for Soling & PCC | 100 |  | 87683 | 2020-10-10 | 334699.39 | 2020-10-17 14:34 | -99999.49 | VNE INFRA PROJECTS P LTD