## Work_Completion_Browse638598632
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : R K INTERIOR
From Date : 16/08/2024 To date: 16/08/2024
Page 1 of 1
Total Records: 33 Records 1 to 33
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Master Toilet dado-(No.) | 20 | 141.75 | 0 | 2835 | 510.3 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120011.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Parents Toilet dado-(No.) | 30 | 141.75 | 0 | 4252.5 | 765.46 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118593.87 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Powder Toilet dado-(No.) | 26 | 141.75 | 0 | 3685.5 | 663.4 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -119160.87 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Staff Toilet dado-(No.) | 10 | 141.75 | 0 | 1417.5 | 255.16 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121428.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2701 Staff Toilet dado-(No.) | 115 | 70.875 | 0 | 8150.625 | 1467.12 | 2024-08-18 14:59 | Labour Charges for 600 x 300mm Dado Fixing work for staff toilet. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -114695.745 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Master Toilet dado-(No.) - 1 No. | 120 | 70.875 | 0 | 8505 | 1530.9 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -114341.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Powder Toilet dado-(No.) - 1 No. | 80 | 70.875 | 0 | 5670 | 1020.6 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Children Toilet-(No.) | 143 | 70.875 | 0 | 10135.125 | 1824.32 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -112711.245 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Dry Balcony dado-(No.) | 82.83 | 70.875 | 0 | 5870.5763 | 1056.7 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -116975.7937 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Master Toilet dado-(No.) | 100 | 70.875 | 0 | 7087.5 | 1275.76 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -115758.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Parents Toilet dado-(No.) | 120 | 70.875 | 0 | 8505 | 1530.9 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -114341.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Powder Toilet dado-(No.) | 70 | 70.875 | 0 | 4961.25 | 893.02 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117885.12 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Master Toilet dado-(No.) - 1 No. | 60 | 70.875 | 0 | 4252.5 | 765.46 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118593.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Powder Toilet dado-(No.) - 1 No. | 30 | 70.875 | 0 | 2126.25 | 382.72 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120720.12 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Children Toilet-(No.) | 35 | 70.875 | 0 | 2480.625 | 446.52 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120365.745 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Master Toilet dado-(No.) | 60 | 70.875 | 0 | 4252.5 | 765.46 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118593.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Parents Toilet dado-(No.) | 80 | 70.875 | 0 | 5670 | 1020.6 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Powder Toilet dado-(No.) | 40 | 70.875 | 0 | 2835 | 510.3 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120011.37 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Children Toilet Vitrified Flooring | 52.29 | 33.075 | 0 | 1729.4917 | 311.3 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121116.8782 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Master Toilet Vitrified Flooring | 45 | 33.075 | 0 | 1488.375 | 267.9 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121357.995 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Parents Toilet Vitrified Flooring | 50 | 33.075 | 0 | 1653.75 | 297.68 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121192.62 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Powder Toilet Vitrified Flooring | 36.279 | 33.075 | 0 | 1199.9279 | 215.98 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121646.4421 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Staff Toilet Vitrified Flooring | 20 | 33.075 | 0 | 661.5 | 119.08 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122184.87 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Balcony Vitrified Flooring | 40 | 33.075 | 0 | 1323 | 238.14 | 2024-08-18 14:18 | Labour Charges for Vitrified Skirting work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121523.37 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Kitchen Vitrified Flooring | 25.256 | 33.075 | 0 | 835.3422 | 150.36 | 2024-08-18 14:18 | Labour Charges for Vitrified Skirting work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122011.0278 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Staff Room Vitrified Flooring | 15 | 33.075 | 0 | 496.125 | 89.3 | 2024-08-18 14:18 | Labour Charges for Vitrified Skirting work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122350.245 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Children Toilet dado-(No.)-(No.) - 1 No. | 40 | 141.75 | 0 | 5670 | 1020.6 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Dry Balcony dado-(No.) - 1 No. | 5 | 141.75 | 0 | 708.75 | 127.58 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122137.62 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Guest Toilet dado-(No.) - 1 No. | 28 | 141.75 | 0 | 3969 | 714.42 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118877.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Master Toilet dado-(No.) - 1 No. | 40 | 141.75 | 0 | 5670 | 1020.6 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Powder Toilet dado-(No.) - 1 No. | 4.5 | 141.75 | 0 | 637.875 | 114.82 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122208.495 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Children Toilet-(No.) | 25 | 141.75 | 0 | 3543.75 | 637.88 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -119302.62 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Dry Balcony dado-(No.) | 4 | 141.75 | 0 | 567 | 102.06 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122279.37 | R K INTERIOR