## Work_Completion_Browse638599390
Work Completion Browse
Project : GANGA ALTUS
Executed By : VEER BHADRA ENTERPRISES
From Date : 12/08/2024 To date: 12/08/2024
Page 1 of 1
Total Records: 90 Records 1 to 90
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 20th Fl-Lobby Wall Texture Paint Work | 948.785 | 3.5 | 0 | 3320.7475 | 597.74 | 2024-08-18 | Labour charges for Scaffolding Fixing and Removing work for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -82069.9025 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 21st Fl-Lobby Wall Texture Paint Work | 948.785 | 3.5 | 0 | 3320.7475 | 597.74 | 2024-08-18 | Labour charges for Scaffolding Fixing and Removing work for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -82069.9025 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 22nd Fl-Lobby Wall Texture Paint Work | 948.785 | 3.5 | 0 | 3320.7475 | 597.74 | 2024-08-18 | Labour charges for Scaffolding Fixing and Removing work for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -82069.9025 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 23rd Fl-Lobby Wall Texture Paint Work | 948.785 | 3.5 | 0 | 3320.7475 | 597.74 | 2024-08-18 | Labour charges for Scaffolding Fixing and Removing work for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -82069.9025 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 24th Fl-Lobby Wall Texture Paint Work | 948.785 | 3.5 | 0 | 3320.7475 | 597.74 | 2024-08-18 | Labour charges for Scaffolding Fixing and Removing work for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -82069.9025 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 20th Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -71633.2675 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 21st Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -71633.2675 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 22nd Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -71633.2675 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 23rd Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -71633.2675 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | YUGESH KUMAR | 515 | 2022-08-08 | D-Bldg 24th Fl-Lobby Wall Texture Paint Work | 1897.57 | 7.25 | 0 | 13757.3825 | 2476.32 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Common Lobby Painting work. | 100 |  | 109918 | 2024-08-19 | 85390.65 | 1900-01-01 | -71633.2675 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Ground Floor External Texture Acrylic Paint | 283.6724 | 3.5 | 0 | 992.8534 | 178.72 | 2024-08-19 | Labour charges for Scaffolding fixing & Removing work for Parking area External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -97210.9466 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg P1 Floor External Texture Acrylic Paint | 677.237 | 3.5 | 0 | 2370.3295 | 426.66 | 2024-08-19 | Labour charges for Scaffolding fixing & Removing work for Parking area External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -95833.4705 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg P2 Floor External Texture Acrylic Paint | 705.0098 | 3.5 | 0 | 2467.5343 | 444.16 | 2024-08-19 | Labour charges for Scaffolding fixing & Removing work for Parking area External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -95736.2657 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg P3 Floor External Texture Acrylic Paint | 766.0246 | 3.5 | 0 | 2681.0861 | 482.6 | 2024-08-19 | Labour charges for Scaffolding fixing & Removing work for Parking area External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -95522.7139 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg P5 Floor External Texture Acrylic Paint | 661.6038 | 3.5 | 0 | 2315.6133 | 416.8 | 2024-08-19 | Labour charges for Scaffolding fixing & Removing work for Parking area External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -95888.1867 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg Stilt Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 2nd Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 3rd Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 4th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 5th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 6th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 7th Floor Eastside Acrylic Texture Paint | 598.85 | 3.5 | 0 | 2095.975 | 377.28 | 2024-08-19 17:27 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.825 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 8th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 9th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Eastside Acrylic Texture Paint | 598.855 | 3.5 | 0 | 2095.9925 | 377.28 | 2024-08-18 | Labour charges for Scaffolding fixing & Removing work for East side External Texture Painting work for D-Bldg. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -96107.8075 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Eastside Acrylic Texture Paint | 932.71 | 7.5 | 0 | 6995.325 | 1259.16 | 2024-08-18 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -91208.475 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Eastside Acrylic Texture Paint | 932.71 | 7.5 | 0 | 6995.325 | 1259.16 | 2024-08-18 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -91208.475 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Eastside Acrylic Texture Paint | 932.71 | 7.5 | 0 | 6995.325 | 1259.16 | 2024-08-18 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -91208.475 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Eastside Acrylic Texture Paint | 932.71 | 7.5 | 0 | 6995.325 | 1259.16 | 2024-08-18 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -91208.475 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Eastside Acrylic Texture Paint | 932.71 | 7.5 | 0 | 6995.325 | 1259.16 | 2024-08-18 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg East side External Texture Painting work. | 100 |  | 109938 | 2024-08-19 | 98203.8 | 1900-01-01 | -91208.475 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Eastside Acrylic Texture Paint | 620 | 8 | 0 | 4960 | 892.8 | 2024-08-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -162719.88 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Eastside Acrylic Texture Paint | 620 | 8 | 0 | 4960 | 892.8 | 2024-08-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -162719.88 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Eastside Acrylic Texture Paint | 620 | 8 | 0 | 4960 | 892.8 | 2024-08-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -162719.88 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Eastside Acrylic Texture Paint | 620 | 8 | 0 | 4960 | 892.8 | 2024-08-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -162719.88 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Eastside Acrylic Texture Paint | 620 | 8 | 0 | 4960 | 892.8 | 2024-08-18 | Material supply charges for External Texture Paint for East side D-Bldg. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -162719.88 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 1st Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg Stilt Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 2nd Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 3rd Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 4th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 5th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 6th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 7th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 8th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 10th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 11th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 13th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 14th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 15th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 16th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 17th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 19th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 20th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 21st Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 22nd Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 23rd Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | RAHUL PATIL | 911 | 2024-01-19 | D-Bldg 24th Floor Ext Duct Acrylic Texture Paint | 811.8175 | 8 | 0 | 6494.54 | 1169.02 | 2024-08-18 | Material supply charges for Texture Paint for D-Bldg External Duct Texture Paint. | 100 |  | 109934 | 2024-08-19 | 167679.88 | 1900-01-01 | -161185.34 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-L.G Floor Driveway & Ramp -Texture Work | 1829.62 | 0.5 | 0 | 914.81 | 164.66 | 2024-08-19 | Labour charges for Ghodi Fixing & Removing work for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -69585.71 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-Ground Floor Driveway & Ramp -Texture Work | 1574.11 | 0.5 | 0 | 787.055 | 141.68 | 2024-08-19 | Labour charges for Ghodi Fixing & Removing work for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -69713.465 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P1 Floor Driveway & Ramp -Texture Work | 1574.11 | 0.5 | 0 | 787.055 | 141.68 | 2024-08-19 | Labour charges for Ghodi Fixing & Removing work for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -69713.465 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P2 Floor Driveway & Ramp -Texture Work | 1574.11 | 0.5 | 0 | 787.055 | 141.68 | 2024-08-19 | Labour charges for Ghodi Fixing & Removing work for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -69713.465 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P3 Floor Driveway & Ramp -Texture Work | 1659.28 | 0.5 | 0 | 829.64 | 149.34 | 2024-08-19 | Labour charges for Ghodi Fixing & Removing work for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -69670.88 | VEER BHADRA ENTERPRISES
Scaffolding Fixing Work - DER | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P5 Floor Driveway & Ramp -Texture Work | 601.33 | 0.5 | 0 | 300.665 | 54.12 | 2024-08-19 | Labour charges for Ghodi Fixing & Removing work for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -70199.855 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-L.G Floor Driveway & Ramp -Texture Work | 1829.62 | 7.5 | 0 | 13722.15 | 2469.98 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -56778.37 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-Ground Floor Driveway & Ramp -Texture Work | 1574.11 | 7.5 | 0 | 11805.825 | 2125.04 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -58694.695 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P1 Floor Driveway & Ramp -Texture Work | 1574.11 | 7.5 | 0 | 11805.825 | 2125.04 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -58694.695 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P2 Floor Driveway & Ramp -Texture Work | 1574.11 | 7.5 | 0 | 11805.825 | 2125.04 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -58694.695 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P3 Floor Driveway & Ramp -Texture Work | 1659.28 | 7.5 | 0 | 12444.6 | 2240.02 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -58055.92 | VEER BHADRA ENTERPRISES
Texture Paint (L) | N/C | N/C | VEER BHADRA ENTERPRISES | 985 | 2024-05-14 | D-P5 Floor Driveway & Ramp -Texture Work | 601.33 | 7.5 | 0 | 4509.975 | 811.8 | 2024-08-18 | Labour charges for Applying Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109920 | 2024-08-19 | 70500.52 | 1900-01-01 | -65990.545 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 986 | 2024-05-14 | D-L.G Floor Driveway & Ramp -Texture Work | 1829.62 | 8 | 0 | 14636.96 | 2634.66 | 2024-08-18 | Material supply charges of Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109921 | 2024-08-19 | 51270.48 | 1900-01-01 | -36633.52 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 986 | 2024-05-14 | D-Ground Floor Driveway & Ramp -Texture Work | 787.055 | 8 | 0 | 6296.44 | 1133.36 | 2024-08-18 | Material supply charges of Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109921 | 2024-08-19 | 51270.48 | 1900-01-01 | -44974.04 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 986 | 2024-05-14 | D-P1 Floor Driveway & Ramp -Texture Work | 787.055 | 8 | 0 | 6296.44 | 1133.36 | 2024-08-18 | Material supply charges of Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109921 | 2024-08-19 | 51270.48 | 1900-01-01 | -44974.04 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 986 | 2024-05-14 | D-P2 Floor Driveway & Ramp -Texture Work | 1574.11 | 8 | 0 | 12592.88 | 2266.72 | 2024-08-18 | Material supply charges of Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109921 | 2024-08-19 | 51270.48 | 1900-01-01 | -38677.6 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 986 | 2024-05-14 | D-P3 Floor Driveway & Ramp -Texture Work | 829.64 | 8 | 0 | 6637.12 | 1194.68 | 2024-08-18 | Material supply charges of Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109921 | 2024-08-19 | 51270.48 | 1900-01-01 | -44633.36 | VEER BHADRA ENTERPRISES
Texture Paint (M) | N/C | N/C | VEER BHADRA ENTERPRISES (MATERIAL) | 986 | 2024-05-14 | D-P5 Floor Driveway & Ramp -Texture Work | 601.33 | 8 | 0 | 4810.64 | 865.92 | 2024-08-18 | Material supply charges of Texture Paint for D-Bldg Ramp + Driveway Texture painting work includes Beam, Columns, Parapet wall. | 100 |  | 109921 | 2024-08-19 | 51270.48 | 1900-01-01 | -46459.84 | VEER BHADRA ENTERPRISES