## Work_Completion_Browse638600194
Work Completion Browse
Project : GANGA DHAM TOWERS
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 2918 Records 1 to 2918
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1068 | 2021-05-26 | B Ground Floor Gypsum Plaster On Blockwork | 2463 | 9 | 0 | 22167 | 3990.06 | 2024-08-22 17:01 | Material Supply for Gypsum Plaster Tikki Dhada for Blockwork | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1068 | 2021-05-26 | B P1 Floor Gypsum Plaster On Blockwork | 1207 | 9 | 0 | 10863 | 1955.34 | 2024-08-22 17:01 | Material Supply for Gypsum Plaster Tikki Dhada for Blockwork | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1068 | 2021-05-26 | B P2 Floor Gypsum Plaster On Blockwork | 1469 | 9 | 0 | 13221 | 2379.78 | 2024-08-22 17:01 | Material Supply for Gypsum Plaster Tikki Dhada for Blockwork | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1068 | 2021-05-26 | B P3 Floor Gypsum Plaster On Blockwork | 1016.55 | 9 | 0 | 9148.95 | 1646.82 | 2024-08-22 17:01 | Material Supply for Gypsum Plaster Tikki Dhada for Blockwork | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 601 Electrical Work (L) | 1 | 26925 | 0 | 2019.375 | 363.48 | 2024-08-20 16:39 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 604 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 16:39 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 2702 Electrical Work (L) | 1 | 46389 | 0 | 13916.7 | 2505 | 2024-08-20 13:52 | Internal Wiring Work. | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 2702 Electrical Work (L) | 1 | 46389 | 0 | 2319.45 | 417.5 | 2024-08-20 13:52 | Electrical Testing. | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 2103 Electrical Work (L) | 1 | 23237 | 0 | 9294.8 | 1673.06 | 2024-08-20 13:54 | Internal Wiring | 40 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 2103 Electrical Work (L) | 1 | 23237 | 0 | 10456.65 | 1882.2 | 2024-08-20 13:54 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 2103 Electrical Work (L) | 1 | 23237 | 0 | 1742.775 | 313.7 | 2024-08-20 13:54 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 3002 Electrical Work (L) | 1 | 46389 | 0 | 13916.7 | 2505 | 2024-08-20 13:56 | Internal Wiring Work. | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 3002 Electrical Work (L) | 1 | 46389 | 0 | 11597.25 | 2087.5 | 2024-08-20 13:56 | Switch & Socket Fixing work. | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 3002 Electrical Work (L) | 1 | 46389 | 0 | 2319.45 | 417.5 | 2024-08-20 13:56 | Electrical Testing. | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 104 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 14:05 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 201 Electrical Work (L) | 0.0067 | 26925 | 0 | 81.1789 | 14.62 | 2024-08-20 14:26 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 201 Electrical Work (L) | 1 | 26925 | 0 | 2019.375 | 363.48 | 2024-08-20 14:26 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 202 Electrical Work (L) | 0.069 | 26015 | 0 | 807.7658 | 145.4 | 2024-08-20 14:26 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 202 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 14:26 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 203 Electrical Work (L) | 0.1 | 23237 | 0 | 1045.665 | 188.22 | 2024-08-20 14:26 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 203 Electrical Work (L) | 1 | 23237 | 0 | 1742.775 | 313.7 | 2024-08-20 14:26 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 204 Electrical Work (L) | 0.069 | 26015 | 0 | 807.7658 | 145.4 | 2024-08-20 14:26 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 204 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 14:26 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 402 Electrical Work (L) | 0.0069 | 26015 | 0 | 80.7766 | 14.54 | 2024-08-20 14:38 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 402 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 14:38 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 403 Electrical Work (L) | 1 | 23237 | 0 | 1742.775 | 313.7 | 2024-08-20 14:38 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 404 Electrical Work (L) | 0.009 | 26015 | 0 | 105.3607 | 18.96 | 2024-08-20 14:38 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 404 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 14:38 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 502 Electrical Work (L) | 0.0669 | 26015 | 0 | 783.1816 | 140.98 | 2024-08-20 15:00 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 502 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 15:00 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 503 Electrical Work (L) | 0.2 | 23237 | 0 | 2091.33 | 376.44 | 2024-08-20 15:00 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 503 Electrical Work (L) | 1 | 23237 | 0 | 1742.775 | 313.7 | 2024-08-20 15:00 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 504 Electrical Work (L) | 0.0169 | 26015 | 0 | 197.8441 | 35.62 | 2024-08-20 15:00 | Switch Socket & DB | 45 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Electrical Work (Labour) -Bco | N/C | N/C | VAISHALI ELECTRICAL | 1118 | 2021-07-07 | A 504 Electrical Work (L) | 1 | 26015 | 0 | 1951.125 | 351.2 | 2024-08-20 15:00 | Electrical Testing | 7.5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | VAISHALI ELECTRICAL
Labour Lumpsum | N/C | N/C | PRAKASH CONTRACTOR | 1130 | 2021-07-12 | Labour Charges For Plumbing Material Shifting | 1 | 23000 | 0 | 23000 | 0 | 2024-08-05 12:45 | Charges for Plumbing Material Shifting from 105 level to 99 level Parking for C-Bldg. | 100 |  | 109630 | 2024-08-05 | 23000 | 2024-08-19 13:22 | 0 | PRAKASH CONTRACTOR
SITC Pressure Gauge (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting 14 Floors | 31 | 915 | 0 | 28365 | 5105.7 | 2024-08-10 16:22 | Supply of SITC Pressure Gauge. | 100 |  | 109836 | 2024-08-12 | 259880 | 1900-01-01 | -231515 | SAITECH FIRE SYSTEM PRIVATE LIMITED
SITC Pressure Gauge (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting 14 Floors | 5 | 915 | 0 | 4575 | 823.5 | 2024-08-10 16:22 | Supply of SITC Pressure Gauge. | 100 |  | 109836 | 2024-08-12 | 259880 | 1900-01-01 | -255305 | SAITECH FIRE SYSTEM PRIVATE LIMITED
SS Branch Pipe with Nozzle-(M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting 14 Floors | 31 | 1265 | 0 | 39215 | 7058.7 | 2024-08-10 16:30 | Tower A-Bldg. Fire Fitting. Supply of SS Branch Pipe Nozzle. | 100 |  | 109836 | 2024-08-12 | 259880 | 1900-01-01 | -220665 | SAITECH FIRE SYSTEM PRIVATE LIMITED
SS Branch Pipe with Nozzle-(M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting 14 Floors | 5 | 1265 | 0 | 6325 | 1138.5 | 2024-08-10 16:30 | Supply of SS Branch Pipe Nozzle. | 100 |  | 109836 | 2024-08-12 | 259880 | 1900-01-01 | -253555 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Fire Extinguisher 4.0Kg DCP Type (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting 14 Floors | 80 | 1255 | 0 | 100400 | 18072 | 2024-08-10 16:32 | Supply of Fire Extinguisher 4.0 kg DCP Type. | 100 |  | 109836 | 2024-08-12 | 259880 | 1900-01-01 | -159480 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Flow Switch 100mm dia (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting 14 Floors | 36 | 2250 | 0 | 81000 | 14580 | 2024-08-10 15:49 | Supply of Flow Switch 100mm dia. | 100 |  | 109836 | 2024-08-12 | 259880 | 1900-01-01 | -178880 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Shank Reducer (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1169 | 2021-10-01 | A Fire Fighting Extra Items | 36 | 1500 | 0 | 54000 | 9720 | 2024-08-16 16:00 | Supply of Shank Reducer Adaptor. | 100 |  | 109882 | 2024-08-16 | 54000 | 1900-01-01 | 0 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Gypsum Touch-up work- (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1182 | 2021-10-05 | A 2303 Gypsum Repairing work | 1 | 10000 | 0 | 10000 | 1800 | 2024-08-01 15:57 | Labour Charges for A Building internal Flat Gypsum touch up work,Dhar Core,Kutch & all repairing work. | 100 |  | 109569 | 2024-08-05 | 30000 | 1900-01-01 | -20000 | A K INTERIOR CONTRACTOR
Gypsum Touch-up work- (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1182 | 2021-10-05 | A 2403 Gypsum Repairing work | 1 | 10000 | 0 | 10000 | 1800 | 2024-08-01 15:57 | Labour Charges for A Building internal Flat Gypsum touch up work,Dhar Core,Kutch & all repairing work. | 100 |  | 109569 | 2024-08-05 | 30000 | 1900-01-01 | -20000 | A K INTERIOR CONTRACTOR
Gypsum Touch-up work- (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1182 | 2021-10-05 | A 2404 Gypsum Repairing work | 1 | 10000 | 0 | 10000 | 1800 | 2024-08-01 15:58 | Labour Charges for A Building internal Flat Gypsum touch up work,Dhar Core,Kutch & all repairing work. | 100 |  | 109569 | 2024-08-05 | 30000 | 1900-01-01 | -20000 | A K INTERIOR CONTRACTOR
Departmental Labour | N/C | N/C | PRAKASH CONTRACTOR | 1192 | 2021-11-02 | Labour Charges For Departmental Work | 29 | 650 | 0 | 18850 | 0 | 2024-08-05 12:47 | Charges for Male Coolie for Miscellaneous Departmental work for C-Building. | 100 |  | 109631 | 2024-08-05 | 27950 | 1900-01-01 | -9100 | PRAKASH CONTRACTOR
Breaker - BRE | N/C | N/C | PRAKASH CONTRACTOR | 1192 | 2021-11-02 | Rain water harvesting Chamber work | 7 | 1300 | 0 | 9100 | 0 | 2024-08-05 12:47 | Charges for Breaker for Side concrete breaking for Rainwater Harvesting Chamber work. | 100 |  | 109631 | 2024-08-05 | 27950 | 1900-01-01 | -18850 | PRAKASH CONTRACTOR
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
SITC GI Pipe C Class 100mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 20 | 1900 | 0 | 5700 | 1026 | 2024-08-12 15:55 | Against Material Installation | 15 |  | 109859 | 2024-08-13 | 206175 | 1900-01-01 | -200475 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 150mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 495 | 2700 | 0 | 200475 | 36085.5 | 2024-08-12 15:55 | Against Material Installation | 15 |  | 109859 | 2024-08-13 | 206175 | 1900-01-01 | -5700 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Single Door Hose Box (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 1400 | 0 | 34720 | 6249.6 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -962774.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Single Door Hose Box (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 1400 | 0 | 6510 | 1171.8 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -990984.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Orifice Plate (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 900 | 0 | 22320 | 4017.6 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -975174.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Orifice Plate (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 900 | 0 | 4185 | 753.3 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -993309.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 150mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 8 | 7000 | 0 | 44800 | 8064 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -952694.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 150mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 8 | 7000 | 0 | 8400 | 1512 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -989094.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 100 mm | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 1 | 4125 | 0 | 3300 | 594 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -994194.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 100 mm | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 1 | 4125 | 0 | 618.75 | 111.38 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -996875.55 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
ABC Type Fire Extinguisher 6 kg (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 65 | 1525 | 0 | 79300 | 14274 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -918194.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
ABC Type Fire Extinguisher 6 kg (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 65 | 1525 | 0 | 14868.75 | 2676.38 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -982625.55 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Fire Extinguisher 4.5 Kg CO2 (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 70 | 4300 | 0 | 240800 | 43344 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -756694.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Fire Extinguisher 4.5 Kg CO2 (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 70 | 4300 | 0 | 45150 | 8127 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -952344.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Double Hydrant Valve (M+L) - No. | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 13324 | 0 | 330435.2 | 59478.34 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -667059.1 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Double Hydrant Valve (M+L) - No. | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 13324 | 0 | 61956.6 | 11152.18 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -935537.7 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Hose Pipe 15 Mtr. length (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 3400 | 0 | 84320 | 15177.6 | 2024-08-13 13:15 | Against material Supply | 80 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -913174.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Hose Pipe 15 Mtr. length (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 3400 | 0 | 15810 | 2845.8 | 2024-08-13 13:15 | Against material installation | 15 |  | 109869 | 2024-08-14 | 997494.3 | 1900-01-01 | -981684.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 100mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 100 | 1900 | 0 | 28500 | 5130 | 2024-08-12 15:57 | Against material installation | 15 |  | 109858 | 2024-08-13 | 124890 | 1900-01-01 | -96390 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 150mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 238 | 2700 | 0 | 96390 | 17350.2 | 2024-08-12 15:57 | Against material installation | 15 |  | 109858 | 2024-08-13 | 124890 | 1900-01-01 | -28500 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Flow Switch 80mm dia (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting 11 to 31 floor OUSTFIRE | 19.95 | 2500 | 0 | 49875 | 8977.5 | 2024-08-12 | Supply and Installation of Flow Switch 80mm dia. | 100 |  | 109861 | 2024-08-13 | 49875 | 1900-01-01 | 0 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Floor to Riser Connection (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 31 | 11345 | 0 | 52754.25 | 9495.76 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -80444.55 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Flow Switch 80mm dia (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 10 | 8425 | 0 | 12637.5 | 2274.76 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -120561.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Inspection Test Valve 50mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 10 | 6185 | 0 | 9277.5 | 1669.96 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -123921.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Installation,Testing & Commissioning | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 1 | 15000 | 0 | 2250 | 405 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -130948.8 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Misc Work DCW | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 1 | 18000 | 0 | 2700 | 486 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -130498.8 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Sprinkler 93 deg. (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 20 | 685 | 0 | 2055 | 369.9 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -131143.8 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Welding Work (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 1 | 4000 | 0 | 600 | 108 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -132598.8 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 40mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 9 | 4475 | 0 | 6041.25 | 1087.42 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -127157.55 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 65mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 11 | 5230 | 0 | 8629.5 | 1553.32 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -124569.3 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Butterfly Valve 80mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 17 | 5476 | 0 | 13963.8 | 2513.48 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -119235 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Drain Valve 50mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 10 | 4960 | 0 | 7440 | 1339.2 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -125758.8 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Flexible Connection (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fighting Work Lobby to Riser Connection | 360 | 275 | 0 | 14850 | 2673 | 2024-08-12 14:40 | Against material installation | 15 |  | 109860 | 2024-08-13 | 133198.8 | 1900-01-01 | -118348.8 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Ball Valve 3/4'' (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 35 | 700 | 0 | 3675 | 661.5 | 2024-08-12 14:51 | Against material installation | 15 |  | 109853 | 2024-08-13 | 23325 | 1900-01-01 | -19650 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Hose pipe 63mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 10 | 3400 | 0 | 5100 | 918 | 2024-08-12 14:52 | Against material installation | 15 |  | 109853 | 2024-08-13 | 23325 | 1900-01-01 | -18225 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Hose Reel Drum (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 10 | 5200 | 0 | 7800 | 1404 | 2024-08-12 14:52 | Against material installation | 15 |  | 109853 | 2024-08-13 | 23325 | 1900-01-01 | -15525 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Hydrant Valve 63mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting Riser work | 10 | 4500 | 0 | 6750 | 1215 | 2024-08-12 14:52 | Against material installation | 15 |  | 109853 | 2024-08-13 | 23325 | 1900-01-01 | -16575 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting 11 to 31 floor OUSTFIRE | 14.4 | 319 | 0 | 4593.6 | 826.84 | 2024-08-13 19:17 | Supply and Installation of Sprinkler 15mm 68 dg Pendent. | 100 |  | 109868 | 2024-08-14 | 12303.6 | 1900-01-01 | -7710 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Rossete Plate (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting 11 to 31 floor OUSTFIRE | 120 | 62 | 0 | 7440 | 1339.2 | 2024-08-13 19:17 | Supply and Installation of Rossete Plate. | 100 |  | 109868 | 2024-08-14 | 12303.6 | 1900-01-01 | -4863.6 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Air Release Valve 25mm (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting 11 to 31 floor OUSTFIRE | 0.3 | 900 | 0 | 270 | 48.6 | 2024-08-13 19:17 | Supply and Installation of Air Release Valve 25mm | 100 |  | 109868 | 2024-08-14 | 12303.6 | 1900-01-01 | -12033.6 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Sprinkler Support (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting 11 to 31 floor OUSTFIRE | 820 | 266 | 0 | 218120 | 39261.6 | 2024-08-13 19:38 | Supply and Installation of Sprinkler Support. | 100 |  | 109867 | 2024-08-14 | 268733.75 | 1900-01-01 | -50613.75 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Fabrication Work (M+L) - Mkt | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1229 | 2021-12-13 | B Fire Fighting 11 to 31 floor OUSTFIRE | 511.25 | 99 | 0 | 50613.75 | 9110.48 | 2024-08-13 19:38 | Supply and Installation of Fabrication material. | 100 |  | 109867 | 2024-08-14 | 268733.75 | 1900-01-01 | -218120 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 25mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 215.385 | 510 | 0 | 109846.35 | 19772.34 | 2024-08-16 14:19 | Supply and Installation of SITC GI Pipe C Class 25mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -733581.91 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 32mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 69.465 | 660 | 0 | 45846.9 | 8252.44 | 2024-08-16 14:19 | Supply and Installation of SITC GI Pipe C Class 32mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -797581.36 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 40mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 71.1735 | 760 | 0 | 54091.86 | 9736.54 | 2024-08-16 14:19 | Supply and Installation of SITC GI Pipe C Class 40mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -789336.4 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 50mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 9.21 | 970 | 0 | 8933.7 | 1608.06 | 2024-08-16 14:19 | Supply and Installation of SITC GI Pipe C Class 50mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -834494.56 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 65mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 2.715 | 1170 | 0 | 3176.55 | 571.78 | 2024-08-16 14:19 | Supply and Installation of SITC GI Pipe C Class 65mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -840251.71 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 80mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 11.37 | 1400 | 0 | 15918 | 2865.24 | 2024-08-16 14:19 | Supply and Installation of SITC GI Pipe C Class 80mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -827510.26 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 125.85 | 319 | 0 | 40146.15 | 7226.3 | 2024-08-16 14:24 | Supply and Installation of Sprinkler 15mm 68dg pendent. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -803282.11 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 20 | 319 | 0 | 6380 | 1148.4 | 2024-08-16 14:29 | Supply and Installation of Sprinkler 15mm 68dg pendent. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -837048.26 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Sprinkler 15mm 68 dg Pendent (M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 380 | 319 | 0 | 121220 | 21819.6 | 2024-08-16 14:31 | Supply and Installation of Sprinkler 15mm 68dg pendent. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -722208.26 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 150mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 13.11 | 2750 | 0 | 36052.5 | 6489.46 | 2024-08-16 14:46 | Supply and Installation of SITC GI Pipe C Class 150mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -807375.76 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
SITC GI Pipe C Class 150mm dia.(M+L) | N/C | N/C | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | 1231 | 2021-12-14 | Tower A& B Parking 2 & 4 Fire Fighting | 146.115 | 2750 | 0 | 401816.25 | 72326.92 | 2024-08-16 14:51 | Supply and Installation of SITC GI Pipe C Class 150mm dia. | 100 |  | 109874 | 2024-08-16 | 843428.26 | 1900-01-01 | -441612.01 | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED
Italian Marble Skirting Mirror polish. | N/C | N/C | Kishan Enterprises | 1251 | 2021-12-30 | A 1604 NOC - 1 No. | 48.752 | 45 | 0 | 2193.84 | 394.9 | 2024-08-21 11:50 | Labour Charges for- Italian Marble Skirting Mirror Polish Work in Children room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish - AIE | N/C | N/C | Kishan Enterprises | 1251 | 2021-12-30 | A 1604 NOC - 1 No. | 177.4909 | 45 | 0 | 7987.0905 | 1437.68 | 2024-08-21 11:50 | Labour Charges for- Italian Marble Mirror Polish Work in Children room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish - AIE | N/C | N/C | Kishan Enterprises | 1251 | 2021-12-30 | A 1604 NOC - 1 No. | 160 | 45 | 0 | 7200 | 1296 | 2024-08-21 11:50 | Labour Charges for- Italian Marble Mirror Polish Work in kitchen room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Skirting Mirror polish. | N/C | N/C | Kishan Enterprises | 1251 | 2021-12-30 | A 1604 NOC - 1 No. | 45 | 45 | 0 | 2025 | 364.5 | 2024-08-21 11:50 | Labour Charges for- Italian Marble Skirting Mirror Polish Work in Kitchen room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 2501 Ledge wall BBM/Plaster Work - | 14.6 | 55 | 0 | 803 | 0 | 2024-08-05 13:00 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -8709.86 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 1501 Ledge wall BBM/Plaster Work | 33.92 | 55 | 0 | 1865.6 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -7647.26 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 1503 Ledge wall BBM/Plaster Work | 43.6 | 55 | 0 | 2398 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -7114.86 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 1802 Ledge wall BBM/Plaster Work | 52.9 | 55 | 0 | 2909.5 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -6603.36 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 2101 Ledge wall BBM/Plaster Work - | 5.6 | 55 | 0 | 308 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -9204.86 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 2103 Ledge wall BBM/Plaster Work | 14.6 | 55 | 0 | 803 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -8709.86 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 2204 Ledge wall BBM/Plaster Work | 2.6 | 55 | 0 | 143 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -9369.86 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 2301 Ledge wall BBM/Plaster Work | 3.392 | 55 | 0 | 186.56 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -9326.3 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 2302 Ledge wall BBM/Plaster Work | 1.749 | 55 | 0 | 96.195 | 0 | 2024-08-05 13:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109615 | 2024-08-05 | 9512.86 | 2024-08-19 13:18 | -9416.665 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 1104 Ledge wall BBM/Plaster Work | 61.4182 | 55 | 0 | 3378.001 | 0 | 2024-08-19 17:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109978 | 2024-08-19 | 4250 | 1900-01-01 | -871.999 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster - Sq.Ft | N/C | N/C | SANTOSH HMMAT CHAVHAN | 1261 | 2022-01-21 | A 1202 Ledge wall BBM/Plaster Work | 15.8545 | 55 | 0 | 871.9975 | 0 | 2024-08-19 17:08 | Labour Charges for- A Tower Ledge Wall ( BBM & Plaster) | 100 |  | 109978 | 2024-08-19 | 4250 | 1900-01-01 | -3378.0025 | SURESH KUMAR MURALIDHAR
MS Sheet Fixing - UST | N/C | N/C | PARTH ENTERPRISES | 1275 | 2022-01-27 | Labour Camp making godown removing in A,B,C Bldg | 1184 | 5 | 0 | 5920 | 0 | 2024-08-19 15:52 | Labour charges for MS Sheet fixing work for Labour Camp making | 100 |  | 109974 | 2024-08-19 | 20740.76 | 1900-01-01 | -14820.76 | PARTH ENTERPRISES
MS Pipe 40 x 40 x 2mm (L) | N/C | N/C | PARTH ENTERPRISES | 1275 | 2022-01-27 | Labour Camp making godown removing in A,B,C Bldg | 337.23 | 12 | 0 | 4046.76 | 0 | 2024-08-19 15:52 | Labour charges for MS Square Pipe (40 x 40 x 2mm) fixing work for Labour Camp making | 100 |  | 109974 | 2024-08-19 | 20740.76 | 1900-01-01 | -16694 | PARTH ENTERPRISES
Door Making Fabrication Work | N/C | N/C | PARTH ENTERPRISES | 1275 | 2022-01-27 | Labour Camp making godown removing in A,B,C Bldg | 4 | 800 | 0 | 3200 | 0 | 2024-08-19 15:52 | Labour charges for Door making & fixing work for Labour Camp making | 100 |  | 109974 | 2024-08-19 | 20740.76 | 1900-01-01 | -17540.76 | PARTH ENTERPRISES
MS Sheet Removing | N/C | N/C | PARTH ENTERPRISES | 1275 | 2022-01-27 | Labour Camp making godown removing in A,B,C Bldg | 1760 | 2.5 | 0 | 4400 | 0 | 2024-08-19 15:52 | Labour charges for MS Sheet removing work for Godown Removing. | 100 |  | 109974 | 2024-08-19 | 20740.76 | 1900-01-01 | -16340.76 | PARTH ENTERPRISES
MS Pipe Removing | N/C | N/C | PARTH ENTERPRISES | 1275 | 2022-01-27 | Labour Camp making godown removing in A,B,C Bldg | 529 | 6 | 0 | 3174 | 0 | 2024-08-19 15:52 | Labour charges for MS Square Pipe (40 x 40 x 2mm) removing for Godown Removing. | 100 |  | 109974 | 2024-08-19 | 20740.76 | 1900-01-01 | -17566.76 | PARTH ENTERPRISES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 3.5 | 0 | 582.61 | 104.86 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31612.67 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 3.5 | 0 | 506.03 | 91.08 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31689.25 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 3.5 | 0 | 582.61 | 104.86 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31612.67 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 3.5 | 0 | 506.03 | 91.08 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31689.25 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 3.5 | 0 | 582.61 | 104.86 | 2024-08-03 | Labour charges for Providing, Fixing and Removing of Scaffolding/Gandola for Texture Painting work. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31612.67 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32124.2 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32028.82 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg North Side 27th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32050.7 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1.75 | 0 | 124.39 | 22.4 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32070.89 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 10th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 11th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 12th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 13th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 14th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 15th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 16th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 17th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 18th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 19th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 1st floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 20th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 21st floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 22nd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 23rd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 24th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 25th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 26th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 2nd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 3rd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 4th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 5th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 6th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 7th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 8th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 9th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 27th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 28th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 29th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 30th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 31st Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Labour charges for Applying 1 coat Water Base Primer with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14347.6 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 27th Floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 28th Floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 29th Floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 30th Floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 31st Floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 21st floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 22nd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 23rd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 24th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 25th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 26th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 2nd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 3rd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 4th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 5th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 6th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 7th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 8th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 9th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 27th Floor External Texture Painting | 71.98 | 1.75 | 0 | 125.965 | 22.68 | 2024-08-06 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14293.615 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 28th Floor External Texture Painting | 71.98 | 1.75 | 0 | 125.965 | 22.68 | 2024-08-06 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14293.615 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 29th Floor External Texture Painting | 71.98 | 1.75 | 0 | 125.965 | 22.68 | 2024-08-06 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14293.615 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 30th Floor External Texture Painting | 71.98 | 1.75 | 0 | 125.965 | 22.68 | 2024-08-06 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14293.615 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg South Side 31st Floor External Texture Painting | 71.98 | 1.75 | 0 | 125.965 | 22.68 | 2024-08-06 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14293.615 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 281 | 1 | 0 | 281 | 50.58 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14138.58 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 200 | 1 | 0 | 200 | 36 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14219.58 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 280 | 1 | 0 | 280 | 50.4 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14139.58 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 200 | 1 | 0 | 200 | 36 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14219.58 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 280 | 1 | 0 | 280 | 50.4 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14139.58 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 164 | 1 | 0 | 164 | 29.52 | 2024-08-06 | Labour Charges for- Water Base Primer with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14255.58 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 281 | 1.5 | 0 | 421.5 | 75.88 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -13998.08 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 10th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 11th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 12th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 13th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 14th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 15th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 16th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 17th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 18th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 19th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 1st floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 20th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 21st floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 22nd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 23rd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 24th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 25th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 26th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 2nd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 3rd floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 4th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 5th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 6th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 7th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 10th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 11th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 12th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 13th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 14th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 15th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 16th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 17th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 18th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 19th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 1st floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A South side 20th floor External Texture Painting | 71.98 | 1.5 | 0 | 107.97 | 19.44 | 2024-08-06 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109728 | 2024-08-12 | 14419.58 | 1900-01-01 | -14311.61 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1.5 | 0 | 106.62 | 19.2 | 2024-08-03 | Labour charges for Applying 1 coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -32088.66 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 1st Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 10th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 11th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 12th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 13th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 14th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 15th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 16th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 17th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 18th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 19th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 1st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 20th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 21st floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 22nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 23rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 24th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 25th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 26th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 2nd floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 3rd floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 4th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 5th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 6th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 7th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 8th floor External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside 9th floor External Texture Painting | 166.46 | 1.5 | 0 | 249.69 | 44.94 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31945.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A Eastside FC Flr External Texture Painting | 144.58 | 1.5 | 0 | 216.87 | 39.04 | 2024-08-03 | Labour Charges for- 2nd Coat Acrylic Paint with Scaffolding/ Gandola. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31978.41 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1.75 | 0 | 291.305 | 52.44 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31903.975 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1.75 | 0 | 253.015 | 45.54 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31942.265 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1.75 | 0 | 291.305 | 52.44 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31903.975 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1.75 | 0 | 253.015 | 45.54 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31942.265 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1292 | 2022-02-08 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1.75 | 0 | 291.305 | 52.44 | 2024-08-03 | Labour charges for Applying 2nd coat Acrylic Paint with scaffolding/Gandola on External surface for A-Bldg. | 100 |  | 109578 | 2024-08-05 | 32195.28 | 1900-01-01 | -31903.975 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 281 | 2 | 0 | 562 | 101.16 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19523.09 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 281 | 2 | 0 | 562 | 101.16 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19523.09 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 281 | 2 | 0 | 562 | 101.16 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19523.09 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 281 | 2 | 0 | 562 | 101.16 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19523.09 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 281 | 2 | 0 | 562 | 101.16 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19523.09 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 200 | 1 | 0 | 200 | 36 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19885.09 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 200 | 1 | 0 | 200 | 36 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19885.09 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 200 | 1 | 0 | 200 | 36 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19885.09 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 200 | 1 | 0 | 200 | 36 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19885.09 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 300 | 1 | 0 | 300 | 54 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19785.09 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 300 | 1 | 0 | 300 | 54 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19785.09 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 10th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 11th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 12th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 13th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 14th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 15th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 16th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 17th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 18th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 19th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 1st floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 20th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 21st floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 22nd floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 23rd floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 24th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 25th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 26th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 2nd floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 3rd floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 4th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 5th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 6th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 7th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 8th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 9th floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 27th Floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 28th Floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 29th Floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 30th Floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 31st Floor External Texture Painting | 71.98 | 2.5 | 0 | 179.95 | 32.4 | 2024-08-06 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19905.14 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 10th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 11th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 12th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 13th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 14th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 15th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 16th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 17th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 18th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 19th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 1st floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 20th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 21st floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 22nd floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 23rd floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 24th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 25th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 26th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 2nd floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 3rd floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 4th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 5th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 6th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 7th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 8th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 9th floor External Texture Painting | 71.98 | 2 | 0 | 143.96 | 25.92 | 2024-08-06 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19941.13 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 27th Floor External Texture Painting | 71.98 | 2.25 | 0 | 161.955 | 29.16 | 2024-08-06 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19923.135 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 28th Floor External Texture Painting | 71.98 | 2.25 | 0 | 161.955 | 29.16 | 2024-08-06 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19923.135 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 29th Floor External Texture Painting | 71.98 | 2.25 | 0 | 161.955 | 29.16 | 2024-08-06 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19923.135 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 8th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 9th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 27th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 28th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 29th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 30th Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 31st Floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 30th Floor External Texture Painting | 71.98 | 2.25 | 0 | 161.955 | 29.16 | 2024-08-06 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19923.135 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg South Side 31st Floor External Texture Painting | 71.98 | 2.25 | 0 | 161.955 | 29.16 | 2024-08-06 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19923.135 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 2.5 | 0 | 177.7 | 31.98 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39722.63 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 281 | 2.5 | 0 | 702.5 | 126.46 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19382.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 281 | 2.5 | 0 | 702.5 | 126.46 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19382.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 281 | 2.5 | 0 | 702.5 | 126.46 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19382.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 281 | 2.5 | 0 | 702.5 | 126.46 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19382.59 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 281 | 2.5 | 0 | 702.5 | 126.46 | 2024-08-06 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -19382.59 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 10th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 11th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 12th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 13th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 14th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 15th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 16th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 17th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 18th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 19th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 1st floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 20th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 21st floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 22nd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 23rd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 24th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 25th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 26th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 2nd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 3rd floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 4th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 5th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 6th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A South side 7th floor External Texture Painting | 71.98 | 1 | 0 | 71.98 | 12.96 | 2024-08-06 | Material Supply for- Water Base Primer | 100 |  | 109729 | 2024-08-12 | 20085.09 | 1900-01-01 | -20013.11 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-02 14:16 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply for- Water Base Primer | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 1 | 0 | 71.08 | 12.8 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39829.25 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 10th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 11th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 12th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 13th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 14th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 15th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 16th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 17th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 18th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 19th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 1st floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 20th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 21st floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 22nd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 23rd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 24th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 25th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 26th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 2nd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 71.08 | 2 | 0 | 142.16 | 25.58 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39758.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 71.08 | 2.25 | 0 | 159.93 | 28.78 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39740.4 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 3rd floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 4th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 5th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 6th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside FC Flr External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply for- 2nd Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 2.5 | 0 | 361.45 | 65.06 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39538.88 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 2.5 | 0 | 416.15 | 74.9 | 2024-08-03 | Material Supply Charges of 2nd Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39484.18 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 1 | 0 | 144.58 | 26.02 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39755.75 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 1 | 0 | 166.46 | 29.96 | 2024-08-03 | Material Supply Charges of Water Base Primer for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39733.87 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 7th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 8th floor External Texture Painting | 144.58 | 2 | 0 | 289.16 | 52.04 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39611.17 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A Eastside 9th floor External Texture Painting | 166.46 | 2 | 0 | 332.92 | 59.92 | 2024-08-03 | Material Supply for- 1st Coat Acrylic Paint. | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39567.41 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 27th Floor External Texture Painting | 166.46 | 2.25 | 0 | 374.535 | 67.42 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39525.795 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 28th Floor External Texture Painting | 144.58 | 2.25 | 0 | 325.305 | 58.56 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39575.025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 29th Floor External Texture Painting | 166.46 | 2.25 | 0 | 374.535 | 67.42 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39525.795 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 30th Floor External Texture Painting | 144.58 | 2.25 | 0 | 325.305 | 58.56 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39575.025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1295 | 2022-02-09 | A-Bldg East Side 31st Floor External Texture Painting | 166.46 | 2.25 | 0 | 374.535 | 67.42 | 2024-08-03 | Material Supply Charges of 1st Coat Acrylic Paint for External Surface of A-Bldg | 100 |  | 109588 | 2024-08-05 | 39900.33 | 1900-01-01 | -39525.795 | SAI NIRMAL COLOURS & TEXTURES
Marketing Operating Expenses | N/C | N/C | SHREYA PRAKASH OSWAL | 1296 | 2022-02-09 | Miscellaneous expenses | 7.2228 | 30000 | 0 | 18056.9278 | 0 | 2024-08-12 | JULY-2024 | 8.3333 |  | 109824 | 2024-08-12 | 18056.93 | 2024-08-20 17:14 | -0.002228 | SUYASH SHRINIVAS BHATI
IPS W/P | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A Fire Check Floor (Internal) Chemical & IPS Waterproofing | 566.621 | 15 | 0 | 8499.315 | 0 | 2024-08-09 15:16 | Labour charges for IPS Waterproofing work for Fire Check Floor Lobby Tower A. | 100 |  | 109758 | 2024-08-12 | 8499.32 | 1900-01-01 | -0.005 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 2801 Chemical Grouting- | 154.5 | 2 | 0 | 309 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 2804 Chemical Grouting- | 1473.6 | 2 | 0 | 2947.2 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 2901 Chemical Grouting | 1520 | 2 | 0 | 3040 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3001 Chemical Grouting- | 152 | 2 | 0 | 304 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3002 Chemical Grouting- | 147.7 | 2 | 0 | 295.4 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3003 Chemical Grouting | 119.19 | 2 | 0 | 238.38 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3004Chemical Grouting | 147.379 | 2 | 0 | 294.758 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3101 Chemical Grouting- | 1520 | 2 | 0 | 3040 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3102 Chemical Grouting | 1477 | 2 | 0 | 2954 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3103 Chemical Grouting- | 1191.9 | 2 | 0 | 2383.8 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 3104 Chemical Grouting | 1473.79 | 2 | 0 | 2947.58 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | AJAY KUMAR GUPTA | 1303 | 2022-02-16 | A 2701 Chemical Grouting | 155 | 2 | 0 | 310 | 0 | 2024-08-20 12:59 | Chemical Grouting work for Internal Flats for Tower A | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chamber Making DLD | N/C | N/C | PRAKASH CONTRACTOR | 1308 | 2022-02-24 | Rain water Harvesting Chamber & Road work after chamber work | 2 | 10000 | 0 | 20000 | 0 | 2024-08-18 12:41 | Charges for Construction of Rainwater Harvesting Chamber including Brickwork, Plaster, Internal & External Cover fixing, etc. | 100 |  | 109956 | 2024-08-19 | 28000 | 1900-01-01 | -8000 | PRAKASH CONTRACTOR
Road Work | N/C | N/C | PRAKASH CONTRACTOR | 1308 | 2022-02-24 | Rain water Harvesting Chamber & Road work after chamber work | 2 | 4000 | 0 | 8000 | 0 | 2024-08-18 12:41 | Charges for Concrete breaking & Finishing Road after Chamber work | 100 |  | 109956 | 2024-08-19 | 28000 | 1900-01-01 | -20000 | PRAKASH CONTRACTOR
Dado Fixing | N/C | N/C | PAPPU BAGELA | 1311 | 2022-02-24 | D Parking Toilet Dado | 184.94 | 21 | 0 | 3883.74 | 0 | 2024-08-18 | Labour charges for Dado Fixing work for D-Bldg Ground Floor Parking Toilet Dado work. | 100 |  | 109952 | 2024-08-19 | 4682.44 | 1900-01-01 | -798.7 | PAPPU BAGELA
Flooring & Floor Guard Laying | N/C | N/C | PAPPU BAGELA | 1311 | 2022-02-24 | D Parking Toilet Flooring | 43 | 16 | 0 | 688 | 0 | 2024-08-18 | Labour charges for Flooring work and Floor Guard sheet laying for D-Bldg Parking Toilet Flooring work. | 100 |  | 109952 | 2024-08-19 | 4682.44 | 1900-01-01 | -3994.44 | PAPPU BAGELA
Granite Cutting & fixing (L) | N/C | N/C | PAPPU BAGELA | 1311 | 2022-02-24 | D Parking Toilet Umbra Patti | 2.46 | 45 | 0 | 110.7 | 0 | 2024-08-18 | Labour charges for Granite Cutting and Fixing for D-Bldg Parking Toilet Umbra Patti work. | 100 |  | 109952 | 2024-08-19 | 4682.44 | 1900-01-01 | -4571.74 | PAPPU BAGELA
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 29th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 2nd Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 30th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 31st Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 3rd Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 4th Floor Lift Openings Brickwork&Plaster | 0.25 | 15500 | 0 | 3875 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137625 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 5th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 6th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 7th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 8th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 9th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg Terrace Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | A 27th Floor Lift Opening Brickwork/Plaster | 1 | 4500 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work. | 100 |  | 109723 | 2024-08-12 | 27000 | 1900-01-01 | -22500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | A 28th Floor Lift Opening Brickwork/Plaster | 1 | 4500 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work. | 100 |  | 109723 | 2024-08-12 | 27000 | 1900-01-01 | -22500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | A 29th Floor Lift Opening Brickwork/Plaster | 1 | 4500 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work. | 100 |  | 109723 | 2024-08-12 | 27000 | 1900-01-01 | -22500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | A 2nd Floor Lift Opening Brickwork/Plaster | 1 | 4500 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work. | 100 |  | 109723 | 2024-08-12 | 27000 | 1900-01-01 | -22500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | A 30th Floor Lift Opening Brickwork/Plaster | 1 | 4500 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work. | 100 |  | 109723 | 2024-08-12 | 27000 | 1900-01-01 | -22500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | A 31th Floor Lift Opening Brickwork/Plaster | 1 | 4500 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work. | 100 |  | 109723 | 2024-08-12 | 27000 | 1900-01-01 | -22500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B P1 Parking Floor Lift Opening Brickwork/Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109724 | 2024-08-12 | 18000 | 1900-01-01 | -13500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B P2 lvl Lift opening Brickwork/Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109724 | 2024-08-12 | 18000 | 1900-01-01 | -13500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B P3 lvl Lift opening Brickwork/Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109724 | 2024-08-12 | 18000 | 1900-01-01 | -13500 | SURESH KUMAR MURALIDHAR
Brickwork/ Plaster Labour | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B P4 lvl Lift opening Brickwork/Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-06 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109724 | 2024-08-12 | 18000 | 1900-01-01 | -13500 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 10th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 11th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 12th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 13th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 14th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 15th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 16th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 17th Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 18th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 19th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 1st Floor Lift Openings Brickwork&Plaster | 0.25 | 17500 | 0 | 4375 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137125 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 20th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 21st Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 22nd Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 23rd Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 24th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 25th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 26th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 27th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Brickwork/Plaster Labour- Dld | N/C | N/C | JAY GANESH ENTERPRISES | 1321 | 2022-02-26 | B Bldg 28th Floor Lift Openings Brickwork&Plaster | 0.25 | 18000 | 0 | 4500 | 0 | 2024-08-03 | Labour Charges for 9 inch Brickwork and single coat sand face plaster including material shifting,loading,unloading,contractor profit and lintel making and casting work.(For 4 Nos of Lift) | 100 |  | 109590 | 2024-08-05 | 141500 | 2024-08-19 13:19 | -137000 | SURESH KUMAR MURALIDHAR
Gypsum Plaster (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1329 | 2022-03-10 | A 3103 Gypsum Plaster | 2693.925 | 3.5 | 0 | 9428.7375 | 0 | 2024-08-09 11:32 | Material Supply charges of Gypsum for A-Bldg Internal Flat for above 27th Floor. | 100 |  | 109753 | 2024-08-12 | 9428.74 | 1900-01-01 | -0.0025 | A K INTERIOR CONTRACTOR
Printer Repairing- | N/C | N/C | A.S.INFOTECH SOLUTION | 1337 | 2022-03-23 | HO Expensess (L) | 11.775 | 8000 | 0 | 7849.9686 | 1413 | 2024-08-12 | APR-2024 | 8.3333 | 2425/063 | 109863 | 2024-08-13 | 7849.97 | 1900-01-01 | -0.0014 | A.S.INFOTECH SOLUTION
Printer Repairing- | N/C | N/C | A.S.INFOTECH SOLUTION | 1337 | 2022-03-23 | HO Expensess (L) | 11.8425 | 8000 | 0 | 7894.9684 | 1421.1 | 2024-08-12 | MAY-2024 | 8.3333 |  | 109864 | 2024-08-13 | 7894.97 | 1900-01-01 | -0.00158 | A.S.INFOTECH SOLUTION
Printer Repairing- | N/C | N/C | A.S.INFOTECH SOLUTION | 1337 | 2022-03-23 | HO Expensess (L) | 12 | 8000 | 0 | 7999.968 | 1440 | 2024-08-12 | JUNE-2024 | 8.3333 |  | 109865 | 2024-08-13 | 7999.97 | 1900-01-01 | -0.002 | A.S.INFOTECH SOLUTION
Toner refilling | N/C | N/C | SHREE VARAD ENTERPRISES | 1338 | 2022-03-23 | HO Expensess (L) | 11.7 | 4000 | 0.02 | 3899.9844 | 0 | 2024-08-07 | MAY-2024 | 8.3333 | Tonner Refeeling May 2024 | 109680 | 2024-08-08 | 3900 | 2024-08-19 13:32 | -0.0156 | SHREE VARAD ENTERPRISES
Toner refilling | N/C | N/C | SHREE VARAD ENTERPRISES | 1338 | 2022-03-23 | HO Expensess (L) | 10.35 | 4000 | 0.01 | 3449.9862 | 0 | 2024-08-07 | JUNE-2024 | 8.3333 | Tonner Refeeling June 2024 | 109681 | 2024-08-08 | 3450 | 2024-08-19 13:39 | -0.0138 | SHREE VARAD ENTERPRISES
Italian Marble Mirror Polish- BCo | N/C | N/C | Kishan Enterprises | 1350 | 2022-03-29 | A 2104 NOC | 123.417 | 50 | 0 | 6170.85 | 1110.76 | 2024-08-22 14:37 | Labour Charges for Italian marble mirror polish work for children room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | Kishan Enterprises | 1350 | 2022-03-29 | A 2104 NOC | 48.752 | 50 | 0 | 2437.6 | 438.76 | 2024-08-22 14:37 | Labour Charges for Skirting mirror polish work for Children room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish- BCo | N/C | N/C | Kishan Enterprises | 1352 | 2022-03-29 | A 2404 NOC - 1 No. | 337 | 50 | 0 | 16850 | 3033 | 2024-08-22 14:35 | Labour charges for- Italian Mirror Polish work in Kitchen and Children Bed Room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | Kishan Enterprises | 1352 | 2022-03-29 | A 2404 NOC - 1 No. | 93.4635 | 50 | 0 | 4673.175 | 841.18 | 2024-08-22 14:35 | Labour charges for- Italian Marble Skirting Mirror Polish work in Kitchen and Children Bedroom. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Fabrication Work (L) - BCo | N/C | N/C | PARTH ENTERPRISES | 1366 | 2022-04-26 | Tower C Terrace Safety Railing 1st to 31st floor | 660 | 12 | 0 | 7920 | 1425.6 | 2024-08-05 | Labour Charges for Fixing of MS Pipe for Edge Barrication work from 1st floor to 31st floor of C Building. | 100 | Tower C Floor 2 & Floor 3 | 109625 | 2024-08-05 | 7920 | 1900-01-01 | 0 | MAHALAXMI FABRICATORS
Italian Marble Flooring - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2702 Guest Bed Marble Tiling | 50.5556 | 90 | 0 | 4550.004 | 0 | 2024-08-12 11:23 | Labour Charges for Italian marble flooring work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109789 | 2024-08-12 | 4550 | 1900-01-01 | 0.004 | SURESH KUMAR MURALIDHAR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Guest Bed Marble Tiling-(No.) | 85.408 | 90 | 0 | 7686.72 | 1383.6 | 2024-08-18 11:31 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -187718.96 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2801 Living,Dining,Passa. Marble Til - 1 No. | 108.59 | 90 | 0 | 9773.1 | 1759.16 | 2024-08-18 11:36 | Labour Charges for Italian marble flooring work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -185632.58 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2801 Living,Dining,Passa. Marble Til - 1 No. | 105 | 90 | 0 | 9450 | 1701 | 2024-08-18 11:36 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -185955.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2801 Parents Bed Marble Tiling - 1 No. | 50.4 | 90 | 0 | 4536 | 816.48 | 2024-08-18 11:36 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -190869.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2801 Master Bed Marble Tiling - 1 No. | 50.4 | 90 | 0 | 4536 | 816.48 | 2024-08-18 11:36 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -190869.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Bed Marble Tiling - 1 No. | 44 | 90 | 0 | 3960 | 712.8 | 2024-08-18 11:49 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191445.68 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Living,Dining,Passa. Marble Tiling - 1 No. | 35.262 | 80 | 0 | 2820.96 | 507.78 | 2024-08-18 11:49 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192584.72 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Bed Marble Tiling - 1 No. | 18.702 | 80 | 0 | 1496.16 | 269.3 | 2024-08-18 11:49 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193909.52 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Guest Bed Marble Tiling - 1 No. | 9.474 | 80 | 0 | 757.92 | 136.42 | 2024-08-18 11:49 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194647.76 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Master Bed Marble Tiling - 1 No. | 19.686 | 80 | 0 | 1574.88 | 283.48 | 2024-08-18 11:49 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193830.8 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Living,Dining,Passa. Marble Tiling-(No.) | 101.7 | 90 | 0 | 9153 | 1647.54 | 2024-08-18 11:56 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -186252.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Master Bed Marble Tiling-(No.) | 60 | 90 | 0 | 5400 | 972 | 2024-08-18 11:56 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -190005.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Bed Marble Tiling-(No.)-(No.) | 50 | 90 | 0 | 4500 | 810 | 2024-08-18 11:56 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -190905.68 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Guest Bed Marble Tiling | 9.474 | 80 | 0 | 757.92 | 136.42 | 2024-08-18 11:56 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194647.76 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Living,Dining,Passa. Marble Tiling-(No.) | 34.377 | 80 | 0 | 2750.16 | 495.02 | 2024-08-18 11:56 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192655.52 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Master Bed Marble Tiling-(No.) | 20.07 | 80 | 0 | 1605.6 | 289 | 2024-08-18 11:56 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193800.08 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Bed Marble Tiling-(No.)-(No.) | 14.901 | 80 | 0 | 1192.08 | 214.58 | 2024-08-18 11:56 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194213.6 | R K INTERIOR
Italian Marble Sill- BC- | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2801 Marble Window Sill | 47.088 | 99.22 | 0 | 4672.0714 | 840.98 | 2024-08-18 12:47 | Labour charges for Fixing of Italian Marble Window sill with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for A-Bldg Internal Flat | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -190733.6086 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2801 Marble Window Sill | 15.69 | 61.42 | 0 | 963.6798 | 173.46 | 2024-08-18 12:47 | Labour charges for Italian Marble Mirror Polish work for Window sill for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194442.0002 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Marble Window Sill - 52.32 R.Ft | 14.22 | 61.42 | 0 | 873.3924 | 157.22 | 2024-08-18 12:50 | Labour charges for Italian Marble Mirror Polish work for Window sill for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194532.2876 | R K INTERIOR
Italian Marble Sill- BC- | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Marble Window Sill | 42.64 | 99.22 | 0 | 4230.7408 | 761.54 | 2024-08-18 12:51 | Labour charges for Fixing of Italian Marble Window sill with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for A-Bldg Internal Flat | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191174.9392 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Marble Window Sill | 15.99 | 61.42 | 0 | 982.1058 | 176.78 | 2024-08-18 12:51 | Labour charges for Italian Marble Mirror Polish work for Window sill for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194423.5742 | R K INTERIOR
Italian Marble Sill- BC- | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Marble Window Sill | 23.088 | 99.22 | 0 | 2290.7914 | 412.34 | 2024-08-18 12:54 | Labour charges for Fixing of Italian Marble Window sill with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for A-Bldg Internal Flat | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193114.8886 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Marble Window Sill | 8.658 | 61.42 | 0 | 531.7744 | 95.72 | 2024-08-18 12:54 | Labour charges for Italian Marble Mirror Polish work for Window sill for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194873.9056 | R K INTERIOR
Ceramic Flooring work | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Tiling Below Wooden Flooring | 147.6 | 28.35 | 0 | 4184.46 | 753.2 | 2024-08-18 14:07 | Labour charges for Fixing of Ceramic Flooring work with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat Below Wooden Flooring. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191221.22 | R K INTERIOR
Ceramic Flooring work | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Tiling Below Wooden Flooring | 147.6 | 28.35 | 0 | 4184.46 | 753.2 | 2024-08-18 14:09 | Labour charges for Fixing of Ceramic Flooring work with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat Below Wooden Flooring. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191221.22 | R K INTERIOR
Ceramic Flooring work | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Tiling Below Wooden Flooring | 142.74 | 28.35 | 0 | 4046.679 | 728.4 | 2024-08-18 14:10 | Labour charges for Fixing of Ceramic Flooring work with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat Below Wooden Flooring. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191359.001 | R K INTERIOR
Ceramic Flooring work | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Tiling Below Wooden Flooring | 181.48 | 28.35 | 0 | 5144.958 | 926.1 | 2024-08-18 14:12 | Labour charges for Fixing of Ceramic Flooring work with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat Below Wooden Flooring. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -190260.722 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Guest Bed Marble Tiling-(No.) | 36 | 90 | 0 | 3240 | 583.2 | 2024-08-18 12:11 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192165.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Living,Dining,Passa. Marble Tiling-(No.) | 93.6 | 90 | 0 | 8424 | 1516.32 | 2024-08-18 12:11 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -186981.68 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Master Bed Marble Tiling-(No.) | 40 | 90 | 0 | 3600 | 648 | 2024-08-18 12:11 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191805.68 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Guest Bed Marble Tiling-(No.) | 12.501 | 80 | 0 | 1000.08 | 180.02 | 2024-08-18 12:11 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194405.6 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Living,Dining,Passa. Marble Tiling-(No.) | 30.465 | 80 | 0 | 2437.2 | 438.7 | 2024-08-18 12:11 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192968.48 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3103 Master Bed Marble Tiling-(No.) | 14.067 | 80 | 0 | 1125.36 | 202.56 | 2024-08-18 12:11 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194280.32 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Toilet Counter wash Basin | 1.4268 | 61.42 | 0 | 87.6341 | 15.78 | 2024-08-19 10:21 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195318.0459 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Powder Toilet Counter wash Basin | 1.4268 | 61.42 | 0 | 87.6341 | 15.78 | 2024-08-19 10:21 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195318.0459 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Children Toilet Counter wash Basin | 3.3 | 80.32 | 0 | 265.056 | 47.72 | 2024-08-19 10:21 | Labour charges for Italian Marble Champher Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195140.624 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Toilet Counter wash Basin | 3.3 | 80.32 | 0 | 265.056 | 47.72 | 2024-08-19 10:21 | Labour charges for Italian Marble Champher Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195140.624 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Children Toilet Counter wash Basin | 3.7602 | 756 | 0 | 2842.7112 | 511.68 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192562.9688 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Master Toilet Counter wash Basin | 1.752 | 756 | 0 | 1324.512 | 238.42 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194081.168 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Toilet Counter wash Basin | 3.6612 | 756 | 0 | 2767.8672 | 498.22 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192637.8128 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Powder Toilet Counter wash Basin | 1.4958 | 756 | 0 | 1130.8248 | 203.54 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194274.8552 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Children Toilet Counter wash Basin | 5.0394 | 99.22 | 0 | 500.0093 | 90 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194905.6707 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Master Toilet Counter wash Basin | 2.7756 | 99.22 | 0 | 275.395 | 49.58 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195130.285 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Toilet Counter wash Basin | 4.7442 | 99.22 | 0 | 470.7195 | 84.72 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -194934.9605 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Powder Toilet Counter wash Basin | 2.3028 | 99.22 | 0 | 228.4838 | 41.12 | 2024-08-19 10:38 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195177.1962 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Children Toilet Counter wash Basin | 4.998 | 33.07 | 0 | 165.2839 | 29.76 | 2024-08-19 10:38 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195240.3961 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Master Toilet Counter wash Basin | 2.748 | 33.07 | 0 | 90.8764 | 16.36 | 2024-08-19 10:38 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195314.8036 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Toilet Counter wash Basin | 4.7442 | 33.07 | 0 | 156.8907 | 28.24 | 2024-08-19 10:38 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195248.7893 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Powder Toilet Counter wash Basin | 2.3028 | 33.07 | 0 | 76.1536 | 13.7 | 2024-08-19 10:38 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195329.5264 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Children Toilet Counter wash Basin | 4.0494 | 61.42 | 0 | 248.7141 | 44.76 | 2024-08-19 10:38 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195156.9659 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Master Toilet Counter wash Basin | 1.8924 | 61.42 | 0 | 116.2312 | 20.92 | 2024-08-19 10:38 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195289.4488 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Toilet Counter wash Basin | 4.6368 | 61.42 | 0 | 284.7923 | 51.26 | 2024-08-19 10:38 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195120.8877 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Powder Toilet Counter wash Basin | 1.5498 | 61.42 | 0 | 95.1887 | 17.14 | 2024-08-19 10:38 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195310.4913 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Children Toilet Counter wash Basin | 3.3 | 80.32 | 0 | 265.056 | 47.72 | 2024-08-19 10:38 | Labour charges for Italian Marble Champher Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195140.624 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Toilet Counter wash Basin | 3.3 | 80.32 | 0 | 265.056 | 47.72 | 2024-08-19 10:38 | Labour charges for Italian Marble Champher Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195140.624 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Toilet & Dry Balcony Devider Patti | 35.976 | 99.22 | 0 | 3569.5387 | 642.52 | 2024-08-19 10:42 | Labour charges for Fixing of Italian Marble Patti with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc.for A-Bldg Internal Flat Toilet & Dry Balcony area. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191836.1413 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Toilet & Dry Balcony Devider Patti | 53.964 | 61.42 | 0 | 3314.4689 | 596.6 | 2024-08-19 10:42 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Toilet & dry Balcony divider Patti. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192091.2111 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Toilet & Dry Balcony Devider Patti | 35.976 | 80.32 | 0 | 2889.5923 | 520.12 | 2024-08-19 10:42 | Labour charges for Italian Marble Champher and Polish work for A-Bldg Internal Flat Toilet & Dry Balcony Divider Patti work. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192516.0877 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701Toilet & Dry Balcony Devider Patti | 34.398 | 99.22 | 0 | 3412.9696 | 614.34 | 2024-08-19 10:45 | Labour charges for Fixing of Italian Marble Patti with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc.for A-Bldg Internal Flat Toilet & Dry Balcony area. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -191992.7104 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701Toilet & Dry Balcony Devider Patti | 51.597 | 61.42 | 0 | 3169.0877 | 570.44 | 2024-08-19 10:45 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Toilet & dry Balcony divider Patti. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192236.5923 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701Toilet & Dry Balcony Devider Patti | 34.398 | 80.32 | 0 | 2762.8474 | 497.32 | 2024-08-19 10:45 | Labour charges for Italian Marble Champher and Polish work for A-Bldg Internal Flat Toilet & Dry Balcony Divider Patti work. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192642.8326 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Toilet & Dry Balcony Devider Patti | 24.012 | 99.22 | 0 | 2382.4706 | 428.84 | 2024-08-19 10:47 | Labour charges for Fixing of Italian Marble Patti with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc.for A-Bldg Internal Flat Toilet & Dry Balcony area. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193023.2094 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Toilet & Dry Balcony Devider Patti | 36.018 | 61.42 | 0 | 2212.2256 | 398.2 | 2024-08-19 10:47 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Toilet & dry Balcony divider Patti. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193193.4544 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Toilet & Dry Balcony Devider Patti | 24.012 | 80.32 | 0 | 1928.6438 | 347.16 | 2024-08-19 10:47 | Labour charges for Italian Marble Champher and Polish work for A-Bldg Internal Flat Toilet & Dry Balcony Divider Patti work. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193477.0362 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Toilet & Dry Balcony Devider Patti - 40.02 R.Ft | 24.012 | 99.22 | 0 | 2382.4706 | 428.84 | 2024-08-19 10:49 | Labour charges for Fixing of Italian Marble Patti with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc.for A-Bldg Internal Flat Toilet & Dry Balcony area. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193023.2094 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Toilet & Dry Balcony Devider Patti - 40.02 R.Ft | 36.018 | 61.42 | 0 | 2212.2256 | 398.2 | 2024-08-19 10:49 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Toilet & dry Balcony divider Patti. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193193.4544 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Toilet & Dry Balcony Devider Patti - 40.02 R.Ft | 24.012 | 80.32 | 0 | 1928.6438 | 347.16 | 2024-08-19 10:49 | Labour charges for Italian Marble Champher and Polish work for A-Bldg Internal Flat Toilet & Dry Balcony Divider Patti work. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193477.0362 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Marble Window Sill | 28.86 | 61.42 | 0 | 1772.5812 | 319.06 | 2024-08-18 12:34 | Labour charges for Italian Marble Mirror Polish work for Window sill for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193633.0988 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2702 Guest Bed Marble Tiling | 14.4444 | 90 | 0 | 1299.996 | 0 | 2024-08-19 17:00 | Labour Charges for Italian marble flooring work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109953 | 2024-08-19 | 2600 | 1900-01-01 | -1300.004 | SURESH KUMAR MURALIDHAR
Italian marble Skirting - BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 3002 Parents Bed Marble Tiling-(No.)-(No.) | 14.4444 | 90 | 0 | 1299.996 | 0 | 2024-08-19 17:02 | Labour Charges for Italian Marble Skirting work for internal flat of A Building with line,level,right angle and proper joint filling etc complete. | 100 |  | 109953 | 2024-08-19 | 2600 | 1900-01-01 | -1300.004 | SURESH KUMAR MURALIDHAR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Children Toilet Counter wash Basin | 3.189 | 756 | 0 | 2410.884 | 433.96 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192994.796 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Guest Toilet Counter wash Basin | 2.9526 | 756 | 0 | 2232.1656 | 401.8 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193173.5144 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Master Toilet Counter wash Basin | 3.189 | 756 | 0 | 2410.884 | 433.96 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192994.796 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Powder Toilet Counter wash Basin | 2.9724 | 756 | 0 | 2247.1344 | 404.48 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193158.5456 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Children Toilet Counter wash Basin | 3.504 | 99.22 | 0 | 347.6669 | 62.58 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195058.0131 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Guest Toilet Counter wash Basin | 3.048 | 99.22 | 0 | 302.4226 | 54.44 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195103.2574 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Master Toilet Counter wash Basin | 3.3858 | 99.22 | 0 | 335.9391 | 60.46 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195069.7409 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Powder Toilet Counter wash Basin | 3.0708 | 99.22 | 0 | 304.6848 | 54.84 | 2024-08-19 10:08 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195100.9952 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Children Toilet Counter wash Basin | 3.6036 | 61.42 | 0 | 221.3331 | 39.84 | 2024-08-19 10:08 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195184.3469 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Guest Toilet Counter wash Basin | 2.4216 | 61.42 | 0 | 148.7347 | 26.78 | 2024-08-19 10:08 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195256.9453 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Master Toilet Counter wash Basin | 3.4812 | 61.42 | 0 | 213.8153 | 38.48 | 2024-08-19 10:08 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195191.8647 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2703 Powder Toilet Counter wash Basin | 3.3 | 61.42 | 0 | 202.686 | 36.48 | 2024-08-19 10:08 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195202.994 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Children Toilet Counter wash Basin | 3.189 | 756 | 0 | 2410.884 | 433.96 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192994.796 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Guest Toilet Counter wash Basin | 2.9526 | 756 | 0 | 2232.1656 | 401.8 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193173.5144 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Master Toilet Counter wash Basin | 3.189 | 756 | 0 | 2410.884 | 433.96 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -192994.796 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Powder Toilet Counter wash Basin | 2.9724 | 756 | 0 | 2247.1344 | 404.48 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Counter with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc. for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -193158.5456 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Children Toilet Counter wash Basin | 3.504 | 99.22 | 0 | 347.6669 | 62.58 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195058.0131 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Guest Toilet Counter wash Basin | 3.048 | 99.22 | 0 | 302.4226 | 54.44 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195103.2574 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Master Toilet Counter wash Basin | 3.3858 | 99.22 | 0 | 335.9391 | 60.46 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195069.7409 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Powder Toilet Counter wash Basin | 3.0708 | 99.22 | 0 | 304.6848 | 54.84 | 2024-08-19 10:15 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195100.9952 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Children Toilet Counter wash Basin | 3.504 | 33.07 | 0 | 115.8773 | 20.86 | 2024-08-19 10:15 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195289.8027 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Guest Toilet Counter wash Basin | 3.048 | 33.07 | 0 | 100.7974 | 18.14 | 2024-08-19 10:15 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195304.8826 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Master Toilet Counter wash Basin | 3.3858 | 33.07 | 0 | 111.9684 | 20.16 | 2024-08-19 10:15 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195293.7116 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Powder Toilet Counter wash Basin | 3.0708 | 33.07 | 0 | 101.5514 | 18.28 | 2024-08-19 10:15 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195304.1286 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Children Toilet Counter wash Basin | 3.6036 | 61.42 | 0 | 221.3331 | 39.84 | 2024-08-19 10:15 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195184.3469 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Guest Toilet Counter wash Basin | 2.4216 | 61.42 | 0 | 148.7347 | 26.78 | 2024-08-19 10:15 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195256.9453 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Master Toilet Counter wash Basin | 3.4812 | 61.42 | 0 | 213.8153 | 38.48 | 2024-08-19 10:15 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195191.8647 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Powder Toilet Counter wash Basin | 3.3 | 61.42 | 0 | 202.686 | 36.48 | 2024-08-19 10:15 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195202.994 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Children Toilet Counter wash Basin | 3.3 | 80.32 | 0 | 265.056 | 47.72 | 2024-08-19 10:15 | Labour charges for Italian Marble Champher Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195140.624 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Guest Toilet Counter wash Basin | 3.3 | 80.32 | 0 | 265.056 | 47.72 | 2024-08-19 10:15 | Labour charges for Italian Marble Champher Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195140.624 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Children Toilet Counter wash Basin | 2.9034 | 99.22 | 0 | 288.0753 | 51.86 | 2024-08-19 10:21 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195117.6047 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Master Toilet Counter wash Basin | 3.2286 | 99.22 | 0 | 320.3417 | 57.66 | 2024-08-19 10:21 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195085.3383 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Toilet Counter wash Basin | 3.366 | 99.22 | 0 | 333.9745 | 60.12 | 2024-08-19 10:21 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195071.7055 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Powder Toilet Counter wash Basin | 2.2242 | 99.22 | 0 | 220.6851 | 39.72 | 2024-08-19 10:21 | Labour charges for Fixing of Italian Marble Border with proper cutting, shifting, fixing with proper line level with proper joint filling, right angle etc for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195184.9949 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Children Toilet Counter wash Basin | 2.9034 | 33.07 | 0 | 96.0154 | 17.28 | 2024-08-19 10:21 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195309.6646 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Master Toilet Counter wash Basin | 3.2286 | 33.07 | 0 | 106.7698 | 19.22 | 2024-08-19 10:21 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195298.9102 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Toilet Counter wash Basin | 3.366 | 33.07 | 0 | 111.3136 | 20.04 | 2024-08-19 10:21 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195294.3664 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Powder Toilet Counter wash Basin | 2.2242 | 33.07 | 0 | 73.5543 | 13.24 | 2024-08-19 10:21 | Labour charges for Italian Marble Edge Polish Work for A-Bldg Internal Flat. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195332.1257 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Children Toilet Counter wash Basin | 2.1312 | 61.42 | 0 | 130.8983 | 23.56 | 2024-08-19 10:21 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195274.7817 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Master Toilet Counter wash Basin | 2.88 | 61.42 | 0 | 176.8896 | 31.84 | 2024-08-19 10:21 | Labour charges for Italian Marble Mirror Polish work for A-Bldg Internal Flat Wash Basin Counter. | 100 |  | 109954 | 2024-08-19 | 195405.68 | 1900-01-01 | -195228.7904 | R K INTERIOR
Professional Fees | N/C | N/C | GIRIRAJ DHANSHYAM MANTRI | 1383 | 2022-06-25 | Professional Consultancy (Finalcial) | 1 | 130000 | 0 | 130000 | 0 | 2024-08-05 | Charges for Professional Fees for the Month of JULY-2024 | 100 |  | 109488 | 2024-08-05 | 130000 | 2024-08-05 12:51 | 0 | GIRIRAJ DHANSHYAM MANTRI
G.I. Sheet Fixing - BC | N/C | N/C | MAHALAXMI FABRICATORS | 1398 | 2022-07-07 | Labour Camp making | 2384.441 | 5 | 0 | 11922.205 | 2146 | 2024-08-12 16:31 | Labour Charges for GI Sheet fixing work with self tapping screw for Labour camp hutments making work | 100 |  | 109829 | 2024-08-12 | 27172.21 | 1900-01-01 | -15250.005 | MAHALAXMI FABRICATORS
MS Square Pipe (L) | N/C | N/C | MAHALAXMI FABRICATORS | 1398 | 2022-07-07 | Labour Camp making | 632.143 | 14 | 0 | 8850.002 | 1593 | 2024-08-12 16:31 | Labour Charges for Fixing of MS Square pipe 40 x 40 for labour hutments making work. | 100 |  | 109829 | 2024-08-12 | 27172.21 | 1900-01-01 | -18322.208 | MAHALAXMI FABRICATORS
M.S. Door -BCo | N/C | N/C | MAHALAXMI FABRICATORS | 1398 | 2022-07-07 | Labour Camp making | 8 | 800 | 0 | 6400 | 1152 | 2024-08-12 16:31 | Labour Charges for Making and Fixing of MS Door for labour hutments. | 100 |  | 109829 | 2024-08-12 | 27172.21 | 1900-01-01 | -20772.21 | MAHALAXMI FABRICATORS
Horizontal Core Cutting 125mm | N/C | N/C | SAROJ KUMAR PRADHAN | 1404 | 2022-07-26 | A Building - 111 Lvl. ( Podium ) core cutting work | 9 | 265 | 0 | 2385 | 0 | 2024-08-12 | Charges for 5 inch Horizontal core cutting for Drainage Line at Podium 111 level to 99 level Service Platform at A Building for Plumbing Services | 100 |  | 109806 | 2024-08-12 | 17410 | 1900-01-01 | -15025 | SAROJ KUMAR PRADHAN
Vertical Core Cutting 125mm | N/C | N/C | SAROJ KUMAR PRADHAN | 1404 | 2022-07-26 | A Building - 111 Lvl. ( Podium ) core cutting work | 35 | 175 | 0 | 6125 | 0 | 2024-08-12 | Charges for 5 inch Vertical core cutting for Drainage Line at Podium 111 level to 99 level Service Platform at A Building for Plumbing Services | 100 |  | 109806 | 2024-08-12 | 17410 | 1900-01-01 | -11285 | SAROJ KUMAR PRADHAN
Vertical Core Cutting 200mm | N/C | N/C | SAROJ KUMAR PRADHAN | 1404 | 2022-07-26 | A Building - 111 Lvl. ( Podium ) core cutting work | 10 | 500 | 0 | 5000 | 0 | 2024-08-12 | Charges for 8 inch Vertical core cutting for Drainage Line at Podium 111 level to 99 level Service Platform at A Building for Plumbing Services | 100 |  | 109806 | 2024-08-12 | 17410 | 1900-01-01 | -12410 | SAROJ KUMAR PRADHAN
Horizontal core cutting 200mm | N/C | N/C | SAROJ KUMAR PRADHAN | 1404 | 2022-07-26 | A Building - 111 Lvl. ( Podium ) core cutting work | 6 | 650 | 0 | 3900 | 0 | 2024-08-12 | Charges for 8 inch Horizontal core cutting for Drainage Line at Podium 111 level to 99 level Service Platform at A Building for Plumbing Services | 100 |  | 109806 | 2024-08-12 | 17410 | 1900-01-01 | -13510 | SAROJ KUMAR PRADHAN
Scaffolding Removing | N/C | N/C | PRAKASH CONTRACTOR | 1409 | 2022-08-08 | B 102 to 108 level Scaffolding for Atrium POP, plaster | 581.04 | 2 | 0 | 1162.08 | 0 | 2024-08-12 | Labour Charges for Removing of Scaffolding work at B Building entrance lobby 105 & 108 level. | 100 |  | 109779 | 2024-08-12 | 1162.08 | 1900-01-01 | 0 | PRAKASH CONTRACTOR
TEa Expenses AIE - No. | N/C | N/C | NARPAT SINGH CHOUHAN | 149 | 2016-12-29 | Site Office Indirect Expenses | 604 | 4 | 0 | 2416 | 0 | 2024-08-06 | Tea Expenses for the Month of JULY-2024 | 100 |  | 109725 | 2024-08-12 | 21820 | 2024-08-21 10:44 | -19404 | DILIP KUMAR
TEa Expenses AIE - No. | N/C | N/C | NARPAT SINGH CHOUHAN | 149 | 2016-12-29 | Site Office Indirect Expenses | 4851 | 4 | 0 | 19404 | 0 | 2024-08-06 | Tea Expenses for the Month of JULY-2024 | 100 |  | 109725 | 2024-08-12 | 21820 | 2024-08-21 10:44 | -2416 | DILIP KUMAR
Shifting Charges-SO | N/C | N/C | SIDDHIVINAYAK CORPORATION | 1496 | 2023-01-11 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | 9 | 3500 | 0 | 31500 | 5670 | 2024-08-08 | Charges for Shifting of Gandola location within same building if required including material and labour.(10 Number of Shifting per month) | 100 |  | 109749 | 2024-08-12 | 149500 | 1900-01-01 | -118000 | SIDDHIVINAYAK CORPORATION
Shifting Charges-SO | N/C | N/C | SIDDHIVINAYAK CORPORATION | 1496 | 2023-01-11 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | 4 | 3500 | 0 | 14000 | 2520 | 2024-08-08 | Charges for Shifting of Gandola location within same building (B Building) if required including material and labour.(10 Number of Shifting per month) | 100 |  | 109749 | 2024-08-12 | 149500 | 1900-01-01 | -135500 | SIDDHIVINAYAK CORPORATION
Hiring of Gandola. | N/C | N/C | SIDDHIVINAYAK CORPORATION | 1496 | 2023-01-11 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | 2 | 26000 | 0 | 52000 | 9360 | 2024-08-08 | Hiring Charges for Gandola from 8th JUNE 2024 to 8th JULY-2024 for A-Bldg. | 100 |  | 109749 | 2024-08-12 | 149500 | 1900-01-01 | -97500 | SIDDHIVINAYAK CORPORATION
Hiring of Gandola. | N/C | N/C | SIDDHIVINAYAK CORPORATION | 1496 | 2023-01-11 | A Gondola Fixing & Removing for Facade Work (Rent Basis) | 1 | 26000 | 0 | 26000 | 4680 | 2024-08-08 | Hiring Charges for Gandola from 8th MAY 2024 to 8th JUNE-2024 for A-Bldg. | 100 |  | 109749 | 2024-08-12 | 149500 | 1900-01-01 | -123500 | SIDDHIVINAYAK CORPORATION
Hiring of Gandola. | N/C | N/C | SIDDHIVINAYAK CORPORATION | 1496 | 2023-01-11 | B Gondola Fixing & Removing for Facade Work (Rent Basis) | 1 | 26000 | 0 | 26000 | 4680 | 2024-08-08 | Hiring Charges for Gandola from 8th MAY 2024 to 8th JUNE-2024 for B-Bldg. | 100 |  | 109749 | 2024-08-12 | 149500 | 1900-01-01 | -123500 | SIDDHIVINAYAK CORPORATION
Professional Fees | N/C | N/C | TALENTAX RENAISSANCE PRIVATE LIMITED | 1501 | 2023-01-25 | GST Consultancy | 1 | 11000 | 0 | 11000 | 1980 | 2024-08-03 | Professional Fees towards GST Related Service for the month of JUN-2024 | 100 |  | 109475 | 2024-08-03 | 11000 | 2024-08-03 19:08 | 0 | TALENTAX RENAISSANCE PRIVATE LIMITED
Gypsum Board False Ceiling (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 1506 | 2023-02-06 | B-3002 Internal Gypsum Board False Ceiling | 1615.8 | 55 | 0 | 88869 | 15996.42 | 2024-08-03 13:02 | Material Supply charges for Gypsum Board False Ceiling work. | 100 |  | 109599 | 2024-08-05 | 119517.75 | 1900-01-01 | -30648.75 | J K INTERIOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 1506 | 2023-02-06 | B-3002 Internal Gypsum Board False Ceiling | 557.25 | 55 | 0 | 30648.75 | 5516.78 | 2024-08-03 13:02 | Material Supply charges for Gypsum False Ceiling Vertical Patta Work. | 100 |  | 109599 | 2024-08-05 | 119517.75 | 1900-01-01 | -88869 | J K INTERIOR (MATERIAL)
Security Services. | N/C | N/C | OM SECURITY SERVICES | 1520 | 2023-02-23 | HO Expenses Security Services | 12 | 14000 | 0 | 13999.944 | 2519.98 | 2024-08-03 | JULY-2024 | 8.3333 |  | 109470 | 2024-08-03 | 13999.94 | 2024-08-05 11:46 | 0.004 | OM SECURITY SERVICES
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 2102 Dry Bal,Staff,Toilet False Ceiling Work | 290.268 | 30 | 0 | 8708.04 | 1567.44 | 2024-08-07 12:05 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109735 | 2024-08-12 | 20658.57 | 1900-01-01 | -11950.53 | J K INTERIOR
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 1302 Dry Bal,Staff,Toilet False Ceiling Work | 129.008 | 30 | 0 | 3870.24 | 696.64 | 2024-08-07 12:07 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109735 | 2024-08-12 | 20658.57 | 1900-01-01 | -16788.33 | J K INTERIOR
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 2701 Dry Bal,Staff,Toilet False Ceiling Work | 269.343 | 30 | 0 | 8080.29 | 1454.46 | 2024-08-07 12:09 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109735 | 2024-08-12 | 20658.57 | 1900-01-01 | -12578.28 | J K INTERIOR
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 2103 Dry Bal,Staff,Toilet False Ceiling Work | 188.856 | 30 | 0 | 5665.68 | 1019.82 | 2024-08-07 11:00 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109736 | 2024-08-12 | 5665.68 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 3002 Dry Bal,Staff,Toilet False Ceiling Work | 290.268 | 30 | 0 | 8708.04 | 1567.44 | 2024-08-19 11:54 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109962 | 2024-08-19 | 26124.12 | 1900-01-01 | -17416.08 | J K INTERIOR
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 2302 Dry Bal,Staff,Toilet False Ceiling Work | 290.268 | 30 | 0 | 8708.04 | 1567.44 | 2024-08-19 11:56 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109962 | 2024-08-19 | 26124.12 | 1900-01-01 | -17416.08 | J K INTERIOR
Moisture Proof Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 1523 | 2023-03-03 | A 602 Dry Bal,Staff,Toilet False Ceiling Work | 290.268 | 30 | 0 | 8708.04 | 1567.44 | 2024-08-19 11:57 | Labour Charges for Fixing of Moisturre proof Ceiling for all toilets, dry balcony, & staff room of A Building including all hardware and acessories. | 100 |  | 109962 | 2024-08-19 | 26124.12 | 1900-01-01 | -17416.08 | J K INTERIOR
Moisture Proof Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1527 | 2023-03-15 | A 2701 Dry Bal,Staff,Toilet False Ceiling Work | 299.27 | 130 | 0 | 38905.1 | 7002.92 | 2024-08-07 12:09 | Material Supply Charges Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109739 | 2024-08-12 | 101552.1 | 1900-01-01 | -62647 | J K INTERIOR (MATERIAL)
Moisture Proof Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1527 | 2023-03-15 | A 1302 Dry Bal,Staff,Toilet False Ceiling Work | 160.26 | 130 | 0 | 20833.8 | 3750.08 | 2024-08-07 12:07 | Material Supply Charges Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109739 | 2024-08-12 | 101552.1 | 1900-01-01 | -80718.3 | J K INTERIOR (MATERIAL)
Moisture Proof Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1527 | 2023-03-15 | A 2102 Dry Bal,Staff,Toilet False Ceiling Work | 321.64 | 130 | 0 | 41813.2 | 7526.38 | 2024-08-07 12:05 | Material Supply Charges Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109739 | 2024-08-12 | 101552.1 | 1900-01-01 | -59738.9 | J K INTERIOR (MATERIAL)
Moisture Proof Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1527 | 2023-03-15 | A 602 Dry Bal,Staff,Toilet False Ceiling Work | 321.64 | 130 | 0 | 41813.2 | 7526.38 | 2024-08-19 11:57 | Material Supply Charges Moisturre proof Ceiling for all toilets, dry balcony, & staff room of A Building including all hardware and acessories. | 100 |  | 109963 | 2024-08-19 | 125439.6 | 1900-01-01 | -83626.4 | J K INTERIOR (MATERIAL)
Moisture Proof Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1527 | 2023-03-15 | A 2302 Dry Bal,Staff,Toilet False Ceiling Work | 321.64 | 130 | 0 | 41813.2 | 7526.38 | 2024-08-19 11:56 | Material Supply Charges Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109963 | 2024-08-19 | 125439.6 | 1900-01-01 | -83626.4 | J K INTERIOR (MATERIAL)
Moisture Proof Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1527 | 2023-03-15 | A 3002 Dry Bal,Staff,Toilet False Ceiling Work | 321.64 | 130 | 0 | 41813.2 | 7526.38 | 2024-08-19 11:54 | Material Supply Charges Moisturre proof Ceiling for all toilets & dry balcony of A Building including all hardware and acessories. | 100 |  | 109963 | 2024-08-19 | 125439.6 | 1900-01-01 | -83626.4 | J K INTERIOR (MATERIAL)
Brickwork 9" - BRE | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 108 Level - South-West-North side brickwork, plaster | 279.82 | 28 | 0 | 7834.96 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 9 inch Brickwork for 108 level south-west side and Northside area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -77455.62 | SURESH KUMAR MURALIDHAR
Brickwork 6" --DEn | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 108 Level - South-West-North side brickwork, plaster | 108.3 | 22 | 0 | 2382.6 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 6 inch Brickwork for 108 level south-west side and Northside area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -82907.98 | SURESH KUMAR MURALIDHAR
Patli (Band)- BC | GLAZING SERVICES | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 108 Level - South-West-North side brickwork, plaster | 105 | 12 | 0 | 1260 | 0 | 2024-08-05 14:14 | Labour charges for Construction Patli (Band) Making work for 108 level south-west side and Northside area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84030.58 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 108 Level - South-West-North side brickwork, plaster | 1067.07 | 25 | 0 | 26676.75 | 0 | 2024-08-05 14:14 | Labour charges for Applying Single coat sand Face plaster work for 108 level south-west side and Northside area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -58613.83 | SURESH KUMAR MURALIDHAR
Brickwork 9" - LC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Misc. sampling work at parking | 44.88 | 28 | 0 | 1256.64 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 9 inch Brickwork at Development area for Sample work. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84033.94 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Misc. sampling work at parking | 112.27 | 25 | 0 | 2806.75 | 0 | 2024-08-05 14:14 | Labour charges for Applying single coat sand face plaster work at Development area for Sample work. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -82483.83 | SURESH KUMAR MURALIDHAR
Curb stone Fixing - Ded | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Misc. sampling work at parking | 31 | 30 | 0 | 930 | 0 | 2024-08-05 14:14 | Labour charges for Fixing of Curb Stone (12inch x 20inch) at Development area for Sample work. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84360.58 | SURESH KUMAR MURALIDHAR
PCC AIE | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Misc. sampling work at parking | 170 | 6 | 0 | 1020 | 0 | 2024-08-05 14:14 | Labour charges for Laying of PCC work 70mm at Development area for Sample work. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84270.58 | SURESH KUMAR MURALIDHAR
PCC AIE | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Misc. sampling work at parking | 90 | 6 | 0 | 540 | 0 | 2024-08-05 14:14 | Labour charges for Laying of PCC work 150mm at Development area for Sample work. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84750.58 | SURESH KUMAR MURALIDHAR
Brickwork 9" DCW | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club house front side Pantry work | 8.16 | 28 | 0 | 228.48 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 9 inch Brickwork for Club House Front side Pantry area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -85062.1 | SURESH KUMAR MURALIDHAR
9" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 154.94 | 28 | 0 | 4338.32 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 9 inch Brickwork for Club House Back side screen wall (Feature Wall) | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -80952.26 | SURESH KUMAR MURALIDHAR
Double Coat Plaster work (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 155 | 35 | 0 | 5425 | 0 | 2024-08-05 14:14 | Labour charges for Applying Double Coat Tar Plaster for Club House Back side screen wall (Feature Wall) | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -79865.58 | SURESH KUMAR MURALIDHAR
Double Coat Plaster work (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 155 | 35 | 0 | 5425 | 0 | 2024-08-05 14:14 | Labour charges for Applying Double coat Sponge Finish Plaster for Club House Back side screen wall (Feature Wall) | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -79865.58 | SURESH KUMAR MURALIDHAR
Patli (Band)- BC | GLAZING SERVICES | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 47.24 | 12 | 0 | 566.88 | 0 | 2024-08-05 14:14 | Labour charges for Patli Making work for Club House Back side screen wall (Feature Wall) | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84723.7 | SURESH KUMAR MURALIDHAR
Dhar Making - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 36.74 | 25 | 0 | 918.5 | 0 | 2024-08-05 14:14 | Labour charges for Dhar Making work for Club House Back side screen wall (Feature Wall) | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84372.08 | SURESH KUMAR MURALIDHAR
Misc RCC Work | No category | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club House back side Pathway, Feature wall Granite work | 3 | 500 | 0 | 1500 | 0 | 2024-08-05 14:14 | Labour charges for Mullion making work for Club House Back side screen wall (Feature Wall) | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -83790.58 | SURESH KUMAR MURALIDHAR
Brickwork 4" (L) - LC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club house front side Pantry work | 58.12 | 20 | 0 | 1162.4 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 4 inch Brickwork for Club House Front side Pantry area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84128.18 | SURESH KUMAR MURALIDHAR
Patli (Band)- BC | GLAZING SERVICES | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club house front side Pantry work | 18.76 | 12 | 0 | 225.12 | 0 | 2024-08-05 14:14 | Labour charges for Patli making work for Club House Front side Pantry area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -85065.46 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club house front side Pantry work | 120.55 | 25 | 0 | 3013.75 | 0 | 2024-08-05 14:14 | Labour charges for Applying single coat sand face plaster work for Club House Front side Pantry area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -82276.83 | SURESH KUMAR MURALIDHAR
Dhar Making - Dld | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | Club house front side Pantry work | 20.72 | 25 | 0 | 518 | 0 | 2024-08-05 14:14 | Labour charges for Dhar Making work for Club House Front side Pantry area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84772.58 | SURESH KUMAR MURALIDHAR
9" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 192.25 | 28 | 0 | 5383 | 0 | 2024-08-05 14:14 | Labour charges for Construction of 9 inch Brickwork for 105 level south west side area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -79907.58 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 368 | 25 | 0 | 9200 | 0 | 2024-08-05 14:14 | Labour charges for Applying Single Coat Sand Face Plaster work for 105 level south west side area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -76090.58 | SURESH KUMAR MURALIDHAR
Patli Mkt - R.Ft | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 72.39 | 12 | 0 | 868.68 | 0 | 2024-08-05 14:14 | Labour charges for Patli (Band) Making work for 105 level south west side area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -84421.9 | SURESH KUMAR MURALIDHAR
Dhar Making - Mkt | N/C | N/C | SURESH KUMAR MURALIDHAR | 1530 | 2023-03-15 | 105 Level South-West side Brickwork, Plaster | 72.39 | 25 | 0 | 1809.75 | 0 | 2024-08-05 14:14 | Labour charges for Dhar Making work for 105 level south west side area. | 100 |  | 109616 | 2024-08-05 | 85290.58 | 2024-08-19 13:17 | -83480.83 | SURESH KUMAR MURALIDHAR
Plumbing Work lumpsum-BRE | N/C | N/C | SAROJ KUMAR PRADHAN | 1532 | 2023-03-15 | Flat no. A2903 Temporary water connection. | 1 | 2000 | 0 | 2000 | 0 | 2024-08-09 15:19 | Lumpsum Charges for A 2903 Temporary Plumbing Connection to RCC Tank top terrace | 100 |  | 109759 | 2024-08-12 | 2000 | 1900-01-01 | 0 | SAROJ KUMAR PRADHAN
Lift Electrical work-BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 1553 | 2023-04-08 | A Lift 3 Electrical Work | 0.1 | 70000 | 0 | 7000 | 1260 | 2024-08-12 | Labour charges for Lift Electrical work for Strecher lift A-Bldg. | 100 |  | 109839 | 2024-08-12 | 7000 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
After Meter Work Completed | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS | 1570 | 2023-04-12 | A Bldg Mainline Electrical Work- | 4 | 850 | 0 | 3400 | 612 | 2024-08-12 14:17 | Labour Charges for- After Meter work completed for A Building . | 100 |  | 109823 | 2024-08-12 | 3400 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
After Completion Conduiting in Electrical Duct | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS | 1570 | 2023-04-12 | A Bldg Mainline Electrical Work- | 12.4 | 4250 | 0 | 52700 | 0 | 2024-08-20 13:42 | Labour Charges for After Complition of Conduiting in Electrical Duct for A Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS
Main Line Wiring Bldg to Main Meter | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS | 1575 | 2023-04-12 | B Bldg Mainline Electrical | 8 | 5950 | 0 | 47600 | 0 | 2024-08-22 19:43 | Labour Charges for- Main line elecrical wiring work from B Building to Main Meter | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
IPS W/P | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Podium Part A4 IPS Work | 1811.58 | 18 | 0 | 32608.44 | 0 | 2024-08-21 | Labour charges for IPS W/P Work for Podium A4 area above Chemical coat for Protection. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
PCC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Podium Part A2 siporex broken blocks filling & PCC | 910.835 | 11 | 0 | 10019.185 | 0 | 2024-08-14 16:23 | Labour charges for PCC Work for Podium A2 area. | 100 |  | 109948 | 2024-08-19 | 10019.19 | 1900-01-01 | -0.005 | SURESH KUMAR MURALIDHAR
AAC Block Filling BC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Podium Part A2 siporex broken blocks filling & PCC | 383.658 | 7.5 | 0 | 2877.435 | 0 | 2024-08-07 11:26 | Labour charges for AAC Block Filling work at Podium A2 area. | 100 |  | 109732 | 2024-08-12 | 196175.64 | 1900-01-01 | -193298.205 | SURESH KUMAR MURALIDHAR
Screeding W/P-BCo | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Part A2 area screeding above Membrane waterproofing | 182.167 | 18 | 0 | 3279.006 | 0 | 2024-08-07 11:26 | Labour charges for Screeding work for Podium A2 area. | 100 |  | 109732 | 2024-08-12 | 196175.64 | 1900-01-01 | -192896.634 | SURESH KUMAR MURALIDHAR
PCC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Podium Part A2 siporex broken blocks filling & PCC | 910.835 | 11 | 0 | 10019.185 | 0 | 2024-08-07 11:26 | Labour charges for PCC Work for Podium A2 area. | 100 |  | 109732 | 2024-08-12 | 196175.64 | 1900-01-01 | -186156.455 | SURESH KUMAR MURALIDHAR
IPS W/P | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Amenity area IPS Work | 6000 | 18 | 0 | 108000 | 0 | 2024-08-06 12:47 | Labour charges for IPS W/P Work for Podium Amenity area above Chemical coat for Protection. | 100 |  | 109732 | 2024-08-12 | 196175.64 | 1900-01-01 | -88175.64 | SURESH KUMAR MURALIDHAR
IPS W/P | N/C | N/C | SURESH KUMAR MURALIDHAR | 1580 | 2023-04-17 | Amenity area IPS Work | 4000 | 18 | 0 | 72000 | 0 | 2024-08-11 | Labour charges for IPS W/P Work for Podium Amenity area above Chemical coat for Protection. | 100 |  | 109732 | 2024-08-12 | 196175.64 | 1900-01-01 | -124175.64 | SURESH KUMAR MURALIDHAR
G.I.Cable tray 200 x 50mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 10 | 490 | 0 | 1225 | 220.5 | 2024-08-12 10:53 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -288829.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
G.I.Cable tray 200 x 50mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 10 | 490 | 0 | 2940 | 529.2 | 2024-08-12 10:53 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -287114.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
G.I.Cable tray 150 x 50mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 16 | 410 | 0 | 1640 | 295.2 | 2024-08-12 10:53 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -288414.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
G.I.Cable tray 150 x 50mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 16 | 410 | 0 | 3936 | 708.48 | 2024-08-12 10:53 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -286118.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Exhaust pipe 150mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 30 | 1925 | 0 | 14437.5 | 2598.76 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -275617.35 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Exhaust pipe 150mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 30 | 1925 | 0 | 34650 | 6237 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -255404.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Butterfly Valve 250mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 1 | 22190 | 0 | 5547.5 | 998.56 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -284507.35 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Butterfly Valve 250mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 1 | 22190 | 0 | 13314 | 2396.52 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -276740.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sluice Valve 200mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 2 | 26125 | 0 | 13062.5 | 2351.26 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -276992.35 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sluice Valve 200mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 2 | 26125 | 0 | 31350 | 5643 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -258704.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
CI Y-type Strainer- 100mm Dia. (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 1 | 7091 | 0 | 1772.75 | 319.1 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -288282.1 | SAITECH FIRE SYSTEM PRIVATE LIMITED
CI Y-type Strainer- 100mm Dia. (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 1 | 7091 | 0 | 4254.6 | 765.82 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -285800.25 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Pressure Switch (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 15 | 2100 | 0 | 7875 | 1417.5 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -282179.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Pressure Switch (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 15 | 2100 | 0 | 18900 | 3402 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -271154.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 3 | 40250 | 0 | 30187.5 | 5433.76 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -259867.35 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sprinkler Alarm Valve 150mm dia (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 3 | 40250 | 0 | 72450 | 13041 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -217604.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 17 | 2250 | 0 | 9562.5 | 1721.26 | 2024-08-12 | Advance along with work order | 25 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -280492.35 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1601 | 2023-04-29 | A,B & C Tower Fire Pump Room | 17 | 2250 | 0 | 22950 | 4131 | 2024-08-12 | Before Material Dispatch | 60 |  | 109837 | 2024-08-12 | 290054.85 | 1900-01-01 | -267104.85 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Cement Painting -BRE | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1603 | 2023-05-01 | A Bldg Garbage Room Ceiling Painting at 105 Lvl | 177.6 | 2 | 0 | 355.2 | 63.94 | 2024-08-13 18:02 | Labour charges for Applying Cement Paint on ceiling for A & B-Bldg Garbage room at 105 level. | 100 |  | 109943 | 2024-08-19 | 557.91 | 1900-01-01 | -202.71 | SAI NIRMAL COLOURS & TEXTURES
Cement Painting -BRE | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1603 | 2023-05-01 | B 105 Lvl Garbage Room Ceiling Paint | 101.355 | 2 | 0 | 202.71 | 36.48 | 2024-08-13 18:02 | Labour charges for Applying Cement Paint on ceiling for A & B-Bldg Garbage room at 105 level. | 100 |  | 109943 | 2024-08-19 | 557.91 | 1900-01-01 | -355.2 | SAI NIRMAL COLOURS & TEXTURES
Oil base Primer-BC | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 1 | 0 | 2732.652 | 491.88 | 2024-08-01 14:47 | Labour Charges for Applying Oil Base primer for internal wall Flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -18930.988 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 1 | 0 | 2732.652 | 491.88 | 2024-08-01 14:47 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -18930.988 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 1 | 0 | 2732.652 | 491.88 | 2024-08-01 14:47 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -18930.988 | SHAHI ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 0.5 | 0 | 1366.326 | 245.94 | 2024-08-01 14:47 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 1. | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20297.314 | SHAHI ENTERPRISES
Astar Coat | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 0.5 | 0 | 1366.326 | 245.94 | 2024-08-01 14:47 | Labour Charges for Applying of Astar coat for internal walls of Flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20297.314 | SHAHI ENTERPRISES
Touch up Lambi | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 0.5 | 0 | 1366.326 | 245.94 | 2024-08-01 14:47 | Labour Charges for Touch up lambi work for internal flat series 1. | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20297.314 | SHAHI ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 2732.652 | 1.5 | 0 | 4098.978 | 737.82 | 2024-08-01 14:47 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat series 1 including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -17564.662 | SHAHI ENTERPRISES
Water Base Primer | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1316.934 | 1 | 0 | 1316.934 | 237.04 | 2024-08-01 14:47 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20346.706 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1316.934 | 1 | 0 | 1316.934 | 237.04 | 2024-08-01 14:47 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20346.706 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1316.934 | 1 | 0 | 1316.934 | 237.04 | 2024-08-01 14:47 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 1 | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20346.706 | SHAHI ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1316.934 | 1 | 0 | 1316.934 | 237.04 | 2024-08-01 14:47 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 1 including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109560 | 2024-08-05 | 21663.64 | 1900-01-01 | -20346.706 | SHAHI ENTERPRISES
Oil base Primer-BC | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 303.628 | 1 | 0 | 303.628 | 54.66 | 2024-08-12 15:55 | Labour Charges for Applying Oil Base primer for internal wall Flat series 1 | 100 |  | 109825 | 2024-08-12 | 1366.32 | 1900-01-01 | -1062.692 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 303.628 | 1 | 0 | 303.628 | 54.66 | 2024-08-12 15:55 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 1 | 100 |  | 109825 | 2024-08-12 | 1366.32 | 1900-01-01 | -1062.692 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 303.628 | 1 | 0 | 303.628 | 54.66 | 2024-08-12 15:55 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 1 | 100 |  | 109825 | 2024-08-12 | 1366.32 | 1900-01-01 | -1062.692 | SHAHI ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 303.628 | 0.5 | 0 | 151.814 | 27.32 | 2024-08-12 15:55 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 1. | 100 |  | 109825 | 2024-08-12 | 1366.32 | 1900-01-01 | -1214.506 | SHAHI ENTERPRISES
Astar Coat | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 303.628 | 0.5 | 0 | 151.814 | 27.32 | 2024-08-12 15:55 | Labour Charges for Applying of Astar coat for internal walls of Flat series 1 | 100 |  | 109825 | 2024-08-12 | 1366.32 | 1900-01-01 | -1214.506 | SHAHI ENTERPRISES
Touch up Lambi | N/C | N/C | AKBARALI A.SATTAR | 1609 | 2023-05-02 | A-Bldg 2701 Walls Satin Matt Painting | 303.628 | 0.5 | 0 | 151.814 | 27.32 | 2024-08-12 15:55 | Labour Charges for Touch up lambi work for internal flat series 1. | 100 |  | 109825 | 2024-08-12 | 1366.32 | 1900-01-01 | -1214.506 | SHAHI ENTERPRISES
Oil base Primer-BC | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-12 16:21 | Labour Charges for Applying Oil Base primer on wall for internal flat series 3 | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -13002.87 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-12 16:21 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 3 | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -13002.87 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-12 16:21 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 3 | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -13002.87 | SHAHI ENTERPRISES
Sanding Gattu (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Walls Satin Matt Painting | 2762.4 | 0.5 | 0 | 1381.2 | 248.62 | 2024-08-12 16:21 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 3 | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -14384.07 | SHAHI ENTERPRISES
Astar Coat | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Walls Satin Matt Painting | 2762.4 | 0.5 | 0 | 1381.2 | 248.62 | 2024-08-12 16:21 | Labour Charges for Applying of Astar coat for internal walls of Flat series 3 | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -14384.07 | SHAHI ENTERPRISES
Touch up Lambi | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Walls Satin Matt Painting | 2762.4 | 0.5 | 0 | 1381.2 | 248.62 | 2024-08-12 16:21 | Labour Charges for Touch up lambi work for internal flat series 3 | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -14384.07 | SHAHI ENTERPRISES
Water Base Primer | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-12 16:21 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -14653.78 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-12 16:21 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -14653.78 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 2103 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-12 16:21 | Labour Charges for 2nd Coat Lambi putty for ceiling premium emulsion paint for internal flat. | 100 |  | 109827 | 2024-08-12 | 15765.27 | 1900-01-01 | -14653.78 | SHAHI ENTERPRISES
Oil base Primer-BC | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-19 15:30 | Labour Charges for Applying Oil Base primer on wall for internal flat series 3 | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -17732.45 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-19 15:30 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 3 | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -17732.45 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-19 15:30 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 3 | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -17732.45 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2762.4 | 0.5 | 0 | 1381.2 | 248.62 | 2024-08-19 15:30 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 3 | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19113.65 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2762.4 | 0.5 | 0 | 1381.2 | 248.62 | 2024-08-19 15:30 | Labour Charges for Applying of Astar coat for internal walls of Flat series 3 | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19113.65 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2762.4 | 0.5 | 0 | 1381.2 | 248.62 | 2024-08-19 15:30 | Labour Charges for Touch up lambi work for internal flat series 3 | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19113.65 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Walls Satin Matt Painting | 2486.16 | 1.5 | 0 | 3729.24 | 671.26 | 2024-08-19 15:30 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -16765.61 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-19 15:30 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19383.36 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-19 15:30 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19383.36 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-19 15:30 | Labour Charges for 2nd Coat Lambi putty for ceiling premium emulsion paint for internal flat. | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19383.36 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1611 | 2023-05-03 | A 703 Ceiling Premium Emulsion Painting | 1000.341 | 1 | 0 | 1000.341 | 180.06 | 2024-08-19 15:30 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109981 | 2024-08-20 | 20494.85 | 1900-01-01 | -19494.509 | RISHIPRASAD ENTERPRISES
Oil base Primer-BC | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 1 | 0 | 2497.248 | 449.5 | 2024-08-07 11:47 | Labour Charges for Applying Oil Base primer for internal flat Series No. 4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -17578.432 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 1 | 0 | 2497.248 | 449.5 | 2024-08-07 11:47 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series No.4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -17578.432 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 1 | 0 | 2497.248 | 449.5 | 2024-08-07 11:47 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat Series No. 4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -17578.432 | SHAHI ENTERPRISES
Sanding Gattu (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 0.5 | 0 | 1248.624 | 224.76 | 2024-08-07 11:47 | Labour Charges for Applying of Sanding Gattu for internal walls of flat Series No. 4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18827.056 | SHAHI ENTERPRISES
Astar Coat | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 0.5 | 0 | 1248.624 | 224.76 | 2024-08-07 11:47 | Labour Charges for Applying of Astar coat for internal walls of Flat Series No.4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18827.056 | SHAHI ENTERPRISES
Touch up Lambi | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 0.5 | 0 | 1248.624 | 224.76 | 2024-08-07 11:47 | Labour Charges for Touch up lambi work for internal flat painting work for Flat Series no.4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18827.056 | SHAHI ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 2497.248 | 1.5 | 0 | 3745.872 | 674.26 | 2024-08-07 11:47 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -16329.808 | SHAHI ENTERPRISES
Water Base Primer | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1273.05 | 1 | 0 | 1273.05 | 229.14 | 2024-08-07 11:47 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flats Series No.4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18802.63 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1273.05 | 1 | 0 | 1273.05 | 229.14 | 2024-08-07 11:47 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18802.63 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1273.05 | 1 | 0 | 1273.05 | 229.14 | 2024-08-07 11:47 | Labour Charges for 2nd Coat Lambi putty for ceiling premium emulsion paint for internal flat Series no.4 | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18802.63 | SHAHI ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1273.05 | 1 | 0 | 1273.05 | 229.14 | 2024-08-07 11:47 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109737 | 2024-08-12 | 20075.68 | 1900-01-01 | -18802.63 | SHAHI ENTERPRISES
Oil base Primer-BC | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 1 | 0 | 277.472 | 49.94 | 2024-08-12 16:08 | Labour Charges for Applying Oil Base primer for internal flat Series No. 4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1811.718 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 1 | 0 | 277.472 | 49.94 | 2024-08-12 16:08 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series No.4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1811.718 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 1 | 0 | 277.472 | 49.94 | 2024-08-12 16:08 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat Series No. 4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1811.718 | SHAHI ENTERPRISES
Sanding Gattu (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 0.5 | 0 | 138.736 | 24.98 | 2024-08-12 16:08 | Labour Charges for Applying of Sanding Gattu for internal walls of flat Series No. 4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1950.454 | SHAHI ENTERPRISES
Astar Coat | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 0.5 | 0 | 138.736 | 24.98 | 2024-08-12 16:08 | Labour Charges for Applying of Astar coat for internal walls of Flat Series No.4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1950.454 | SHAHI ENTERPRISES
Touch up Lambi | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 0.5 | 0 | 138.736 | 24.98 | 2024-08-12 16:08 | Labour Charges for Touch up lambi work for internal flat painting work for Flat Series no.4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1950.454 | SHAHI ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Walls Satin Matt Painting | 277.472 | 1.5 | 0 | 416.208 | 74.92 | 2024-08-12 16:08 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1672.982 | SHAHI ENTERPRISES
Water Base Primer | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 25.46 | 2024-08-12 16:08 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flats Series No.4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1947.74 | SHAHI ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 25.46 | 2024-08-12 16:08 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1947.74 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 25.46 | 2024-08-12 16:08 | Labour Charges for 2nd Coat Lambi putty for ceiling premium emulsion paint for internal flat Series no.4 | 100 |  | 109826 | 2024-08-12 | 2089.19 | 1900-01-01 | -1947.74 | SHAHI ENTERPRISES
Oil base Primer-BC | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-19 15:54 | Labour Charges for Applying Oil Base primer for internal flat Series No. 4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -18165.54 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-19 15:54 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series No.4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -18165.54 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-19 15:54 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat Series No. 4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -18165.54 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 0.5 | 0 | 1387.36 | 249.72 | 2024-08-19 15:54 | Labour Charges for Applying of Sanding Gattu for internal walls of flat Series No. 4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -19552.9 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 0.5 | 0 | 1387.36 | 249.72 | 2024-08-19 15:54 | Labour Charges for Applying of Astar coat for internal walls of Flat Series No.4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -19552.9 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 0.5 | 0 | 1387.36 | 249.72 | 2024-08-19 15:54 | Labour Charges for Touch up lambi work for internal flat painting work for Flat Series no.4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -19552.9 | RISHIPRASAD ENTERPRISES
2nd Coat Satin Matt Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-19 15:54 | Labour Charges for Applying of 2nd coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -15390.82 | RISHIPRASAD ENTERPRISES
Cleaning Work - Bco | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Walls Satin Matt Painting | 2774.72 | 0.5 | 0 | 1387.36 | 249.72 | 2024-08-19 15:54 | Labour Charges for Cleaning work for internal painting work. | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -19552.9 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Ceiling Premium Emulsion Painting | 758.61 | 1 | 0 | 758.61 | 136.54 | 2024-08-19 15:54 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flats Series No.4 | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -20181.65 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Ceiling Premium Emulsion Painting | 758.61 | 1 | 0 | 758.61 | 136.54 | 2024-08-19 15:54 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109975 | 2024-08-19 | 20940.26 | 1900-01-01 | -20181.65 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1304 Ceiling Premium Emulsion Painting | 758.61 | 1 | 0 | 758.61 | 136.54 | 2024-08-21 18:21 | Labour Charges for 2nd Coat Lambi putty for ceiling premium emulsion paint for internal flat Series no.4 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RISHIPRASAD ENTERPRISES
Oil base Primer-BC | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Labour Charges for Applying Oil Base primer for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 12:14 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 12:14 | Labour Charges for Applying of Astar coat for internal walls of Flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 12:14 | Labour Charges for Touch up lambi work for internal flat series 2 painting work. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2645.49 | 1.5 | 0 | 3968.235 | 714.28 | 2024-08-19 12:14 | Labour Charges for Applying of 1st coat Satin matt paint for internal walls of flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for brush Cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -41690.055 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 12:14 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 12:14 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 12:14 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1300 | 1 | 0 | 1300 | 234 | 2024-08-19 12:14 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44358.29 | RISHIPRASAD ENTERPRISES
Oil base Primer-BC | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 1 | 0 | 2645.46 | 476.18 | 2024-08-01 11:54 | Labour Charges for Applying Oil Base primer for internal walls of flat series 2 | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -18427.62 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 1 | 0 | 2645.46 | 476.18 | 2024-08-01 11:54 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 2 | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -18427.62 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 1 | 0 | 2645.46 | 476.18 | 2024-08-01 11:54 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 2 | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -18427.62 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 0.5 | 0 | 1322.73 | 238.1 | 2024-08-01 11:54 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 2 | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19750.35 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 0.5 | 0 | 1322.73 | 238.1 | 2024-08-01 11:54 | Labour Charges for Applying of Astar coat for internal walls of Flat series 2. | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19750.35 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 0.5 | 0 | 1322.73 | 238.1 | 2024-08-01 11:54 | Labour Charges for Touch up lambi work for internal flat series 2 painting work. | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19750.35 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2645.46 | 1.5 | 0 | 3968.19 | 714.28 | 2024-08-01 11:54 | Labour Charges for Applying of 1st coat Satin matt paint for internal walls of flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for brush Cleaning. | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -17104.89 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1300.077 | 1 | 0 | 1300.077 | 234.02 | 2024-08-01 11:54 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 2 | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19773.003 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1300.077 | 1 | 0 | 1300.077 | 234.02 | 2024-08-01 11:54 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 2 | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19773.003 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1300.077 | 1 | 0 | 1300.077 | 234.02 | 2024-08-01 11:54 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 2. | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19773.003 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1300.077 | 1 | 0 | 1300.077 | 234.02 | 2024-08-01 11:54 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109705 | 2024-08-12 | 21073.08 | 1900-01-01 | -19773.003 | RISHIPRASAD ENTERPRISES
Oil base Primer-BC | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Labour Charges for Applying Oil Base primer for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 15:42 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 15:42 | Labour Charges for Applying of Astar coat for internal walls of Flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 15:42 | Labour Charges for Touch up lambi work for internal flat series 2 painting work. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2645.46 | 1.5 | 0 | 3968.19 | 714.28 | 2024-08-19 15:42 | Labour Charges for Applying of 1st coat Satin matt paint for internal walls of flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for brush Cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -41690.1 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1300.077 | 1 | 0 | 1300.077 | 234.02 | 2024-08-19 15:42 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44358.213 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-19 15:54 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -20441.37 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-19 15:54 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -20441.37 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-19 15:54 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -20441.37 | RISHIPRASAD ENTERPRISES
Sanding Gattu (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-19 15:54 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -23216.09 | RISHIPRASAD ENTERPRISES
Astar Coat (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-19 15:54 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of Flats. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -23216.09 | RISHIPRASAD ENTERPRISES
Water Base Primer (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Ceiling Premium Emulsion Painting | 758.61 | 1 | 0 | 758.61 | 136.54 | 2024-08-19 15:54 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -25232.2 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Ceiling Premium Emulsion Painting | 758.61 | 2 | 0 | 1517.22 | 273.1 | 2024-08-19 15:54 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -24473.59 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A 1304 Ceiling Premium Emulsion Painting | 758.61 | 2 | 0 | 1517.22 | 273.1 | 2024-08-19 15:54 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109976 | 2024-08-19 | 25990.81 | 1900-01-01 | -24473.59 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-07 11:47 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -51549.44 | SHAHI ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-07 11:47 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -51549.44 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 2 | 0 | 5549.44 | 998.9 | 2024-08-07 11:47 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -51549.44 | SHAHI ENTERPRISES
Sanding Gattu (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-07 11:47 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -54324.16 | SHAHI ENTERPRISES
Astar Coat (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 1 | 0 | 2774.72 | 499.44 | 2024-08-07 11:47 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of Flats. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -54324.16 | SHAHI ENTERPRISES
1st Coat Satin Matt Paint (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 4 | 0 | 11098.88 | 1997.8 | 2024-08-07 11:47 | Material Supply Charges for 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -46000 | SHAHI ENTERPRISES
2nd Coat Satin Matt Paint (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Walls Satin Matt Painting | 2774.72 | 4.5 | 0 | 12486.24 | 2247.52 | 2024-08-07 11:47 | Material Supply Charges for 2nd coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -44612.64 | SHAHI ENTERPRISES
Water Base Primer (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1414.5 | 1 | 0 | 1414.5 | 254.62 | 2024-08-07 11:47 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -55684.38 | SHAHI ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1414.5 | 2 | 0 | 2829 | 509.22 | 2024-08-07 11:47 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -54269.88 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1414.5 | 2 | 0 | 2829 | 509.22 | 2024-08-07 11:47 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -54269.88 | SHAHI ENTERPRISES
1st Coat Premium Emulsion Paint (M) | N/C | N/C | POONA PAINTING | 1614 | 2023-05-04 | A-Bldg 2704 Ceiling Premium Emulsion Painting | 1414.5 | 3 | 0 | 4243.5 | 763.84 | 2024-08-07 11:47 | Material Supply Charges for 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109738 | 2024-08-12 | 57098.88 | 1900-01-01 | -52855.38 | SHAHI ENTERPRISES
2nd Coat Satin Matt Paint (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 4.5 | 0 | 12430.8 | 2237.54 | 2024-08-19 15:30 | Material Supply Charges for 2nd coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -36182.47 | RISHIPRASAD ENTERPRISES
Water Base Primer (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-19 15:30 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -47501.78 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Ceiling Premium Emulsion Painting | 1111.49 | 2 | 0 | 2222.98 | 400.14 | 2024-08-19 15:30 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -46390.29 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Ceiling Premium Emulsion Painting | 1111.49 | 2 | 0 | 2222.98 | 400.14 | 2024-08-19 15:30 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -46390.29 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Ceiling Premium Emulsion Painting | 1000.341 | 3 | 0 | 3001.023 | 540.18 | 2024-08-19 15:30 | Material Supply Charges for 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -45612.247 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 2 | 0 | 5524.8 | 994.46 | 2024-08-19 15:30 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RISHABH ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 2 | 0 | 5524.8 | 994.46 | 2024-08-19 15:30 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -43088.47 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 2 | 0 | 5524.8 | 994.46 | 2024-08-19 15:30 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -43088.47 | RISHIPRASAD ENTERPRISES
Sanding Gattu (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-19 15:30 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -45850.87 | RISHIPRASAD ENTERPRISES
Astar Coat (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-19 15:30 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of flat. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -45850.87 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 703 Walls Satin Matt Painting | 2762.4 | 4 | 0 | 11049.6 | 1988.92 | 2024-08-19 15:30 | Material Supply Charges for 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109973 | 2024-08-19 | 48613.27 | 1900-01-01 | -37563.67 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Walls Satin Matt Painting | 2762.4 | 2 | 0 | 5524.8 | 994.46 | 2024-08-12 16:21 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -22131.85 | SHAHI ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Walls Satin Matt Painting | 2762.4 | 2 | 0 | 5524.8 | 994.46 | 2024-08-12 16:21 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -22131.85 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Walls Satin Matt Painting | 2762.4 | 2 | 0 | 5524.8 | 994.46 | 2024-08-12 16:21 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -22131.85 | SHAHI ENTERPRISES
Sanding Gattu (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-12 16:21 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -24894.25 | SHAHI ENTERPRISES
Astar Coat (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Walls Satin Matt Painting | 2762.4 | 1 | 0 | 2762.4 | 497.24 | 2024-08-12 16:21 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of flat. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -24894.25 | SHAHI ENTERPRISES
Water Base Primer (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Ceiling Premium Emulsion Painting | 1111.49 | 1 | 0 | 1111.49 | 200.06 | 2024-08-12 16:21 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -26545.16 | SHAHI ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Ceiling Premium Emulsion Painting | 1111.49 | 2 | 0 | 2222.98 | 400.14 | 2024-08-12 16:21 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -25433.67 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | PROFESSIONAL PAINTING PARTNER | 1615 | 2023-05-04 | A 2103 Ceiling Premium Emulsion Painting | 1111.49 | 2 | 0 | 2222.98 | 400.14 | 2024-08-12 16:21 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109828 | 2024-08-12 | 27656.65 | 1900-01-01 | -25433.67 | SHAHI ENTERPRISES
Oil Base Primer (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Walls Satin Matt Painting | 3036.28 | 2 | 0 | 6072.56 | 1093.06 | 2024-08-01 14:47 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -41214.08 | SHAHI ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Walls Satin Matt Painting | 3036.28 | 2 | 0 | 6072.56 | 1093.06 | 2024-08-01 14:47 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -41214.08 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Walls Satin Matt Painting | 3036.28 | 2 | 0 | 6072.56 | 1093.06 | 2024-08-01 14:47 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -41214.08 | SHAHI ENTERPRISES
Sanding Gattu (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Walls Satin Matt Painting | 3036.28 | 1 | 0 | 3036.28 | 546.54 | 2024-08-01 14:47 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -44250.36 | SHAHI ENTERPRISES
Astar Coat (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Walls Satin Matt Painting | 3036.28 | 1 | 0 | 3036.28 | 546.54 | 2024-08-01 14:47 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of flat. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -44250.36 | SHAHI ENTERPRISES
1st Coat Satin Matt Paint (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Walls Satin Matt Painting | 3036.28 | 4 | 0 | 12145.12 | 2186.12 | 2024-08-01 14:47 | Material Supply Charges for 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -35141.52 | SHAHI ENTERPRISES
Water Base Primer (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1356.41 | 1 | 0 | 1356.41 | 244.16 | 2024-08-07 11:07 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -45930.23 | SHAHI ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1356.41 | 2 | 0 | 2712.82 | 488.3 | 2024-08-07 11:07 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -44573.82 | SHAHI ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1356.41 | 2 | 0 | 2712.82 | 488.3 | 2024-08-07 11:07 | Material Supply Charges for 2nd Coat Lambi putty for internal flat celeing premium emulsion paint. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -44573.82 | SHAHI ENTERPRISES
1st Coat Premium Emulsion Paint (M) | N/C | N/C | AKBARALI A.SATTAR | 1616 | 2023-05-04 | A-Bldg 2701 Ceiling Premium Emulsion Painting | 1356.41 | 3 | 0 | 4069.23 | 732.46 | 2024-08-07 11:07 | Material Supply Charges for 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110001 | 2024-08-21 | 47286.64 | 1900-01-01 | -43217.41 | SHAHI ENTERPRISES
Oil Base Primer (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-19 15:42 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -91662.82 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-19 15:42 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -91662.82 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-19 15:42 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -91662.82 | RISHIPRASAD ENTERPRISES
Sanding Gattu (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94602.22 | RISHIPRASAD ENTERPRISES
Astar Coat (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of Flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94602.22 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2645.46 | 4 | 0 | 10581.84 | 1904.74 | 2024-08-19 15:42 | Material Supply Charges for 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -86959.78 | RISHIPRASAD ENTERPRISES
Water Base Primer (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -96097.09 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 2 | 0 | 2889.06 | 520.04 | 2024-08-19 15:42 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94652.56 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 2 | 0 | 2889.06 | 520.04 | 2024-08-19 15:42 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94652.56 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 3 | 0 | 4333.59 | 780.04 | 2024-08-19 15:42 | Material Supply Charges for 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -93208.03 | RISHIPRASAD ENTERPRISES
2nd Coat Premium Emulsion Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 3.5 | 0 | 5055.855 | 910.06 | 2024-08-19 15:42 | Material Supply Charges for 2nd coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -92485.765 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-19 12:14 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -91662.82 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-19 12:14 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -91662.82 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-19 12:14 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -91662.82 | RISHIPRASAD ENTERPRISES
Sanding Gattu (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94602.22 | RISHIPRASAD ENTERPRISES
Astar Coat (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of Flat. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94602.22 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 4 | 0 | 11757.6 | 2116.36 | 2024-08-19 12:14 | Material Supply Charges for 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -85784.02 | RISHIPRASAD ENTERPRISES
Water Base Primer (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.96 | 1 | 0 | 1444.96 | 260.1 | 2024-08-19 12:14 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -96096.66 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.96 | 2 | 0 | 2889.92 | 520.18 | 2024-08-19 12:14 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94651.7 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.96 | 2 | 0 | 2889.92 | 520.18 | 2024-08-19 12:14 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -94651.7 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.96 | 3 | 0 | 4334.88 | 780.28 | 2024-08-19 12:14 | Material Supply Charges for 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109971 | 2024-08-19 | 97541.62 | 1900-01-01 | -93206.74 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-01 11:54 | Material Supply Charges for Oil Base primer for Satin matt Paint of internal walls of flat. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -40953.68 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-01 11:54 | Material Supply Charges for 1st coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -40953.68 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2939.4 | 2 | 0 | 5878.8 | 1058.18 | 2024-08-01 11:54 | Material Supply Charges for 2nd coat lambi putty for Satin matt Paint of internal walls of flat. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -40953.68 | RISHIPRASAD ENTERPRISES
Sanding Gattu (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-01 11:54 | Material Supply Charges for Sanding Gattu for Satin Matt Paint of internal walls of flat. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -43893.08 | RISHIPRASAD ENTERPRISES
Astar Coat (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-01 11:54 | Material Supply Charges for Astar Coat for Satin Matt Paint of internal walls of Flat. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -43893.08 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Walls Satin Matt Painting | 2939.4 | 4 | 0 | 11757.6 | 2116.36 | 2024-08-01 11:54 | Material Supply Charges for 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -35074.88 | RISHIPRASAD ENTERPRISES
Water Base Primer (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1444.96 | 1 | 0 | 1444.96 | 260.1 | 2024-08-01 11:54 | Material Supply Charges for Water base perimer for Premium emulsion paint for ceiling of internal flats. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -45387.52 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1444.96 | 2 | 0 | 2889.92 | 520.18 | 2024-08-01 11:54 | Material Supply Charges for 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -43942.56 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1444.96 | 2 | 0 | 2889.92 | 520.18 | 2024-08-01 11:54 | Material Supply Charges for 2nd Coat Lambi putty for internal flat ceiling premium emulsion paint. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -43942.56 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (M) | N/C | N/C | AAKRUTI ENTERPRISES | 1617 | 2023-05-04 | A 2102 Ceiling Premium Emulsion Painting | 1444.96 | 3 | 0 | 4334.88 | 780.28 | 2024-08-01 11:54 | Material Supply Charges for 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109556 | 2024-08-05 | 46832.48 | 2024-08-19 13:44 | -42497.6 | RISHIPRASAD ENTERPRISES
Labour lumpsum | N/C | N/C | SAROJ KUMAR PRADHAN | 1622 | 2023-05-09 | A 303 & 403 Temporary water tank provision with fittings | 1 | 4000 | 0 | 4000 | 0 | 2024-08-09 15:33 | Charges for fixing of Temporary Sintax Water tank -1000 litres including ASTM Inlet & Outlet line for A Building Flat No. 303 & 403 | 100 |  | 109760 | 2024-08-12 | 7000 | 1900-01-01 | -3000 | SAROJ KUMAR PRADHAN
Lumpsum work- DCW | N/C | N/C | SAROJ KUMAR PRADHAN | 1622 | 2023-05-09 | A 1501 Staff Toilet Temp Plumbing Work | 1 | 3000 | 0 | 3000 | 0 | 2024-08-09 15:33 | Lumpsum Charges for A 1501 Water tank 1000 liter Temporary Connection to Staff toilet.Inlet line 3/4 inch and Outlet line 1.25 inch. | 100 |  | 109760 | 2024-08-12 | 7000 | 1900-01-01 | -4000 | SAROJ KUMAR PRADHAN
Lift Scaffolding Work BC | N/C | N/C | ADLER | 1629 | 2023-05-18 | B building Lift Scaffolding Rental | 1 | 80000 | 0 | 80000 | 14400 | 2024-08-14 | Charges for MS Scaffolding work for Tower A Lift Shaft 2 including providing,fixing and removing from 99 level to top terrace total height upto 126 to 130 meters. | 100 |  | 109945 | 2024-08-19 | 80000 | 1900-01-01 | 0 | ADLER
RCC Superstructure (B-up area) | N/C | N/C | VIMAL CONSTRUCTION | 1634 | 2023-05-24 | Tower C Podium P3 slab incl. ramp area (105 to 111) Built-up | 2045 | 200 | 0 | 409000 | 73620 | 2024-08-05 | Charges for RCC Column,Beam and Slab. | 100 | podium pour 6a part slab | 109623 | 2024-08-05 | 996760 | 2024-08-23 10:48 | -587760 | SHILPI CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | VIMAL CONSTRUCTION | 1634 | 2023-05-24 | Tower C P4 Podium slab Built-up Area (L) | 2480 | 237 | 0 | 587760 | 105796.8 | 2024-08-05 | Charges for RCC Column,Beam and Slab. | 100 | Podim Pour 05. 4th slab (Fite Ramp) | 109623 | 2024-08-05 | 996760 | 2024-08-23 10:48 | -409000 | SHILPI CONSTRUCTION
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 27th Floor Texture Painting | 173.92 | 1.75 | 0 | 304.36 | 54.78 | 2024-08-22 | Labour Charges for Applying 2nd Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 28th Floor Texture Painting | 200.31 | 1.75 | 0 | 350.5425 | 63.1 | 2024-08-22 | Labour Charges for Applying 2nd Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 29th Floor Texture Painting | 173.92 | 1.75 | 0 | 304.36 | 54.78 | 2024-08-22 | Labour Charges for Applying 2nd Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 30th Floor Texture Painting | 200.31 | 1.75 | 0 | 350.5425 | 63.1 | 2024-08-22 | Labour Charges for Applying 2nd Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 31st Floor Texture Painting | 173.92 | 1.75 | 0 | 304.36 | 54.78 | 2024-08-22 | Labour Charges for Applying 2nd Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 27th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for Applying 1st Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 28th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for Applying 1st Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 29th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for Applying 1st Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 30th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for Applying 1st Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 31st Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for Applying 1st Coat Acrylic Paint with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 27th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for Applying 1 Coat Water Base Primer with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 28th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for Applying 1 Coat Water Base Primer with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 29th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for Applying 1 Coat Water Base Primer with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 30th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for Applying 1 Coat Water Base Primer with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1659 | 2023-06-29 | B Eastside 31st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for Applying 1 Coat Water Base Primer with Scaffolding/Gandola on External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 27th Floor Texture Painting | 173.92 | 2.25 | 0 | 391.32 | 70.44 | 2024-08-22 | Material Supply charges of 1st Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 28th Floor Texture Painting | 200.31 | 2.25 | 0 | 450.6975 | 81.12 | 2024-08-22 | Material Supply charges of 1st Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 29th Floor Texture Painting | 173.92 | 2.25 | 0 | 391.32 | 70.44 | 2024-08-22 | Material Supply charges of 1st Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 30th Floor Texture Painting | 200.31 | 2.25 | 0 | 450.6975 | 81.12 | 2024-08-22 | Material Supply charges of 1st Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 31st Floor Texture Painting | 173.92 | 2.25 | 0 | 391.32 | 70.44 | 2024-08-22 | Material Supply charges of 1st Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 27th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply charges of Water Base Primer for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 28th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply charges of Water Base Primer for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 29th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply charges of Water Base Primer for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 30th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply charges of Water Base Primer for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 31st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply charges of Water Base Primer for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 27th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply charges of 2nd Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 28th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply charges of 2nd Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 29th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply charges of 2nd Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 30th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply charges of 2nd Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 1660 | 2023-06-29 | B Eastside 31st Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply charges of 2nd Coat Acrylic Paint for External Surface B-Bldg. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
SWR 4" Pipe | N/C | N/C | SAROJ KUMAR PRADHAN | 1689 | 2023-08-01 | A Service platform Rain water line plumbing work | 700 | 40 | 0 | 28000 | 0 | 2024-08-10 | Charges for 4" Soil, Waste & Rainwater Pipe fitting above MS Platform for A-Building. | 100 |  | 109770 | 2024-08-12 | 62000 | 1900-01-01 | -34000 | SAROJ KUMAR PRADHAN
160mm Rain Water Pipe (L) | N/C | N/C | SAROJ KUMAR PRADHAN | 1689 | 2023-08-01 | A Service platform Rain water line plumbing work | 500 | 50 | 0 | 25000 | 0 | 2024-08-10 | Charges for 6" Soil, Waste & Rainwater Pipe fitting above MS Platform for A-Building. | 100 |  | 109770 | 2024-08-12 | 62000 | 1900-01-01 | -37000 | SAROJ KUMAR PRADHAN
Bullet Fastner | N/C | N/C | SAROJ KUMAR PRADHAN | 1689 | 2023-08-01 | A Service platform Rain water line plumbing work | 450 | 20 | 0 | 9000 | 0 | 2024-08-10 | Charges for 10mm Bullet Fastener fitting above MS Platform for A-Building Plumbing work. | 100 |  | 109770 | 2024-08-12 | 62000 | 1900-01-01 | -53000 | SAROJ KUMAR PRADHAN
Panel Testing (L) | N/C | N/C | ASK & COMPANY | 1694 | 2023-08-12 | A Bldg Solar PV | 6 | 697.5 | 0 | 4185 | 753.3 | 2024-08-05 11:51 | Panel Testing of Open Circuit | 100 |  | 109608 | 2024-08-05 | 57195 | 1900-01-01 | -53010 | ASK & COMPANY
Engineering & Supervision Charges | N/C | N/C | ASK & COMPANY | 1694 | 2023-08-12 | A Bldg Solar PV | 6 | 1860 | 0 | 11160 | 2008.8 | 2024-08-05 11:51 | Engineering & Supervision charges | 100 |  | 109608 | 2024-08-05 | 57195 | 1900-01-01 | -46035 | ASK & COMPANY
Solar Panel Installation | N/C | N/C | ASK & COMPANY | 1694 | 2023-08-12 | A Bldg Solar PV | 6 | 6975 | 0 | 41850 | 7533 | 2024-08-05 11:51 | Solar panel Installation charges | 100 |  | 109608 | 2024-08-05 | 57195 | 1900-01-01 | -15345 | ASK & COMPANY
MSEB Liassioning Fee | N/C | N/C | ASK & COMPANY | 1694 | 2023-08-12 | A Bldg Solar PV | 6 | 4650 | 0 | 27900 | 5022 | 2024-08-10 12:42 | Mseb Liasoning Fee | 100 |  | 109771 | 2024-08-12 | 27900 | 1900-01-01 | 0 | ASK & COMPANY
Module Mounting Structure | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 60450 | 0 | 30225 | 5440.5 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -81155.6 | ASK & COMPANY
String inverter | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 60450 | 0 | 30225 | 5440.5 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -81155.6 | ASK & COMPANY
Inverter Mounting Stand | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 1860 | 0 | 930 | 167.4 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -110450.6 | ASK & COMPANY
DC Cables | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 20 | 32 | 0 | 320 | 57.6 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -111060.6 | ASK & COMPANY
AC Cable | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 10 | 209.25 | 0 | 1046.25 | 188.32 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -110334.35 | ASK & COMPANY
DC Connector | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 10 | 29.76 | 0 | 148.8 | 26.78 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -111231.8 | ASK & COMPANY
MCCB with Box | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 4185 | 0 | 2092.5 | 376.66 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -109288.1 | ASK & COMPANY
ACDB/Combiner box 1 in 1 out | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 6975 | 0 | 3487.5 | 627.76 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -107893.1 | ASK & COMPANY
DCDB | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 6975 | 0 | 3487.5 | 627.76 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -107893.1 | ASK & COMPANY
Solar Bi Directional meter | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 52080 | 0 | 26040 | 4687.2 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -85340.6 | ASK & COMPANY
Generation meter | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 1 | 11625 | 0 | 5812.5 | 1046.26 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -105568.1 | ASK & COMPANY
UPVC Pipe | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 100 | 66.96 | 0 | 3348 | 602.64 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -108032.6 | ASK & COMPANY
Ring Type Terminal lugs | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 100 | 7.626 | 0 | 381.3 | 68.64 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -110999.3 | ASK & COMPANY
Insulation Tape | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 10 | 18.6 | 0 | 93 | 16.74 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -111287.6 | ASK & COMPANY
Plastic Cable Tie 300mm | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 10 | 139.5 | 0 | 697.5 | 125.56 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -110683.1 | ASK & COMPANY
Earthing Screw | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 150 | 23.25 | 0 | 1743.75 | 313.88 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -109636.85 | ASK & COMPANY
Anchor Fastener (M) | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 10 | 167.4 | 0 | 837 | 150.66 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -110543.6 | ASK & COMPANY
1/2 inch Nails | N/C | N/C | ASK & COMPANY | 1695 | 2023-08-12 | B Bldg Solar PV | 200 | 4.65 | 0 | 465 | 83.7 | 2024-08-10 12:28 | Advance Along with Work Order | 50 |  | 109832 | 2024-08-12 | 111380.6 | 1900-01-01 | -110915.6 | ASK & COMPANY
Module Mounting Structure | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 60450 | 0 | 30225 | 5440.5 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -81955.6 | ASK & COMPANY
String inverter | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 60450 | 0 | 30225 | 5440.5 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -81955.6 | ASK & COMPANY
Inverter Mounting Stand | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 1860 | 0 | 930 | 167.4 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111250.6 | ASK & COMPANY
DC Cables | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 50 | 32 | 0 | 800 | 144 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111380.6 | ASK & COMPANY
DC Cables | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 20 | 32 | 0 | 320 | 57.6 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111860.6 | ASK & COMPANY
AC Cable | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 10 | 209.25 | 0 | 1046.25 | 188.32 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111134.35 | ASK & COMPANY
DC Connector | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 10 | 29.76 | 0 | 148.8 | 26.78 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -112031.8 | ASK & COMPANY
MCCB with Box | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 4185 | 0 | 2092.5 | 376.66 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -110088.1 | ASK & COMPANY
ACDB/Combiner box 1 in 1 out | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 6975 | 0 | 3487.5 | 627.76 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -108693.1 | ASK & COMPANY
DCDB | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 6975 | 0 | 3487.5 | 627.76 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -108693.1 | ASK & COMPANY
Solar Bi Directional meter | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 52080 | 0 | 26040 | 4687.2 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -86140.6 | ASK & COMPANY
Generation meter | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 1 | 11625 | 0 | 5812.5 | 1046.26 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -106368.1 | ASK & COMPANY
UPVC Pipe | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 100 | 66.96 | 0 | 3348 | 602.64 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -108832.6 | ASK & COMPANY
Ring Type Terminal lugs | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 100 | 7.626 | 0 | 381.3 | 68.64 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111799.3 | ASK & COMPANY
Insulation Tape | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 10 | 18.6 | 0 | 93 | 16.74 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -112087.6 | ASK & COMPANY
Plastic Cable Tie 300mm | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 10 | 139.5 | 0 | 697.5 | 125.56 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111483.1 | ASK & COMPANY
Earthing Screw | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 150 | 23.25 | 0 | 1743.75 | 313.88 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -110436.85 | ASK & COMPANY
Anchor Fastener (M) | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 10 | 167.4 | 0 | 837 | 150.66 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111343.6 | ASK & COMPANY
1/2 inch Nails | N/C | N/C | ASK & COMPANY | 1696 | 2023-08-12 | A Bldg Solar PV | 200 | 4.65 | 0 | 465 | 83.7 | 2024-08-10 12:37 | Advance Along with Work Order | 50 |  | 109833 | 2024-08-12 | 112180.6 | 1900-01-01 | -111715.6 | ASK & COMPANY
Solar Panel Installation | N/C | N/C | ASK & COMPANY | 1697 | 2023-08-12 | B Bldg Solar PV | 6 | 6975 | 0 | 41850 | 7533 | 2024-08-05 11:53 | Installation charges for Solar Panel. | 100 |  | 109628 | 2024-08-05 | 57195 | 1900-01-01 | -15345 | ASK & COMPANY
Engineering & Supervision Charges | N/C | N/C | ASK & COMPANY | 1697 | 2023-08-12 | B Bldg Solar PV | 6 | 1860 | 0 | 11160 | 2008.8 | 2024-08-05 11:53 | Engineering and Supervision Charges for B-Bldg. | 100 |  | 109628 | 2024-08-05 | 57195 | 1900-01-01 | -46035 | ASK & COMPANY
Panel Testing (L) | N/C | N/C | ASK & COMPANY | 1697 | 2023-08-12 | B Bldg Solar PV | 6 | 697.5 | 0 | 4185 | 753.3 | 2024-08-05 11:53 | Charges for Panel Testing for Open Circuit for B-Bldg. | 100 |  | 109628 | 2024-08-05 | 57195 | 1900-01-01 | -53010 | ASK & COMPANY
MSEB Liassioning Fee | N/C | N/C | ASK & COMPANY | 1697 | 2023-08-12 | B Bldg Solar PV | 6 | 4650 | 0 | 27900 | 5022 | 2024-08-10 12:43 | Labour Charges for MSEB Liasoning for B-Bldg. | 100 |  | 109772 | 2024-08-12 | 27900 | 1900-01-01 | 0 | ASK & COMPANY
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2701 Staff Toilet dado-(No.) | 115 | 70.875 | 0 | 8150.625 | 1467.12 | 2024-08-18 14:59 | Labour Charges for 600 x 300mm Dado Fixing work for staff toilet. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -114695.745 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Children Toilet-(No.) | 25 | 141.75 | 0 | 3543.75 | 637.88 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -119302.62 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Dry Balcony dado-(No.) | 4 | 141.75 | 0 | 567 | 102.06 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122279.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Master Toilet dado-(No.) | 20 | 141.75 | 0 | 2835 | 510.3 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120011.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Parents Toilet dado-(No.) | 30 | 141.75 | 0 | 4252.5 | 765.46 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118593.87 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Powder Toilet dado-(No.) | 26 | 141.75 | 0 | 3685.5 | 663.4 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -119160.87 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Staff Toilet dado-(No.) | 10 | 141.75 | 0 | 1417.5 | 255.16 | 2024-08-18 15:04 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121428.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Children Toilet-(No.) | 143 | 70.875 | 0 | 10135.125 | 1824.32 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -112711.245 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Dry Balcony dado-(No.) | 82.83 | 70.875 | 0 | 5870.5763 | 1056.7 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -116975.7937 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Master Toilet dado-(No.) | 100 | 70.875 | 0 | 7087.5 | 1275.76 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -115758.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Parents Toilet dado-(No.) | 120 | 70.875 | 0 | 8505 | 1530.9 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -114341.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Powder Toilet dado-(No.) | 70 | 70.875 | 0 | 4961.25 | 893.02 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117885.12 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Children Toilet-(No.) | 35 | 70.875 | 0 | 2480.625 | 446.52 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120365.745 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Master Toilet dado-(No.) | 60 | 70.875 | 0 | 4252.5 | 765.46 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118593.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Parents Toilet dado-(No.) | 80 | 70.875 | 0 | 5670 | 1020.6 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 Powder Toilet dado-(No.) | 40 | 70.875 | 0 | 2835 | 510.3 | 2024-08-18 15:04 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120011.37 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Children Toilet Vitrified Flooring | 52.29 | 33.075 | 0 | 1729.4917 | 311.3 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121116.8782 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Master Toilet Vitrified Flooring | 45 | 33.075 | 0 | 1488.375 | 267.9 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121357.995 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Parents Toilet Vitrified Flooring | 50 | 33.075 | 0 | 1653.75 | 297.68 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121192.62 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Powder Toilet Vitrified Flooring | 36.279 | 33.075 | 0 | 1199.9279 | 215.98 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121646.4421 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Staff Toilet Vitrified Flooring | 20 | 33.075 | 0 | 661.5 | 119.08 | 2024-08-18 14:18 | Labour Charges for Vitrified flooring work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122184.87 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Balcony Vitrified Flooring | 40 | 33.075 | 0 | 1323 | 238.14 | 2024-08-18 14:18 | Labour Charges for Vitrified Skirting work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -121523.37 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Kitchen Vitrified Flooring | 25.256 | 33.075 | 0 | 835.3422 | 150.36 | 2024-08-18 14:18 | Labour Charges for Vitrified Skirting work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122011.0278 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 3002 A 102 Staff Room Vitrified Flooring | 15 | 33.075 | 0 | 496.125 | 89.3 | 2024-08-18 14:18 | Labour Charges for Vitrified Skirting work for A Building internal Flat area with proper line,level,right angle and joint filling. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122350.245 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Children Toilet dado-(No.)-(No.) - 1 No. | 40 | 141.75 | 0 | 5670 | 1020.6 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Dry Balcony dado-(No.) - 1 No. | 5 | 141.75 | 0 | 708.75 | 127.58 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122137.62 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Guest Toilet dado-(No.) - 1 No. | 28 | 141.75 | 0 | 3969 | 714.42 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118877.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Master Toilet dado-(No.) - 1 No. | 40 | 141.75 | 0 | 5670 | 1020.6 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
L Groove - BCV | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Powder Toilet dado-(No.) - 1 No. | 4.5 | 141.75 | 0 | 637.875 | 114.82 | 2024-08-18 14:42 | Labour Charges for L Groove work in vitrified tile for A Building Dado. | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -122208.495 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Master Toilet dado-(No.) - 1 No. | 120 | 70.875 | 0 | 8505 | 1530.9 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -114341.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Powder Toilet dado-(No.) - 1 No. | 80 | 70.875 | 0 | 5670 | 1020.6 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 600mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -117176.37 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Master Toilet dado-(No.) - 1 No. | 60 | 70.875 | 0 | 4252.5 | 765.46 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -118593.87 | R K INTERIOR
Dado BC | N/C | N/C | R K INTERIOR | 1707 | 2023-08-18 | A 2903 Powder Toilet dado-(No.) - 1 No. | 30 | 70.875 | 0 | 2126.25 | 382.72 | 2024-08-18 14:42 | Labour Charges for Fixing of 600 x 1200mm Dado | 100 |  | 109958 | 2024-08-19 | 122846.37 | 1900-01-01 | -120720.12 | R K INTERIOR
Fogging work-SO | N/C | N/C | S.R.Enterprises | 1719 | 2023-08-26 | Fogging Work | 1 | 12000 | 0 | 12000 | 2160 | 2024-08-16 | Fogging Work for the Month of JULY- 2024 (8 times in month) | 100 |  | 109949 | 2024-08-19 | 12000 | 1900-01-01 | 0 | S.R.Enterprises
Lift Electrical work-BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 1734 | 2023-09-02 | B Lift 1 Electrical work (PL-1) | 0.9 | 70000 | 0 | 63000 | 11340 | 2024-08-12 | Labour Charges for Lift all Electrical work for Passange Lift 1 of B Building. | 100 |  | 109840 | 2024-08-12 | 84000 | 1900-01-01 | -21000 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Lift Electrical work-BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 1734 | 2023-09-02 | B Lift 2 Electrical work (PL-2) | 0.1 | 70000 | 0 | 7000 | 1260 | 2024-08-12 | Labour Charges for Lift all Electrical work for Passange Lift 2 of B Building. | 100 |  | 109840 | 2024-08-12 | 84000 | 1900-01-01 | -77000 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Lift Electrical work-BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 1734 | 2023-09-02 | B Lift 3 Electrical work (SL) | 0.1 | 70000 | 0 | 7000 | 1260 | 2024-08-12 | Labour Charges for Lift all Electrical work for Strecher Lift of B Building. | 100 |  | 109840 | 2024-08-12 | 84000 | 1900-01-01 | -77000 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Lift Electrical work-BC | N/C | N/C | P.L. VISHWAKARMA ELECTRICALS (FIRM) | 1734 | 2023-09-02 | B Lift 4 Electrical work (Private Lift) | 0.1 | 70000 | 0 | 7000 | 1260 | 2024-08-12 | Labour Charges for Lift all Electrical work for Private Lift of B Building. | 100 |  | 109840 | 2024-08-12 | 84000 | 1900-01-01 | -77000 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Back Coat Plaster | N/C | N/C | JAY GANESH ENTERPRISES | 1758 | 2023-09-20 | A 30th Floor Back Coat Plaster | 2 | 2000 | 0 | 4000 | 0 | 2024-08-19 | Labour charges for Applying 25 to 60mm thick Back Coat Plaster work on RCC Wall for A-Bldg Bathroom area including fixing of Chicken Mesh. | 100 |  | 109959 | 2024-08-19 | 4000 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Department Labour - DEn | N/C | N/C | JAISAN | 1765 | 2023-09-23 | A,B,C D & Development Housekeeping | 38 | 650 | 0 | 24700 | 0 | 2024-08-06 | Charges for Male coolie for Material shifting & Housekeeping work for Podium 111 level, 102 level & 105 level for A,B,C & D Development work. | 100 |  | 109726 | 2024-08-12 | 32800 | 2024-08-21 10:47 | -8100 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1765 | 2023-09-23 | A,B,C D & Development Housekeeping | 18 | 450 | 0 | 8100 | 0 | 2024-08-06 | Charges for Female coolie for Material shifting & Housekeeping work for Podium 111 level, 102 level & 105 level for A,B,C & D Development work. | 100 |  | 109726 | 2024-08-12 | 32800 | 2024-08-21 10:47 | -24700 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1766 | 2023-09-23 | A,B,C D & Development Housekeeping | 70.5 | 650 | 0 | 45825 | 0 | 2024-08-06 | Charges for Male coolie for Material shifting & Housekeeping work for A,B,C & D Development work. | 100 |  | 109727 | 2024-08-12 | 61125 | 2024-08-21 10:48 | -15300 | JAISAN
Department Labour - DEn | N/C | N/C | JAISAN | 1766 | 2023-09-23 | A,B,C D & Development Housekeeping | 34 | 450 | 0 | 15300 | 0 | 2024-08-06 | Charges for Female coolie for Material shifting & Housekeeping work for A,B,C & D Development work. | 100 |  | 109727 | 2024-08-12 | 61125 | 2024-08-21 10:48 | -45825 | JAISAN
Gypsum Plaster (L) | N/C | N/C | J K INTERIOR | 1773 | 2023-10-02 | A 3002 NOC | 404.3 | 11 | 0 | 4447.3 | 800.52 | 2024-08-05 14:52 | Labour charges for applying Gypsum on both for Guest Bedroom for A-Tower Flat No-3002 | 100 |  | 109632 | 2024-08-05 | 4447.3 | 1900-01-01 | 0 | J K INTERIOR
Back Coat Plaster (Rate Diff.) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1781 | 2023-10-03 | A 30th Floor Back Coat Plaster | 2 | 1000 | 0 | 2000 | 0 | 2024-08-19 | Labour charges & Rate Difference for Applying 25mm to 60mm thick Back coat Plaster on RCC Wall including Fixing of chicken Mesh for A-Bldg Ledge wall in Bathroom area. | 100 |  | 109960 | 2024-08-19 | 2000 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Breaker - BRE | N/C | N/C | JAISAN | 1786 | 2023-10-09 | Labour Charges for Rabbit,kota,soil shifting | 0.5 | 1300 | 0 | 650 | 0 | 2024-08-08 | Charges for Breaker for PCC Breaking near STP Planter. | 100 |  | 109750 | 2024-08-12 | 20500 | 2024-08-21 10:48 | -19850 | JAISAN
Departmental Labour -Utv | N/C | N/C | JAISAN | 1786 | 2023-10-09 | Labour Charges for Rabbit,kota,soil shifting | 25 | 650 | 0 | 16250 | 0 | 2024-08-08 | Charges for Male Coolie for Material Shifting, Soil shifting & filling in Planter for Kota shifting for Behind Club House & Poyta Soil Shifting. | 100 |  | 109750 | 2024-08-12 | 20500 | 2024-08-21 10:48 | -4250 | JAISAN
Departmental Labour -Utv | N/C | N/C | JAISAN | 1786 | 2023-10-09 | Labour Charges for Rabbit,kota,soil shifting | 8 | 450 | 0 | 3600 | 0 | 2024-08-08 | Charges for Female Coolie for Material Shifting, Soil shifting & filling in Planter for Kota shifting for Behind Club House & Poyta Soil Shifting. | 100 |  | 109750 | 2024-08-12 | 20500 | 2024-08-21 10:48 | -16900 | JAISAN
Unloading work-SO | N/C | N/C | SAGARSINGH BINDUSINGH TAK | 1829 | 2023-11-24 | Loading / Unloading Expenses | 0.03 | 100000 | 0 | 3000 | 0 | 2024-08-10 | Charges for Unloading work at site for- AAC Blocks, Tile Box, Tile Adhesive, Italian Marble, etc all unloading work. | 100 |  | 109698 | 2024-08-10 | 3000 | 2024-08-19 13:55 | 0 | SAGARSINGH BINDUSINGH TAK
Unloading work-SO | N/C | N/C | SAGARSINGH BINDUSINGH TAK | 1829 | 2023-11-24 | Loading / Unloading Expenses | 0.02 | 100000 | 0 | 2000 | 0 | 2024-08-09 | Charges for Unloading work at site for- AAC Blocks, Tile Box, Tile Adhesive, Italian Marble, etc all unloading work. | 100 |  | 109686 | 2024-08-09 | 2000 | 2024-08-19 13:32 | 0 | SAGARSINGH BINDUSINGH TAK
Brickwork 4" BC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1834 | 2023-11-24 | A 102 level Lobby Brickwork & single coat plaster | 384.4 | 20 | 0 | 7688 | 0 | 2024-08-03 17:36 | Construction of 4" Brick Work with in-situ 1:6 Cement mortar with Fly ash Brick, Cement, Sand & water etc. with Plumb & Right angle at corner, with proper joint filling & striking joints on unexposed faces, raking out joints on exposed faces etc. | 100 |  | 109567 | 2024-08-05 | 28120.06 | 2024-08-19 13:17 | -20432.06 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1834 | 2023-11-24 | A 102 level Lobby Brickwork & single coat plaster | 327.63 | 22 | 0 | 7207.86 | 0 | 2024-08-03 17:44 | Labour charges for Sand face plaster (Single Coat) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparation between RCC (column beam) & Blockwork using Chicken mesh, nails, drill machine etc | 100 |  | 109567 | 2024-08-05 | 28120.06 | 2024-08-19 13:17 | -20912.2 | SURESH KUMAR MURALIDHAR
Single Coat Plaster (L) | N/C | N/C | SURESH KUMAR MURALIDHAR | 1834 | 2023-11-24 | A 105 level Lobby Brickwork & single coat plaster | 22.5 | 22 | 0 | 495 | 0 | 2024-08-01 15:13 | Labour charges for Sand face plaster (Single Coat) in Cement, crush sand mortar with specified proportion. with scaffolding With proper joint preparation between RCC (column beam) & Blockwork using Chicken mesh, nails, drill machine etc | 100 |  | 109567 | 2024-08-05 | 28120.06 | 2024-08-19 13:17 | -27625.06 | SURESH KUMAR MURALIDHAR
Brickwork 4" BC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1834 | 2023-11-24 | A 99 level Lobby Brickwork & single coat plaster | 252.06 | 20 | 0 | 5041.2 | 0 | 2024-08-01 15:13 | Construction of 4" Brick Work with in-situ 1:6 Cement mortar with Fly ash Brick, Cement, Sand & water etc. with Plumb & Right angle at corner, with proper joint filling & striking joints on unexposed faces, raking out joints on exposed faces etc. | 100 |  | 109567 | 2024-08-05 | 28120.06 | 2024-08-19 13:17 | -23078.86 | SURESH KUMAR MURALIDHAR
Brickwork 4" BC | N/C | N/C | SURESH KUMAR MURALIDHAR | 1834 | 2023-11-24 | A 105 level Lobby Brickwork & single coat plaster | 384.4 | 20 | 0 | 7688 | 0 | 2024-08-01 15:13 | Construction of 4" Brick Work with in-situ 1:6 Cement mortar with Fly ash Brick, Cement, Sand & water etc. with Plumb & Right angle at corner, with proper joint filling & striking joints on unexposed faces, raking out joints on exposed faces etc. | 100 |  | 109567 | 2024-08-05 | 28120.06 | 2024-08-19 13:17 | -20432.06 | SURESH KUMAR MURALIDHAR
Professional Fees | N/C | N/C | OMKAR PRADEEP MANE | 1841 | 2023-11-29 | Professional Consultancy | 1 | 40000 | 0 | 40000 | 7200 | 2024-08-05 | Charges for Professional fees for the Month of JULY-2024 | 100 |  | 109487 | 2024-08-05 | 40000 | 2024-08-05 12:50 | 0 | OMKAR PRADEEP MANE
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1852 | 2023-12-09 | GDT Electricity expenses | 0.7007 | 550000 | -5 | 385385 | 0 | 2024-08-10 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109693 | 2024-08-10 | 385380 | 2024-08-10 17:02 | 5 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1852 | 2023-12-09 | GDT Electricity expenses | 0.0357 | 550000 | -25 | 19635 | 0 | 2024-08-10 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109694 | 2024-08-10 | 19610 | 1900-01-01 | 25 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1852 | 2023-12-09 | GDT Electricity expenses | 0.036 | 550000 | -20 | 19800 | 0 | 2024-08-16 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109877 | 2024-08-16 | 19780 | 2024-08-16 17:25 | 20 | MSEDCL
Murum Levelling- DR | N/C | N/C | HOLE ENTERPRISES | 1853 | 2023-12-22 | Mandir Peripheral Trimix work | 3860.07 | 3 | 0 | 11580.21 | 2084.44 | 2024-08-05 11:39 | Labour charges for Manually Murum Levelling work for Mandir side area including loading, unloading with all leads and lifts, stacking, filling & Compaction with all tool, Equipments & machinery | 100 |  | 109627 | 2024-08-05 | 50180.91 | 1900-01-01 | -38600.7 | HOLE ENTERPRISES
Trimix Work | N/C | N/C | HOLE ENTERPRISES | 1853 | 2023-12-22 | Mandir Peripheral Trimix work | 3860.07 | 10 | 0 | 38600.7 | 6948.12 | 2024-08-05 11:39 | Labour charges for Trimix Laying work in situ cement concrete M20 with tremix treatment for 100 mm thickness for flooring with groove cutting of 4mm wide and 20mm deep with necessary refilling with bitumen etc. | 100 |  | 109627 | 2024-08-05 | 50180.91 | 1900-01-01 | -11580.21 | HOLE ENTERPRISES
Granite Skirting | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 39.672 | 94.5 | 0 | 3749.004 | 674.82 | 2024-08-07 14:38 | Labour charges for Fixing of Granite Skirting for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -615635.386 | R K INTERIOR
Granite Top..- Dld | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 166.212 | 94.5 | 0 | 15707.034 | 2827.26 | 2024-08-07 14:38 | Labour charges for Fixing of Granite sitting Top for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -603677.356 | R K INTERIOR
Granite Dado- ARW | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 185.994 | 120.75 | 0 | 22458.7755 | 4042.58 | 2024-08-07 14:38 | Labour charges for Fixing of Granite Dado for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -596925.6145 | R K INTERIOR
Granite Thickness cutting | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 167.292 | 21 | 0 | 3513.132 | 632.36 | 2024-08-07 14:38 | Labour charges for Granite Thickness Cutting for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -615871.258 | R K INTERIOR
Granite Cutting & Fitting- BCE | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 4.5 | 1200 | 0 | 5400 | 972 | 2024-08-07 14:38 | Labour charges for Chamber cover cutting & Fitting work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -613984.39 | R K INTERIOR
Zero Point Joint Making | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 101.052 | 210 | 0 | 21220.92 | 3819.76 | 2024-08-07 14:38 | Labour charges for Zero Point Joint Making work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -598163.47 | R K INTERIOR
Champher/ Bullnose Moulding Polish | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 57.06 | 89.25 | 0 | 5092.605 | 916.66 | 2024-08-07 14:38 | Labour charges for Granite Bullnose Moulding work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -614291.785 | R K INTERIOR
Chamfer - BCo | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 933.498 | 89.25 | 0 | 83314.6965 | 14996.64 | 2024-08-07 14:38 | Labour charges for Granite Champher work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -536069.6935 | R K INTERIOR
Edge Polish - BCE | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 1979.352 | 36.75 | 0 | 72741.186 | 13093.42 | 2024-08-07 14:38 | Labour charges for Fixing of Granite Edge polish work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -546643.204 | R K INTERIOR
V Groove Polish- BCo | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 856.26 | 126 | 0 | 107888.76 | 19419.98 | 2024-08-07 14:38 | Labour charges for Granite V-Groove making work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -511495.63 | R K INTERIOR
Granite Border Fixing- | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 2341.026 | 94.5 | 0 | 221226.957 | 39820.86 | 2024-08-07 14:38 | Labour charges for Fixing of Granite Top/Border for Club House Extended Area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -398157.433 | R K INTERIOR
Granite Round Border | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 149.85 | 189 | 0 | 28321.65 | 5097.9 | 2024-08-07 14:38 | Labour charges for Fixing of Granite Round Top/Border for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -591062.74 | R K INTERIOR
Granite Cutting- AIE | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 127.197 | 21 | 0 | 2671.137 | 480.8 | 2024-08-07 14:38 | Labour charges for Granite cutting work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -616713.253 | R K INTERIOR
Demolish Work. | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 150.444 | 36.75 | 0 | 5528.817 | 995.18 | 2024-08-07 14:38 | Labour charges for Granite Demolishing work for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -613855.573 | R K INTERIOR
Granite Flooring | N/C | N/C | R K INTERIOR | 1874 | 2024-01-03 | Club House extended area hardscape Granite work | 68.499 | 300 | 0 | 20549.7 | 3698.94 | 2024-08-07 14:38 | Labour charges for Fixing of Granite Flooring work (Cragi Pattern) for Club House Extended area. | 100 |  | 109740 | 2024-08-12 | 619384.39 | 1900-01-01 | -598834.69 | R K INTERIOR
Composite Pipe (Size-1620) (L) | N/C | N/C | M G S THERMO SYSTEMS | 1879 | 2024-01-04 | Dham-A-Solar Water Heater System & Heat pump water heater | 1015.2 | 150 | 0 | 144666 | 26039.88 | 2024-08-19 15:21 | After Completion of Work | 95 |  | 109972 | 2024-08-19 | 695514 | 1900-01-01 | -550848 | M G S THERMO SYSTEMS
Composite Pipe (Size-2025) (L) | N/C | N/C | M G S THERMO SYSTEMS | 1879 | 2024-01-04 | Dham-A-Solar Water Heater System & Heat pump water heater | 79.2 | 250 | 0 | 18810 | 3385.8 | 2024-08-19 15:23 | After Completion of Work | 95 |  | 109972 | 2024-08-19 | 695514 | 1900-01-01 | -676704 | M G S THERMO SYSTEMS
Composite Pipe (Size-2532) (L) | N/C | N/C | M G S THERMO SYSTEMS | 1879 | 2024-01-04 | Dham-A-Solar Water Heater System & Heat pump water heater | 501.6 | 250 | 0 | 119130 | 21443.4 | 2024-08-19 15:24 | After Completion of Work | 95 |  | 109972 | 2024-08-19 | 695514 | 1900-01-01 | -576384 | M G S THERMO SYSTEMS
Composite Pipe (Size-3240) (L) | N/C | N/C | M G S THERMO SYSTEMS | 1879 | 2024-01-04 | Dham-A-Solar Water Heater System & Heat pump water heater | 1448.8 | 300 | 0 | 412908 | 74323.44 | 2024-08-19 15:24 | After Completion of Work | 95 |  | 109972 | 2024-08-19 | 695514 | 1900-01-01 | -282606 | M G S THERMO SYSTEMS
Italian Marbal Mirror Polish- DCH | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 388.99 | 68.25 | 0 | 26548.5675 | 4778.74 | 2024-08-01 15:55 | Labour charges for Italian Marble Flooring Mirror Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -221670.7025 | R K INTERIOR
Italian Marble Skirting Mirror polish. | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 84.888 | 57.75 | 0 | 4902.282 | 882.42 | 2024-08-01 16:00 | Labour charges for Italian Marble Skirting Mirror Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -243316.988 | R K INTERIOR
Italian Marble Cladding Polish - BCo | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 222.111 | 73.5 | 0 | 16325.1585 | 2938.52 | 2024-08-01 16:00 | Labour charges for Italian Marble Cladding Mirror Polish work work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -231894.1115 | R K INTERIOR
Italian Marble Top/ Botom Mirror Polish - | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 309.636 | 68.25 | 0 | 21132.657 | 3803.88 | 2024-08-01 16:00 | Labour charges for Italian Marble Top / Border / Jamb Mirror Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -227086.613 | R K INTERIOR
Chemical Coating (for-Flooring) | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 1445.067 | 8 | 0 | 11560.536 | 2080.9 | 2024-08-01 16:00 | Labour charges for Italian Marble Back Coat Chemical Coating work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -236658.734 | R K INTERIOR
Floor Guard Laying | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 813.132 | 7 | 0 | 5691.924 | 1024.54 | 2024-08-01 16:00 | Labour charges for Floor Guard (Protection) Sheet Laying work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -242527.346 | R K INTERIOR
Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 268.686 | 36.75 | 0 | 9874.2105 | 1777.36 | 2024-08-01 16:00 | Labour charges for Italian Marble Edge Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -238345.0595 | R K INTERIOR
Champher/ Bullnose Moulding Polish | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 102 lvl Common lobby flooring & cladding work | 186.534 | 89.25 | 0 | 16648.1595 | 2996.66 | 2024-08-01 16:00 | Labour charges for Italian Marble Bull Nose Moulding work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -231571.1105 | R K INTERIOR
Italian Marbal Mirror Polish- DCH | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 350.97 | 68.25 | 0 | 23953.7025 | 4311.66 | 2024-08-01 16:22 | Labour charges for Italian Marble Flooring Mirror Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -224265.5675 | R K INTERIOR
V Groove Polish- BCo | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 59.175 | 126 | 0 | 7456.05 | 1342.08 | 2024-08-01 16:25 | Labour charges for Italian Marble V-Groove making work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -240763.22 | R K INTERIOR
Italian Marble Skirting Mirror polish. | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 69.507 | 57.75 | 0 | 4014.0293 | 722.52 | 2024-08-01 16:25 | Labour charges for Italian Marble Skirting Mirror Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -244205.2407 | R K INTERIOR
Italian Marble Cladding Polish - BCo | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 246.987 | 73.5 | 0 | 18153.5445 | 3267.64 | 2024-08-01 16:25 | Labour charges for Italian Marble Cladding Mirror Polish work work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -230065.7255 | R K INTERIOR
Italian Marble Top/ Botom Mirror Polish - | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 415.719 | 68.25 | 0 | 28372.8217 | 5107.1 | 2024-08-01 16:25 | Labour charges for Italian Marble Top / Border / Jamb Mirror Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -219846.4482 | R K INTERIOR
Chemical Coating (for Flooring) | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 1379.259 | 8 | 0 | 11034.072 | 1986.14 | 2024-08-01 16:25 | Labour charges for Italian Marble Back Coat Chemical Coating work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -237185.198 | R K INTERIOR
Floor Guard Laying | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 631.746 | 7 | 0 | 4422.222 | 796 | 2024-08-01 16:25 | Labour charges for Floor Guard (Protection) Sheet Laying work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -243797.048 | R K INTERIOR
Edge Polish- BCo | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 392.004 | 36.75 | 0 | 14406.147 | 2593.1 | 2024-08-01 16:25 | Labour charges for Italian Marble Edge Polish work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -233813.123 | R K INTERIOR
Champher/ Bullnose Moulding Polish | N/C | N/C | R K INTERIOR | 1884 | 2024-01-05 | B 108 lvl Common lobby flooring & cladding work | 265.806 | 89.25 | 0 | 23723.1855 | 4270.18 | 2024-08-01 16:25 | Labour charges for Italian Marble Bull Nose Moulding work for B-Bldg Entrance Lobby. | 100 |  | 109570 | 2024-08-05 | 248219.27 | 1900-01-01 | -224496.0845 | R K INTERIOR
Breaker | N/C | N/C | PRAKASH CONTRACTOR | 1890 | 2024-01-08 | Excavation, leveling, material shifting for development work | 3.5 | 1300 | 0 | 4550 | 0 | 2024-08-12 11:28 | Charges for Breaker for Hard Concrete breaking between Expansion joint, C Bldg 99 Level Rainwaterline breaking, C-Bldg 99 level Hard Murum breaking, OWC machine area Backside wall Excess Concrete breaking, etc | 100 |  | 109790 | 2024-08-12 | 18200 | 1900-01-01 | -13650 | PRAKASH CONTRACTOR
Departmental Labour | N/C | N/C | PRAKASH CONTRACTOR | 1890 | 2024-01-08 | Excavation, leveling, material shifting for development work | 21 | 650 | 0 | 13650 | 0 | 2024-08-12 11:28 | Charges for Male coolie for Breaking, Material Shifting & Excavation work at Development. | 100 |  | 109790 | 2024-08-12 | 18200 | 1900-01-01 | -4550 | PRAKASH CONTRACTOR
SS Railing (L) | N/C | N/C | HELIOS | 1896 | 2024-01-11 | A.27th Floor Staircase 1 Railling | 10 | 300 | 0 | 3000 | 540 | 2024-08-01 13:04 | Labour Charges for A-Tower Staircase-1 SS Railing work | 100 |  | 109603 | 2024-08-05 | 3000 | 2024-08-21 10:44 | 0 | HELIOS
Tikki Dhada (L) | N/C | N/C | JAY GANESH ENTERPRISES | 1911 | 2024-01-18 | A 2802 NOC | 334.32 | 11 | 0 | 3677.52 | 661.96 | 2024-08-05 15:01 | Labour Charges for Applying Tikki Dhada for Both side on Extra Blockwork in Master Bedroom & Staff room . | 100 |  | 109633 | 2024-08-05 | 3677.52 | 1900-01-01 | 0 | J K INTERIOR
Site Expenses -SO | N/C | N/C | INTEKHAB PATEL | 1913 | 2024-01-30 | Site Expenses | 1 | 30000 | 0 | 30000 | 0 | 2024-08-08 | Charges for Petty Cash Expenses including Mathadi (Loading/Unloading) for the Month JULY-2024. | 100 |  | 109687 | 2024-08-09 | 38940 | 2024-08-21 10:51 | -8940 | INTEKHAB PATEL
Site Expenses -SO | N/C | N/C | INTEKHAB PATEL | 1913 | 2024-01-30 | Site Expenses | 0.298 | 30000 | 0 | 8940 | 0 | 2024-08-08 | Charges for Petty Cash Expenses including Mathadi (Loading/Unloading) for the Month APR-2024. | 100 |  | 109687 | 2024-08-09 | 38940 | 2024-08-21 10:51 | -30000 | INTEKHAB PATEL
Oil base Primer-BC | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 1 | 0 | 5196 | 935.28 | 2024-08-03 19:23 | Labour charges for Applying Oil Base Primer on Wall for B-Bldg Internal Flat. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -25514.67 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 1 | 0 | 5196 | 935.28 | 2024-08-03 19:23 | Labour charges for Applying 1st Coat Lambi Putty on wall for B-bldg Internal Flat area. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -25514.67 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 1 | 0 | 5196 | 935.28 | 2024-08-03 19:23 | Labour charges for Applying 2nd Coat Lambi Putty on wall for B-bldg Internal Flat area. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -25514.67 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 0.5 | 0 | 2598 | 467.64 | 2024-08-03 19:23 | Labour charges for Applying Sanding Gattu on wall for B-bldg Internal Flat area. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -28112.67 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 0.5 | 0 | 2598 | 467.64 | 2024-08-03 19:23 | Labour charges for Applying Astar Coat on wall for B-bldg Internal Flat area. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -28112.67 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 0.5 | 0 | 2598 | 467.64 | 2024-08-03 19:23 | Labour charges for Applying Touch up Lambi on wall for B-bldg Internal Flat area. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -28112.67 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Ceiling Premium Emulsion Painting | 2442.89 | 1 | 0 | 2442.89 | 439.72 | 2024-08-03 19:33 | Labour charges for Applying Water Base Primer on Ceiling for B-Bldg Internal Flat Painting work. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -28267.78 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Ceiling Premium Emulsion Painting | 2442.89 | 1 | 0 | 2442.89 | 439.72 | 2024-08-03 19:33 | Labour charges for Applying 1st Coat Lambi Putty on Ceiling for B-Bldg Internal Flat Painting work. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -28267.78 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | PAINT DECOR | 1926 | 2024-02-14 | B 2401 Ceiling Premium Emulsion Painting | 2442.89 | 1 | 0 | 2442.89 | 439.72 | 2024-08-03 19:33 | Labour charges for Applying 2nd Coat Lambi Putty on Ceiling for B-Bldg Internal Flat Painting work. | 100 |  | 109602 | 2024-08-05 | 30710.67 | 2024-08-21 10:46 | -28267.78 | RISHIPRASAD ENTERPRISES
Water Base Primer (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Ceiling Premium Emulsion Painting | 2442.89 | 1 | 0 | 2442.89 | 439.72 | 2024-08-03 19:33 | Material Supply charges of Water Base Primer on ceiling for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -51339.56 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Ceiling Premium Emulsion Painting | 2442.89 | 2 | 0 | 4885.78 | 879.44 | 2024-08-03 19:33 | Material Supply charges of 1st Coat Lambi Putty on ceiling for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -48896.67 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Ceiling Premium Emulsion Painting | 2442.89 | 2 | 0 | 4885.78 | 879.44 | 2024-08-03 19:33 | Material Supply charges of 2nd Coat Lambi Putty on ceiling for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -48896.67 | RISHIPRASAD ENTERPRISES
Oil Base Primer (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 2 | 0 | 10392 | 1870.56 | 2024-08-03 19:23 | Material Supply charges of Oil Base Primer on wall for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -43390.45 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 2 | 0 | 10392 | 1870.56 | 2024-08-03 19:23 | Material Supply charges of 1st Coat Lambi on wall for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -43390.45 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 2 | 0 | 10392 | 1870.56 | 2024-08-03 19:23 | Material Supply charges of 2nd Coat Lambi Putty on wall for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -43390.45 | RISHIPRASAD ENTERPRISES
Sanding Gattu (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 1 | 0 | 5196 | 935.28 | 2024-08-03 19:23 | Material Supply charges of sanding Gattu on wall for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -48586.45 | RISHIPRASAD ENTERPRISES
Astar Coat (M) | N/C | N/C | PAINT DECOR | 1927 | 2024-02-14 | B 2401 Walls Satin Matt Painting | 5196 | 1 | 0 | 5196 | 935.28 | 2024-08-03 19:23 | Material Supply charges of Astar Coat on wall for B-Bldg Internal Flat Painting work. | 100 |  | 109600 | 2024-08-05 | 53782.45 | 2024-08-21 10:46 | -48586.45 | RISHIPRASAD ENTERPRISES
R & D Purpose | N/C | N/C | INTEKHAB PATEL | 1938 | 2024-03-01 | R & D Purpose | 0.03 | 100000 | 0 | 3000 | 540 | 2024-08-03 | Charges for Testing & Certification for Various items as per requirement. | 100 | CTM calibration | 109592 | 2024-08-05 | 3000 | 1900-01-01 | 0 | OM ENGINEERING & SCIENTIFIC EQUIPMENTS
JCB Charges | N/C | N/C | SHIVAM ENTERPRISES | 1941 | 2024-03-09 | Mandir area excavation & murum levelling work | 12.5 | 850 | 0 | 10625 | 0 | 2024-08-05 11:36 | Charges for JCB hiring for Excavation & Murum Levelling at Mandir Area & Rainwater Harvesting Chamber. | 100 |  | 110007 | 2024-08-22 | 11475 | 1900-01-01 | -850 | GYANDEEP ENTERPRISES
JCB Charges | N/C | N/C | SHIVAM ENTERPRISES | 1941 | 2024-03-09 | Mandir area excavation & murum levelling work | 26 | 850 | 0 | 22100 | 0 | 2024-08-12 16:34 | Charges for JCB hiring for Excavation & Murum Levelling at Mandir Area & Rainwater Harvesting Chamber. | 100 |  | 109830 | 2024-08-12 | 22100 | 1900-01-01 | 0 | GYANDEEP ENTERPRISES
JCB Charges | N/C | N/C | SHIVAM ENTERPRISES | 1941 | 2024-03-09 | Mandir area excavation & murum levelling work | 1 | 850 | 0 | 850 | 0 | 2024-08-22 17:53 | Charges for JCB hiring for Excavation & Murum Levelling at Mandir Area & Rainwater Harvesting Chamber. | 100 |  | 110007 | 2024-08-22 | 11475 | 1900-01-01 | -10625 | GYANDEEP ENTERPRISES
Departmental Labour | N/C | N/C | AARYAN ENTERPRISES | 1948 | 2024-04-04 | A flats, lobbies & staircases Housekeeping work | 1 | 13000 | 0 | 13000 | 0 | 2024-08-02 | Departmental Labour (Male Coolie) charges for Housekeeping work with all tools,equipments for A-Bldg MAY-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | CHATU ARUN KASABE
Departmental Labour | N/C | N/C | AARYAN ENTERPRISES | 1948 | 2024-04-04 | A flats, lobbies & staircases Housekeeping work | 0.322 | 13000 | 0 | 4186 | 0 | 2024-08-02 | Departmental Labour (Male Coolie) charges for Housekeeping work with all tools,equipments for A-Bldg JUNE-2024 | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | CHATU ARUN KASABE
Departmental Labour | N/C | N/C | AARYAN ENTERPRISES | 1948 | 2024-04-04 | A flats, lobbies & staircases Housekeeping work | 0.86 | 11000 | 0 | 9460 | 0 | 2024-08-02 | Departmental Labour (Female Coolie) charges for Housekeeping work with all tools, equipments for A-Bldg for JULY-2024. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | CHATU ARUN KASABE
Departmental Labour | N/C | N/C | AARYAN ENTERPRISES | 1948 | 2024-04-04 | A flats, lobbies & staircases Housekeeping work | 0.8629 | 11000 | 0 | 9491.9 | 0 | 2024-08-02 | Departmental Labour (Female Coolie) charges for Housekeeping work with all tools, equipments for A-Bldg for JULY-2024. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | CHATU ARUN KASABE
Departmental Labour | N/C | N/C | AARYAN ENTERPRISES | 1949 | 2024-04-04 | B flats, lobbies & staircases Housekeeping work | 0.806 | 11000 | 0 | 8866 | 0 | 2024-08-02 | Departmental Labour (Female Coolie) charges for Housekeeping work with all tools, equipments for B-Bldg for JULY-2024 | 100 |  | 109604 | 2024-08-05 | 19916 | 1900-01-01 | -11050 | CHATU ARUN KASABE
Departmental Labour | N/C | N/C | AARYAN ENTERPRISES | 1949 | 2024-04-04 | B flats, lobbies & staircases Housekeeping work | 0.85 | 13000 | 0 | 11050 | 0 | 2024-08-02 | Departmental Labour (Male Coolie) charges for Housekeeping work with all tools, equipments for B-Bldg for JULY-2024. | 100 |  | 109604 | 2024-08-05 | 19916 | 1900-01-01 | -8866 | CHATU ARUN KASABE
Pressure Guage 100mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1966 | 2024-04-27 | A Booster Pump Supply & Installation (Terrace) | 3 | 1415 | 0 | 4245 | 764.1 | 2024-08-10 16:03 | Material supply charges of Pressure Guage 100mm (Make- H Guro) for Booster Pump Work. | 100 |  | 109776 | 2024-08-12 | 8490 | 1900-01-01 | -4245 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 1966 | 2024-04-27 | B Booster Pump Supply & Installation (Terrace) | 3 | 1415 | 0 | 4245 | 764.1 | 2024-08-10 16:03 | Material supply charges of Pressure Guage 100mm (Make- H Guro) for Booster Pump Work. | 100 |  | 109776 | 2024-08-12 | 8490 | 1900-01-01 | -4245 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1975 | 2024-05-07 | A 99 Level Parking Floor Lobby Gypsum plaster | 1187 | 13.11 | 0 | 15561.57 | 2801.08 | 2024-08-22 17:08 | Material Supply Charges of Gypsum for Tikki Dhada Work at A-Bldg Parking Lobby for 99, 102, 105 & 108 Level. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1975 | 2024-05-07 | A 102 Level Parking Floor Lobby Gypsum plaster | 1063 | 13.11 | 0 | 13935.93 | 2508.46 | 2024-08-22 17:08 | Material Supply Charges of Gypsum for Tikki Dhada Work at A-Bldg Parking Lobby for 99, 102, 105 & 108 Level. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1975 | 2024-05-07 | A 105 Level Parking Floor Lobby Gypsum plaster | 995 | 13.11 | 0 | 13044.45 | 2348 | 2024-08-22 17:08 | Material Supply Charges of Gypsum for Tikki Dhada Work at A-Bldg Parking Lobby for 99, 102, 105 & 108 Level. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 1975 | 2024-05-07 | A 108 Level Parking Floor Lobby Gypsum plaster | 950.28 | 13.11 | 0 | 12458.1708 | 2242.48 | 2024-08-22 17:08 | Material Supply Charges of Gypsum for Tikki Dhada Work at A-Bldg Parking Lobby for 99, 102, 105 & 108 Level. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SHRIRAM TRADERS
Vitrified Flooring - BRE | N/C | N/C | R K INTERIOR | 2013 | 2024-06-04 | B 105 Lvl. Ramp Store Room Flooring Work | 1500 | 30 | 0 | 45000 | 8100 | 2024-08-11 | Charges for (1200 X 600mm) Vitrified Flooring for Ramp Store Room at B-Bldg 105 level. | 100 |  | 109769 | 2024-08-12 | 45000 | 1900-01-01 | 0 | R K INTERIOR
SITC GI Pipe C Class 150mm dia.(L) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2016 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 411.9 | 615 | 0 | 253318.5 | 45597.34 | 2024-08-16 12:45 | Labour charges for Fixing of GI Pipe C Class 150mm Dia. including painting with red colour for 3 way Extenal Hydrant Feeding work. | 100 |  | 109872 | 2024-08-16 | 293518.5 | 1900-01-01 | -40200 | SAITECH FIRE SYSTEM PRIVATE LIMITED
SITC NRV 150mm Dia. (L) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2016 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 12 | 1200 | 0 | 14400 | 2592 | 2024-08-16 12:45 | Labour charges for Installation of Non Return valve 150mm Dia. for A-Bldg 3 way External Hydrant Feeding work. | 100 |  | 109872 | 2024-08-16 | 293518.5 | 1900-01-01 | -279118.5 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sluice Valve 150mm (L) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2016 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 12 | 1200 | 0 | 14400 | 2592 | 2024-08-16 12:45 | Labour charges for Installation of Sluice valve 150mm Dia. for A-Bldg 3 way External Hydrant Feeding work. | 100 |  | 109872 | 2024-08-16 | 293518.5 | 1900-01-01 | -279118.5 | SAITECH FIRE SYSTEM PRIVATE LIMITED
3 Way, 63mm fire service inlet connection (L) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2016 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 12 | 950 | 0 | 11400 | 2052 | 2024-08-16 12:45 | Labour charges for Installation of 3 way, 63mm fire service inlet connection for A-Bldg 3 way External Hydrant Feeding work. | 100 |  | 109872 | 2024-08-16 | 293518.5 | 1900-01-01 | -282118.5 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sluice Valve 150mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2017 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 3 | 16450 | 0 | 37012.5 | 6662.26 | 2024-08-16 12:48 | Against Delivery | 75 |  | 109873 | 2024-08-16 | 108562.5 | 1900-01-01 | -71550 | SAITECH FIRE SYSTEM PRIVATE LIMITED
3 Way, 63mm fire service inlet connection (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2017 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 12 | 7950 | 0 | 71550 | 12879 | 2024-08-16 12:48 | Against Delivery | 75 |  | 109873 | 2024-08-16 | 108562.5 | 1900-01-01 | -37012.5 | SAITECH FIRE SYSTEM PRIVATE LIMITED
SITC NRV 150mm Dia. (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2017 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 12 | 12500 | 0 | 112500 | 20250 | 2024-08-12 10:48 | Against Delivery | 75 |  | 109842 | 2024-08-12 | 223537.5 | 1900-01-01 | -111037.5 | SAITECH FIRE SYSTEM PRIVATE LIMITED
Sluice Valve 150mm (M) | N/C | N/C | SAITECH FIRE SYSTEM PRIVATE LIMITED | 2017 | 2024-06-08 | A Building 3-way External Hydrant Feeding Work | 9 | 16450 | 0 | 111037.5 | 19986.76 | 2024-08-12 10:48 | Against Delivery | 75 |  | 109842 | 2024-08-12 | 223537.5 | 1900-01-01 | -112500 | SAITECH FIRE SYSTEM PRIVATE LIMITED
AMC Charges | N/C | N/C | KLAUS WORLD EQUIPMENT | 2021 | 2024-06-17 | Tower Crane A & C Annual maintenance for tower crane & lift | 1 | 6800 | 0 | 6800 | 1224 | 2024-08-05 | Charges for Annual Maintenance Contract for C Building Tower Crane.12 Visits in a year.(Per Month visit or when breakdown occures) | 100 |  | 109624 | 2024-08-05 | 6800 | 1900-01-01 | 0 | KLAUS WORLD EQUIPMENT
Kota Skirting (L)- BCO | N/C | N/C | MOHAN PARSHURAM YADAV | 2048 | 2024-07-01 | A 31st to TerraceFloor Regular Staircase Flooring | 66.294 | 40 | 0 | 2651.76 | 0 | 2024-08-20 | Labour charges for Fixing of Kota Skirting work including 2nd quality POP laying or Floor guard sheet laying, removing, acid wash etc. Loading, shifting & unloading for A-Bldg staircase-1 & 2 from 31st Floor to Terrace Floor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | MOHAN PARSHURAM YADAV | 2048 | 2024-07-01 | A 31st to Terrace Floor Fire Staircase Flooring | 77.958 | 40 | 0 | 3118.32 | 0 | 2024-08-20 | Labour charges for Fixing of Kota Skirting work including 2nd quality POP laying or Floor guard sheet laying, removing, acid wash etc. Loading, shifting & unloading for A-Bldg staircase-1 & 2 from 31st Floor to Terrace Floor. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Flooring (L)- BCO | N/C | N/C | MOHAN PARSHURAM YADAV | 2048 | 2024-07-01 | A Garbage room Flooring & Dado Work | 101.35 | 60 | 0 | 6081 | 0 | 2024-08-13 17:56 | Labour charges for Fixing of Kota Flooring work with proper joint filling, right angle, etc including 2nd quality POP laying or Floor guard sheet laying, removing, acid wash, etc for A-Bldg Garbage room. | 100 |  | 109942 | 2024-08-19 | 12762.75 | 1900-01-01 | -6681.75 | MOHAN PARSHURAM YADAV
Dado - AIE | N/C | N/C | MOHAN PARSHURAM YADAV | 2048 | 2024-07-01 | A Garbage room Flooring & Dado Work | 267.27 | 25 | 0 | 6681.75 | 0 | 2024-08-13 17:56 | Labour charges for Fixing of Dado work with proper joint filling, right angle, etc for A-Building Garbage Room. | 100 |  | 109942 | 2024-08-19 | 12762.75 | 1900-01-01 | -6081 | MOHAN PARSHURAM YADAV
Granite Top (L) - BCo | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 864.513 | 94.5 | 0 | 81696.4785 | 14705.36 | 2024-08-01 15:33 | Labour charges for Granite Top/Border/Skirting Fixing work with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Back Side Area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -210832.7615 | R K INTERIOR
Granite Round Border | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 61.344 | 189 | 0 | 11594.016 | 2086.92 | 2024-08-01 15:33 | Labour charges for Granite Round Top/Border Fixing work with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Back Side Area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -280935.224 | R K INTERIOR
Granite Cross Skirting | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 6.147 | 157.5 | 0 | 968.1525 | 174.26 | 2024-08-01 15:33 | Labour charges for Fixing of Granite Cross Skirting work with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Backside area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -291561.0875 | R K INTERIOR
Granite Flooring | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 64.368 | 94.5 | 0 | 6082.776 | 1094.9 | 2024-08-01 15:33 | Labour charges for Fixing of Granite Flooring work with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Backside area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -286446.464 | R K INTERIOR
Granite Tappa (L) - BCo | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 113.481 | 94.5 | 0 | 10723.9545 | 1930.32 | 2024-08-01 15:33 | Labour charges for Fixing of Granite Tappa work with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Backside area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -281805.2855 | R K INTERIOR
Granite Dado- ARW | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 79.875 | 120.75 | 0 | 9644.9062 | 1736.08 | 2024-08-01 15:33 | Labour charges for Fixing of Granite Dado with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Back side area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -282884.3337 | R K INTERIOR
Granite Border-BCo | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 1492.362 | 94.5 | 0 | 141028.209 | 25385.08 | 2024-08-01 15:33 | Labour charges for Fixing of Granite Border (Mandna Floor Border) with proper cutting, shifting, fixing with proper line level, right angle, corner etc. for Club House Back side area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -151501.031 | R K INTERIOR
Zero Point Joint Making | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 11.385 | 210 | 0 | 2390.85 | 430.36 | 2024-08-01 15:33 | Labour charges for Zero Point Joint Making work for Club House Back side area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -290138.39 | R K INTERIOR
V Groove- Dld | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 78.669 | 126 | 0 | 9912.294 | 1784.22 | 2024-08-01 15:33 | Labour charges for V-Groove making work for Club House Back side area Granite work. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -282616.946 | R K INTERIOR
Granite Full Moulding (L) | N/C | N/C | R K INTERIOR | 2069 | 2024-07-11 | Club House back side Pathway, Feature wall Granite work | 83.844 | 220.5 | 0 | 18487.602 | 3327.76 | 2024-08-01 15:33 | Labour charges for Granite 2inch Full Moulding work for Club House Back side area. | 100 |  | 109568 | 2024-08-05 | 292529.24 | 1900-01-01 | -274041.638 | R K INTERIOR
Tractor Trip - DCW | N/C | N/C | THIPPANNA | 2074 | 2024-07-24 | A,B,C,D & Development Garbage Shifting | 30 | 1000 | 0 | 30000 | 0 | 2024-08-12 | Charges for Tractor Trips Site to outside with labour loading, unloading for Garbage shifting at A, B, C & D Development. | 100 |  | 109813 | 2024-08-12 | 30000 | 1900-01-01 | 0 | THIPPANNA
Tractor Trip - DCW | N/C | N/C | SURESH PAWAR | 2076 | 2024-07-26 | A,B,C,D & Development Garbage Shifting | 20 | 1000 | 0 | 20000 | 0 | 2024-08-12 | Charges for Tractor Trips Site to outside with labour loading, unloading for Garbage shifting at A, B, C & D Development. | 100 |  | 109812 | 2024-08-12 | 20000 | 1900-01-01 | 0 | SURESH KUMAR
Departmental Labour | N/C | N/C | JAISAN | 2077 | 2024-07-30 | B Bldg Material Lift Erection & dismantling work | 45 | 650 | 0 | 29250 | 0 | 2024-08-05 | Departmental Labour Charges for Material Lift Erection and Dismanteling work at B-Bldg. | 100 |  | 109622 | 2024-08-05 | 29250 | 1900-01-01 | 0 | JAISAN
6" Brick Work | N/C | N/C | SURESH KUMAR MURALIDHAR | 2078 | 2024-07-31 | B 105 Lvl. Ramp Store Room Brickwork & Plaster | 120 | 22 | 0 | 2640 | 0 | 2024-08-06 13:10 | Charges for 6" Brickwork for Ramp Store Room at B-Bldg 105 level. | 100 |  | 109733 | 2024-08-12 | 5640 | 2024-08-21 10:48 | -3000 | SURESH KUMAR MURALIDHAR
Sand face Plaster- BC | GLAZING SERVICES | N/C | SURESH KUMAR MURALIDHAR | 2078 | 2024-07-31 | B 105 Lvl. Ramp Store Room Brickwork & Plaster | 120 | 25 | 0 | 3000 | 0 | 2024-08-06 13:10 | Charges for Sand Face plaster for Ramp Store Room at B-Bldg 105 level. | 100 |  | 109733 | 2024-08-12 | 5640 | 2024-08-21 10:48 | -2640 | SURESH KUMAR MURALIDHAR
1 Coat Primer (Water Base) (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 2079 | 2024-07-31 | B 105 Lvl. Ramp Store Room Painting Work | 2670 | 1 | 0 | 2670 | 480.6 | 2024-08-12 | Labour charges for 1 coat Water base primer for ceiling & wall at B-Bldg 105 level. | 100 |  | 109787 | 2024-08-12 | 5340 | 1900-01-01 | -2670 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Primer (water Base) (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 2079 | 2024-07-31 | B 105 Lvl. Ramp Store Room Painting Work | 2670 | 1 | 0 | 2670 | 480.6 | 2024-08-12 | Labour charges for 2nd coat Water base primer for ceiling & wall at B-Bldg 105 level. | 100 |  | 109787 | 2024-08-12 | 5340 | 1900-01-01 | -2670 | SAI NIRMAL COLOURS & TEXTURES
Hacking Work | N/C | N/C | UNIQUE ENTERPRISES | 209 | 2017-02-25 | A Bldg 5th Girder Slab (Podium Floor) Built-up Area (L) | 111.58 | 5 | 0 | 557.9 | 100.42 | 2024-08-13 18:09 | Hacking Work & Quality | 100 | 105 level garbage level ceiling grinding work A,B | 109944 | 2024-08-19 | 557.9 | 1900-01-01 | 0 | SAI NIRMAL COLOURS & TEXTURES
Departmental Labour | N/C | N/C | PRAKASH CONTRACTOR | 247 | 2017-07-25 | Labour Charges For Departmental Work | 12 | 650 | 0 | 7800 | 0 | 2024-08-05 12:43 | Charges for Male coolie for Miscellaneous Departmental work for D-Bldg | 100 |  | 109629 | 2024-08-05 | 10400 | 2024-08-21 10:46 | -2600 | PRAKASH CONTRACTOR
Breaker - BRE | N/C | N/C | PRAKASH CONTRACTOR | 247 | 2017-07-25 | STP to main gate drainage line work | 2 | 1300 | 0 | 2600 | 0 | 2024-08-05 12:43 | Charges for Breaker for STP to Main Gate Drainage line Breaking work. | 100 |  | 109629 | 2024-08-05 | 10400 | 2024-08-21 10:46 | -7800 | PRAKASH CONTRACTOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 10th Slab Built-up Area (L) | 36.0117 | 133 | 0 | 4789.5561 | 862.12 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.0439 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 11th Slab Built-up Area (L) | 36.0117 | 133 | 0 | 4789.5561 | 862.12 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.0439 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 12th Slab Built-up Area (L) | 36.0117 | 133 | 0 | 4789.5561 | 862.12 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.0439 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 13th Slab Built-up Area (L) | 36.0117 | 133 | 0 | 4789.5561 | 862.12 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.0439 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 14th Slab Built-up Area (L) | 33.61 | 142.5 | 0 | 4789.425 | 862.1 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.175 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 15th Slab Built-up Area (L) | 33.61 | 142.5 | 0 | 4789.425 | 862.1 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.175 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 16th Slab Built-up Area (L) | 33.61 | 142.5 | 0 | 4789.425 | 862.1 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.175 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 18th Slab Built-up Area (L) | 31.51 | 152 | 0 | 4789.52 | 862.12 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105365.08 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 19th Slab Built-up Area (L) | 63.02 | 152 | 0 | 9579.04 | 1724.22 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -100575.56 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 21st Slab Built-up Area (L) | 29.65 | 152 | 0 | 4506.8 | 811.22 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105647.8 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 21st Slab Built-up Area (L) | 29.65 | 152 | 0 | 4506.8 | 811.22 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105647.8 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 22nd Slab Built-up Area (L) | 29.65 | 161.5 | 0 | 4788.475 | 861.92 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105366.125 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 23rd Slab Built-up Area (L) | 29.65 | 161.5 | 0 | 4788.475 | 861.92 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105366.125 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 11th Slab Built-up Area (L) | 36.48 | 133 | 0 | 4851.84 | 873.34 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.76 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 12th Slab Built-up Area (L) | 36.48 | 133 | 0 | 4851.84 | 873.34 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.76 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 13th Slab Built-up Area (L) | 36.48 | 133 | 0 | 4851.84 | 873.34 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.76 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 14th Slab Built-up Area (L) | 34.05 | 142.5 | 0 | 4852.125 | 873.38 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.475 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 15th Slab Built-up Area (L) | 34.05 | 142.5 | 0 | 4852.125 | 873.38 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.475 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 16th Slab Built-up Area (L) | 34.05 | 142.5 | 0 | 4852.125 | 873.38 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.475 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 18th Slab Built-up Area (L) | 31.92 | 152 | 0 | 4851.84 | 873.34 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -105302.76 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 19th Slab Built-up Area (L) | 63.85 | 152 | 0 | 9705.2 | 1746.94 | 2024-08-08 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109743 | 2024-08-12 | 110154.6 | 1900-01-01 | -100449.4 | SAI NIRMAL COLOURS & TEXTURES
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 17th Slab Built-up Area (L) | 77.9 | 142.5 | 0 | 11100.75 | 0 | 2024-08-09 18:22 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | PRAKASH CONTRACTOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 17th Slab Built-up Area (L) | 150 | 142.5 | 0 | 21375 | 0 | 2024-08-05 10:07 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109606 | 2024-08-05 | 21375 | 2024-08-19 13:19 | 0 | SURESH KUMAR MURALIDHAR
Sorting & Shifting Work | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg Terrace Slab Built-up Area (L) | 287.5 | 40 | 0 | 11500 | 0 | 2024-08-07 17:54 | Sorting & Shifting for Aluform Shuttering/Reinforcement/Concreting for Slab,Beam,Staircase & all Sherwalls | 100 |  | 109870 | 2024-08-14 | 11500 | 1900-01-01 | 0 | PRAKASH CONTRACTOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 27th Slab Built-up Area (L) | 38.59 | 171 | 0 | 6598.89 | 1187.8 | 2024-08-03 20:00 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 | Tikki dhada work due to rcc wall bulging | 109607 | 2024-08-05 | 6598.89 | 1900-01-01 | 0 | J K INTERIOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 17th Slab Built-up Area (L) | 80.8772 | 142.5 | 0 | 11525.001 | 0 | 2024-08-12 11:12 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109741 | 2024-08-12 | 11525 | 1900-01-01 | 0.001 | SURESH KUMAR MURALIDHAR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 18th Slab Built-up Area (L) | 17.1053 | 152 | 0 | 2600.0056 | 0 | 2024-08-19 16:32 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | PRAKASH CONTRACTOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 17th Slab Built-up Area (L) | 74.0351 | 142.5 | 0 | 10550.0017 | 0 | 2024-08-19 16:44 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 109941 | 2024-08-19 | 10550 | 1900-01-01 | 0.00175 | SURESH KUMAR MURALIDHAR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 17th Slab Built-up Area (L) | 77.8947 | 142.5 | 0 | 11099.9947 | 0 | 2024-08-19 13:01 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | PRAKASH CONTRACTOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 32nd Slab Built-up Area (L) | 18 | 181.3 | 0 | 3263.4 | 587.42 | 2024-08-19 08:27 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 | Gypsum tikki dhada work due to rcc wall bulging | 109946 | 2024-08-19 | 7916.22 | 1900-01-01 | -4652.82 | J K INTERIOR
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | GOURI INFRA | 272 | 2017-09-18 | A Bldg 22nd Slab Built-up Area (L) | 28.81 | 161.5 | 0 | 4652.815 | 837.5 | 2024-08-19 08:49 | Labour Charges for Aluform Shuttering / Reinforcement / Concreting for Slab ,Beam,Staircase & All Sherwalls | 100 | Gypsum tikki dhada work due to rcc wall bulging | 109946 | 2024-08-19 | 7916.22 | 1900-01-01 | -3263.405 | J K INTERIOR
Departmental Labour | N/C | N/C | PRAKASH CONTRACTOR | 366 | 2018-04-11 | Mat. Shifting Work from Ganga Collidium | 50 | 650 | 0 | 32500 | 0 | 2024-08-18 12:42 | Charges for Male Coolie for Material shifting from Ganga Colidium to Ganga Dham Towers. | 100 |  | 109957 | 2024-08-19 | 32500 | 1900-01-01 | 0 | PRAKASH CONTRACTOR
Sorting & Shifting Work | No category | N/C | B & B ENTERPRISES | 372 | 2018-04-30 | B Bldg Terrace Slab Built-up Area (L) | 246 | 40 | 0 | 9840 | 1771.2 | 2024-08-08 | Aluform Shuttering Plate Cleaning & Shifting | 100 |  | 109747 | 2024-08-12 | 30240 | 1900-01-01 | -20400 | SAI NIRMAL COLOURS & TEXTURES
Sorting & Shifting Work | No category | N/C | B & B ENTERPRISES | 372 | 2018-04-30 | B Bldg Terrace Slab Built-up Area (L) | 170 | 120 | 0 | 20400 | 3672 | 2024-08-08 | Labour Charges for-Sorting and Shifting, Cleaning for Aluform Shuttering,Reinforcement,concreting for Slab,Beam,Staircase and all Shearwalls. | 100 |  | 109747 | 2024-08-12 | 30240 | 1900-01-01 | -9840 | SAI NIRMAL COLOURS & TEXTURES
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2401 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 177 | 5.5 | 0 | 973.5 | 48.68 | 2024-08-05 18:00 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14971 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2402 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144 | 5.5 | 0 | 792 | 39.6 | 2024-08-05 18:00 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -15152.5 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2501 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 177 | 5.5 | 0 | 973.5 | 48.68 | 2024-08-05 18:00 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14971 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2502 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144 | 5.5 | 0 | 792 | 39.6 | 2024-08-05 18:00 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -15152.5 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2601 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 177 | 5.5 | 0 | 973.5 | 48.68 | 2024-08-05 18:00 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14971 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2602 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144 | 5.5 | 0 | 792 | 39.6 | 2024-08-05 18:00 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -15152.5 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2702 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144 | 9.5 | 0 | 1368 | 68.4 | 2024-08-05 18:00 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14576.5 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2801 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 177 | 9.5 | 0 | 1681.5 | 84.08 | 2024-08-05 18:00 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14263 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2802 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144 | 9.5 | 0 | 1368 | 68.4 | 2024-08-05 18:00 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14576.5 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2901 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada - 1 | 177 | 9.5 | 0 | 1681.5 | 84.08 | 2024-08-05 18:00 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14263 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 2902 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144 | 9.5 | 0 | 1368 | 68.4 | 2024-08-05 18:00 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14576.5 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 3001 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 177 | 9.5 | 0 | 1681.5 | 84.08 | 2024-08-05 18:00 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14263 | SHRIRAM TRADERS
Tikki Dhada (M) | N/C | N/C | J K INTERIOR | 392 | 2018-06-04 | A 3101 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 157.842 | 9.5 | 0 | 1499.499 | 74.98 | 2024-08-05 18:13 | Material Supply for- Gypsum Plaster (Tikki Dhada) for Kitchen, Dry Balcony & Common Toilet. | 100 |  | 109685 | 2024-08-09 | 15944.5 | 2024-08-09 12:52 | -14445.001 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 901 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 160.61 | 5.5 | 0 | 883.355 | 44.16 | 2024-08-09 17:35 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109691 | 2024-08-09 | 2879.37 | 2024-08-21 16:15 | -1996.015 | LAXMI STRUCTURES & FIXTURES LLP
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 902 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 127.85 | 5.5 | 0 | 703.175 | 35.16 | 2024-08-09 17:35 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109691 | 2024-08-09 | 2879.37 | 2024-08-21 16:15 | -2176.195 | LAXMI STRUCTURES & FIXTURES LLP
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 1601 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 90.169 | 5.5 | 0 | 495.9295 | 24.8 | 2024-08-09 17:35 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109691 | 2024-08-09 | 2879.37 | 2024-08-21 16:15 | -2383.4405 | LAXMI STRUCTURES & FIXTURES LLP
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | J K INTERIOR | 392 | 2018-06-04 | A 1602 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 144.89 | 5.5 | 0 | 796.895 | 39.84 | 2024-08-09 17:35 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109691 | 2024-08-09 | 2879.37 | 2024-08-21 16:15 | -2082.475 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (L) | N/C | N/C | J K INTERIOR | 393 | 2018-06-04 | A 2902 Gypsum Plaster | 295.46 | 11 | 0 | 3250.06 | 0 | 2024-08-09 14:38 | Labour charges for Internal Flat Dhar Core Work for A-Bldg. | 100 | Debris cleaning work | 109757 | 2024-08-12 | 3250.06 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 103 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 203 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 303 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 304 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 287 | 5.5 | 0 | 1578.5 | 78.92 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16046.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 403 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada - 1 | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 404 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 287 | 5.5 | 0 | 1578.5 | 78.92 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16046.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 504 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 287 | 5.5 | 0 | 1578.5 | 78.92 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16046.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 603 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 604 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 287 | 5.5 | 0 | 1578.5 | 78.92 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16046.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 703 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 704 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 287 | 5.5 | 0 | 1578.5 | 78.92 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16046.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 803 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 65.54 | 5.5 | 0 | 360.47 | 18.02 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -17264.5 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 903 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Tikki Dhada Rate Diff (M) | GLAZING SERVICES | N/C | A K INTERIOR CONTRACTOR | 394 | 2018-06-04 | A 1003 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | 213 | 5.5 | 0 | 1171.5 | 58.58 | 2024-08-05 17:38 | Rate Difference for Gypsum Tikki Dhada Plaster Work (M) | 100 |  | 109684 | 2024-08-09 | 17624.97 | 2024-08-09 12:52 | -16453.47 | SHRIRAM TRADERS
Gypsum on Wall (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 803 Gypsum Plaster | 526.78 | 4 | 0 | 2107.12 | 379.28 | 2024-08-09 11:04 | Gypsum Plaster on Wall (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -10792.03 | A K INTERIOR CONTRACTOR
Dhar Core (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 803 Gypsum Plaster | 183.23 | 10 | 0 | 1832.3 | 329.82 | 2024-08-09 11:04 | Gypsum Dhar Core (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -11066.85 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 103 Gypsum Plaster | 211.38 | 4 | 0 | 845.52 | 152.2 | 2024-08-09 11:13 | Gypsum Plaster on Wall (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12053.63 | A K INTERIOR CONTRACTOR
Dhar Core (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 103 Gypsum Plaster | 183.23 | 10 | 0 | 1832.3 | 329.82 | 2024-08-09 11:13 | Gypsum Dhar Core (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -11066.85 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1404 Gypsum Plaster | 189.5649 | 4 | 0 | 758.2596 | 136.48 | 2024-08-09 11:17 | Gypsum Plaster on Wall (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12140.8904 | A K INTERIOR CONTRACTOR
Dhar Core (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1404 Gypsum Plaster | 66.891 | 10 | 0 | 668.91 | 120.4 | 2024-08-09 11:17 | Gypsum Dhar Core (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12230.24 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1704 Gypsum Plaster | 189.0229 | 4 | 0 | 756.0916 | 136.1 | 2024-08-09 11:22 | Gypsum Plaster on Wall (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12143.0584 | A K INTERIOR CONTRACTOR
Dhar Core (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1704 Gypsum Plaster | 67.081 | 10 | 0 | 670.81 | 120.74 | 2024-08-09 11:22 | Gypsum Dhar Core (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12228.34 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1703 Gypsum Plaster | 126.78 | 4 | 0 | 507.12 | 91.28 | 2024-08-09 11:24 | Gypsum Plaster on Wall (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12392.03 | A K INTERIOR CONTRACTOR
Dhar Core (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1703 Gypsum Plaster | 183.23 | 10 | 0 | 1832.3 | 329.82 | 2024-08-09 11:24 | Gypsum Dhar Core (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -11066.85 | A K INTERIOR CONTRACTOR
Gypsum on Wall (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1503 Gypsum Plaster | 86.53 | 4 | 0 | 346.12 | 62.3 | 2024-08-09 11:26 | Gypsum Plaster on Wall (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12553.03 | A K INTERIOR CONTRACTOR
Dhar Core (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A Bldg Flat No. 1503 Gypsum Plaster | 74.23 | 10 | 0 | 742.3 | 133.62 | 2024-08-09 11:26 | Gypsum Dhar Core (L) | 100 |  | 109752 | 2024-08-12 | 12899.15 | 1900-01-01 | -12156.85 | A K INTERIOR CONTRACTOR
Gypsum Plaster (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 395 | 2018-06-04 | A 3103 Gypsum Plaster | 2447.802 | 6 | 0 | 14686.812 | 2643.62 | 2024-08-19 17:46 | Labour charges for applying Gypsum Plaster Patra Finish work for A-Bldg Internal flat | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR
8 Way TPN DB | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 1400 | 0 | 420 | 75.6 | 2024-08-22 20:38 | Switch, Socket Fixing for 8 Way TPN DB | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
8 Way TPN DB | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 1400 | 0 | 70 | 12.6 | 2024-08-22 20:38 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
TV/Tel DB Fixing | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 500 | 0 | 125 | 22.5 | 2024-08-22 20:43 | Internal Wiring for TV/Telephone DB | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
TV/Tel DB Fixing | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 500 | 0 | 150 | 27 | 2024-08-22 20:43 | Switch, Socket Fixing for TV/Telephone DB | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
TV/Tel DB Fixing | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 500 | 0 | 25 | 4.5 | 2024-08-22 20:43 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Power Point (2.5 & 1.5 Sqmm) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 2 | 220 | 0 | 110 | 19.8 | 2024-08-22 20:43 | Internal Wiring for 16 Amp Power Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Power Point (2.5 & 1.5 Sqmm) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 2 | 220 | 0 | 132 | 23.76 | 2024-08-22 20:43 | Switch, Socket Fixing for 16 Amp Power Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Power Point (2.5 & 1.5 Sqmm) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 2 | 220 | 0 | 22 | 3.96 | 2024-08-22 20:43 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Secondary Light Points (Looping) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 55 | 67 | 0 | 921.25 | 165.82 | 2024-08-22 19:50 | Internal Wiring for Secondary Light Point in Wall & Ceiling | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Secondary Light Points (Looping) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 55 | 67 | 0 | 1105.5 | 199 | 2024-08-22 19:50 | Switch, Socket Fixing for Secondary Light Point in Wall & Ceiling | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Secondary Light Points (Looping) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 55 | 67 | 0 | 184.25 | 33.16 | 2024-08-22 19:50 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Fan Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 11 | 200 | 0 | 550 | 99 | 2024-08-22 19:50 | Internal Wiring for Fan Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Fan Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 11 | 200 | 0 | 660 | 118.8 | 2024-08-22 19:50 | Switch, Socket Fixing for Fan Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Fan Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 11 | 200 | 0 | 110 | 19.8 | 2024-08-22 19:50 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
TV Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 8 | 220 | 0 | 440 | 79.2 | 2024-08-22 19:50 | Internal Wiring for TV Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
TV Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 8 | 220 | 0 | 528 | 95.04 | 2024-08-22 19:50 | Switch, Socket Fixing for TV Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
TV Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 8 | 220 | 0 | 88 | 15.84 | 2024-08-22 19:50 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Telephone Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 6 | 220 | 0 | 330 | 59.4 | 2024-08-22 19:50 | Internal Wiring for Telephone Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Telephone Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 6 | 220 | 0 | 396 | 71.28 | 2024-08-22 19:50 | Switch, Socket Fixing for Telephone Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Telephone Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 6 | 220 | 0 | 66 | 11.88 | 2024-08-22 19:50 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
AC Point BC | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 9 | 220 | 0 | 495 | 89.1 | 2024-08-22 19:50 | Internal Wiring for 20 Amp AC Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
AC Point BC | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 9 | 220 | 0 | 594 | 106.92 | 2024-08-22 19:50 | Switch, Socket Fixing for 20 Amp AC Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
AC Point BC | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 9 | 220 | 0 | 99 | 17.82 | 2024-08-22 19:50 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Video Door Phone (L)- BC | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 200 | 0 | 50 | 9 | 2024-08-22 20:05 | Internal Wiring for VDP | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Video Door Phone (L)- BC | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 200 | 0 | 10 | 1.8 | 2024-08-22 20:05 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Primary Light Pt. (Controlled by Sw. Board) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 79 | 200 | 0 | 3950 | 711 | 2024-08-22 20:09 | Internal Wiring for Primary Light Point in Wall & Ceiling | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Primary Light Pt. (Controlled by Sw. Board) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 79 | 200 | 0 | 4740 | 853.2 | 2024-08-22 20:09 | Switch, Socket Fixing for Primary Light Point in Wall & Ceiling | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Primary Light Pt. (Controlled by Sw. Board) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 79 | 200 | 0 | 790 | 142.2 | 2024-08-22 20:09 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Data Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 7 | 220 | 0 | 385 | 69.3 | 2024-08-22 20:13 | Internal Wiring for Data Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Data Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 7 | 220 | 0 | 462 | 83.16 | 2024-08-22 20:13 | Switch, Socket Fixing for Data Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Data Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 7 | 220 | 0 | 77 | 13.86 | 2024-08-22 20:13 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
6 AMP Plug point (Independent) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 84 | 200 | 0 | 4200 | 756 | 2024-08-22 20:30 | Internal Wiring for 6 Amp Point for Curtains,TV,Chimney,Aquaguard etc | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
6 AMP Plug point (Independent) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 84 | 200 | 0 | 5040 | 907.2 | 2024-08-22 20:30 | Switch, Socket Fixing for 6 Amp Point for Curtains,TV,Chimney,Aquaguard etc | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
6 AMP Plug point (Independent) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 84 | 200 | 0 | 840 | 151.2 | 2024-08-22 20:30 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
6 AMP Plug point (Dependent) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 15 | 67 | 0 | 251.25 | 45.22 | 2024-08-22 20:38 | Internal Wiring for 6 Amp Dependent Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
6 AMP Plug point (Dependent) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 15 | 67 | 0 | 301.5 | 54.28 | 2024-08-22 20:38 | Switch, Socket Fixing for 6 Amp Dependent Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
6 AMP Plug point (Dependent) | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 15 | 67 | 0 | 50.25 | 9.04 | 2024-08-22 20:38 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Exhaust Fan Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 5 | 200 | 0 | 250 | 45 | 2024-08-22 20:38 | Internal Wiring for Exhaust Fan Point | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Exhaust Fan Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 5 | 200 | 0 | 300 | 54 | 2024-08-22 20:38 | Switch, Socket Fixing for Exhaust Fan Point | 30 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
Exhaust Fan Point | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 5 | 200 | 0 | 50 | 9 | 2024-08-22 20:38 | D B Fixing | 5 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
8 Way TPN DB | N/C | N/C | SAHOO ELECTRICAL | 399 | 2018-06-28 | B Bldg Flat No. 2601 Internal Electrical Work | 1 | 1400 | 0 | 350 | 63 | 2024-08-22 20:38 | Internal Wiring for 8 Way TPN DB | 25 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | P.L. VISHWAKARMA ELECTRICALS (FIRM)
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1903 Chemical & IPS Waterproofing | 90.6325 | 11 | 0 | 996.9575 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93562.4925 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1904 Chemical & IPS Waterproofing | 44.52 | 11 | 0 | 489.72 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94069.73 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2001 Chemical & IPS Waterproofing | 43.605 | 11 | 0 | 479.655 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94079.795 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2004 Chemical & IPS Waterproofing | 268.2 | 11 | 0 | 2950.2 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91609.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2101 Chemical & IPS Waterproofing | 109.05 | 11 | 0 | 1199.55 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93359.9 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2103 Chemical & IPS Waterproofing | 4.53 | 11 | 0 | 49.83 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94509.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2104 Chemical & IPS Waterproofing | 39.2 | 11 | 0 | 431.2 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94128.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2201 Chemical & IPS Waterproofing | 59.05 | 11 | 0 | 649.55 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93909.9 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2203 Chemical & IPS Waterproofing | 50.53 | 11 | 0 | 555.83 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94003.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2204 Chemical & IPS Waterproofing | 246.2909 | 11 | 0 | 2709.1999 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91850.2501 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2301 Chemical & IPS Waterproofing | 286.05 | 11 | 0 | 3146.55 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91412.9 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2303 Chemical & IPS Waterproofing | 237.53 | 11 | 0 | 2612.83 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91946.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2304 Chemical & IPS Waterproofing | 289.2 | 11 | 0 | 3181.2 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91378.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2401 Chemical & IPS Waterproofing | 259.05 | 11 | 0 | 2849.55 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91709.9 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2402 Chemical & IPS Waterproofing | 56.36 | 11 | 0 | 619.96 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93939.49 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2403 Chemical & IPS Waterproofing | 68.53 | 11 | 0 | 753.83 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93805.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2502 Chemical & IPS Waterproofing | 22.868 | 11 | 0 | 251.548 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94307.902 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2503 Chemical & IPS Waterproofing | 18.1265 | 11 | 0 | 199.3915 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94360.0585 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2504 Chemical & IPS Waterproofing | 22.26 | 11 | 0 | 244.86 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94314.59 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2601 Chemical & IPS Waterproofing | 21.8025 | 11 | 0 | 239.8275 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94319.6225 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2602 Chemical & IPS Waterproofing | 22.868 | 11 | 0 | 251.548 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94307.902 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2603 Chemical & IPS Waterproofing | 18.1265 | 11 | 0 | 199.3915 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94360.0585 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2604 Chemical & IPS Waterproofing | 22.26 | 11 | 0 | 244.86 | 0 | 2024-08-09 15:03 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94314.59 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 901 Chemical Grouting Work | 1447 | 1 | 0 | 1447 | 0 | 2024-08-20 11:57 | Internal Flat Chemocal Grouting Work (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2601 Chemical Grouting Work | 1347 | 1 | 0 | 1347 | 0 | 2024-08-20 12:03 | Internal Flat Chemocal Grouting Work (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting.- BC | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2101 Chemical Grouting Work | 144.7 | 1 | 0 | 144.7 | 0 | 2024-08-20 12:03 | Internal Flat Chemocal Grouting Work (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting Rate Diff. BCo | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1404 Chemical Grouting Work | 908.79 | 1 | 0 | 908.79 | 0 | 2024-08-20 12:12 | Rate Difference for Cutouts Joint Grouting & Testing | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting Rate Diff. BCo | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1802 Chemical Grouting Work | 297.428 | 1 | 0 | 297.428 | 0 | 2024-08-20 12:16 | Rate Difference for Cutouts Joint Grouting & Testing | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting Rate Diff. BCo | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1803 Chemical Grouting Work | 1124.36 | 1 | 0 | 1124.36 | 0 | 2024-08-20 12:16 | Rate Difference for Cutouts Joint Grouting & Testing | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical Grouting Rate Diff. BCo | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2201 Chemical Grouting Work | 1447 | 1 | 0 | 1447 | 0 | 2024-08-20 12:16 | Rate Difference for Cutouts Joint Grouting & Testing | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 101 Chemical & IPS Waterproofing | 177.05 | 19 | 0 | 3363.95 | 0 | 2024-08-05 15:23 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109621 | 2024-08-05 | 8245.62 | 1900-01-01 | -4881.67 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 103 Chemical & IPS Waterproofing | 183.53 | 19 | 0 | 3487.07 | 0 | 2024-08-05 15:23 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109621 | 2024-08-05 | 8245.62 | 1900-01-01 | -4758.55 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 904 Chemical & IPS Waterproofing | 21.2 | 19 | 0 | 402.8 | 0 | 2024-08-05 15:23 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109621 | 2024-08-05 | 8245.62 | 1900-01-01 | -7842.82 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1004 Chemical & IPS Waterproofing | 52.2 | 19 | 0 | 991.8 | 0 | 2024-08-05 15:23 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109621 | 2024-08-05 | 8245.62 | 1900-01-01 | -7253.82 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1102 Chemical & IPS Waterproofing | 30.36 | 19 | 0 | 576.84 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93982.61 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1202 Chemical & IPS Waterproofing | 43.36 | 19 | 0 | 823.84 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93735.61 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1401 Chemical & IPS Waterproofing | 39.05 | 19 | 0 | 741.95 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93817.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1504 Chemical & IPS Waterproofing | 295.2 | 19 | 0 | 5608.8 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -88950.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1601 Chemical & IPS Waterproofing | 59.05 | 19 | 0 | 1121.95 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93437.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1603 Chemical & IPS Waterproofing | 37.53 | 19 | 0 | 713.07 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93846.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1604 Chemical & IPS Waterproofing | 47.2 | 19 | 0 | 896.8 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93662.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1704 Chemical & IPS Waterproofing | 95.2 | 19 | 0 | 1808.8 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -92750.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1803 Chemical & IPS Waterproofing | 37.53 | 19 | 0 | 713.07 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93846.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1904 Chemical & IPS Waterproofing | 45.2 | 19 | 0 | 858.8 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93700.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2001 Chemical & IPS Waterproofing | 43.605 | 19 | 0 | 828.495 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93730.955 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2004 Chemical & IPS Waterproofing | 268.2 | 19 | 0 | 5095.8 | 0 | 2024-08-09 11:55 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -89463.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2101 Chemical & IPS Waterproofing | 109.05 | 19 | 0 | 2071.95 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -92487.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2103 Chemical & IPS Waterproofing | 4.53 | 19 | 0 | 86.07 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94473.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2104 Chemical & IPS Waterproofing | 39.2 | 19 | 0 | 744.8 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93814.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2201 Chemical & IPS Waterproofing | 59.05 | 19 | 0 | 1121.95 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93437.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2203 Chemical & IPS Waterproofing | 50.53 | 19 | 0 | 960.07 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93599.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2204 Chemical & IPS Waterproofing | 246.3053 | 19 | 0 | 4679.8007 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -89879.6493 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2301 Chemical & IPS Waterproofing | 75.05 | 19 | 0 | 1425.95 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93133.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2303 Chemical & IPS Waterproofing | 68.53 | 19 | 0 | 1302.07 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93257.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2304 Chemical & IPS Waterproofing | 289.2 | 19 | 0 | 5494.8 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -89064.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2401 Chemical & IPS Waterproofing | 30.05 | 19 | 0 | 570.95 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93988.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2402 Chemical & IPS Waterproofing | 50 | 19 | 0 | 950 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93609.45 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2403 Chemical & IPS Waterproofing | 68.53 | 19 | 0 | 1302.07 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93257.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2501 Chemical & IPS Waterproofing | 30.05 | 19 | 0 | 570.95 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93988.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2502 Chemical & IPS Waterproofing | 56.36 | 19 | 0 | 1070.84 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93488.61 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2503 Chemical & IPS Waterproofing | 108.53 | 19 | 0 | 2062.07 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -92497.38 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2504 Chemical & IPS Waterproofing | 41.2 | 19 | 0 | 782.8 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93776.65 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2601 Chemical & IPS Waterproofing | 30.05 | 19 | 0 | 570.95 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93988.5 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2602 Chemical & IPS Waterproofing | 50 | 19 | 0 | 950 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93609.45 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2603 Chemical & IPS Waterproofing | 36.253 | 19 | 0 | 688.807 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93870.643 | AJAY KUMAR GUPTA
Chemical W/P (L+M) | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 2604 Chemical & IPS Waterproofing | 44.52 | 19 | 0 | 845.88 | 0 | 2024-08-09 12:50 | Chemical Waterproofing 1st Coat,2nd Coat & Testing (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) M+L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93713.57 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 101 Chemical & IPS Waterproofing | 21.8025 | 11 | 0 | 239.8275 | 0 | 2024-08-09 12:50 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94319.6225 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 102 Chemical & IPS Waterproofing | 301.36 | 11 | 0 | 3314.96 | 0 | 2024-08-09 12:50 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91244.49 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 103 Chemical & IPS Waterproofing | 316.53 | 11 | 0 | 3481.83 | 0 | 2024-08-09 12:50 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91077.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 904 Chemical & IPS Waterproofing | 22.2 | 11 | 0 | 244.2 | 0 | 2024-08-09 13:57 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94315.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1004 Chemical & IPS Waterproofing | 268.2 | 11 | 0 | 2950.2 | 0 | 2024-08-09 13:57 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91609.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1102 Chemical & IPS Waterproofing | 30.36 | 11 | 0 | 333.96 | 0 | 2024-08-09 13:57 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94225.49 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1202 Chemical & IPS Waterproofing | 43.36 | 11 | 0 | 476.96 | 0 | 2024-08-09 13:57 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94082.49 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1401 Chemical & IPS Waterproofing | 39.05 | 11 | 0 | 429.55 | 0 | 2024-08-09 13:57 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94129.9 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1504 Chemical & IPS Waterproofing | 295.2 | 11 | 0 | 3247.2 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -91312.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1601 Chemical & IPS Waterproofing | 59.05 | 11 | 0 | 649.55 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93909.9 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1603 Chemical & IPS Waterproofing | 162.53 | 11 | 0 | 1787.83 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -92771.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1604 Chemical & IPS Waterproofing | 47.2 | 11 | 0 | 519.2 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94040.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1704 Chemical & IPS Waterproofing | 95.2 | 11 | 0 | 1047.2 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -93512.25 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1803 Chemical & IPS Waterproofing | 180.53 | 11 | 0 | 1985.83 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -92573.62 | AJAY KUMAR GUPTA
IPS W/P | N/C | N/C | SHREE GURUDATTA ENTERPRISES | 401 | 2018-06-30 | A 1902 Chemical & IPS Waterproofing | 45.736 | 11 | 0 | 503.096 | 0 | 2024-08-09 14:32 | IPS/Screeding Work (Dry Balcony,Staff Toilet,Master Toilet,Common Toilet,Parents Toilet,Children Toilet & Attached Terrace) L | 100 |  | 109755 | 2024-08-12 | 94559.45 | 1900-01-01 | -94056.354 | AJAY KUMAR GUPTA
Chamber 18" x 18" -UDR | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 1 | 1200 | 0 | 1200 | 0 | 2024-08-05 12:32 | Charges for 18" x 18" x 800mm depth Chamber Making work including Bottom PCC with Cement Ghotai, Internal Single coat plaster, Brickwork 9 inch, outer chat plaster, Top Plaster Ghotai & Chamber cover fixing Behind Club House Rainwater Pipe laying. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -19352.28 | PRAKASH CONTRACTOR
Chamber 24" x 24" (3ft Ht) USL | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 2 | 1800 | 0 | 3600 | 0 | 2024-08-05 12:32 | Charges for 24" x 24" x 1m depth Chamber Making work including Bottom PCC with Cement Ghotai, Internal Single coat plaster, Brickwork 9 inch, outer chat plaster, Top Plaster Ghotai & Chamber cover fixing for External Rainwater Pipe | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -16952.28 | PRAKASH CONTRACTOR
Chamber 24" x 18" (3ft Ht) - UDR | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 1 | 1800 | 0 | 1800 | 0 | 2024-08-05 12:32 | Charges for 18" x 24" x 1200mm depth Chamber Making work including Bottom PCC with Cement Ghotai, Internal Single coat plaster, Brickwork 9 inch, outer chat plaster, Top Plaster Ghotai & Chamber cover fixing for Openspace washroom sewage line | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -18752.28 | PRAKASH CONTRACTOR
Chamber 18" x 18" -UDR | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 1 | 1200 | 0 | 1200 | 0 | 2024-08-05 12:32 | Charges for 18" x 18" x 600mm depth Chamber Making work including Bottom PCC with Cement Ghotai, Internal Single coat plaster, Brickwork 9 inch, outer chat plaster, Top Plaster Ghotai & Chamber cover fixing for C-Bldg 99 level. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -19352.28 | PRAKASH CONTRACTOR
Chamber 18" x 18" -UDR | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 1 | 1200 | 0 | 1200 | 0 | 2024-08-05 12:32 | Charges for 18" x 18" x 1m depth Chamber Making work including Bottom PCC with Cement Ghotai, Internal Single coat plaster, Brickwork 9 inch, outer chat plaster, Top Plaster Ghotai & Chamber cover fixing for Club House | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -19352.28 | PRAKASH CONTRACTOR
12" Dia Derex Pipe line | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 13.776 | 25 | 0 | 344.4 | 0 | 2024-08-05 12:32 | Labour charges for 300mm Derex Pipe laying with Concrete covering Behind Club House Rainwater Pipe laying. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -20207.88 | PRAKASH CONTRACTOR
8" Derex Pipe Laying | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 126.43 | 21 | 0 | 2655.03 | 0 | 2024-08-05 12:32 | Labour charges for 200 mm Drex Pipe laying with Concrete covering for External Rainwater Pipe. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -17897.25 | PRAKASH CONTRACTOR
12" Dia Derex Pipe line | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 13.124 | 25 | 0 | 328.1 | 0 | 2024-08-05 12:32 | Labour charges for 300 mm Drex Pipe laying with Concrete covering for Openspace washroom Sewage line. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -20224.18 | PRAKASH CONTRACTOR
6" Derex Pipe Laying - DER | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 87.02 | 19 | 0 | 1653.38 | 0 | 2024-08-05 12:32 | Labour charges for 150 mm Drex Pipe laying with Concrete covering for Electric line laying | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -18898.9 | PRAKASH CONTRACTOR
6" Derex Pipe Laying - DER | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 13.02 | 19 | 0 | 247.38 | 0 | 2024-08-05 12:32 | Labour charges for 150 mm Drex Pipe laying with Concrete covering for C Bldg 99 level. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -20304.9 | PRAKASH CONTRACTOR
8" Derex Pipe Laying | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 20.19 | 21 | 0 | 423.99 | 0 | 2024-08-05 12:32 | Labour charges for 200mm Drex Pipe laying with Concrete covering for Club House | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -20128.29 | PRAKASH CONTRACTOR
Chamber 36" x 18" (3ft Ht) - UDR | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 3 | 1800 | 0 | 5400 | 0 | 2024-08-05 12:32 | Charges for 36" x 18" x 1m Depth Chamber making work including Bottom PCC with Cement Ghotai, Internal Single coat Plaster, Brickwork 9 inch, Outer chat plaster, Top Plaster Ghotai & Chamber cover fixing for Electric Line laying | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -15152.28 | PRAKASH CONTRACTOR
Labour Lumsum | N/C | N/C | PRAKASH CONTRACTOR | 461 | 2018-11-24 | Club house, Mandir & C bldg. area Storm Water Line | 1 | 500 | 0 | 500 | 0 | 2024-08-05 12:32 | Charges for Excavation for pipe laying & Backfilling (manually) for externel Rainwater pipe. | 100 |  | 109609 | 2024-08-05 | 20552.28 | 2024-08-21 10:44 | -20052.28 | PRAKASH CONTRACTOR
Gypsum on Wall (M) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 902 Gypsum Plaster | 31.2929 | 3.5 | 0 | 109.5251 | 5.48 | 2024-08-09 17:40 | Internal Flat Gypsum Plaster on Wall (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -25582.1149 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1802 Gypsum Plaster | 29.8643 | 3.5 | 0 | 104.525 | 5.22 | 2024-08-09 17:40 | Internal Flat Gypsum Plaster on Wall (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -25587.1149 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1902 Gypsum Plaster | 54.15 | 3.5 | 0 | 189.525 | 9.48 | 2024-08-09 17:40 | Internal Flat Gypsum Plaster on Wall (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -25502.115 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 102 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 202 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 302 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 402 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 502 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 602 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 702 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 802 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 902 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1002 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1102 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1202 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1302 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1402 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:40 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 2502 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:51 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1502 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1602 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1702 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1802 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 1902 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 2002 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 2102 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 2202 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 2302 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Dhar Core (Material) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 2402 Gypsum Plaster | 4 | 200 | 0 | 800 | 40 | 2024-08-09 17:52 | Internal Flat Dhar Core Gypsum 4 Bags (M) | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -24891.64 | LAXMI STRUCTURES & FIXTURES LLP
Gypsum on Wall (M) | N/C | N/C | J K INTERIOR | 496 | 2019-01-08 | B 3101 Gypsum Plaster | 1510.87 | 3.5 | 0 | 5288.045 | 264.4 | 2024-08-09 18:00 | Material supply charges for Applying Gypsum Plaster Patra Finish work for B-Bldg Internal Flat. | 100 |  | 109690 | 2024-08-09 | 25691.64 | 2024-08-19 13:20 | -20403.595 | LAXMI STRUCTURES & FIXTURES LLP
Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 27.9 | 355 | 0 | 9904.5 | 0 | 2024-08-03 18:27 | Material Supply For Rate Difference for Copper Pipe with insulation 1ton to 1.5 ton | 100 |  | 109595 | 2024-08-05 | 23206.69 | 1900-01-01 | -13302.19 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 33.03 | 15.5 | 0 | 511.965 | 0 | 2024-08-03 18:27 | Material Supply for Cable for Indoor to Outdoor 1Ton to 1.5 Ton(Rate Differance) | 100 |  | 109595 | 2024-08-05 | 23206.69 | 1900-01-01 | -22694.725 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for Drain Pipe with Installation (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 16.2 | 23 | 0 | 372.6 | 0 | 2024-08-03 18:27 | Material Suppy for-Drain Pipe With Insulation (Rate Difference) | 100 |  | 109595 | 2024-08-05 | 23206.69 | 1900-01-01 | -22834.09 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 204 AC Installation & Commissioning - 1 No. | 5.63 | 355 | 0 | 1998.65 | 359.76 | 2024-08-19 16:25 | Material Supply For Rate Difference for Copper Pipe with insulation 1ton to 1.5 ton | 100 |  | 109977 | 2024-08-19 | 1998.65 | 1900-01-01 | 0 | HIGH COOL SERVICES
Drain Pipe with Insulation (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 3.8061 | 49 | 0 | 186.4989 | 33.58 | 2024-08-19 17:37 | Supply of Drain Pipe with Insulation (Material) | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9840.4011 | DIPAK NANDKISHOR JAYALWAL
Nitrogen Pressure & Leak Testing (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 6 | 35 | 0 | 210 | 37.8 | 2024-08-19 17:37 | Supply of Nitrogen Pressure & Leak (Material) | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9816.9 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 8.1 | 355 | 0 | 2875.5 | 517.6 | 2024-08-19 17:37 | Material Supply For Rate Difference for Copper Pipe with insulation 1ton to 1.5 ton | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -7151.4 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 7.3194 | 15.5 | 0 | 113.4507 | 20.42 | 2024-08-19 17:37 | Material Supply for Cable for Indoor to Outdoor 1Ton to 1.5 Ton(Rate Differance) | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9913.4493 | DIPAK NANDKISHOR JAYALWAL
Rate Difference with Nitrogen Pressure and Leake Testing (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 6 | 5 | 0 | 30 | 5.4 | 2024-08-19 17:37 | Material Supply for Nitrogen Pressure Test and Leack (Rate Difference) | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9996.9 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Copper Piping with Insula. for 1 to 1.5 Ton(M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 3.4 | 355 | 0 | 1207 | 0 | 2024-08-12 12:59 | Material Supply For Rate Difference for Copper Pipe with insulation 1ton to 1.5 ton | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -3107.67 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Cable for Indoor and Outdoor 1 to 1.5 TR (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 3.7968 | 15.5 | 0 | 58.8504 | 0 | 2024-08-12 12:59 | Material Supply for Cable for Indoor to Outdoor 1Ton to 1.5 Ton(Rate Differance) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4255.8196 | DIPAK NANDKISHOR JAYALWAL
Rate Difference with Nitrogen Pressure and Leake Testing (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 5 | 5 | 0 | 25 | 0 | 2024-08-12 12:59 | Material Supply for Nitrogen Pressure Test and Leack (Rate Difference) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4289.67 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for table Top Stand with Fastner (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 4 | 37.5 | 0 | 150 | 0 | 2024-08-12 12:59 | Material Supply for Table top stand with fastner (Rate Differance) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4164.67 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for L Type Stand with Fastner (M) - No. | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 1 | 32.5 | 0 | 32.5 | 0 | 2024-08-12 12:59 | Material Supply for L type stand with fastner (Rate Differance) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4282.17 | DIPAK NANDKISHOR JAYALWAL
Nitrogen Pressure & Leak Testing (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 5 | 35 | 0 | 175 | 0 | 2024-08-12 13:16 | Supply of Nitrogen Pressure & Leak (Material) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4139.67 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 0.003 | 60.5 | 0 | 0.1815 | 0 | 2024-08-12 13:16 | 4C Cable for Indoor to Outdoor | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4314.4885 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 0.0081 | 345 | 0 | 2.7945 | 0 | 2024-08-12 13:16 | Supply Of Copper Piping with Insulation for 1 to 1.5 Ton | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4311.8755 | DIPAK NANDKISHOR JAYALWAL
L type Stand with Fastener (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 1 | 467.5 | 0 | 467.5 | 0 | 2024-08-12 13:16 | Supply of L-Type Stand with Fastener | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -3847.17 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for table Top Stand with Fastner (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 4 | 37.5 | 0 | 150 | 0 | 2024-08-12 13:16 | Material Supply for Table top stand with fastner (Rate Differance) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4164.67 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 3.8074 | 60.5 | 0 | 230.3477 | 0 | 2024-08-12 12:59 | 4C Cable for Indoor to Outdoor | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4084.3223 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 3.4 | 345 | 0 | 1173 | 0 | 2024-08-12 12:59 | Supply Of Copper Piping with Insulation for 1 to 1.5 Ton | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -3141.67 | DIPAK NANDKISHOR JAYALWAL
L type Stand with Fastener (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 1 | 467.5 | 0 | 467.5 | 0 | 2024-08-12 12:59 | Supply of L-Type Stand with Fastener | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -3847.17 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for table Top Stand with Fastner (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 5 | 37.5 | 0 | 187.5 | 33.76 | 2024-08-19 17:37 | Material Supply for Table top stand with fastner (Rate Differance) | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9839.4 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for L Type Stand with Fastner (M) - No. | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 1 | 32.5 | 0 | 32.5 | 5.86 | 2024-08-19 17:37 | Material Supply for L type stand with fastner (Rate Differance) | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9994.4 | DIPAK NANDKISHOR JAYALWAL
Nitrogen Pressure & Leak Testing (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 5 | 35 | 0 | 175 | 0 | 2024-08-12 12:59 | Supply of Nitrogen Pressure & Leak (Material) | 100 |  | 109809 | 2024-08-12 | 4314.67 | 1900-01-01 | -4139.67 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 33.03 | 60.5 | 0 | 1998.315 | 0 | 2024-08-03 18:27 | 4C Cable for Indoor to Outdoor | 100 |  | 109595 | 2024-08-05 | 23206.69 | 1900-01-01 | -21208.375 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 27.9 | 345 | 0 | 9625.5 | 0 | 2024-08-03 18:27 | Supply Of Copper Piping with Insulation for 1 to 1.5 Ton | 100 |  | 109595 | 2024-08-05 | 23206.69 | 1900-01-01 | -13581.19 | DIPAK NANDKISHOR JAYALWAL
Drain Pipe with Insulation (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 16.2 | 49 | 0 | 793.8 | 0 | 2024-08-03 18:27 | Supply of Drain Pipe with Insulation (Material) | 100 |  | 109595 | 2024-08-05 | 23206.69 | 1900-01-01 | -22412.89 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 7.305 | 60.5 | 0 | 441.9525 | 79.56 | 2024-08-19 17:37 | 4C Cable for Indoor to Outdoor | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9584.9475 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 8.1 | 345 | 0 | 2794.5 | 503.02 | 2024-08-19 17:37 | Supply Of Copper Piping with Insulation for 1 to 1.5 Ton | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -7232.4 | DIPAK NANDKISHOR JAYALWAL
L type Stand with Fastener (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 1 | 467.5 | 0 | 467.5 | 84.16 | 2024-08-19 17:37 | Supply of L-Type Stand with Fastener | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -9559.4 | DIPAK NANDKISHOR JAYALWAL
Table Top Stand with Fastner (M) | N/C | N/C | NEPTUNE ENGINEERS | 530 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 5 | 537.5 | 0 | 2687.5 | 483.76 | 2024-08-19 17:37 | Supply of Table Top Stand with Fastener | 100 |  | 109979 | 2024-08-19 | 10026.9 | 1900-01-01 | -7339.4 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Installation of Copper Pipe - (L) - Mtrs | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 8.1 | 15 | 0 | 121.5 | 21.88 | 2024-08-19 17:37 | Labour Charges for-Insullation of Copper Pipe with Insulation for 1 Ton- 1.5 Ton | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for Installation and Commissioning of AC (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 6 | 125 | 0 | 750 | 135 | 2024-08-19 17:37 | Rate Difference for Installation & Commissioning of AC | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 27.9 | 105 | 0 | 2929.5 | 0 | 2024-08-03 18:27 | Installation of Copper Pipe with Insulation for 1 Ton -1.5 Ton (Labour) | 100 |  | 109597 | 2024-08-05 | 4332.29 | 1900-01-01 | -1402.79 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 33.03 | 19.5 | 0 | 644.085 | 0 | 2024-08-03 18:27 | Installation of Cable for Indoor to Outdoor for 1 Ton -1.5 Ton (Labour) | 100 |  | 109597 | 2024-08-05 | 4332.29 | 1900-01-01 | -3688.205 | DIPAK NANDKISHOR JAYALWAL
Drain Pipe with Insulation (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 16.2 | 21 | 0 | 340.2 | 0 | 2024-08-03 18:27 | Installation of Drain Pipe with Insulation (Labour) | 100 |  | 109597 | 2024-08-05 | 4332.29 | 1900-01-01 | -3992.09 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Installation of Copper Pipe - (L) - Mtrs | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2103 AC Installation & Commissioning - 1 No. | 27.9 | 15 | 0 | 418.5 | 0 | 2024-08-03 18:27 | Labour Charges for-Insullation of Copper Pipe with Insulation for 1 Ton- 1.5 Ton | 100 |  | 109597 | 2024-08-05 | 4332.29 | 1900-01-01 | -3913.79 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 3.7769 | 19.5 | 0 | 73.6496 | 0 | 2024-08-12 12:59 | Installation of Cable for Indoor to Outdoor for 1 Ton -1.5 Ton (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2345.6505 | DIPAK NANDKISHOR JAYALWAL
Nitrogen Pressure & Leak Testing (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 5 | 15 | 0 | 75 | 0 | 2024-08-12 12:59 | Insallation & Testing of Nitrogen Pressure & Leak (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2344.3 | DIPAK NANDKISHOR JAYALWAL
L type Stand with Fastener (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 1 | 157.5 | 0 | 157.5 | 0 | 2024-08-12 12:59 | Installation of L Type Stand With Fastner (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2261.8 | DIPAK NANDKISHOR JAYALWAL
Rate Diff for Installation of Copper Pipe - (L) - Mtrs | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 31 | 15 | 0 | 465 | 0 | 2024-08-12 12:59 | Labour Charges for-Insullation of Copper Pipe with Insulation for 1 Ton- 1.5 Ton | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -1954.3 | DIPAK NANDKISHOR JAYALWAL
Rate Difference for Installation and Commissioning of AC (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 203 AC Installation & Commissioning - 1 No. | 5 | 125 | 0 | 625 | 0 | 2024-08-12 12:59 | Rate Difference for Installation & Commissioning of AC | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -1794.3 | DIPAK NANDKISHOR JAYALWAL
AC Installation & Commissioning (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 1 | 750 | 0 | 750 | 0 | 2024-08-12 13:16 | Installation & Commissioning of AC (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -1669.3 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 0.2952 | 105 | 0 | 30.996 | 0 | 2024-08-12 13:16 | Installation of Copper Pipe with Insulation for 1 Ton -1.5 Ton (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2388.304 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 0.4949 | 19.5 | 0 | 9.6506 | 0 | 2024-08-12 13:16 | Installation of Cable for Indoor to Outdoor for 1 Ton -1.5 Ton (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2409.6494 | DIPAK NANDKISHOR JAYALWAL
Nitrogen Pressure & Leak Testing (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 5 | 15 | 0 | 75 | 0 | 2024-08-12 13:16 | Insallation & Testing of Nitrogen Pressure & Leak (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2344.3 | DIPAK NANDKISHOR JAYALWAL
L type Stand with Fastener (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 403 AC Installation & Commissioning - 1 No. | 1 | 157.5 | 0 | 157.5 | 0 | 2024-08-12 13:16 | Installation of L Type Stand With Fastner (Labour) | 100 |  | 109808 | 2024-08-12 | 2419.3 | 1900-01-01 | -2261.8 | DIPAK NANDKISHOR JAYALWAL
AC Installation & Commissioning (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 6 | 750 | 0 | 4500 | 810 | 2024-08-19 17:37 | Installation & Commissioning of AC (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Copper Piping with Insulation for 1to1.5 Ton (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 8.1 | 105 | 0 | 850.5 | 153.1 | 2024-08-19 17:37 | Installation of Copper Pipe with Insulation for 1 Ton -1.5 Ton (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Cable 4C for Indoor to Outdoor (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 7.29 | 19.5 | 0 | 142.155 | 25.58 | 2024-08-19 17:37 | Installation of Cable for Indoor to Outdoor for 1 Ton -1.5 Ton (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Nitrogen Pressure & Leak Testing (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 6 | 15 | 0 | 90 | 16.2 | 2024-08-19 17:37 | Insallation & Testing of Nitrogen Pressure & Leak (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Table Top Stand with Fastner (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 5 | 187.5 | 0 | 937.5 | 168.76 | 2024-08-19 17:37 | Insallation of Table Top Stand With Fastner (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
L type Stand with Fastener (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 1 | 157.5 | 0 | 157.5 | 28.36 | 2024-08-19 17:37 | Installation of L Type Stand With Fastner (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Drain Pipe with Insulation (L) | N/C | N/C | NEPTUNE ENGINEERS | 532 | 2019-03-19 | A 2204 AC Installation & Commissioning - 1 No. | 3.7857 | 21 | 0 | 79.4997 | 14.32 | 2024-08-19 17:37 | Installation of Drain Pipe with Insulation (Labour) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | DIPAK NANDKISHOR JAYALWAL
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2301 Dry Balcony dado | 23 | 28 | 0 | 644 | 0 | 2024-08-01 16:34 | 600 x 600 Dado Fixing | 100 |  | 109572 | 2024-08-05 | 3212.88 | 1900-01-01 | -2568.88 | PRAKASH CONTRACTOR
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2301 Master Toilet dado | 91.7457 | 28 | 0 | 2568.8796 | 0 | 2024-08-01 16:34 | 600 x 600 Dado Fixing | 100 |  | 109572 | 2024-08-05 | 3212.88 | 1900-01-01 | -644.0004 | PRAKASH CONTRACTOR
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 701 Terrace Vitrified Flooring | 35.98 | 20 | 0 | 719.6 | 0 | 2024-08-12 11:43 | 1200 x 800 Vitrified Skirting | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5779.22 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 702 Kitchen Vitrified Flooring | 42.97 | 20 | 0 | 859.4 | 0 | 2024-08-12 11:43 | 1200 x 800 Vitrified Skirting | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5639.42 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 702 Terrace Vitrified Flooring | 35.98 | 20 | 0 | 719.6 | 0 | 2024-08-12 11:43 | 1200 x 800 Vitrified Skirting | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5779.22 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 902 Terrace Vitrified Flooring | 35.98 | 20 | 0 | 719.6 | 0 | 2024-08-12 11:43 | 1200 x 800 Vitrified Skirting | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5779.22 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1401 Kitchen Vitrified Flooring | 44.94 | 24 | 0 | 1078.56 | 0 | 2024-08-12 11:44 | 1200 x 800 Vitrified Skirting | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5420.26 | JAISAN
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1602 Kitchen Vitrified Flooring | 2.1367 | 24 | 0 | 51.2808 | 0 | 2024-08-12 11:44 | 1200 x 800 Vitrified Skirting | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -6447.5392 | JAISAN
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Master Toilet dado | 37.053 | 14 | 0 | 518.742 | 0 | 2024-08-12 12:02 | 600 x 600 Dado Fixing | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5980.078 | JAISAN
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Parents Toilet dado | 45.756 | 14 | 0 | 640.584 | 0 | 2024-08-12 12:02 | 600 x 600 Dado Fixing | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5858.236 | JAISAN
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Children Toilet | 56.529 | 14 | 0 | 791.406 | 0 | 2024-08-12 12:02 | 600 x 600 Dado Fixing | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -5707.414 | JAISAN
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 602 Powder Toilet dado | 28.575 | 14 | 0 | 400.05 | 0 | 2024-08-12 12:02 | 600 x 600 Dado Fixing | 100 |  | 109792 | 2024-08-12 | 6498.82 | 1900-01-01 | -6098.77 | JAISAN
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Master Toilet dado | 129.8973 | 36 | 0 | 4676.3028 | 841.74 | 2024-08-10 12:54 | 600 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -25955.5372 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Children Toilet dado | 129.8973 | 36 | 0 | 4676.3028 | 841.74 | 2024-08-10 12:54 | 600 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -25955.5372 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Powder Toilet dado | 79.0679 | 36 | 0 | 2846.4444 | 512.36 | 2024-08-10 12:54 | 600 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -27785.3956 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Guest Toilet dado | 117.0796 | 36 | 0 | 4214.8656 | 758.68 | 2024-08-10 12:54 | 600 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -26416.9744 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Master Toilet dado | 58.9175 | 34 | 0 | 2003.195 | 360.58 | 2024-08-10 12:54 | 1200 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -28628.645 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Children Toilet dado | 58.871 | 34 | 0 | 2001.614 | 360.28 | 2024-08-10 12:54 | 1200 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -28630.226 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Powder Toilet dado | 34.5835 | 34 | 0 | 1175.839 | 211.66 | 2024-08-10 12:54 | 1200 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29456.001 | RAHUL ENTERPRISES (Prop Laburi)
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Guest Toilet dado | 58.28 | 34 | 0 | 1981.52 | 356.68 | 2024-08-10 12:54 | 1200 x 600 Dado Fixing (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -28650.32 | RAHUL ENTERPRISES (Prop Laburi)
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Master Toilet dado | 40.1472 | 20 | 0 | 802.944 | 144.52 | 2024-08-10 12:54 | Dado L Groove in Vitrified Tile | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29828.896 | RAHUL ENTERPRISES (Prop Laburi)
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Children Toilet dado | 40.1472 | 20 | 0 | 802.944 | 144.52 | 2024-08-10 12:54 | Dado L Groove in Vitrified Tile | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29828.896 | RAHUL ENTERPRISES (Prop Laburi)
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Powder Toilet dado | 5.3136 | 20 | 0 | 106.272 | 19.12 | 2024-08-10 12:54 | Dado L Groove in Vitrified Tile | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -30525.568 | RAHUL ENTERPRISES (Prop Laburi)
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Guest Toilet dado | 28.6344 | 20 | 0 | 572.688 | 103.08 | 2024-08-10 12:54 | Dado L Groove in Vitrified Tile | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -30059.152 | RAHUL ENTERPRISES (Prop Laburi)
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Master Toilet Vitrified Flooring | 45.7085 | 31.5 | 0 | 1439.8177 | 259.16 | 2024-08-10 13:16 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29192.0223 | RAHUL ENTERPRISES (Prop Laburi)
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Children Toilet Vitrified Flooring | 45.7085 | 31.5 | 0 | 1439.8177 | 259.16 | 2024-08-10 13:16 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29192.0223 | RAHUL ENTERPRISES (Prop Laburi)
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Powder Toilet Vitrified Flooring | 22.5153 | 31.5 | 0 | 709.2319 | 127.66 | 2024-08-10 13:16 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29922.608 | RAHUL ENTERPRISES (Prop Laburi)
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 2603 Guest Toilet Vitrified Flooring | 37.5255 | 31.5 | 0 | 1182.0532 | 212.76 | 2024-08-10 13:16 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 109773 | 2024-08-12 | 30631.84 | 1900-01-01 | -29449.7867 | RAHUL ENTERPRISES (Prop Laburi)
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 620 | 2019-09-04 | C Total Station Survey Pt. Marking - | 100 | 100 | 0 | 10000 | 0 | 2024-08-05 18:22 | Labour charges for Total Station Point Marking work From 4th slab to 36th slab per Slab 100 points for Tower C. | 100 | Tower C Floor no 5 | 109620 | 2024-08-05 | 10000 | 1900-01-01 | 0 | VECTOR SURVEYORS
Gypsum Board False Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 629 | 2019-09-11 | A 2103 Gypsum Board False Ceiling | 469.344 | 55 | 0 | 25813.92 | 4646.5 | 2024-08-01 15:06 | Supply of Internal Gypsum False Ceiling Material. | 100 |  | 109564 | 2024-08-05 | 36065.92 | 2024-08-21 10:50 | -10252 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 629 | 2019-09-11 | A 2103 Gypsum Board False Ceiling | 186.4 | 55 | 0 | 10252 | 1845.36 | 2024-08-01 15:06 | Supply of Internal Gypsum False Ceiling Patta Material. | 100 |  | 109564 | 2024-08-05 | 36065.92 | 2024-08-21 10:50 | -25813.92 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum Board False Ceiling (M) | N/C | N/C | A K INTERIOR CONTRACTOR (MATERIAL) | 629 | 2019-09-11 | A 2103 Gypsum Board False Ceiling | 104.94 | 55 | 0 | 5771.7 | 1038.9 | 2024-08-19 17:51 | Material Supply Charges for Quantity Differnace of Gupsum Board Flase Ceiling work for Kitchen | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum Board False Ceiling (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 2501 Gypsum Board False Ceiling | 1517.38 | 55 | 0 | 83455.9 | 15022.06 | 2024-08-19 11:59 | Supply of Internal Gypsum False Ceiling Material. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | J K INTERIOR (MATERIAL)
Gypsum Board False Ceiling (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 3002 Gypsum Board False Ceiling | 1508 | 55 | 0 | 82940 | 14929.2 | 2024-08-19 12:09 | Supply of Internal Gypsum False Ceiling Material. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | J K INTERIOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 3002 Gypsum Board False Ceiling | 523.32 | 55 | 0 | 28782.6 | 5180.86 | 2024-08-19 12:09 | Supply of Internal Gypsum False Ceiling Patta Material. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | J K INTERIOR (MATERIAL)
Gypsum Board False Ceiling (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 2703 Gypsum Board False Ceiling | 1173.36 | 55 | 0 | 64534.8 | 11616.26 | 2024-08-19 17:57 | Supply of Internal Gypsum False Ceiling Material. | 100 |  | 109966 | 2024-08-19 | 128885.68 | 1900-01-01 | -64350.88 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 2703 Gypsum Board False Ceiling | 466 | 55 | 0 | 25630 | 4613.4 | 2024-08-19 17:57 | Supply of Internal Gypsum False Ceiling Patta Material. | 100 |  | 109966 | 2024-08-19 | 128885.68 | 1900-01-01 | -103255.68 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum Board False Ceiling (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 2803 Gypsum Board False Ceiling | 704.016 | 55 | 0 | 38720.88 | 6969.76 | 2024-08-19 17:53 | Supply of Internal Gypsum False Ceiling Material. | 100 |  | 109966 | 2024-08-19 | 128885.68 | 1900-01-01 | -90164.8 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum False Ceiling Patta (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 2803 Gypsum Board False Ceiling | 279.6 | 55 | 0 | 15378 | 2768.04 | 2024-08-19 17:53 | Supply of Internal Gypsum False Ceiling Patta Material. | 100 |  | 109964 | 2024-08-19 | 15378 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR
Gypsum Board False Ceiling (M) | N/C | N/C | J K INTERIOR (MATERIAL) | 630 | 2019-09-11 | A 1502 Gypsum Board False Ceiling | 603.2 | 55 | 0 | 33176 | 5971.68 | 2024-08-12 14:09 | Supply of Internal Gypsum False Ceiling Material. | 100 |  | 109822 | 2024-08-12 | 33176 | 1900-01-01 | 0 | J K INTERIOR (MATERIAL)
Gypsum Board False Ceiling (L) | N/C | N/C | J K INTERIOR | 631 | 2019-09-11 | A 2803 Gypsum Board False Ceiling | 704.016 | 20 | 0 | 14080.32 | 2534.46 | 2024-08-19 17:53 | Labour Charges for Fixing Internal Gypsum False Ceiling with all necessary Hardware,Sections,Line and Level as per drawing complete. | 100 |  | 109965 | 2024-08-19 | 14080.32 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR
Gypsum False Ceiling Patta (L) | N/C | N/C | J K INTERIOR | 631 | 2019-09-11 | A 2803 Gypsum Board False Ceiling | 279.6 | 20 | 0 | 5592 | 1006.56 | 2024-08-19 17:53 | Labour Charges for Fixing Internal Gypsum False Ceiling Vertical Patta with all necessary Hardware,Sections,Line and Level as per drawing complete. | 100 |  | 109967 | 2024-08-19 | 5592 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR (MATERIAL)
Gypsum Board False Ceiling (L) | N/C | N/C | J K INTERIOR | 631 | 2019-09-11 | A 3002 Gypsum Board False Ceiling | 1357.2 | 20 | 0 | 27144 | 4885.92 | 2024-08-19 12:09 | Labour Charges for Fixing Internal Gypsum False Ceiling with all necessary Hardware,Sections,Line and Level as per drawing complete. | 100 |  | 109968 | 2024-08-19 | 36563.76 | 1900-01-01 | -9419.76 | J K INTERIOR
Gypsum False Ceiling Patta (L) | N/C | N/C | J K INTERIOR | 631 | 2019-09-11 | A 3002 Gypsum Board False Ceiling | 470.988 | 20 | 0 | 9419.76 | 1695.56 | 2024-08-19 12:09 | Labour Charges for Fixing Internal Gypsum False Ceiling Vertical Patta with all necessary Hardware,Sections,Line and Level as per drawing complete. | 100 |  | 109968 | 2024-08-19 | 36563.76 | 1900-01-01 | -27144 | J K INTERIOR
Gypsum Board False Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 632 | 2019-09-11 | A 2103 Gypsum Board False Ceiling | 104.94 | 20 | 0 | 2098.8 | 377.78 | 2024-08-19 17:51 | Labour Charges for Quantity Differnace of Gupsum Board Flase Ceiling work for Kitchen | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | A K INTERIOR CONTRACTOR
Gypsum Board False Ceiling (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 632 | 2019-09-11 | A 2103 Gypsum Board False Ceiling | 352 | 20 | 0 | 7040 | 1267.2 | 2024-08-01 15:06 | Fixing Internal Gypsum False Ceiling with all necessary Hardware,Sections,Line and Level as per drawing complete. | 100 |  | 109566 | 2024-08-05 | 9836 | 2024-08-21 10:49 | -2796 | A K INTERIOR CONTRACTOR
Gypsum False Ceiling Patta (L) | N/C | N/C | A K INTERIOR CONTRACTOR | 632 | 2019-09-11 | A 2103 Gypsum Board False Ceiling | 139.8 | 20 | 0 | 2796 | 503.28 | 2024-08-01 15:06 | Fixing Internal Gypsum False Ceiling Vertical Patta with all necessary Hardware,Sections,Line and Level as per drawing complete. | 100 |  | 109566 | 2024-08-05 | 9836 | 2024-08-21 10:49 | -7040 | A K INTERIOR CONTRACTOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Toilet Counter wash Basin | 4 | 55 | 0 | 220 | 39.6 | 2024-08-09 17:16 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7850.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Toilet Counter wash Basin | 4 | 55 | 0 | 220 | 39.6 | 2024-08-09 17:16 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7850.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Children Toilet Counter wash Basin | 4 | 55 | 0 | 220 | 39.6 | 2024-08-09 17:16 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7850.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Powder Toilet Counter wash Basin | 4 | 55 | 0 | 220 | 39.6 | 2024-08-09 17:16 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7850.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Toilet Counter wash Basin | 4 | 27.5 | 0 | 110 | 19.8 | 2024-08-09 17:16 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7960.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Master Bed Marble Flooring | 35.22 | 50 | 0 | 1761 | 316.98 | 2024-08-22 14:58 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Guest Bed Marble Flooring | 13.925 | 50 | 0 | 696.25 | 125.32 | 2024-08-22 14:58 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Toilet Counter wash Basin | 4 | 27.5 | 0 | 110 | 19.8 | 2024-08-09 17:16 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7960.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Children Toilet Counter wash Basin | 4 | 27.5 | 0 | 110 | 19.8 | 2024-08-09 17:16 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7960.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Powder Toilet Counter wash Basin | 4 | 27.5 | 0 | 110 | 19.8 | 2024-08-09 17:16 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7960.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Toilet Counter wash Basin | 4 | 55 | 0 | 220 | 39.6 | 2024-08-09 17:16 | Wash Basin Counter Champher & Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7850.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Children Toilet Counter wash Basin | 4 | 55 | 0 | 220 | 39.6 | 2024-08-09 17:16 | Wash Basin Counter Champher & Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7850.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Children Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Powder Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Children Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Powder Toilet Counter wash Basin | 4 | 45 | 0 | 180 | 32.4 | 2024-08-09 17:16 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7890.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Parents Toilet Counter wash Basin | 4 | 60 | 0 | 240 | 43.2 | 2024-08-09 17:25 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7830.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Master Toilet Counter wash Basin | 4 | 60 | 0 | 240 | 43.2 | 2024-08-09 17:25 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7830.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Children Toilet Counter wash Basin | 4 | 60 | 0 | 240 | 43.2 | 2024-08-09 17:25 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7830.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Powder Toilet Counter wash Basin | 3.75 | 60 | 0 | 225 | 40.5 | 2024-08-09 17:25 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7845.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Parents Toilet Counter wash Basin | 4 | 30 | 0 | 120 | 21.6 | 2024-08-09 17:25 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7950.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Master Toilet Counter wash Basin | 4 | 30 | 0 | 120 | 21.6 | 2024-08-09 17:25 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7950.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Children Toilet Counter wash Basin | 4 | 30 | 0 | 120 | 21.6 | 2024-08-09 17:25 | Wash Basin Counter Edge Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7950.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Parents Toilet Counter wash Basin | 4 | 60 | 0 | 240 | 43.2 | 2024-08-09 17:25 | Wash Basin Counter Champher & Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7830.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Children Toilet Counter wash Basin | 4 | 60 | 0 | 240 | 43.2 | 2024-08-09 17:25 | Wash Basin Counter Champher & Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7830.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Parents Toilet Counter wash Basin | 4 | 50 | 0 | 200 | 36 | 2024-08-09 17:25 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7870.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Master Toilet Counter wash Basin | 3.34 | 50 | 0 | 167 | 30.06 | 2024-08-09 17:25 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7903.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Children Toilet Counter wash Basin | 4 | 50 | 0 | 200 | 36 | 2024-08-09 17:25 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7870.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Powder Toilet Counter wash Basin | 2.62 | 50 | 0 | 131 | 23.58 | 2024-08-09 17:25 | Wash Basin Counter Mirror Polish (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7939.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Parents Toilet Counter wash Basin | 4 | 50 | 0 | 200 | 36 | 2024-08-09 17:25 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7870.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Master Toilet Counter wash Basin | 4 | 50 | 0 | 200 | 36 | 2024-08-09 17:25 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7870.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Children Toilet Counter wash Basin | 4 | 50 | 0 | 200 | 36 | 2024-08-09 17:25 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7870.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2102 Powder Toilet Counter wash Basin | 3.75 | 50 | 0 | 187.5 | 33.76 | 2024-08-09 17:25 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7883 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Guest Toilet Counter wash Basin | 5 | 45 | 0 | 225 | 40.5 | 2024-08-09 16:37 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7845.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Master Toilet Counter wash Basin | 5 | 45 | 0 | 225 | 40.5 | 2024-08-09 16:37 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7845.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Children Toilet Counter wash Basin | 5 | 45 | 0 | 225 | 40.5 | 2024-08-09 16:37 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7845.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Powder Toilet Counter wash Basin | 5 | 45 | 0 | 225 | 40.5 | 2024-08-09 16:37 | Wash Basin Counter Zero Joint (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7845.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Guest Toilet Counter wash Basin | 5 | 35 | 0 | 175 | 31.5 | 2024-08-09 16:37 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7895.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Master Toilet Counter wash Basin | 5 | 35 | 0 | 175 | 31.5 | 2024-08-09 16:37 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7895.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Children Toilet Counter wash Basin | 5 | 35 | 0 | 175 | 31.5 | 2024-08-09 16:37 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7895.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 403 Powder Toilet Counter wash Basin | 5 | 35 | 0 | 175 | 31.5 | 2024-08-09 16:37 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 109765 | 2024-08-12 | 8070.5 | 1900-01-01 | -7895.5 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1803 Living,Dining,Passa. Marble Flooring | 30.465 | 45 | 0 | 1370.925 | 246.76 | 2024-08-20 16:57 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1803 Master Bed Marble Flooring | 14.067 | 45 | 0 | 633.015 | 113.94 | 2024-08-20 16:57 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1803 Guest Bed Marble Flooring | 12.501 | 45 | 0 | 562.545 | 101.26 | 2024-08-20 16:57 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2403 Living,Dining,Passa. Marble Flooring | 30.465 | 60 | 0 | 1827.9 | 329.02 | 2024-08-20 16:49 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2403 Master Bed Marble Flooring | 14.067 | 60 | 0 | 844.02 | 151.92 | 2024-08-20 16:49 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2403 Guest Bed Marble Flooring | 12.501 | 60 | 0 | 750.06 | 135.02 | 2024-08-20 16:49 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2403 Living,Dining,Passa. Marble Flooring | 30.465 | 50 | 0 | 1523.25 | 274.18 | 2024-08-20 16:49 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2403 Master Bed Marble Flooring | 14.067 | 50 | 0 | 703.35 | 126.6 | 2024-08-20 16:49 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2403 Guest Bed Marble Flooring | 12.501 | 50 | 0 | 625.05 | 112.5 | 2024-08-20 16:49 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 802 Living,Dining,Passa. Marble Flooring | 34.377 | 50 | 0 | 1718.85 | 309.4 | 2024-08-20 16:53 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 802 Master Bed Marble Flooring | 20.07 | 50 | 0 | 1003.5 | 180.64 | 2024-08-20 16:53 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 802 Parents Bed Marble Flooring | 14.901 | 50 | 0 | 745.05 | 134.1 | 2024-08-20 16:53 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 802 Living,Dining,Passa. Marble Flooring | 34.377 | 40 | 0 | 1375.08 | 247.52 | 2024-08-20 16:53 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 802 Master Bed Marble Flooring | 20.07 | 40 | 0 | 802.8 | 144.5 | 2024-08-20 16:53 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 802 Parents Bed Marble Flooring | 14.901 | 40 | 0 | 596.04 | 107.28 | 2024-08-20 16:53 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Living,Dining,Passa. Marble Flooring | 195.196 | 45 | 0 | 8783.82 | 1581.08 | 2024-08-20 17:00 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Bed Marble Flooring | 80.128 | 45 | 0 | 3605.76 | 649.04 | 2024-08-20 17:00 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Bed Marble Flooring | 57.632 | 45 | 0 | 2593.44 | 466.82 | 2024-08-20 17:00 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Living,Dining,Passa. Marble Flooring | 40.62 | 55 | 0 | 2234.1 | 402.14 | 2024-08-20 17:00 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Bed Marble Flooring | 18.756 | 55 | 0 | 1031.58 | 185.68 | 2024-08-20 17:00 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Bed Marble Flooring | 16.668 | 55 | 0 | 916.74 | 165.02 | 2024-08-20 17:00 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Living,Dining,Passa. Marble Flooring | 40.62 | 45 | 0 | 1827.9 | 329.02 | 2024-08-20 17:00 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Master Bed Marble Flooring | 18.756 | 45 | 0 | 844.02 | 151.92 | 2024-08-20 17:00 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1703 Guest Bed Marble Flooring | 16.668 | 45 | 0 | 750.06 | 135.02 | 2024-08-20 17:00 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAHUL ENTERPRISES (Prop Laburi)
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Parents Bed Marble Flooring | 26 | 50 | 0 | 1300 | 234 | 2024-08-22 14:58 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Living,Dining,Passa. Marble Flooring | 93.008 | 60 | 0 | 5580.48 | 1004.48 | 2024-08-22 14:58 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Master Bed Marble Flooring | 45.936 | 60 | 0 | 2756.16 | 496.1 | 2024-08-22 14:58 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Guest Bed Marble Flooring | 25.264 | 60 | 0 | 1515.84 | 272.86 | 2024-08-22 14:58 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Parents Bed Marble Flooring | 34.384 | 60 | 0 | 2063.04 | 371.34 | 2024-08-22 14:58 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Living,Dining,Passa. Marble Flooring | 42.138 | 50 | 0 | 2106.9 | 379.24 | 2024-08-22 14:58 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Master Bed Marble Flooring | 20.71 | 50 | 0 | 1035.5 | 186.4 | 2024-08-22 14:58 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Guest Bed Marble Flooring | 9.794 | 50 | 0 | 489.7 | 88.14 | 2024-08-22 14:58 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1904 Parents Bed Marble Flooring | 12.49 | 50 | 0 | 624.5 | 112.42 | 2024-08-22 14:58 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Living,Dining,Passa. Marble Flooring | 295.445 | 50 | 0 | 14772.25 | 2659 | 2024-08-22 15:11 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Master Bed Marble Flooring | 105.22 | 50 | 0 | 5261 | 946.98 | 2024-08-22 15:11 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Guest Bed Marble Flooring | 66.925 | 50 | 0 | 3346.25 | 602.32 | 2024-08-22 15:11 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Parents Bed Marble Flooring | 75.995 | 50 | 0 | 3799.75 | 683.96 | 2024-08-22 15:11 | Italian Marble Flooring Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Living,Dining,Passa. Marble Flooring | 81.382 | 60 | 0 | 4882.92 | 878.92 | 2024-08-22 15:11 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Master Bed Marble Flooring | 40.194 | 60 | 0 | 2411.64 | 434.1 | 2024-08-22 15:11 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Guest Bed Marble Flooring | 22.106 | 60 | 0 | 1326.36 | 238.74 | 2024-08-22 15:11 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Parents Bed Marble Flooring | 30.086 | 60 | 0 | 1805.16 | 324.92 | 2024-08-22 15:11 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Living,Dining,Passa. Marble Flooring | 18.13 | 50 | 0 | 906.5 | 163.18 | 2024-08-22 15:11 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Master Bed Marble Flooring | 28.71 | 50 | 0 | 1435.5 | 258.4 | 2024-08-22 15:11 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Guest Bed Marble Flooring | 5.794 | 50 | 0 | 289.7 | 52.14 | 2024-08-22 15:11 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 2104 Parents Bed Marble Flooring | 12.33 | 50 | 0 | 616.5 | 110.98 | 2024-08-22 15:11 | Italian Marble Skirting Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1801 Living,Dining,Passa. Marble Flooring | 35.262 | 55 | 0 | 1939.41 | 349.1 | 2024-08-22 18:29 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1801 Master Bed Marble Flooring | 19.686 | 55 | 0 | 1082.73 | 194.9 | 2024-08-22 18:29 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1801 Guest Bed Marble Flooring | 25.26 | 55 | 0 | 1389.3 | 250.08 | 2024-08-22 18:29 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 1801 Parents Bed Marble Flooring | 18.702 | 55 | 0 | 1028.61 | 185.14 | 2024-08-22 18:29 | Italian Marble Skirting Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 1st Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 1st Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 2nd Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 2nd Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 3rd Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 3rd Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 4th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 4th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 5th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 5th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 6th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 6th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 7th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 7th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 8th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 8th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 9th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A 9th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-10th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-10th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-11th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-11th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-12th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-12th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-13th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-13th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-14th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-14th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-15th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-15th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-16th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-16th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-17th Floor Staircase 1 Railling | 32.634 | 300 | 0 | 9790.2 | 1762.24 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -452725.2 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-17th Floor Staircase 2 Railling | 32.634 | 300 | 0 | 9790.2 | 1762.24 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -452725.2 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-18th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-18th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-19th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-19th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-20th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-20th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:27 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-21th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-21th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-22nd Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-22nd Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-23rd Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-23rd Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-24th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-24th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-25th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-25th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-26th Floor Staircase 1 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
SS Railing (L) | N/C | N/C | HELIOS | 684 | 2019-11-30 | A-26th Floor Staircase 2 Railling | 29.529 | 300 | 0 | 8858.7 | 1594.56 | 2024-08-01 12:40 | SS Railing Fixing work for Staircase including Shifting,Cutting & Fixing of SS Pipe with core cutting,Chemical Grout,Buffing & Line Level Plumb etc | 100 |  | 109558 | 2024-08-05 | 462515.4 | 2024-08-21 10:49 | -453656.7 | HELIOS
Gypsum Plaster (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Beam & Ceiling Plaster | 245.27 | 4 | 0 | 981.08 | 176.6 | 2024-08-05 11:55 | Beam Gypsum (Plaster Patra) Finish with Required Thickness Including Finishing Even & Smooth,Butt Finish,Line Level,Plumb & Right Angle etc,Loading,Shifting & Unloading of Material From Store to Required Place to be Done by Contractor.(L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -37939.05 | J K INTERIOR
Gypsum on Ceiling (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Beam & Ceiling Plaster | 4734.83 | 4 | 0 | 18939.32 | 3409.08 | 2024-08-05 11:55 | Ceiling Gypsum (Plaster Patra) Finish with Required Thickness Including Finishing Even & Smooth,Butt Finish,Line Level,Plumb & Right Angle etc,Loading,Shifting & Unloading of Material From Store to Required Place to be Done by Contractor.(L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -19980.81 | J K INTERIOR
Gypsum Plaster (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Floor Column Plaster | 846.83 | 4 | 0 | 3387.32 | 609.72 | 2024-08-05 12:07 | Column Above 1 Mtr Gypsum (Plaster Patra) Finish with Required Thickness Including Finishing Even & Smooth,Butt Finish,Line Level,Plumb & Right Angle etc,Loading,Shifting & Unloading of Material From Store to Required Place to be Done by Contractor.(L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -35532.81 | J K INTERIOR
Gypsum Plaster (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Beam & Ceiling Plaster | 64.67 | 4 | 0 | 258.68 | 46.56 | 2024-08-05 12:07 | Beam Gypsum (Plaster Patra) Finish with Required Thickness Including Finishing Even & Smooth,Butt Finish,Line Level,Plumb & Right Angle etc,Loading,Shifting & Unloading of Material From Store to Required Place to be Done by Contractor.(L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -38661.45 | J K INTERIOR
Tikki Dhada rate diff. (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Beam & Ceiling Plaster | 489.94 | 5 | 0 | 2449.7 | 440.94 | 2024-08-05 12:07 | Rate Difference for Gypsum Tikki Dhada Plaster Work (L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -36470.43 | J K INTERIOR
Tikki Dhada rate diff. (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Floor Column Plaster | 903 | 5 | 0 | 4515 | 812.7 | 2024-08-05 12:07 | Rate Difference for Gypsum Tikki Dhada Plaster Work (L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -34405.13 | J K INTERIOR
Tikki Dhada rate diff. (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Staircase & Lobby Plaster | 1070 | 5 | 0 | 5350 | 963 | 2024-08-05 12:07 | Rate Difference for Gypsum Tikki Dhada Plaster Work (L) | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -33570.13 | J K INTERIOR
Tikki Dhada (L) | N/C | N/C | J K INTERIOR | 696 | 2019-12-02 | B P2 Parking Expansion Joint | 337.67 | 9 | 0 | 3039.03 | 547.02 | 2024-08-05 12:13 | Gypsum Tikki Dhada Plaster Work | 100 |  | 109613 | 2024-08-05 | 38920.13 | 1900-01-01 | -35881.1 | J K INTERIOR
Trimix Work - BC | N/C | N/C | MUKESH CONSTRUCTIONS | 724 | 2019-12-11 | A Parking Floor 1 Trimix work (L) - | 5146.05 | 9 | 0 | 46314.45 | 0 | 2024-08-16 12:52 | Trimix work- Laying in situ cement concrete M20 with tremix treatment for 100mm thickness for flooring with groove cutting of 4 mm wide & 20 mm deep with necessary refilling with bitumin etc | 100 |  | 109950 | 2024-08-19 | 51460.5 | 1900-01-01 | -5146.05 | DEVARAJ
Weld mesh fixing(L) BCo | N/C | N/C | MUKESH CONSTRUCTIONS | 724 | 2019-12-11 | A Parking Floor 1 Trimix work (L) - | 5146.05 | 1 | 0 | 5146.05 | 0 | 2024-08-16 12:52 | Shifting, cutting & fixing weld mesh jali for trimix work with all necessary items & material from store to required place to shifted by contractor | 100 |  | 109950 | 2024-08-19 | 51460.5 | 1900-01-01 | -46314.45 | DEVARAJ
Deep Cleaning work | N/C | N/C | MMAK PROPERTY MANAGEMENT SERVICES | 763 | 2020-02-24 | A 2701 Deep Cleaning Work | 1937.41 | 4 | 0 | 7749.64 | 0 | 2024-08-09 15:41 | Internal Flat Flooring, Skirting, Dado, window, Switch Socket, Kitchen otta, Mirror, Ledge wall, Doors, Jams, CP sanitory Fitting and False ceiling etc Proper cleaning with all necessary tools and Equipments (M+L) | 100 |  | 109763 | 2024-08-12 | 19246.95 | 1900-01-01 | -11497.31 | NEW SAI SERVICES
Deep Cleaning Work (Rate Diff) | N/C | N/C | MMAK PROPERTY MANAGEMENT SERVICES | 763 | 2020-02-24 | A 2701 Deep Cleaning Work | 1937.41 | 1 | 0 | 1937.41 | 0 | 2024-08-09 15:41 | Deep Cleaning Rate Difference for A Tower | 100 |  | 109763 | 2024-08-12 | 19246.95 | 1900-01-01 | -17309.54 | NEW SAI SERVICES
Deep Cleaning work | N/C | N/C | MMAK PROPERTY MANAGEMENT SERVICES | 763 | 2020-02-24 | A 2702 Deep Cleaning Work | 1911.98 | 4 | 0 | 7647.92 | 0 | 2024-08-09 15:42 | Internal Flat Flooring, Skirting, Dado, window, Switch Socket, Kitchen otta, Mirror, Ledge wall, Doors, Jams, CP sanitory Fitting and False ceiling etc Proper cleaning with all necessary tools and Equipments (M+L) | 100 |  | 109763 | 2024-08-12 | 19246.95 | 1900-01-01 | -11599.03 | NEW SAI SERVICES
Deep Cleaning Work (Rate Diff) | N/C | N/C | MMAK PROPERTY MANAGEMENT SERVICES | 763 | 2020-02-24 | A 2702 Deep Cleaning Work | 1911.98 | 1 | 0 | 1911.98 | 0 | 2024-08-09 15:42 | Deep Cleaning Rate Difference for A Tower | 100 |  | 109763 | 2024-08-12 | 19246.95 | 1900-01-01 | -17334.97 | NEW SAI SERVICES
Italian Marbal Mirror Polish- DCH | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 772 | 2020-03-05 | A 1904 NOC | 160.758 | 50 | 0 | 8037.9 | 1446.82 | 2024-08-22 14:43 | Labour charges for Italian Marble Flooring Mirror Polish work for A-Bldg 1904 Children Room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Italian Marble Skirting Mirror polish. | N/C | N/C | RAHUL ENTERPRISES (Prop Laburi) | 772 | 2020-03-05 | A 1904 NOC | 42.021 | 50 | 0 | 2101.05 | 378.18 | 2024-08-22 14:43 | Labour charges for Italian Marble Skirting Mirror Polish work for A-Bldg 1904 Children Room. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | JUBAIR AHMAD
Trimix Work - BC | N/C | N/C | MUKESH CONSTRUCTIONS | 774 | 2020-03-06 | B GF Parking Flooring Trimix work | 530.04 | 9 | 0 | 4770.36 | 0 | 2024-08-16 12:53 | Trimix work- Laying in situ cement concrete M20 with tremix treatment for 100mm thickness for flooring with groove cutting of 4 mm wide & 20 mm deep with necessary refilling with bitumin etc | 100 |  | 109951 | 2024-08-19 | 40300.4 | 1900-01-01 | -35530.04 | DEVARAJ
Trimix Work - BC | N/C | N/C | MUKESH CONSTRUCTIONS | 774 | 2020-03-06 | B Parking Floor 1 Trimix work | 3500 | 9 | 0 | 31500 | 0 | 2024-08-16 12:53 | Trimix work- Laying in situ cement concrete M20 with tremix treatment for 100mm thickness for flooring with groove cutting of 4 mm wide & 20 mm deep with necessary refilling with bitumin etc | 100 |  | 109951 | 2024-08-19 | 40300.4 | 1900-01-01 | -8800.4 | DEVARAJ
Weld mesh fixing(L) BCo | N/C | N/C | MUKESH CONSTRUCTIONS | 774 | 2020-03-06 | B GF Parking Flooring Trimix work | 530.04 | 1 | 0 | 530.04 | 0 | 2024-08-16 12:53 | hifting, cutting & fixing weld mesh jali for trimix work with all necessary item & material from store to required place to shifted by contractor | 100 |  | 109951 | 2024-08-19 | 40300.4 | 1900-01-01 | -39770.36 | DEVARAJ
Weld mesh fixing(L) BCo | N/C | N/C | MUKESH CONSTRUCTIONS | 774 | 2020-03-06 | B Parking Floor 1 Trimix work | 3500 | 1 | 0 | 3500 | 0 | 2024-08-16 12:53 | hifting, cutting & fixing weld mesh jali for trimix work with all necessary item & material from store to required place to shifted by contractor | 100 |  | 109951 | 2024-08-19 | 40300.4 | 1900-01-01 | -36800.4 | DEVARAJ
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-26th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 901 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 902 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Flat No 1 Walls Semi-Acrylic Painting - | 484.38 | 1.25 | 0 | 605.475 | 108.98 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79809.615 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Flat No 2 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Flat No 2 Walls Semi-Acrylic Painting - | 441.75 | 1.25 | 0 | 552.1875 | 99.4 | 2024-08-19 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79862.9025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Lv, Electrical shaft Semi-Acrylic Paint | 158.87 | 1.25 | 0 | 198.5875 | 35.74 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80216.5025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-19 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2201 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2202 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2301 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2302 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2401 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2402 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2501 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2502 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 564.34 | 1.25 | 0 | 705.425 | 126.98 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79709.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2601 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2601 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2602 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2602 Walls Semi-Acrylic Painting | 564.34 | 1.25 | 0 | 705.425 | 126.98 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79709.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 201 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 202 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 301 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 302 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 401 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 402 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 501 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 502 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 601 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 602 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 701 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 702 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 801 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 802 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1001 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1002 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1101 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1102 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1201 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1202 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1301 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1302 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1401 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1402 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1501 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1502 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1601 Ceilings Semi-Acrylic Painting. | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1602 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.4 | 1.25 | 0 | 123 | 22.14 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80292.09 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1701 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1702 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1801 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1802 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1901 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1902 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Fire Shaft Semi-Acrylic Paint Paint - 98.49 S | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 101 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 102 Ceilings Semi-Acrylic Painting - | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2001 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2002 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Fire Shaft with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2101 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2102 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-17 | Applying 2nd coat semiacrylic paint for Duct Wall & Ceiling with proper cleaning/Scrapping with Jhula in contractor scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1001 Ceilings Semi-Acrylic Painting | 8.39 | 1 | 0 | 8.39 | 1.52 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80406.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1002 Ceilings Semi-Acrylic Painting | 17 | 1 | 0 | 17 | 3.06 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80398.09 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Fire Shaft Semi-Acrylic Paint Paint - 98.49 S | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 362.34 | 1 | 0 | 362.34 | 65.22 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80052.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2601 Ceilings Semi-Acrylic Painting | 8.39 | 1 | 0 | 8.39 | 1.52 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80406.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2601 Walls Semi-Acrylic Painting | 592.39 | 1 | 0 | 592.39 | 106.64 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79822.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2602 Ceilings Semi-Acrylic Painting | 17 | 1 | 0 | 17 | 3.06 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80398.09 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2602 Walls Semi-Acrylic Painting | 564.34 | 1 | 0 | 564.34 | 101.58 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79850.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1 | 0 | 227.87 | 41.02 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80187.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1 | 0 | 227.87 | 41.02 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80187.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80316.6 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80348.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80259.75 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Fire Shaft Semi-Acrylic Paint - 69.75 | 69.75 | 1 | 0 | 69.75 | 12.56 | 2024-08-14 | Applying 1 coat Primer for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80345.34 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Flat No 1 Ceilings Semi-Acrylic Painting | 8.39 | 1 | 0 | 8.39 | 1.52 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80406.7 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B Fire Check Floor Flat No 2 Ceilings Semi-Acrylic Painting | 17 | 1 | 0 | 17 | 3.06 | 2024-08-14 | Applying 1 coat Primer for duct wall & ceiling with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80398.09 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 802 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 902 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-26th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 Coat Primer for LV Shaft,Electric Shaft & Service Shaft with all tools & equipments in contractor sope. Loading,Shfting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80265.22 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (L) - | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B-26th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1 | 0 | 227.87 | 41.02 | 2024-08-14 | Applying 1 coat Primer for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80187.22 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1002 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1102 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1202 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1302 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1402 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1502 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1602 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1702 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1802 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1902 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Fire Shaft Semi-Acrylic Paint Paint - 98.49 S | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Flat No 102 Ceilings Semi-Acrylic Painting - | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2002 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2102 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2202 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2302 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2402 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2501 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2502 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 564.34 | 1.25 | 0 | 705.425 | 126.98 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79709.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2601 Ceilings Semi-Acrylic Painting | 8.39 | 1.25 | 0 | 10.4875 | 1.88 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80404.6025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2601 Walls Semi-Acrylic Painting | 592.39 | 1.25 | 0 | 740.4875 | 133.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79674.6025 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2602 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor 2602 Walls Semi-Acrylic Painting | 564.34 | 1.25 | 0 | 705.425 | 126.98 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79709.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 26th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 202 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 302 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 402 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 502 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 602 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.25 | 0 | 123.1125 | 22.16 | 2024-08-16 | Applying 1st coat semiacrylic paint for Fire Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80291.9775 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 702 Ceilings Semi-Acrylic Painting | 17 | 1.25 | 0 | 21.25 | 3.82 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80393.84 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 357.14 | 1.25 | 0 | 446.425 | 80.36 | 2024-08-16 | Applying 1st coat semiacrylic paint for Duct Wall & Ceilingwith all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -79968.665 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (L) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 829 | 2020-07-08 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.25 | 0 | 284.8375 | 51.28 | 2024-08-16 | Applying 1st coat semiacrylic paint for LV shaft, Electric Shaft & Service Shaft with all tools & equipments in contractors scope. Loading, shifting & unloading of all raw material from store to required place to be done by contractor. | 100 |  | 109984 | 2024-08-20 | 80415.09 | 1900-01-01 | -80130.2525 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-26th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1 | 0 | 227.87 | 41.02 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113248.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Fire Shaft Semi-Acrylic Paint Paint - 98.49 S | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 362.34 | 1 | 0 | 362.34 | 65.22 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113114.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2601 Ceilings Semi-Acrylic Painting | 8.39 | 1 | 0 | 8.39 | 1.52 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113468.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2601 Walls Semi-Acrylic Painting | 592.39 | 1 | 0 | 592.39 | 106.64 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112884.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2602 Ceilings Semi-Acrylic Painting | 17 | 1 | 0 | 17 | 3.06 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113459.82 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2602 Walls Semi-Acrylic Painting | 564.34 | 1 | 0 | 564.34 | 101.58 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112912.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 350.39 | 1 | 0 | 350.39 | 63.08 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113126.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 38.26 | 1 | 0 | 38.26 | 6.88 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113438.56 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1 | 0 | 98.49 | 17.72 | 2024-08-16 | Providing 1 coat Primer for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113378.33 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 66.39 | 1 | 0 | 66.39 | 11.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113410.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 155.34 | 1 | 0 | 155.34 | 27.96 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113321.48 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 1 Ceilings Semi-Acrylic Painting | 8.39 | 1 | 0 | 8.39 | 1.52 | 2024-08-16 | Providing 1 coat Primer for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113468.43 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1 Coat Primer (External) (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 149.87 | 1 | 0 | 149.87 | 26.98 | 2024-08-16 | Providing 1 coat Primer for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113326.95 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1002 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1102 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1202 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1302 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1402 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1502 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1602 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1702 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1802 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1902 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Fire Shaft Semi-Acrylic Paint Paint - 98.49 S | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 102 Ceilings Semi-Acrylic Painting - | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2002 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2102 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2202 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2302 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2402 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2501 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2502 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 564.34 | 1.75 | 0 | 987.595 | 177.76 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112489.225 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2601 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2601 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2602 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2602 Walls Semi-Acrylic Painting | 564.34 | 1.75 | 0 | 987.595 | 177.76 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112489.225 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 202 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 302 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 357.48 | 1.75 | 0 | 625.59 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.23 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 402 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 502 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 602 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 702 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 802 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 902 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Fire Shaft Semi-Acrylic Paint - 69.75 | 69.75 | 1.75 | 0 | 122.0625 | 21.98 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113354.7575 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 1 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 1 Walls Semi-Acrylic Painting - | 484.38 | 1.75 | 0 | 847.665 | 152.58 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112629.155 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 2 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 2 Walls Semi-Acrylic Painting - | 441.75 | 1.75 | 0 | 773.0625 | 139.16 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112703.7575 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Lv, Electrical shaft Semi-Acrylic Paint | 158.87 | 1.75 | 0 | 278.0225 | 50.04 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113198.7975 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-26th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-16 | Providing 1st coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 302 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 401 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 402 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 501 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 502 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 601 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 602 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 701 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 702 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 801 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 802 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 901 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 902 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Fire Shaft Semi-Acrylic Paint - 69.75 | 69.75 | 1.75 | 0 | 122.0625 | 21.98 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113354.7575 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 1 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 1 Walls Semi-Acrylic Painting - | 484.38 | 1.75 | 0 | 847.665 | 152.58 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112629.155 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 2 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Flat No 2 Walls Semi-Acrylic Painting - | 441.75 | 1.75 | 0 | 773.0625 | 139.16 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112703.7575 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B Fire Check Floor Garbage, Pressurisation 1, 2 shaft Semi-A | 335.19 | 1.75 | 0 | 586.5825 | 105.58 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Pressurisation Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112890.2375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B-26th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1001 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1002 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1101 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1102 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1201 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1202 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1301 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1302 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1401 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1402 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1501 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1502 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1601 Ceilings Semi-Acrylic Painting. | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1602 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1701 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1702 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1801 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1802 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1901 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1902 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Fire Shaft Semi-Acrylic Paint Paint - 98.49 S | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 101 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 102 Ceilings Semi-Acrylic Painting - | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2001 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2002 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2101 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2102 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2201 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2202 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2301 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2302 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 23rd Floor Garbage, Pressurisation 1, 2 shaft Semi-Acrylic | 563.97 | 1.75 | 0 | 986.9475 | 177.66 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Pressurisation Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112489.8725 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2401 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2402 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2501 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2502 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 564.34 | 1.75 | 0 | 987.595 | 177.76 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112489.225 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2601 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2601 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2602 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor 2602 Walls Semi-Acrylic Painting | 564.34 | 1.75 | 0 | 987.595 | 177.76 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112489.225 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 26th Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 201 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 592.39 | 1.75 | 0 | 1036.6825 | 186.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112440.1375 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 202 Ceilings Semi-Acrylic Painting | 17 | 1.75 | 0 | 29.75 | 5.36 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113447.07 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 357.47 | 1.75 | 0 | 625.5725 | 112.6 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -112851.2475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 227.87 | 1.75 | 0 | 398.7725 | 71.78 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for LV Shaft, Electrical Shaft & Service Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113078.0475 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Fire Shaft Semi-Acrylic Paint - 98.49 Sq.Ft | 98.49 | 1.75 | 0 | 172.3575 | 31.02 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Fire Shaft | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113304.4625 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Semi-Acrylic Paint (M) | N/C | N/C | CHAPLA ADE PENTING CONTRACTOR | 830 | 2020-07-08 | B 3rd Floor Flat No 301 Ceilings Semi-Acrylic Painting | 8.39 | 1.75 | 0 | 14.6825 | 2.64 | 2024-08-19 | Providing 2nd coat Semiacrylic Paint for Duct Wall & Ceiling | 100 |  | 109955 | 2024-08-19 | 113476.82 | 1900-01-01 | -113462.1375 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 14th floor External Texture Painting | 281 | 3.5 | 0 | 983.5 | 177.04 | 2024-08-06 | Providing, Fixing & Removing of Scaffolding/Gondola for Texture Paint work. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -5768.5 | SAI NIRMAL COLOURS & TEXTURES
Scaffolding/Gondola work | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 20th floor External Texture Painting | 281 | 3.5 | 0 | 983.5 | 177.04 | 2024-08-06 | Providing, Fixing & Removing of Scaffolding/Gondola for Texture Paint work. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -5768.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 23rd floor External Texture Painting | 170 | 7.25 | 0 | 1232.5 | 221.86 | 2024-08-06 | Application of One Caot Texture Paint (1.5mm thick) on External Surface. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -5519.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 2nd floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Application of One Caot Texture Paint (1.5mm thick) on External Surface. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -6389.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 4th floor External Texture Painting | 130 | 7.25 | 0 | 942.5 | 169.66 | 2024-08-06 | Application of One Caot Texture Paint (1.5mm thick) on External Surface. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -5809.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 6th floor External Texture Painting | 130 | 7.25 | 0 | 942.5 | 169.66 | 2024-08-06 | Application of One Caot Texture Paint (1.5mm thick) on External Surface. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -5809.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 8th floor External Texture Painting | 130 | 7.25 | 0 | 942.5 | 169.66 | 2024-08-06 | Application of One Caot Texture Paint (1.5mm thick) on External Surface. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -5809.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 844 | 2020-09-15 | A Eastside 9th floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Application of One Caot Texture Paint (1.5mm thick) on External Surface. | 100 |  | 109708 | 2024-08-12 | 6752 | 1900-01-01 | -6389.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 22nd floor External Texture Painting | 20 | 7.25 | 0 | 145 | 26.1 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -4640 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 23rd floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -4422.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 3rd floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -4422.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 4th floor External Texture Painting | 130 | 7.25 | 0 | 942.5 | 169.66 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -3842.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 5th floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -4422.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 6th floor External Texture Painting | 130 | 7.25 | 0 | 942.5 | 169.66 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -3842.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 7th floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -4422.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 8th floor External Texture Painting | 130 | 7.25 | 0 | 942.5 | 169.66 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -3842.5 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (M) | N/C | N/C | SAI NIRMAL COLOURS & TEXTURES | 845 | 2020-09-15 | A Eastside 9th floor External Texture Painting | 50 | 7.25 | 0 | 362.5 | 65.26 | 2024-08-06 | Material Supply for Applcation of External Texture Paint. | 100 |  | 109718 | 2024-08-12 | 4785 | 1900-01-01 | -4422.5 | SAI NIRMAL COLOURS & TEXTURES
Core Cutting Work 4" BCE | N/C | N/C | B.D. DONGARE | 864 | 2020-10-08 | B Core Cutting Work For Ac Work - | 124 | 300 | 0 | 37200 | 0 | 2024-08-21 22:46 | 4" dia and 4" depth Core Cutting work in Non Structural wall for AC Cable and drain line at Tower B | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SAROJ KUMAR PRADHAN
Addressable Control Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 14 | 2281 | 0 | 31934 | 5748.12 | 2024-08-12 12:26 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power Supply as well as the Notifcation Appliance Circuits. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -881206 | GLOTECH FIRE ENGINEERS
Addressable Relay Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 10 | 2461 | 0 | 24610 | 4429.8 | 2024-08-12 12:50 | Supply of Addressable Relay Module with Non Supervised Dual potential free contacts.Shall have Binary Coded Dip Switch address settings,Shall have an LED indiaction for normal and active modes Approval: UL Listed, Make: Ravel. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -888530 | GLOTECH FIRE ENGINEERS
Addressable Relay Module (M) (Rate Diff.) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 5 | 249 | 0 | 1245 | 224.1 | 2024-08-12 12:50 | Rate Difference for Supply of Addressable Relay Module Model No. RE- 717 MR. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -911895 | GLOTECH FIRE ENGINEERS
LPG Detector with base (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 19 | 2510 | 0 | 47690 | 8584.2 | 2024-08-12 12:17 | Supply of conventional type 4wire LPG detector with base and operting voltage 21-27Vdc, inbuilt sounder output ,70dBat 3mtr ,inbuilt alarm relay pot free contact 1Amps at 30vDC .NOTE: For addressable need to connect with Monitor Module (RE - 717 MM) | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -865450 | GLOTECH FIRE ENGINEERS
Conventional Sounder cum Strobe (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 4 | 605 | 0 | 2420 | 435.6 | 2024-08-12 12:18 | Supply of Conventional type Sounder wall/Flush mounted type rated at 100dBA @ 1m for Audible annunciation, It shall operate on 24 VDC and the current rating maximum of 40 mA, Inbuilt protective diode for reverse polarity wiring | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -910720 | GLOTECH FIRE ENGINEERS
Addressable control Module (M) (Rate Diff.) - No. | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 14 | 229 | 0 | 3206 | 577.08 | 2024-08-10 17:07 | Rate Difference for Supply of Addressable Control Module Model No. RE- 717 MC. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -909934 | GLOTECH FIRE ENGINEERS
Addressable Relay Module (M) (Rate Diff.) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 5 | 249 | 0 | 1245 | 224.1 | 2024-08-10 17:08 | Rate Difference for Supply of Addressable Relay Module Model No. RE- 717 MR. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -911895 | GLOTECH FIRE ENGINEERS
Addressable Electric Smoke Detector (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 318 | 1985 | 0 | 631230 | 113621.4 | 2024-08-10 16:44 | Supply of Addressable Smoke detector with base with Binary coded address setting. Dual LED’s for 360° visibility.Polarity Free, Sleek low-profile housing design. Regular 100mm base. IP Rating : IP - 42. Approval: UL Listed, Make: Ravel | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -281910 | GLOTECH FIRE ENGINEERS
Addressable Heat Detector (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 20 | 1787 | 0 | 35740 | 6433.2 | 2024-08-10 16:45 | Supply of Addressable Heat detector with Fixed temperature of 59°C and ROR feature to raise an alarm when the temperatures raises 11.1°per Minute ,Shall have Binary coded address setting. Dual LED’s for 360° visibility. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -877400 | GLOTECH FIRE ENGINEERS
Manual Pull Station (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 6 | 3960 | 0 | 23760 | 4276.8 | 2024-08-10 16:46 | Supply of Manual Pull Station -Single Action/Dual action - with back box and Break Glass Rod,shall be resettable by Align key to avoid unauthenticated restorations - Approval: UL Listed - Make: Ravel | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -889380 | GLOTECH FIRE ENGINEERS
Zone Interface Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 19 | 5000 | 0 | 95000 | 17100 | 2024-08-10 16:47 | Supply of Addressable Zone Interface Module for monitoring the field Conventional devices.,Shall have Binary Coding address DIP switch Settings,Shall supports 16 conventional devices/ Gas detector, Make: Ravel. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -818140 | GLOTECH FIRE ENGINEERS
Addressable Control Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 6 | 2510 | 0 | 15060 | 2710.8 | 2024-08-10 16:55 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power Supply as well as the Notifcation Appliance Circuits. | 100 |  | 109796 | 2024-08-12 | 913140 | 1900-01-01 | -898080 | GLOTECH FIRE ENGINEERS
2C 1.5 sqmm (FRLS) Cable (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 866 | 2020-10-08 | A FAS & PA System | 4000 | 68.5 | 0 | 274000 | 49320 | 2024-08-17 11:15 | Supply of 2core x 1.5sq.mm Unshielded cable for field cabling of Fire Alarm System (without Pvc Conduit) (Un Armoured) (FRLS Flexible Cable in Red Colour) | 100 |  | 109883 | 2024-08-17 | 274000 | 1900-01-01 | 0 | GLOTECH FIRE ENGINEERS
Addressable Electric Smoke Detector (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 550 | 300 | 0 | 165000 | 29700 | 2024-08-17 11:19 | ITC of Addressable Smoke detector with base with Binary coded address setting. Dual LED’s for 360° visibility.Polarity Free, Sleek low-profile housing design. Regular 100mm base. IP Rating : IP - 42. Approval:UL Listed, Make: Ravel | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -169800 | GLOTECH FIRE ENGINEERS
Addressable Electric Smoke Detector (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 101 | 300 | 0 | 30300 | 5454 | 2024-08-17 11:19 | ITC of Addressable Smoke detector with base with Binary coded address setting.Dual LED’s for 360° visibility.Polarity Free, Sleek low-profile housing design. Regular 100mm base. IP Rating : IP - 42. Approval: UL Listed, Make:Ravel | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -304500 | GLOTECH FIRE ENGINEERS
Addressable Heat Detector (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 62 | 300 | 0 | 18600 | 3348 | 2024-08-17 11:20 | I & C of Addressable Heat detector with Fixed temperature of 59°C and ROR feature to raise an alarm when the temperatures raises 11.1°per Minute,Shall have Binary coded address setting.Dual LED’s for 360° visibility. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -316200 | GLOTECH FIRE ENGINEERS
Addressable Monitor Module (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:21 | I & C of Addressable Monitor Module for monitoring the field NO/NC devices.Shall have Binary Coding Setting Dip Switch,Shall have an LED indiaction for normal and Active Modes - Approval: UL Listed, Make: Ravel. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
Addressable Control Module (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:22 | I & C of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power Supply as well as the Notifcation Appliance Circuits. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
LPG Detector with base (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 52 | 300 | 0 | 15600 | 2808 | 2024-08-17 11:22 | I & C of conventional type 4wire LPG detector with base and operting voltage 21-27Vdc, inbuilt sounder output ,70dBat 3mtr ,inbuilt alarm relay pot free contact 1Amps at 30vDC .NOTE: For addressable need to connect with Monitor Module (RE - 717 MM) | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -319200 | GLOTECH FIRE ENGINEERS
LPG Detector with base (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 10 | 300 | 0 | 3000 | 540 | 2024-08-17 11:22 | I & C of conventional type 4wire LPG detector with base and operting voltage 21-27Vdc, inbuilt sounder output ,70dBat 3mtr ,inbuilt alarm relay pot free contact 1Amps at 30vDC .NOTE: For addressable need to connect with Monitor Module (RE - 717 MM) | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -331800 | GLOTECH FIRE ENGINEERS
Zone Interface Module (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 52 | 300 | 0 | 15600 | 2808 | 2024-08-17 11:23 | I & C of Addressable Zone Interface Module for monitoring the field Conventional devices.,Shall have Binary Coding address DIP switch Settings,Shall supports 16 conventional devices/ Gas detector - , Make: Ravel. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -319200 | GLOTECH FIRE ENGINEERS
Zone Interface Module (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 10 | 300 | 0 | 3000 | 540 | 2024-08-17 11:23 | I & C of Addressable Zone Interface Module for monitoring the field Conventional devices.,Shall have Binary Coding address DIP switch Settings,Shall supports 16 conventional devices/ Gas detector,Make: Ravel. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -331800 | GLOTECH FIRE ENGINEERS
Manual Pull Station (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:24 | I & C of Manual Pull Station -Single Action/Dual action - with back box and Break Glass Rod,shall be resettable by Align key to avoid unauthenticated restorations - Approval: UL Listed - Make: Ravel | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
SITC Fireman's Phone Jack (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:26 | IT&C of Firemans Phone Jack with all mounting accessories, complete with MS Powder coated Junction Box for mounting on Surface, Cable Lugs at Ends and all required accesories for mounting at site complete as requried. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
Conventional Sounder cum Strobe (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:31 | IT&C of Conventional type Sounder wall/Flush mounted type rated at 100dBA at 1m for Audible annunciation, It shall operate on 24 VDC and the current rating maximum of 40 mA, Inbuilt protective diode for reverse polarity wiring. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
Fault Isolator Base / Module (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:33 | I & C of Fault isolator Base / Module capable of monitoring shorted loop circuit and automatically restore communications when shorted conditions are corrected - Make: Ravel | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
Addressable Mini Monitor Module (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 31 | 300 | 0 | 9300 | 1674 | 2024-08-17 11:34 | I & C of Addressable Mini Monitor Module with back box of pull station for monitoring the field NO/NC devices.Shall have Binary Coding Setting Dip Switch,Shall have an LED indiaction for normal and Activate mode. Make: Ravel. | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -325500 | GLOTECH FIRE ENGINEERS
Ceiling Mountable ABS Plastic Grill (L) | N/C | N/C | GLOTECH FIRE ENGINEERS | 867 | 2020-10-08 | B FAS & PA System | 62 | 300 | 0 | 18600 | 3348 | 2024-08-17 11:40 | IT&C of Ceiling Mountable ABS plastic grille with metal punched net Speaker,Flush mount 15cm dynamic cone speaker,Shall be Easy to install with spring catch mount, Shall give the Music Power of 10 watts Make RAVEL | 100 |  | 109885 | 2024-08-17 | 334800 | 1900-01-01 | -316200 | GLOTECH FIRE ENGINEERS
Addressable Control Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 14 | 2281 | 0 | 31934 | 5748.12 | 2024-08-10 17:05 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power Supply as well as the Notifcation Appliance Circuits | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -513931 | GLOTECH FIRE ENGINEERS
Addressable Electric Smoke Detector (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 206 | 1985 | 0 | 408910 | 73603.8 | 2024-08-12 12:11 | Supply of Addressable Smoke detector with base with Binary coded address setting. Dual LED’s for 360° visibility.Polarity Free, Sleek low-profile housing design. Regular 100mm base. IP Rating : IP - 42. Approval: UL Listed, Make Ravel | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -136955 | GLOTECH FIRE ENGINEERS
Manual Pull Station (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 4 | 3960 | 0 | 15840 | 2851.2 | 2024-08-12 12:14 | Supply of Manual Pull Station -Single Action/Dual action - with back box and Break Glass Rod,shall be resettable by Align key to avoid unauthenticated restorations - Approval: UL Listed - Make: Ravel | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -530025 | GLOTECH FIRE ENGINEERS
Zone Interface Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 7 | 5000 | 0 | 35000 | 6300 | 2024-08-12 12:14 | Supply of Addressable Zone Interface Module for monitoring the field Conventional devices.,Shall have Binary Coding address DIP switch Settings,Shall supports 16 conventional devices/ Gas detector - , Make: Ravel. | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -510865 | GLOTECH FIRE ENGINEERS
Conventional Sounder cum Strobe (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 3 | 605 | 0 | 1815 | 326.7 | 2024-08-12 12:18 | Supply of Conventional type Sounder wall/Flush mounted type rated at 100dBA @ 1m for Audible annunciation, It shall operate on 24 VDC and the current rating maximum of 40 mA, Inbuilt protective diode for reverse polarity wiring | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -544050 | GLOTECH FIRE ENGINEERS
Addressable Monitor Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 4 | 2250 | 0 | 9000 | 1620 | 2024-08-12 12:20 | Supply of Addressable Monitor Module for monitoring the field NO/NC devices.Shall have Binary Coding Setting Dip Switch,Shall have an LED indiaction for normal and Active Modes - Approval: UL Listed, Make: Ravel. | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -536865 | GLOTECH FIRE ENGINEERS
Addressable Control Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 5 | 2510 | 0 | 12550 | 2259 | 2024-08-12 12:20 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power Supply as well as the Notifcation Appliance Circuits | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -533315 | GLOTECH FIRE ENGINEERS
LPG Detector with base (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 10 | 2510 | 0 | 25100 | 4518 | 2024-08-12 12:17 | Supply of conventional type 4wire LPG detector with base and operting voltage 21-27Vdc, inbuilt sounder output ,70dBat 3mtr ,inbuilt alarm relay pot free contact 1Amps at 30vDC .NOTE: For addressable need to connect with Monitor Module (RE - 717 MM) | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -520765 | GLOTECH FIRE ENGINEERS
Addressable control Module (M) (Rate Diff.) - No. | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 15 | 229 | 0 | 3435 | 618.3 | 2024-08-12 12:52 | Rate Difference for Supply of Addressable Control Module Model No.RE- 717 MC. | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -542430 | GLOTECH FIRE ENGINEERS
2C 1.5 sqmm (FRLS) Cable (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 6000 | 68.5 | 0 | 411000 | 73980 | 2024-08-17 11:14 | Supply of 2core x 1.5sq.mm Unshielded cable for field cabling of Fire Alarm System (without Pvc Conduit) (Un Armoured) (FRLS Flexible Cable in Red Colour) | 100 |  | 109884 | 2024-08-17 | 411000 | 1900-01-01 | 0 | GLOTECH FIRE ENGINEERS
Addressable Control Module (M) | N/C | N/C | GLOTECH FIRE ENGINEERS | 868 | 2020-10-08 | B FAS & PA System | 1 | 2281 | 0 | 2281 | 410.58 | 2024-08-12 12:30 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power Supply as well as the Notifcation Appliance Circuits | 100 |  | 110009 | 2024-08-23 | 545865 | 1900-01-01 | -543584 | GLOTECH FIRE ENGINEERS
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 27th Floor Regular Staircase Flooring | 66.294 | 30 | 0 | 1988.82 | 357.98 | 2024-08-20 | Regular Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 28h Floor Regular Staircase Flooring - 1 No. | 66.294 | 30 | 0 | 1988.82 | 357.98 | 2024-08-20 | Regular Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 29th Floor Regular Staircase Flooring - 1 No. | 66.294 | 30 | 0 | 1988.82 | 357.98 | 2024-08-20 | Regular Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 30th Floor Regular Staircase Flooring - 1 No. | 66.294 | 30 | 0 | 1988.82 | 357.98 | 2024-08-20 | Regular Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 31st Floor Regular Staircase Flooring - 1 No. | 66.294 | 30 | 0 | 1988.82 | 357.98 | 2024-08-20 | Regular Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 27th Floor Fire Staircase Flooring | 77.958 | 30 | 0 | 2338.74 | 420.98 | 2024-08-20 | Fire Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 28th Floor Fire Staircase Flooring | 77.958 | 30 | 0 | 2338.74 | 420.98 | 2024-08-20 | Fire Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 29th Floor Fire Staircase Flooring | 77.958 | 30 | 0 | 2338.74 | 420.98 | 2024-08-20 | Fire Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 30th Floor Fire Staircase Flooring | 77.958 | 30 | 0 | 2338.74 | 420.98 | 2024-08-20 | Fire Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Kota Skirting (L)- BCO | N/C | N/C | R.M.Marbles | 905 | 2020-11-19 | A 31st Floor Fire Staircase Flooring | 77.958 | 30 | 0 | 2338.74 | 420.98 | 2024-08-20 | Fire Staircase Skirting Fixing work for A-Building | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN PARSHURAM YADAV
Back Coat Plaster | N/C | N/C | VENKAT RATHOD | 927 | 2020-12-14 | A 3rd Floor Back Coat Plaster | 2.6 | 2000 | 0 | 5200 | 0 | 2024-08-12 14:04 | Applying 60mm thk Back Coat Plaster on RCC Wall in Bathroom | 100 |  | 109810 | 2024-08-12 | 5200 | 1900-01-01 | 0 | SURESH KUMAR MURALIDHAR
Back Coat Plaster | N/C | N/C | VENKAT RATHOD | 927 | 2020-12-14 | A 24th Floor Back Coat Plaster | 1 | 2000 | 0 | 2000 | 0 | 2024-08-19 | Applying 60mm thk Back Coat Plaster on RCC Wall in Bathroom | 100 |  | 109961 | 2024-08-19 | 7325 | 1900-01-01 | -5325 | SURESH KUMAR MURALIDHAR
Back Coat Plaster | N/C | N/C | VENKAT RATHOD | 927 | 2020-12-14 | A 4th Floor Back Coat Plaster | 2.6625 | 2000 | 0 | 5325 | 0 | 2024-08-19 17:17 | Applying 60mm thk Back Coat Plaster on RCC Wall in Bathroom | 100 |  | 109961 | 2024-08-19 | 7325 | 1900-01-01 | -2000 | SURESH KUMAR MURALIDHAR