## Work_Completion_Browse638600200
Work Completion Browse
Project : TANGEWALA COLONY SRA PROJECT NEW
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 101 Records 1 to 101
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
RCC Raft - DCW | N/C | N/C | SUPREME ENGINEERS | 1 | 2024-06-11 | RAFT & RETAINING WALL | 2900.57 | 90 | 0 | 261051.3 | 46989.24 | 2024-08-20 16:05 | Labour charges for RCC Work for Raft including fixing of Reinforcement, shuttering work & concrete. | 100 |  | 109988 | 2024-08-20 | 1201555.5 | 2024-08-22 15:12 | -940504.2 | SUPREME ENGINEERS
RCC Retaining Wall - DCW | N/C | N/C | SUPREME ENGINEERS | 1 | 2024-06-11 | RAFT & RETAINING WALL | 6172.51 | 150 | 0 | 925876.5 | 166657.78 | 2024-08-20 16:05 | Labour charges for RCC Work for Retaining wall including fixing of Reinforcement, Shuttering work & concrete work. | 100 |  | 109988 | 2024-08-20 | 1201555.5 | 2024-08-22 15:12 | -275679 | SUPREME ENGINEERS
RCC Work - Mkt | N/C | N/C | SUPREME ENGINEERS | 1 | 2024-06-11 | RAFT & RETAINING WALL | 162.53 | 90 | 0 | 14627.7 | 2632.98 | 2024-08-20 16:05 | Labour charges for RCC Work for Lower Ground Sump work including fixing of Reinforcement, Shuttering & Concreting work. | 100 |  | 109988 | 2024-08-20 | 1201555.5 | 2024-08-22 15:12 | -1186927.8 | SUPREME ENGINEERS
RCC Beam | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | A- RCC Plinth Beam Substructure work(L) | 300 | 50 | 0 | 15000 | 2700 | 2024-08-20 18:08 | Labour charges for Plinth Beam RCC work for A-Bldg Sub Structure area including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5326387.9 | SUPREME ENGINEERS
Soling & PCC | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | A-Soling & PCC Substructure work | 2737.37 | 90 | 0 | 246363.3 | 44345.4 | 2024-08-20 18:08 | Labour charges for Soling & PCC work for A-Bldg Sub Structure area including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5095024.6 | SUPREME ENGINEERS
RCC Superstructure Labour (B-up)- DPo | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 1st Floor RCC Slab Built-up | 5783.05 | 175 | 0 | 1012033.75 | 182166.08 | 2024-08-20 18:08 | Labour charges for Slab Shuttering,Reinforcement & Concreting work for slab,Beam,Staircase & Shear wallls,etc including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -4329354.15 | SUPREME ENGINEERS
RCC Superstructure Labour (B-up)- DPo | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 2nd Floor RCC Slab Built-up | 5713.94 | 175 | 0 | 999939.5 | 179989.12 | 2024-08-20 18:08 | Labour charges for Slab Shuttering,Reinforcement & Concreting work for slab,Beam,Staircase & Shear wallls,etc including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -4341448.4 | SUPREME ENGINEERS
RCC Superstructure Labour (B-up)- DPo | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 3rd Floor RCC Slab Built-up | 5713.94 | 175 | 0 | 999939.5 | 179989.12 | 2024-08-20 18:08 | Labour charges for Slab Shuttering,Reinforcement & Concreting work for slab,Beam,Staircase & Shear wallls,etc including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -4341448.4 | SUPREME ENGINEERS
RCC Superstructure Labour (B-up)- DPo | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 4th Floor RCC Slab Built-up | 5713.94 | 185 | 0 | 1057078.9 | 190274.2 | 2024-08-20 18:08 | Labour charges for Slab Shuttering,Reinforcement & Concreting work for slab,Beam,Staircase & Shear wallls,etc including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -4284309 | SUPREME ENGINEERS
RCC Superstructure Labour (B-up)- DPo | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 5th Floor RCC Slab Built-up | 2856.97 | 185 | 0 | 528539.45 | 95137.1 | 2024-08-20 18:08 | Labour charges for Slab Shuttering,Reinforcement & Concreting work for slab,Beam,Staircase & Shear wallls,etc including wastage,Profit, overheads,supervision,loading, unloading,Transport & all legal Compliances,etc. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -4812848.45 | SUPREME ENGINEERS
Schedule- BC | GLAZING SERVICES | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | UG Floor RCC Slab Built-up | 4737.37 | 10 | 0 | 47373.7 | 8527.26 | 2024-08-20 18:08 | Charges for All RCC Work to be Done in Schedule. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5294014.2 | SUPREME ENGINEERS
Schedule- BC | GLAZING SERVICES | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 1st Floor RCC Slab Built-up | 5783.05 | 10 | 0 | 57830.5 | 10409.5 | 2024-08-20 18:08 | Charges for All RCC Work to be Done in Schedule. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5283557.4 | SUPREME ENGINEERS
Schedule- BC | GLAZING SERVICES | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 2nd Floor RCC Slab Built-up | 5713.94 | 10 | 0 | 57139.4 | 10285.1 | 2024-08-20 18:08 | Charges for All RCC Work to be Done in Schedule. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5284248.5 | SUPREME ENGINEERS
Schedule- BC | GLAZING SERVICES | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 3rd Floor RCC Slab Built-up | 5713.94 | 10 | 0 | 57139.4 | 10285.1 | 2024-08-20 18:08 | Charges for All RCC Work to be Done in Schedule. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5284248.5 | SUPREME ENGINEERS
Quality (BC) | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | UG Floor RCC Slab Built-up | 4737.37 | 10 | 0 | 47373.7 | 8527.26 | 2024-08-20 18:08 | Charges for all RCC Work to be Done in Quality | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5294014.2 | SUPREME ENGINEERS
Quality (BC) | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 1st Floor RCC Slab Built-up | 5783.05 | 10 | 0 | 57830.5 | 10409.5 | 2024-08-20 18:08 | Charges for all RCC Work to be Done in Quality | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5283557.4 | SUPREME ENGINEERS
Legal Compliances | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | UG Floor RCC Slab Built-up | 4737.37 | 15 | 0 | 71060.55 | 12790.9 | 2024-08-20 18:08 | Charges for All Legal Compliances of Contractor. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5270327.35 | SUPREME ENGINEERS
Legal Compliances | N/C | N/C | SUPREME ENGINEERS | 11 | 2024-06-19 | 1st Floor RCC Slab Built-up | 5783.05 | 15 | 0 | 86745.75 | 15614.24 | 2024-08-20 18:08 | Charges for All Legal Compliances of Contractor. | 100 |  | 109994 | 2024-08-20 | 5341387.9 | 2024-08-22 15:13 | -5254642.15 | SUPREME ENGINEERS
Concrete work (M). | N/C | N/C | MAHALAXMI BUILDCON | 2 | 2024-06-11 | RAFT & RETAINING WALL | 76.5 | 5949.56 | 0 | 455141.34 | 81925.44 | 2024-08-20 16:40 | Material supply charges of concrete having M-30 Grade for RCC Work for Raft & Retaining wall. | 100 |  | 109995 | 2024-08-20 | 2207714.3 | 1900-01-01 | -1752572.96 | SUPREME ENGINEERS
Concrete work (M). | N/C | N/C | MAHALAXMI BUILDCON | 2 | 2024-06-11 | RAFT & RETAINING WALL | 109.38 | 6330.7 | 0 | 692451.966 | 124641.36 | 2024-08-20 16:40 | Material supply charges of concrete having M-40 Grade for RCC Work for Retaining wall | 100 |  | 109995 | 2024-08-20 | 2207714.3 | 1900-01-01 | -1515262.334 | SUPREME ENGINEERS
Reinforcement (M) | N/C | N/C | MAHALAXMI BUILDCON | 2 | 2024-06-11 | RAFT & RETAINING WALL | 14860.04 | 65 | 0 | 965902.6 | 173862.46 | 2024-08-20 16:40 | Material supply charges of steel of required diameter for RCC work for Raft and Retaining wall. | 100 |  | 109995 | 2024-08-20 | 2207714.3 | 1900-01-01 | -1241811.7 | SUPREME ENGINEERS
Concrete work (M). | N/C | N/C | MAHALAXMI BUILDCON | 2 | 2024-06-11 | RAFT & RETAINING WALL | 6.99 | 6330.7 | 0 | 44251.593 | 7965.28 | 2024-08-20 16:40 | Material supply charges of concrete having M-40 Grade for RCC Work at Lower Ground Sump work. | 100 |  | 109995 | 2024-08-20 | 2207714.3 | 1900-01-01 | -2163462.707 | SUPREME ENGINEERS
Reinforcement (M) | N/C | N/C | MAHALAXMI BUILDCON | 2 | 2024-06-11 | RAFT & RETAINING WALL | 768.72 | 65 | 0 | 49966.8 | 8994.02 | 2024-08-20 16:40 | Material supply charges of steel of required diameter for RCC work at Lower Ground Sump work. | 100 |  | 109995 | 2024-08-20 | 2207714.3 | 1900-01-01 | -2157747.5 | SUPREME ENGINEERS
Plum Concrete (M) | N/C | N/C | MAHALAXMI BUILDCON | 20 | 2024-06-20 | Plum Concrete Work(L) | 258.93 | 3973 | 0 | 1028728.89 | 185171.2 | 2024-08-20 18:29 | Material supply charges of Plum Concrete with 50% clean hard stone of sizes not exceeding 15cm for Plum concreting work. | 100 |  | 109998 | 2024-08-20 | 1158045.09 | 2024-08-22 15:12 | -129316.2 | SUPREME ENGINEERS
Reinforcement (M) | N/C | N/C | MAHALAXMI BUILDCON | 20 | 2024-06-20 | Plum Concrete Work(L) | 1989.48 | 65 | 0 | 129316.2 | 23276.92 | 2024-08-20 18:29 | Material supply charges of TOR Steel for Reinforcement of Plum Concreting work. | 100 |  | 109998 | 2024-08-20 | 1158045.09 | 2024-08-22 15:12 | -1028728.89 | SUPREME ENGINEERS
Plum Concrete | N/C | N/C | SUPREME ENGINEERS | 21 | 2024-06-20 | Plum Concrete Work(L) | 258.93 | 649 | 0 | 168045.57 | 30248.2 | 2024-08-20 18:34 | Labour charges for LAying of Plum Concreting work with 50% Clean hard stone of sizes not exceeding 15cm including loading, shifting & unloading of material. | 100 |  | 109993 | 2024-08-20 | 246886.35 | 1900-01-01 | -78840.78 | SUPREME ENGINEERS
Shuttering work-Mkt | N/C | N/C | SUPREME ENGINEERS | 21 | 2024-06-20 | Plum Concrete Work(L) | 84.38 | 675 | 0 | 56956.5 | 10252.18 | 2024-08-20 18:34 | Labour charges for fixing shuttering in position with proper support, line & Level, oiling the surface for proper finish & removal of form etc for plum concreting work. | 100 |  | 109993 | 2024-08-20 | 246886.35 | 1900-01-01 | -189929.85 | SUPREME ENGINEERS
Reinforcement (L) | No category | N/C | SUPREME ENGINEERS | 21 | 2024-06-20 | Plum Concrete Work(L) | 1989.48 | 11 | 0 | 21884.28 | 3939.18 | 2024-08-20 18:34 | Labour charges for Reinforcement work including fixing in position as per detailed drawings, binding with binding wires etc for plum concreting work. | 100 |  | 109993 | 2024-08-20 | 246886.35 | 1900-01-01 | -225002.07 | SUPREME ENGINEERS
Site Expenses -SO | N/C | N/C | SATISH RAMCHANDRA JAGTAP | 22 | 2024-06-27 | Site Expenses | 0.6734 | 10000 | 0 | 6734 | 0 | 2024-08-16 14:36 | Petty Cash expenses for JULY-2024 | 100 |  | 109875 | 2024-08-16 | 6734 | 1900-01-01 | 0 | SATISH RAMCHANDRA JAGTAP
Department Labour - DEn | N/C | N/C | SUPREME ENGINEERS | 23 | 2024-07-01 | Excavation Work By Department Labour | 16 | 900 | 0 | 14400 | 2592 | 2024-08-13 17:25 | Charges for Departmental Labour for Manual Excavation work | 100 |  | 109907 | 2024-08-19 | 16800 | 1900-01-01 | -2400 | SUPREME ENGINEERS
Breaker | N/C | N/C | SUPREME ENGINEERS | 23 | 2024-07-01 | Excavation Work By Department Labour | 4 | 600 | 0 | 2400 | 432 | 2024-08-13 17:25 | Charges for Breaker for Manual Excavation work | 100 |  | 109907 | 2024-08-19 | 16800 | 1900-01-01 | -14400 | SUPREME ENGINEERS
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 25 | 2024-07-09 | Site Electricity expenses | 0.5555 | 100000 | 0 | 55550 | 0 | 2024-08-07 | Charges for Electricity Bills from June-2024 to Nov-2024 | 100 |  | 109671 | 2024-08-07 | 55550 | 2024-08-07 18:48 | 0 | MSEDCL
Department Labour- BC | N/C | N/C | PRAKASH CONTRACTOR | 29 | 2024-07-19 | Department Labour | 30 | 650 | 0 | 19500 | 0 | 2024-08-01 11:00 | Labour charges for Departmental work for Month JUNE-2024 | 100 |  | 109466 | 2024-08-02 | 39650 | 2024-08-08 11:02 | -20150 | PRAKASH CONTRACTOR
Department Labour- BC | N/C | N/C | PRAKASH CONTRACTOR | 29 | 2024-07-19 | Department Labour | 31 | 650 | 0 | 20150 | 0 | 2024-08-01 11:00 | Labour charges for Departmental work for Month JULY-2024 | 100 |  | 109466 | 2024-08-02 | 39650 | 2024-08-08 11:02 | -19500 | PRAKASH CONTRACTOR
Department Labour- BC | N/C | N/C | PRAKASH CONTRACTOR | 29 | 2024-07-19 | Department Labour | 30 | 650 | 0 | 19500 | 0 | 2024-08-02 11:04 | Labour charges for Departmental work for Month APR-2024 | 100 |  | 109464 | 2024-08-02 | 19500 | 2024-08-07 14:09 | 0 | PRAKASH CONTRACTOR
Department Labour- BC | N/C | N/C | PRAKASH CONTRACTOR | 29 | 2024-07-19 | Department Labour | 31 | 650 | 0 | 20150 | 0 | 2024-08-02 11:04 | Labour charges for Departmental work for Month MAY-2024 | 100 |  | 109465 | 2024-08-02 | 20150 | 2024-08-07 14:10 | 0 | PRAKASH CONTRACTOR
Reinforcement (L) | No category | N/C | SUPREME ENGINEERS | 3 | 2024-06-11 | A & B Building Grade Slab & Soling Work | 2328.04 | 11 | 0 | 25608.44 | 4609.52 | 2024-08-20 16:56 | Labour charges for Providing & Laying steel for Grade slab for A & B-Bldg. | 100 |  | 109989 | 2024-08-20 | 79389.44 | 1900-01-01 | -53781 | SUPREME ENGINEERS
RCC Work - Mkt | N/C | N/C | SUPREME ENGINEERS | 3 | 2024-06-11 | A & B Building Grade Slab & Soling Work | 4481.75 | 12 | 0 | 53781 | 9680.58 | 2024-08-20 16:56 | Labour charges for Grid Slab RCC Work including shuttering work & concreting work for A & B-Bldg Grid Slab. | 100 |  | 109989 | 2024-08-20 | 79389.44 | 1900-01-01 | -25608.44 | SUPREME ENGINEERS
Murrum Filling | N/C | N/C | SUPREME ENGINEERS | 31 | 2024-07-27 | A- Murum filling, Bobcat & Compactor | 351 | 715 | 0 | 250965 | 45173.7 | 2024-08-13 17:25 | Charges for Murum Filling work for Building area. | 100 |  | 109908 | 2024-08-19 | 338490 | 1900-01-01 | -87525 | SUPREME ENGINEERS
Bobcat Hiring Charges | N/C | N/C | SUPREME ENGINEERS | 31 | 2024-07-27 | A- Murum filling, Bobcat & Compactor | 97.25 | 900 | 0 | 87525 | 15754.5 | 2024-08-13 17:25 | Bobcat Charges for Murum Filling work for Building area | 100 |  | 109908 | 2024-08-19 | 338490 | 1900-01-01 | -250965 | SUPREME ENGINEERS
Reinforcement (M) | N/C | N/C | MAHALAXMI BUILDCON | 4 | 2024-06-11 | A & B Building Grade Slab & Soling Work | 2328.04 | 65 | 0 | 151322.6 | 27238.06 | 2024-08-20 16:57 | Material supply charges for providing of steel of required size for Grade slab A & B-Bldg | 100 |  | 109996 | 2024-08-20 | 619830.49 | 1900-01-01 | -468507.89 | SUPREME ENGINEERS
Concrete - M20 | N/C | N/C | MAHALAXMI BUILDCON | 4 | 2024-06-11 | A & B Building Grade Slab & Soling Work | 66.76 | 5487 | 0 | 366312.12 | 65936.18 | 2024-08-20 16:57 | Material supply charges of concrete M20 for A & B-Bldg Grade slab work. | 100 |  | 109996 | 2024-08-20 | 619830.49 | 1900-01-01 | -253518.37 | SUPREME ENGINEERS
Soling Work -Mkt | N/C | N/C | MAHALAXMI BUILDCON | 4 | 2024-06-11 | A & B Building Grade Slab & Soling Work | 4582.77 | 22.3 | 0 | 102195.771 | 18395.24 | 2024-08-20 16:57 | Material supply charges for 230mm thick Rubble soling work at Grade slab Building area at A & B-Bldg. | 100 |  | 109996 | 2024-08-20 | 619830.49 | 1900-01-01 | -517634.719 | SUPREME ENGINEERS
Fabrication work (M) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 31.27 | 62.5 | 0 | 1954.375 | 351.78 | 2024-08-22 16:57 | Material supply charges of MS Angle 50x50x5mm for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 42.88 | 70.5 | 0 | 3023.04 | 544.14 | 2024-08-22 16:57 | Material supply charges of MS Square Pipe 40x40x2mm for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 47.48 | 62.5 | 0 | 2967.5 | 534.16 | 2024-08-22 16:57 | Material supply charges of MS Angle 40x40x5mm for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Fabrication work (M) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 50.14 | 70.5 | 0 | 3534.87 | 636.28 | 2024-08-22 16:57 | Material supply charges of MS Square Pipe 50x50x2mm for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Fastner (M+L) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 4 | 45 | 0 | 180 | 32.4 | 2024-08-22 16:57 | Material supply and Labour charges for Fastner for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Fan Hook (M+L) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 19 | 150 | 0 | 2850 | 513 | 2024-08-22 16:57 | Material supply and Labour charges for Fan Hook for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Base Plate (M+L) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 1 | 150 | 0 | 150 | 27 | 2024-08-22 16:57 | Material supply and Labour charges for Base Plate for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Deck Sheet (M) | N/C | N/C | R.T.S. STEEL SERVICES | 41 | 2024-08-08 | Labour Camp-Extra Work | 668.25 | 85 | 0 | 56801.25 | 10224.22 | 2024-08-22 16:57 | Material supply charges of Deck Sheet 1mm Thick for Labour camp Extra work. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R.T.S. STEEL SERVICES
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 29 Electrical Work | 1 | 1350 | 0 | 202.5 | 36.46 | 2024-08-22 18:27 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3982.5 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 24 Electrical Work | 1 | 900 | 0 | 135 | 24.3 | 2024-08-22 18:27 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4050 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 22 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 23 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 26 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 28 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 13 Electrical Work | 1 | 1350 | 0 | 202.5 | 36.46 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3982.5 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 25 Electrical Work | 1 | 1350 | 0 | 202.5 | 36.46 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3982.5 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 27 Electrical Work | 1 | 1350 | 0 | 202.5 | 36.46 | 2024-08-22 18:07 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3982.5 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A-Shop No 1 Electrical Work | 1 | 1575 | 0 | 236.25 | 42.52 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3948.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 2 Electrical Work | 1 | 1575 | 0 | 236.25 | 42.52 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3948.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 3 Electrical Work | 1 | 1575 | 0 | 236.25 | 42.52 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3948.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 17 Electrical Work | 1 | 1575 | 0 | 236.25 | 42.52 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3948.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 18 Electrical Work | 1 | 1575 | 0 | 236.25 | 42.52 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3948.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 19 Electrical Work | 1 | 1575 | 0 | 236.25 | 42.52 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -3948.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 4 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:29 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 5 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 6 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 7 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 8 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 9 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 10 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 11 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:39 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 12 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:49 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 14 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:49 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 15 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:49 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 16 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:49 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 20 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:49 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 42 | 2024-08-09 | A.Shop No 21 Electrical Work | 1 | 675 | 0 | 101.25 | 18.22 | 2024-08-22 17:49 | Before pouring | 15 |  | 110010 | 2024-08-23 | 4185 | 1900-01-01 | -4083.75 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-101 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-102 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-103 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-201 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-202 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-203 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-204 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:49 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-205 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-206 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-207 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-208 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-301 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-302 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Electrical Work (Labour) | N/C | N/C | DS ELECTRICALS | 43 | 2024-08-09 | A-303 Electrical Work | 1 | 4350 | 0 | 652.5 | 117.46 | 2024-08-22 18:57 | Before Pouring | 15 |  | 110011 | 2024-08-23 | 30667.5 | 1900-01-01 | -30015 | DS ELECTRICALS
Concrete work (M). | N/C | N/C | MAHALAXMI BUILDCON | 5 | 2024-06-11 | Building PCC Work | 202.102 | 5229.76 | 0 | 1056944.9555 | 190250.1 | 2024-08-20 16:59 | Material supply charges & Qty. diff of concrete having M-15 Grade for A & B-Bldg PCC below footing & Screeding Work. | 100 |  | 109999 | 2024-08-20 | 1056944.96 | 1900-01-01 | -0.00448 | SUPREME ENGINEERS
Concreting Work-B.C. | No category | N/C | SUPREME ENGINEERS | 6 | 2024-06-11 | Building PCC Work | 14855.43 | 8 | 0 | 118843.44 | 21391.82 | 2024-08-20 17:00 | Labour charges for Concreting work (M15) for A & B-Bldg below Footing PCC Work & Screeding work. | 100 |  | 109990 | 2024-08-20 | 118843.44 | 1900-01-01 | 0 | SUPREME ENGINEERS
Concreting work (M) | N/C | N/C | MAHALAXMI BUILDCON | 7 | 2024-06-11 | Mass Concreting Work | 8.04 | 5229.76 | 0 | 42047.2704 | 7568.5 | 2024-08-20 17:01 | Material supply charges of Concrete M15 for A & B-Bldg Ground Floor Mass concreting work. | 100 |  | 109997 | 2024-08-20 | 59381.29 | 1900-01-01 | -17334.0196 | SUPREME ENGINEERS
Concreting work (M) | N/C | N/C | MAHALAXMI BUILDCON | 7 | 2024-06-11 | Mass Concreting Work | 2.13 | 6330.7 | 0 | 13484.391 | 2427.2 | 2024-08-20 17:01 | Material supply charges of Concrete M40 for A & B-Bldg Second Floor Mass concreting work. | 100 |  | 109997 | 2024-08-20 | 59381.29 | 1900-01-01 | -45896.899 | SUPREME ENGINEERS
Reinforcement (M) | N/C | N/C | MAHALAXMI BUILDCON | 7 | 2024-06-11 | Mass Concreting Work | 59.225 | 65 | 0 | 3849.625 | 692.94 | 2024-08-20 17:01 | Material supply charges of steel of required size for A & B-Bldg Ground Floor Mass concreting work. | 100 |  | 109997 | 2024-08-20 | 59381.29 | 1900-01-01 | -55531.665 | SUPREME ENGINEERS
RCC Work (M). | N/C | N/C | MAHALAXMI BUILDCON | 9 | 2024-06-17 | 2nd,3rd,4th Slab- RCC Work(M) | 17210.93 | 370 | 0 | 6368044.1 | 1146247.94 | 2024-08-20 17:41 | Material supply charges for all RCC Work for A-Bldg including shuttering, Reinforcement & Concrete with Material Procurement,Loading,Unloading,Transport,Mathadi,etc included. | 100 |  | 110000 | 2024-08-20 | 9539280.8 | 1900-01-01 | -3171236.7 | MAHALAXMI BUILDCON
RCC Work (M). | N/C | N/C | MAHALAXMI BUILDCON | 9 | 2024-06-17 | 5th,6th,7th Slab- RCC Work(M) | 8570.91 | 370 | 0 | 3171236.7 | 570822.6 | 2024-08-20 17:41 | Material supply charges for all RCC Work for A-Bldg including shuttering, Reinforcement & Concrete with Material Procurement,Loading,Unloading,Transport,Mathadi,etc included. | 100 |  | 110000 | 2024-08-20 | 9539280.8 | 1900-01-01 | -6368044.1 | MAHALAXMI BUILDCON