## Work_Completion_Browse638600455
Work Completion Browse
Project : GANGA ALTUS
Labour : Toilet False Ceiling (M) - BC
Executed By : G M ENTERPRISES
From Date : 01/01/2024 To date: 01/01/2024
Page 1 of 1
Total Records: 62 Records 1 to 62
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:22 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1301-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1303-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1305-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1402-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:38 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1403-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:38 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1701-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1702-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1704-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1706-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1801-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 22.668 | 60 | 0 | 1360.08 | 244.82 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -235285.8 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1803-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1805-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1806-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1807-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1808-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1901-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1903-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1905-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1906-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1907-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-1908-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2001-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 16:33 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2002-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2004-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2005-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2006-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2007-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2008-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2101-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2103-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2104-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2105-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2106-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2107-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2108-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2201-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2202-2BHK(Near Refuse Area) Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2203-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2204-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2205-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2206-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232112.28 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2207-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2208-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-07-31 15:58 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109660 | 2024-08-07 | 236645.88 | 2024-08-08 11:16 | -232312.08 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2301-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -30936 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2302-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -30936 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2303-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -31135.8 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2304-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -31135.8 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2305-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -30936 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2306-3BHK Toilet False ceiling work | 75.56 | 60 | 0 | 4533.6 | 816.04 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -30936 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2307-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -31135.8 | G M ENTERPRISES
Toilet False Ceiling (M) - BC | N/C | N/C | RADHEYSHYAM YADAV | 450 | 2022-06-27 | D-2308-2BHK Toilet False ceiling work | 72.23 | 60 | 0 | 4333.8 | 780.08 | 2024-08-11 | Material Supply Charges for- Toilet Flase Ceiling work.Transporatation, Loading/Unloading of material to be done by Contractor. | 100 |  | 109799 | 2024-08-12 | 35469.6 | 1900-01-01 | -31135.8 | G M ENTERPRISES