## Work_Completion_Browse638600460
Work Completion Browse
Project : GANGA ALTUS
Labour : Toilet False Ceiling (L) BC
Executed By : G M ENTERPRISES
From Date : 01/01/2023 To date: 01/01/2023
Page 1 of 1
Total Records: 60 Records 1 to 60
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1402-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1403-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:33 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1701-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1702-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1703-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1704-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1706-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1801-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1802-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1803-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1805-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1806-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1807-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1808-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1901-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1903-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1905-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1906-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1907-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-1908-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2001-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 10:55 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2002-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2004-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2005-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2006-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2007-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2008-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 15:14 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2101-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2103-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2104-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2105-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2106-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2107-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2108-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2201-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2202-2BHK(Near Refuse Area) Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2203-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2204-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2205-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2206-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2207-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2208-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2301-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2302-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2303-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2304-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2305-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2306-3BHK Toilet False ceiling work | 60.448 | 15 | 0 | 906.72 | 163.2 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52377.6 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2307-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES
Toilet False Ceiling (L) BC | N/C | N/C | RADHEYSHYAM YADAV | 449 | 2022-06-27 | D-2308-2BHK Toilet False ceiling work | 57.784 | 15 | 0 | 866.76 | 156.02 | 2024-07-31 | Labour Charges for- Toilet False Ceiling work.Material to be shifted by contractor from site store to required place by own labour/ machine (no extra cost will be paid) | 100 |  | 109491 | 2024-08-05 | 53284.32 | 2024-08-08 11:16 | -52417.56 | G M ENTERPRISES