## Work_Completion_Browse638600993
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : R K INTERIOR
From Date : 20/08/2024 To date: 20/08/2024
Page 1 of 1
Total Records: 53 Records 1 to 53
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Living,Dining,Passa. Marble Tiling - 1 No. | 58.77 | 80 | 0 | 4701.6 | 846.28 | 2024-08-23 17:30 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Parents Bed Marble Tiling - 1 No. | 31.17 | 80 | 0 | 2493.6 | 448.84 | 2024-08-23 17:30 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Guest Bed Marble Tiling - 1 No. | 15.79 | 80 | 0 | 1263.2 | 227.38 | 2024-08-23 17:30 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2701 Master Bed Marble Tiling - 1 No. | 32.81 | 80 | 0 | 2624.8 | 472.46 | 2024-08-23 17:30 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2704 Guest Bed Marble Tiling-(No.) | 25.264 | 80 | 0 | 2021.12 | 363.8 | 2024-08-23 17:33 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2704 Living,Dining,Passa. Marble Tiling-(No.) | 93.008 | 80 | 0 | 7440.64 | 1339.32 | 2024-08-23 17:33 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2704 Master Bed Marble Tiling-(No.) | 45.936 | 80 | 0 | 3674.88 | 661.48 | 2024-08-23 17:33 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2704 Parents Bed Marble Tiling-(No.) | 34.384 | 80 | 0 | 2750.72 | 495.12 | 2024-08-23 17:33 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Guest Bed Marble Tiling-(No.) | 33.336 | 80 | 0 | 2666.88 | 480.04 | 2024-08-23 17:35 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Living,Dining,Passa. Marble Tiling-(No.) | 81.24 | 80 | 0 | 6499.2 | 1169.86 | 2024-08-23 17:35 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 1372 | 2022-05-07 | A 2903 Master Bed Marble Tiling-(No.) | 37.512 | 80 | 0 | 3000.96 | 540.18 | 2024-08-23 17:35 | Labour Charges for Italian marble Champher & Polish work for A Building internal flat. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Dry Balcony dado | 86.7 | 18 | 0 | 1560.6 | 280.9 | 2024-08-23 18:33 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Master Toilet dado | 42.22 | 18 | 0 | 759.96 | 136.8 | 2024-08-23 18:33 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Children Toilet dado | 145.22 | 18 | 0 | 2613.96 | 470.52 | 2024-08-23 18:33 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Powder Toilet dado | 25.57 | 18 | 0 | 460.26 | 82.84 | 2024-08-23 18:33 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Guest Toilet dado | 39.31 | 18 | 0 | 707.58 | 127.36 | 2024-08-23 18:33 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Dry Balcony dado | 54.29 | 18 | 0 | 977.22 | 175.9 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet dado | 148.12 | 18 | 0 | 2666.16 | 479.9 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet dado | 106.04 | 18 | 0 | 1908.72 | 343.56 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Dado | 44.44 | 18 | 0 | 799.92 | 143.98 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet dado | 97.36 | 18 | 0 | 1752.48 | 315.44 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Master Toilet dado | 18.72 | 20 | 0 | 374.4 | 67.4 | 2024-08-23 18:33 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Children Toilet dado | 66.72 | 20 | 0 | 1334.4 | 240.2 | 2024-08-23 18:33 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Powder Toilet dado | 11.79 | 20 | 0 | 235.8 | 42.44 | 2024-08-23 18:33 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Guest Toilet dado | 17.48 | 20 | 0 | 349.6 | 62.92 | 2024-08-23 18:33 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet dado | 67.78 | 20 | 0 | 1355.6 | 244 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet dado | 86.59 | 20 | 0 | 1731.8 | 311.72 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Dado | 20.57 | 20 | 0 | 411.4 | 74.06 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet dado | 38.86 | 20 | 0 | 777.2 | 139.9 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Staff Toilet dado | 135.37 | 17 | 0 | 2301.29 | 414.24 | 2024-08-23 18:33 | 600 x 300 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Toilet dado | 135.37 | 17 | 0 | 2301.29 | 414.24 | 2024-08-24 12:24 | 600 x 300 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Kitchen Vitrified Flooring | 30.44 | 20 | 0 | 608.8 | 109.58 | 2024-08-24 11:57 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Terrace Vitrified Flooring | 32.07 | 20 | 0 | 641.4 | 115.46 | 2024-08-24 11:57 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Master Bed Marble Flooring | 40.58 | 50 | 0 | 2029 | 365.22 | 2024-08-24 12:06 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Living,Dining,Passa. Marble Flooring | 3.73 | 50 | 0 | 186.5 | 33.58 | 2024-08-24 12:18 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Guest Bed Marble Flooring | 7.43 | 50 | 0 | 371.5 | 66.88 | 2024-08-24 12:18 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Bed Marble Flooring | 0.85 | 50 | 0 | 42.5 | 7.66 | 2024-08-24 12:18 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Living,Dining,Passa. Marble Flooring | 5.39 | 50 | 0 | 269.5 | 48.52 | 2024-08-24 12:06 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Toilet & Dry Balcony Devider Patti | 10.02 | 50 | 0 | 501 | 90.18 | 2024-08-23 18:42 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Dry Balcony dado | 6.23 | 20 | 0 | 124.6 | 22.42 | 2024-08-23 18:33 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Master Toilet dado | 13.23 | 20 | 0 | 264.6 | 47.62 | 2024-08-23 18:33 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Children Toilet dado | 13.07 | 20 | 0 | 261.4 | 47.06 | 2024-08-23 18:33 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Powder Toilet dado | 2.74 | 20 | 0 | 54.8 | 9.86 | 2024-08-23 18:33 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Guest Toilet dado | 15.01 | 20 | 0 | 300.2 | 54.04 | 2024-08-23 18:33 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Staff Toilet dado | 24.67 | 20 | 0 | 493.4 | 88.82 | 2024-08-23 18:33 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Dry Balcony dado | 4.26 | 20 | 0 | 85.2 | 15.34 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet dado | 12.87 | 20 | 0 | 257.4 | 46.34 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet dado | 7.332 | 20 | 0 | 146.64 | 26.4 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Dado | 12.9 | 20 | 0 | 258 | 46.44 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet dado | 10.746 | 20 | 0 | 214.92 | 38.68 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Toilet dado | 24.37 | 20 | 0 | 487.4 | 87.74 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish.- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 703 Toilet & Dry Balcony Devider Patti | 30.03 | 40 | 0 | 1201.2 | 216.22 | 2024-08-23 18:42 | Dry Balcony & Toilets Divider Patti Italian Marble Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher & Polish | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 703 Toilet & Dry Balcony Devider Patti | 10.02 | 50 | 0 | 501 | 90.18 | 2024-08-23 18:42 | Dry Balcony & Toilets Divider Patti Italian Marble Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR