## Work_Completion_Browse638601089
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : R K INTERIOR
From Date : 24/08/2024 To date: 24/08/2024
Page 1 of 1
Total Records: 88 Records 1 to 88
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Dry Balcony dado | 54.29 | 18 | 0 | 977.22 | 175.9 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet dado | 148.12 | 18 | 0 | 2666.16 | 479.9 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet dado | 106.04 | 18 | 0 | 1908.72 | 343.56 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Dado | 44.44 | 18 | 0 | 799.92 | 143.98 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet dado | 97.36 | 18 | 0 | 1752.48 | 315.44 | 2024-08-24 12:24 | 600 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet dado | 67.78 | 20 | 0 | 1355.6 | 244 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet dado | 86.59 | 20 | 0 | 1731.8 | 311.72 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Dado | 20.57 | 20 | 0 | 411.4 | 74.06 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet dado | 38.86 | 20 | 0 | 777.2 | 139.9 | 2024-08-24 12:24 | 1200 x 600 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Dado BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Toilet dado | 135.37 | 17 | 0 | 2301.29 | 414.24 | 2024-08-24 12:24 | 600 x 300 Dado Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Kitchen Vitrified Flooring | 30.44 | 20 | 0 | 608.8 | 109.58 | 2024-08-24 11:57 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Terrace Vitrified Flooring | 32.07 | 20 | 0 | 641.4 | 115.46 | 2024-08-24 11:57 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Kitchen Vitrified Flooring | 40.54 | 20 | 0 | 810.8 | 145.94 | 2024-08-24 12:44 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Terrace Vitrified Flooring | 28.88 | 20 | 0 | 577.6 | 103.96 | 2024-08-24 12:44 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Terrace Vitrified Flooring | 18.07 | 20 | 0 | 361.4 | 65.06 | 2024-08-24 14:47 | 1200 x 800 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Dry Balcony Vitrified Flooring | 0.44 | 17 | 0 | 7.48 | 1.34 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet Vitrified Flooring | 51.66 | 17 | 0 | 878.22 | 158.08 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Vitrified Flooring | 51.67 | 17 | 0 | 878.39 | 158.12 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet Vitrified Flooring | 43.59 | 17 | 0 | 741.03 | 133.38 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet Vitrified Flooring | 47.9 | 17 | 0 | 814.3 | 146.58 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Toilet Vitrified Flooring | 0.14 | 17 | 0 | 2.38 | 0.42 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Room Vitrified Flooring | 0.85 | 17 | 0 | 14.45 | 2.6 | 2024-08-24 12:44 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Dry Balcony Vitrified Flooring | 38.32 | 17 | 0 | 651.44 | 117.26 | 2024-08-24 14:47 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Master Toilet Vitrified Flooring | 8.81 | 17 | 0 | 149.77 | 26.96 | 2024-08-24 14:47 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Children Toilet Vitrified Flooring | 8.81 | 17 | 0 | 149.77 | 26.96 | 2024-08-24 14:47 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Powder Toilet Vitrified Flooring | 25.03 | 17 | 0 | 425.51 | 76.6 | 2024-08-24 14:47 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Guest Toilet Vitrified Flooring | 4.171 | 17 | 0 | 70.907 | 12.76 | 2024-08-24 14:47 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Staff Room Vitrified Flooring | 71.69 | 17 | 0 | 1218.73 | 219.38 | 2024-08-24 14:47 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash (L | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Kitchen Vitrified Flooring | 44.94 | 20 | 0 | 898.8 | 161.78 | 2024-08-24 12:44 | 1200 x 800 Vitrified Skirting | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Terrace Vitrified Flooring | 22.98 | 20 | 0 | 459.6 | 82.72 | 2024-08-24 12:44 | 1200 x 800 Vitrified Skirting | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Terrace Vitrified Flooring | 4.57 | 20 | 0 | 91.4 | 16.46 | 2024-08-24 14:47 | 1200 x 800 Vitrified Skirting | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Room Vitrified Flooring | 17.71 | 17 | 0 | 301.07 | 54.2 | 2024-08-24 12:44 | 600 x 600 Vitrified Skirting (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Staff Room Vitrified Flooring | 31.16 | 17 | 0 | 529.72 | 95.34 | 2024-08-24 14:47 | 600 x 600 Vitrified Skirting (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Master Bed Marble Flooring | 40.58 | 50 | 0 | 2029 | 365.22 | 2024-08-24 12:06 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Living,Dining,Passa. Marble Flooring | 3.73 | 50 | 0 | 186.5 | 33.58 | 2024-08-24 12:18 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Guest Bed Marble Flooring | 7.43 | 50 | 0 | 371.5 | 66.88 | 2024-08-24 12:18 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Flooring - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Bed Marble Flooring | 0.85 | 50 | 0 | 42.5 | 7.66 | 2024-08-24 12:18 | Italian Marble Flooring Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 703 Living,Dining,Passa. Marble Flooring | 5.39 | 50 | 0 | 269.5 | 48.52 | 2024-08-24 12:06 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Living,Dining,Passa. Marble Flooring | 25.3875 | 50 | 0 | 1269.375 | 228.48 | 2024-08-24 14:02 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Master Bed Marble Flooring | 11.7225 | 50 | 0 | 586.125 | 105.5 | 2024-08-24 14:02 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Guest Bed Marble Flooring | 10.4175 | 50 | 0 | 520.875 | 93.76 | 2024-08-24 14:02 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Toilet & Dry Balcony Devider Patti | 20.01 | 50 | 0 | 1000.5 | 180.1 | 2024-08-24 14:45 | Italian Marble Divider Patti Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Dry Balcony dado | 4.26 | 20 | 0 | 85.2 | 15.34 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Master Toilet dado | 12.87 | 20 | 0 | 257.4 | 46.34 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet dado | 7.332 | 20 | 0 | 146.64 | 26.4 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Dado | 12.9 | 20 | 0 | 258 | 46.44 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Powder Toilet dado | 10.746 | 20 | 0 | 214.92 | 38.68 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
L Groove - BCV | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Staff Toilet dado | 24.37 | 20 | 0 | 487.4 | 87.74 | 2024-08-24 12:24 | Dado L Groove in Vitrified Tile | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Parents Toilet Counter wash Basin | 0.23 | 700 | 0 | 161 | 28.98 | 2024-08-24 12:36 | Italian Marble Counter Shifting,Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 704 Children Toilet Counter wash Basin | 0.21 | 700 | 0 | 147 | 26.46 | 2024-08-24 12:36 | Italian Marble Counter Shifting,Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Guest Toilet Counter wash Basin | 5.05 | 700 | 0 | 3535 | 636.3 | 2024-08-24 14:38 | Italian Marble Counter Shifting,Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Master Toilet Counter wash Basin | 5.52 | 700 | 0 | 3864 | 695.52 | 2024-08-24 14:38 | Italian Marble Counter Shifting,Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Children Toilet Counter wash Basin | 5.51 | 700 | 0 | 3857 | 694.26 | 2024-08-24 14:38 | Italian Marble Counter Shifting,Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | 551 | 2019-04-26 | A 803 Powder Toilet Counter wash Basin | 5.41 | 700 | 0 | 3787 | 681.66 | 2024-08-24 14:38 | Italian Marble Counter Shifting,Cutting & Fixing (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Parents Toilet Counter wash Basin | 4.66 | 40 | 0 | 186.4 | 33.56 | 2024-08-24 12:36 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Master Toilet Counter wash Basin | 5.66 | 40 | 0 | 226.4 | 40.76 | 2024-08-24 12:36 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Children Toilet Counter wash Basin | 5.66 | 40 | 0 | 226.4 | 40.76 | 2024-08-24 12:36 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Powder Toilet Counter wash Basin | 3.5 | 40 | 0 | 140 | 25.2 | 2024-08-24 12:36 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Guest Toilet Counter wash Basin | 5.08 | 40 | 0 | 203.2 | 36.58 | 2024-08-24 14:38 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Master Toilet Counter wash Basin | 5.66 | 40 | 0 | 226.4 | 40.76 | 2024-08-24 14:38 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Children Toilet Counter wash Basin | 5.66 | 40 | 0 | 226.4 | 40.76 | 2024-08-24 14:38 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Border-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Powder Toilet Counter wash Basin | 5 | 40 | 0 | 200 | 36 | 2024-08-24 14:38 | Wash Basin Counter Border / Facia Patti (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Parents Toilet Counter wash Basin | 4.66 | 50 | 0 | 233 | 41.94 | 2024-08-24 12:36 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Master Toilet Counter wash Basin | 5.66 | 50 | 0 | 283 | 50.94 | 2024-08-24 12:36 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Children Toilet Counter wash Basin | 5.66 | 50 | 0 | 283 | 50.94 | 2024-08-24 12:36 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Powder Toilet Counter wash Basin | 3.5 | 50 | 0 | 175 | 31.5 | 2024-08-24 12:36 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Guest Toilet Counter wash Basin | 5.08 | 50 | 0 | 254 | 45.72 | 2024-08-24 14:38 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Master Toilet Counter wash Basin | 5.66 | 50 | 0 | 283 | 50.94 | 2024-08-24 14:38 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Children Toilet Counter wash Basin | 5.66 | 50 | 0 | 283 | 50.94 | 2024-08-24 14:38 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Zero Joint-BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Powder Toilet Counter wash Basin | 5 | 50 | 0 | 250 | 45 | 2024-08-24 14:38 | Wash Basin Counter Zero Joint (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Parents Toilet Counter wash Basin | 3.23 | 40 | 0 | 129.2 | 23.26 | 2024-08-24 12:36 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Master Toilet Counter wash Basin | 6.06 | 40 | 0 | 242.4 | 43.64 | 2024-08-24 12:36 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Children Toilet Counter wash Basin | 6.06 | 40 | 0 | 242.4 | 43.64 | 2024-08-24 12:36 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Powder Toilet Counter wash Basin | 2.35 | 40 | 0 | 94 | 16.92 | 2024-08-24 12:36 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Guest Toilet Counter wash Basin | 5.09 | 40 | 0 | 203.6 | 36.64 | 2024-08-24 14:38 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Master Toilet Counter wash Basin | 6.06 | 40 | 0 | 242.4 | 43.64 | 2024-08-24 14:38 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Children Toilet Counter wash Basin | 6.06 | 40 | 0 | 242.4 | 43.64 | 2024-08-24 14:38 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Mirror Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Powder Toilet Counter wash Basin | 5.65 | 40 | 0 | 226 | 40.68 | 2024-08-24 14:38 | Wash Basin Counter Mirror Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Parents Toilet Counter wash Basin | 4.66 | 25 | 0 | 116.5 | 20.98 | 2024-08-24 12:36 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Master Toilet Counter wash Basin | 5.66 | 25 | 0 | 141.5 | 25.48 | 2024-08-24 12:36 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Children Toilet Counter wash Basin | 5.66 | 25 | 0 | 141.5 | 25.48 | 2024-08-24 12:36 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 704 Powder Toilet Counter wash Basin | 3.5 | 25 | 0 | 87.5 | 15.76 | 2024-08-24 12:36 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Guest Toilet Counter wash Basin | 5.08 | 25 | 0 | 127 | 22.86 | 2024-08-24 14:38 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Master Toilet Counter wash Basin | 5.66 | 25 | 0 | 141.5 | 25.48 | 2024-08-24 14:38 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Children Toilet Counter wash Basin | 5.66 | 25 | 0 | 141.5 | 25.48 | 2024-08-24 14:38 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Edge Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Powder Toilet Counter wash Basin | 5 | 25 | 0 | 125 | 22.5 | 2024-08-24 14:38 | Wash Basin Counter Edge Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Guest Toilet Counter wash Basin | 5.5 | 50 | 0 | 275 | 49.5 | 2024-08-24 14:38 | Wash Basin Counter Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR
Italian Marble Champher Polish- BCo | N/C | N/C | R K INTERIOR | 641 | 2019-09-30 | A 803 Children Toilet Counter wash Basin | 5.5 | 50 | 0 | 275 | 49.5 | 2024-08-24 14:38 | Wash Basin Counter Champher & Polish (L) | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | R K INTERIOR