## Work_Completion_Browse638602762
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : RISHIPRASAD ENTERPRISES
From Date : 12/08/2024 To date: 12/08/2024
Page 1 of 1
Total Records: 22 Records 1 to 22
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 12:14 | Labour Charges for Touch up lambi work for internal flat series 2 painting work. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 12:14 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
Touch up Lambi | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 15:42 | Labour Charges for Touch up lambi work for internal flat series 2 painting work. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 15:42 | Labour Charges for Applying of Astar coat for internal walls of Flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Astar Coat | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 12:14 | Labour Charges for Applying of Astar coat for internal walls of Flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 12:14 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 12:14 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
Sanding Gattu (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 0.5 | 0 | 1469.7 | 264.54 | 2024-08-19 15:42 | Labour Charges for applying of Sanding Gattu for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44188.59 | RISHIPRASAD ENTERPRISES
Oil base Primer-BC | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Labour Charges for Applying Oil Base primer for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
Oil base Primer-BC | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 12:14 | Labour Charges for Applying Oil Base primer for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1300 | 1 | 0 | 1300 | 234 | 2024-08-19 12:14 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44358.29 | RISHIPRASAD ENTERPRISES
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1300.077 | 1 | 0 | 1300.077 | 234.02 | 2024-08-19 15:42 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44358.213 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Walls Satin Matt Painting | 2645.49 | 1.5 | 0 | 3968.235 | 714.28 | 2024-08-19 12:14 | Labour Charges for Applying of 1st coat Satin matt paint for internal walls of flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for brush Cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -41690.055 | RISHIPRASAD ENTERPRISES
1st Coat Satin Matt Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2645.46 | 1.5 | 0 | 3968.19 | 714.28 | 2024-08-19 15:42 | Labour Charges for Applying of 1st coat Satin matt paint for internal walls of flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for brush Cleaning. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -41690.1 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 602 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 12:14 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
Water Base Primer | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Ceiling Premium Emulsion Painting | 1444.53 | 1 | 0 | 1444.53 | 260.02 | 2024-08-19 15:42 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 2. | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -44213.76 | RISHIPRASAD ENTERPRISES
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A-Bldg 3002 Walls Satin Matt Painting | 2939.4 | 1 | 0 | 2939.4 | 529.1 | 2024-08-19 15:42 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 2 | 100 |  | 109969 | 2024-08-19 | 45658.29 | 1900-01-01 | -42718.89 | RISHIPRASAD ENTERPRISES