## Work_Completion_Browse638602877
Work Completion Browse
Project : GANGA DHAM TOWERS
From Date : 22/08/2024 To date: 22/08/2024
Page 1 of 1
Total Records: 78 Records 1 to 78
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 1st Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1.5 | 0 | 300.465 | 54.08 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19238.805 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1.5 | 0 | 260.88 | 46.96 | 2024-08-22 | Labour Charges for- 2nd Coat Acrylic Paint with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19278.39 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19338.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (L) | N/C | N/C | GODAVARI PAINT PVT LTD | 1199 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Labour Charges for- Water Base Primer with Saffolding/ Gandola | 100 |  | 110076 | 2024-08-26 | 19539.27 | 1900-01-01 | -19365.35 | SAI NIRMAL COLOURS & TEXTURES