## Work_Completion_Browse638602884
Work Completion Browse
Project : GANGA DHAM TOWERS
From Date : 22/08/2024 To date: 22/08/2024
Page 1 of 1
Total Records: 78 Records 1 to 78
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 2 | 0 | 400.62 | 72.12 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26475.65 | SAI NIRMAL COLOURS & TEXTURES
1st Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 2 | 0 | 347.84 | 62.62 | 2024-08-22 | Material Supply for- 1st Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26528.43 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 25th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 26th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 2nd Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 3rd Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 4th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 5th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 6th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 7th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 8th Floor Texture Painting | 200.31 | 1 | 0 | 200.31 | 36.06 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26675.96 | SAI NIRMAL COLOURS & TEXTURES
Water Base Primer (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 9th Floor Texture Painting | 173.92 | 1 | 0 | 173.92 | 31.3 | 2024-08-22 | Material Supply For- Water Base Primerr | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26702.35 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 10th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 11th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 12th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 13th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 14th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 15th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 16th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 17th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 18th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 19th Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 1st Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 20th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 21st Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 22nd Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 23rd Floor Texture Painting | 173.92 | 2.5 | 0 | 434.8 | 78.26 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26441.47 | SAI NIRMAL COLOURS & TEXTURES
2nd Coat Acrylic Paint (M) | N/C | N/C | GODAVARI PAINT PVT LTD | 1200 | 2021-11-13 | B Eastside 24th Floor Texture Painting | 200.31 | 2.5 | 0 | 500.775 | 90.14 | 2024-08-22 | Material Supply for- 2nd Coat Acrylic Paint | 100 |  | 110077 | 2024-08-26 | 26876.27 | 1900-01-01 | -26375.495 | SAI NIRMAL COLOURS & TEXTURES