## Work_Completion_Browse638603537
Work Completion Browse
Project : GANGA ALTUS
Contractor : SFS FIRE PROTECTION INDIA PRIVATE LIMITED
From Date : 27/07/2024 To date: 27/07/2024
Page 1 of 1
Total Records: 31 Records 1 to 31
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Miscellaneous Expenses | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 1068 | 2024-08-07 | Fire Fighting Misc.Work - F Bulding | 1 | 175000 | 0 | 175000 | 0 | 2024-08-07 | Charges for Miscellaneous fire fighting work | 100 |  | 109667 | 2024-08-07 | 175000 | 2024-08-07 14:06 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Side Wall Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 60 | 350 | 0 | 14700 | 2646 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -239470 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Upright Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 338 | 450 | 0 | 106470 | 19164.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -147700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pendent Sprinkler (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 500 | 380 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/7/2024 | 109434 | 2024-07-29 | 254170 | 1900-01-01 | -121170 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 100mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 300 | 1450 | 0 | 304500 | 54810 | 2024-08-23 | Against Material Supply | 70 | Challan No-18884 DT 23.08.2024 | 110112 | 2024-08-26 | 583800 | 1900-01-01 | -279300 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 25mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 600 | 350 | 0 | 147000 | 26460 | 2024-08-23 | Against Material Supply | 70 | Challan No-18884 DT 23.08.2024 | 110112 | 2024-08-26 | 583800 | 1900-01-01 | -436800 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 100 | 500 | 0 | 35000 | 6300 | 2024-08-23 | Against Material Supply | 70 | Challan No-18884 DT 23.08.2024 | 110112 | 2024-08-26 | 583800 | 1900-01-01 | -548800 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 40mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 200 | 500 | 0 | 70000 | 12600 | 2024-08-23 | Against Material Supply | 70 | Challan No-18884 DT 23.08.2024 | 110112 | 2024-08-26 | 583800 | 1900-01-01 | -513800 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | D-Building Automatic Sprinkler System | 40 | 650 | 0 | 18200 | 3276 | 2024-08-23 | Against Material Supply | 70 | Challan No-18884 DT 23.08.2024 | 110112 | 2024-08-26 | 583800 | 1900-01-01 | -565600 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 50mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 590 | 2022-12-14 | Parking Parking Fl -Automatic Sprinkler System | 20 | 650 | 0 | 9100 | 1638 | 2024-08-23 | Against Material Supply | 70 | Challan No-18884 DT 23.08.2024 | 110112 | 2024-08-26 | 583800 | 1900-01-01 | -574700 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 20 | 350 | 0 | 4900 | 882 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 TOTAL RECEIVED-20 MTRS | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 50 | 95 | 0 | 3325 | 598.5 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 TOTAL RECEIVED-200 mtrs | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 150 | 95 | 0 | 9975 | 1795.5 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 TOTAL RECEIVED-200 mtrs | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 40 | 1150 | 0 | 32200 | 5796 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 TOTAL RECEIVED-60 MTRS | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 20 | 1150 | 0 | 16100 | 2898 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT Challan No-18896 DT 26.08.2024 TOTAL RECEIVED-60 MTRS | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 40 | 2950 | 0 | 82600 | 14868 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 WO QTY-40 MTRS RECEIVED 60 MTRS.BALANCE 10 MTRS. | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 10 | 2950 | 0 | 20650 | 3717 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 WO QTY-40 MTRS RECEIVED 60 MTRS.BALANCE 10 MTRS. | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Rate Diff. Control Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 290000 | 0 | 203000 | 36540 | 2024-08-21 | Against Material Supply | 70 | Challan No-18786 DT 16.08.2024 | 110134 | 2024-08-26 | 203000 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Control Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 410000 | 0 | 287000 | 51660 | 2024-08-19 | Against Material Supply | 70 | Challan No-18786 DT 16.08.2024 | 109926 | 2024-08-19 | 287000 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Pressure Guage 100mm (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 8 | 3200 | 0 | 17920 | 3225.6 | 2024-07-29 | Against Material Supply | 70 | Challan No-18613 DT 18/07/2024 | 109433 | 2024-07-29 | 20300 | 2024-08-08 11:24 | -2380 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI- 200mm Dia. Heavy Grade Pipe (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 635 | 2023-03-10 | Pumproom Fire Equipment - 1 No. | 1 | 3400 | 0 | 2380 | 428.4 | 2024-07-29 | Against Material Supply | 70 | Total Challan Qty-30 Mtrs. RA Bill Released Qty-29 Mtrs(RA-108232 Challan No-18352 (Amendment Qty 1 Mtrs released from this Completion) | 109433 | 2024-07-29 | 20300 | 2024-08-08 11:24 | -17920 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Sprinkler 15mm 68 dg Upright (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 30 | 450 | 0 | 9450 | 1701 | 2024-07-29 | Against Material Supply | 70 | Challan No-18668 DT 27/07/2024 Total Received-400 -We have released 338 Nos from D Building Remaining Qty released from F Building (Balance for amendment 32 Nos) | 109419 | 2024-07-29 | 40950 | 2024-08-08 11:26 | -31500 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Fire Repeater Panel (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 1 | 45000 | 0 | 31500 | 5670 | 2024-07-29 | Against Material Supply | 70 | Challan No-18179 DT 27/7/2024 | 109419 | 2024-07-29 | 40950 | 2024-08-08 11:26 | -9450 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm Armoured cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Building Fire Alarm System Work | 200 | 80 | 0 | 11200 | 2016 | 2024-08-26 | Against Material Supply | 70 | Challan No-18896 DT 26.08.2024 TOTAL RECEIVED-200 MTRS | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
SITC GI Pipe C Class 65mm dia.(M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 688 | 2023-06-02 | F-Supply & Installation of Fire Hydrant System | 60 | 800 | 0 | 33600 | 6048 | 2024-08-23 | After Installation & Pressure Testing | 70 | Challan No-18884 DT 23.08.2024 | 110116 | 2024-08-26 | 33600 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
Network Active Repeater (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 1 | 42500 | 0 | 29750 | 5355 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27/07/2024 | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -238000 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
20 Watt Cabinet Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 76 | 2500 | 0 | 133000 | 23940 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27.07.2024 Total Received-78 Nos. 2 Balnace Relesed from E Building. | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -134750 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 core x 1.5 sqmm Armoured cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-PA System | 1000 | 75 | 0 | 52500 | 9450 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024 | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -215250 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 Core x 1.5 Sqmm FRLS Armd. cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FAS System | 955 | 75 | 0 | 50137.5 | 9024.76 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024. | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -217612.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
2 Core x 1.5 Sqmm FRLS Armd. cable (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 913 | 2024-01-20 | D Bldg.-FFT System | 45 | 75 | 0 | 2362.5 | 425.26 | 2024-07-29 | Against Material Supply | 70 | Challan No-18602 DT16/07/2024. | 109418 | 2024-07-29 | 267750 | 2024-08-08 11:26 | -265387.5 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED
20 Watt Cabinet Speakers (M) | N/C | N/C | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | 916 | 2024-01-27 | E Bldg.-PA System | 2 | 2500 | 0 | 3500 | 630 | 2024-07-29 | Against Material Supply | 70 | Challan No-18667 DT 27.07.2024 Total Received-78 Nos. 2 Balnace Relesed from E Building.Amendment Needed. | 109834 | 2024-08-12 | 3500 | 1900-01-01 | 0 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED