## Work_Completion_Browse638603539
Work Completion Browse
Project : GANGA ARCADIA - A BUILDING
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 23 Records 1 to 23
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Fabrication work (L) | N/C | N/C | R.T.S. STEEL SERVICES | 14 | 2021-12-09 | Fabrication Work for site barrication | 230 | 17 | 0 | 3910 | 0 | 2024-08-24 | Fabrication work for Site Barrication. | 100 |  | 110040 | 2024-08-26 | 3910 | 1900-01-01 | 0 | SURESH RANGNATH SHITOLE
Footing & Column | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Footing & Column | 1225 | 80 | 0 | 98000 | 16380 | 2024-08-08 13:57 | Charges for Footing and Column work for A-Bldg Sub structure area. | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -231550 | ROHIT CONSTRUCTION
RCC Beam | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Plinth Beam | 1225 | 70 | 0 | 85750 | 15435 | 2024-08-08 13:57 | Charges for Plinth Beam work for A-Bldg Sub structure area. | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -243800 | ROHIT CONSTRUCTION
Soling & PCC | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Soling & PCC | 1225 | 60 | 0 | 73500 | 13230 | 2024-08-08 13:57 | Charges for Soling and PCC Work for A-Bldg Sub structure area. | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -256050 | ROHIT CONSTRUCTION
Shuttering Work-Mkt | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Raft & Retaining Wall-(External)-RCC Work(L) | 10 | 600 | 0 | 6000 | 1080 | 2024-08-08 18:59 | Labour charges for Shuttering work of Retaining wall Raft wall for Tower A . | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -323550 | ROHIT CONSTRUCTION
Shuttering Work-Mkt | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Raft & Retaining Wall-(External)-RCC Work(L) | 76 | 600 | 0 | 45600 | 8208 | 2024-08-08 18:59 | Labour charges for Shuttering work of Retaining wall for Tower A . | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -283950 | ROHIT CONSTRUCTION
Concreting DPo | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Raft & Retaining Wall-(External)-RCC Work(L) | 5 | 300 | 0 | 1500 | 270 | 2024-08-08 18:59 | Labour charges for Concreting work of Retaining wall Raft for Tower A . | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -328050 | ROHIT CONSTRUCTION
Concreting DPo | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Raft & Retaining Wall-(External)-RCC Work(L) | 8 | 300 | 0 | 2400 | 432 | 2024-08-08 18:59 | Labour charges for Concreting work of Retaining wall for Tower A . | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -327150 | ROHIT CONSTRUCTION
Reinforcement BC | No category | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Raft & Retaining Wall-(External)-RCC Work(L) | 600 | 8 | 0 | 4800 | 864 | 2024-08-08 18:59 | Labour charges for Reinforcement work of Retaining wall Raft wall for Tower A . | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -324750 | ROHIT CONSTRUCTION
Reinforcement BC | No category | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A-Raft & Retaining Wall-(External)-RCC Work(L) | 1500 | 8 | 0 | 12000 | 2160 | 2024-08-08 18:59 | Labour charges for Reinforcement work of Retaining wall for Tower A . | 100 |  | 109910 | 2024-08-19 | 329550 | 1900-01-01 | -317550 | ROHIT CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | ROHIT CONSTRUCTION | 25 | 2023-03-23 | A - Ground Floor RCC - 1st Slab BUA (L) | 2880 | 135 | 0 | 388800 | 69984 | 2024-08-23 13:11 | Labour charges for Slab Shuttering, Reinforcement and Concreting work for Slab, Beam, Staircase and all Shear walls. | 100 |  | 110039 | 2024-08-26 | 388800 | 1900-01-01 | 0 | ROHIT CONSTRUCTION
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.6989 | 45000 | -0.5 | 31450.5 | 0 | 2024-08-07 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109669 | 2024-08-07 | 31450 | 1900-01-01 | 0.5 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.0098 | 45000 | -1 | 441 | 0 | 2024-08-23 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 110013 | 2024-08-23 | 440 | 2024-08-23 16:49 | 1 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.0098 | 45000 | -1 | 441 | 0 | 2024-08-23 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 110014 | 2024-08-23 | 440 | 2024-08-23 16:49 | 1 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.1102 | 45000 | 1 | 4959 | 0 | 2024-08-23 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 110015 | 2024-08-23 | 4960 | 2024-08-23 16:49 | -1 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.0116 | 45000 | -2 | 522 | 0 | 2024-08-23 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 110016 | 2024-08-23 | 520 | 2024-08-23 16:49 | 2 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 58 | 2023-12-09 | Arcadia- Electricity Bill | 0.7047 | 45000 | -1.5 | 31711.5 | 0 | 2024-08-16 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109878 | 2024-08-16 | 31710 | 2024-08-16 17:25 | 1.5 | MSEDCL
RCC Slab- cc | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | Pump Room - RCC Work (L) | 269 | 190 | 0 | 51110 | 9199.8 | 2024-08-08 19:07 | Labour charges for RCC Work for Slab at STP & UGWT Pumproom including Shuttering, Reinforcement & Concreting work. | 100 |  | 109911 | 2024-08-19 | 250265.43 | 1900-01-01 | -199155.43 | ROHIT CONSTRUCTION
UGWT Labour | N/C | N/C | ROHIT CONSTRUCTION | 85 | 2024-05-27 | UGWT- RCC Work (L) | 133886 | 4.25 | 0 | 199155.425 | 35847.98 | 2024-08-08 19:18 | RCC Work for Top Slab | 35 |  | 109911 | 2024-08-19 | 250265.43 | 1900-01-01 | -51110.005 | ROHIT CONSTRUCTION
Murum Filling (avail earth in site) | N/C | N/C | SHIVAM ENTERPRISES | 93 | 2024-07-23 | Murum Filling Work | 2854 | 60 | 0 | 171240 | 0 | 2024-08-08 13:02 | Charges for Murum Filling work with available earth at site including loading, unloading including all leads and lifts, stacking and spreading with all tool, Equipments & machinery. Ensuring all required safety precautions etc. | 100 |  | 109683 | 2024-08-09 | 302220 | 2024-08-19 13:58 | -130980 | SHIVAM ENTERPRISES
Murum Filling (avail earth in site) | N/C | N/C | SHIVAM ENTERPRISES | 93 | 2024-07-23 | Murum Filling Work | 504 | 60 | 0 | 30240 | 0 | 2024-08-08 19:22 | Charges for Murum Filling work with available earth at site including loading, unloading including all leads and lifts, stacking and spreading with all tool, Equipments & machinery. Ensuring all required safety precautions etc. for STP,UGWT,Pumproom. | 100 |  | 109683 | 2024-08-09 | 302220 | 2024-08-19 13:58 | -271980 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 93 | 2024-07-23 | Murum Filling Work | 2854 | 30 | 0 | 85620 | 0 | 2024-08-08 13:02 | Murum Spreading & Levelling work with available / dumped earth material including Lifting, shifting & unloading at requird Place including all leads and lifts, stacking and spreading with all tool, Equipments etc. for all Building area | 100 |  | 109683 | 2024-08-09 | 302220 | 2024-08-19 13:58 | -216600 | SHIVAM ENTERPRISES
Spreading & Levelling Work | N/C | N/C | SHIVAM ENTERPRISES | 93 | 2024-07-23 | Murum Filling Work | 504 | 30 | 0 | 15120 | 0 | 2024-08-08 13:02 | Murum Spreading & Levelling work with available / dumped earth material including Lifting, shifting & unloading at requird Place including all leads and lifts, stacking and spreading with all tool, Equipments etc. for STP, UGWT & Pumproom. | 100 |  | 109683 | 2024-08-09 | 302220 | 2024-08-19 13:58 | -287100 | SHIVAM ENTERPRISES