## Work_Completion_Browse638603540
Work Completion Browse
Project : SRA MORWADI
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 161 Records 1 to 161
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Concrete Floater | N/C | N/C | JAI SAIRAM CONSTRUCTION | 107 | 2024-05-11 | A Building 2nd Slab Trimix Floater work | 169.12 | 8 | 0 | 1352.96 | 243.54 | 2024-08-17 | Charges for Slab Trimix work by Floater Machine and Brush | 100 |  | 109890 | 2024-08-19 | 1352.96 | 1900-01-01 | 0 | JAI SAIRAM CONSTRUCTION
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 302 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 303 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 304 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 305 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 306 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 307 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 308 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Flat No 301 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 309 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 310 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 311 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 312 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 313 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A.Flat No 314 Electrical Work (L) | 1 | 8250 | 0 | 2475 | 0 | 2024-08-24 | Conduiting work for RCC Shear wall & Slab | 30 |  | 110163 | 2024-08-26 | 34650 | 1900-01-01 | -32175 | TAHA ELECTRICALS
Light Point - DSP | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-2nd SLAB ELECTRICAL WORK | 57 | 250 | 0 | 4275 | 0 | 2024-08-19 | Conducting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -16500 | TAHA ELECTRICALS
Light Point - DSP | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-3rd SLAB ELECTRICAL WORK | 59 | 250 | 0 | 4425 | 0 | 2024-08-19 | Conducting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -16350 | TAHA ELECTRICALS
Light Point - DSP | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-SHOP LOBBY ELECTRICAL WORK | 20 | 250 | 0 | 1500 | 0 | 2024-08-19 | Conducting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -19275 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 1 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 10 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 11 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 12 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 13 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 14 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 15 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 16 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 17 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 18 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 19 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 2 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 20 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 21 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 22 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 23 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 24 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 25 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 26 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 27 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 28 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 29 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 3 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 30 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 31 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 32 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 33 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 34 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 35 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 36 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 51 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 52 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 53 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 54 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 55 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 56 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 57 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 58 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 59 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 6 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 60 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 61 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 62 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 63 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 7 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 8 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 113 | 2024-05-18 | A-Shop No 9 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall and Slab | 30 |  | 109939 | 2024-08-19 | 20775 | 1900-01-01 | -20550 | TAHA ELECTRICALS
Mobile Toilet Fixing | N/C | N/C | SHAFIK SHAIKH | 116 | 2024-05-20 | Phase 2 Labour Camp Room Fabrication,FRP toilet fixing Work | 2 | 4500 | 0 | 9000 | 0 | 2024-08-23 | Charges for FRP Toilet Fixing for Labour Camp for Phase -2. | 100 |  | 110026 | 2024-08-26 | 31800 | 1900-01-01 | -22800 | SHAFIK SHAIKH
Concrete Foundation - Dld | N/C | N/C | SHAFIK SHAIKH | 116 | 2024-05-20 | Phase 2 Labour Camp Room Fabrication,FRP toilet fixing Work | 0.76 | 30000 | 0 | 22800 | 0 | 2024-08-23 | Charges for Foundation work (12ft x 7 ft x 4ft ) for Drinking Water Tank (2 Tank-10000 litres each) i.e., PCC, Masonry, Foundation, Plumbing & Plaster work for Phase-2 Labour Camp. | 100 |  | 110026 | 2024-08-26 | 31800 | 1900-01-01 | -9000 | SHAFIK SHAIKH
Barrication work (L) | N/C | N/C | SHAFIK SHAIKH | 116 | 2024-05-20 | Plot Barrication & Gate Fixing | 1295 | 20 | 0 | 25900 | 0 | 2024-08-12 | Charges for Plot Barrication work with Pit Excavation, Plum Concrete, Cement, Sand, Metal& Rubble, ISMC 100MM, Horizontal MS Square Tube (40 x 40 x2mm) with Red Oxide GI Sheet 10feet x 3.5feet with self tapping Screw. | 100 |  | 109815 | 2024-08-12 | 30860 | 1900-01-01 | -4960 | SHAFIK SHAIKH
Fabrication work (L) | N/C | N/C | SHAFIK SHAIKH | 116 | 2024-05-20 | Plot Barrication & Gate Fixing | 200 | 20 | 0 | 4000 | 0 | 2024-08-12 | Labour charges for Fabrication work of Main Entrance Gate with Wicket Gate with Pit Excavation, Plum Concrete, Cement, Sand, Metal & Rubble, ISMC 100MM,Horizontal Square tube 40 x 40x 2mm, with Red Oxide GI Sheet12ft x3.5ft. | 100 |  | 109815 | 2024-08-12 | 30860 | 1900-01-01 | -26860 | SHAFIK SHAIKH
Fabrication work (L) | N/C | N/C | SHAFIK SHAIKH | 116 | 2024-05-20 | Plot Barrication & Gate Fixing | 48 | 20 | 0 | 960 | 0 | 2024-08-12 | Labour charges for Fabrication work of Main Entrance Gate with Wicket Gate with Pit Excavation, Plum Concrete,Cement, sand,Metal & Rubble,ISMC 100,Horizontal square Tube 40x40x2mm with Red oxide GI Sheet 12ft x 3.5ft. | 100 |  | 109815 | 2024-08-12 | 30860 | 1900-01-01 | -29900 | SHAFIK SHAIKH
Barrication work (M) | N/C | N/C | SHAFIK SHAIKH | 117 | 2024-05-20 | Plot Barrication & Gate Fixing | 1295 | 90 | 0 | 116550 | 0 | 2024-08-12 | Material Supply Charges for Plot Barrication work with Pit Excavation, Plum Concrete, Cement, Sand, Metal& Rubble, ISMC 100MM, Horizontal MS Square Tube (40 x 40 x2mm) with Red Oxide GI Sheet 10feet x 3.5feet with self tapping Screw. | 100 |  | 109816 | 2024-08-12 | 146310 | 1900-01-01 | -29760 | SHAFIK SHAIKH
Fabrication Work (M) - DEn | N/C | N/C | SHAFIK SHAIKH | 117 | 2024-05-20 | Plot Barrication & Gate Fixing | 200 | 120 | 0 | 24000 | 0 | 2024-08-12 | Material Supply charges for Fabrication work of Main Entrance Gate with Wicket Gate with Pit Excavation, Plum Concrete, Cement, Sand, Metal & Rubble, ISMC 100MM,Horizontal Square tube 40 x 40x 2mm, with Red Oxide GI Sheet 12ft x 3.5ft . | 100 |  | 109816 | 2024-08-12 | 146310 | 1900-01-01 | -122310 | SHAFIK SHAIKH
Fabrication Work (M) - DEn | N/C | N/C | SHAFIK SHAIKH | 117 | 2024-05-20 | Plot Barrication & Gate Fixing | 48 | 120 | 0 | 5760 | 0 | 2024-08-12 | Material supply charges for Fabrication work of Main Entrance Gate with Wicket Gate with Pit Excavation, Plum Concrete,Cement, sand,Metal & Rubble,ISMC 100,Horizontal square Tube 40x40x2mm with Red oxide GI Sheet 12ft x 3.5ft. | 100 |  | 109816 | 2024-08-12 | 146310 | 1900-01-01 | -140550 | SHAFIK SHAIKH
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 119 | 2024-05-23 | B1- 2nd Slab RCC (L) | 1906.568 | 192 | 0 | 366061.056 | 65891 | 2024-08-03 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109498 | 2024-08-05 | 366061.06 | 1900-01-01 | -0.004 | KRISHNA CONSTRUCTION (Prop BHISE)
RCC Superstructure (B-up area) | N/C | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 119 | 2024-05-23 | B1. 3rd Slab RCC (L) | 1906.568 | 192 | 0 | 366061.056 | 65891 | 2024-08-10 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab,Beam, Column & Staircase. | 100 |  | 109709 | 2024-08-12 | 366061.06 | 1900-01-01 | -0.004 | KRISHNA CONSTRUCTION (Prop BHISE)
Department Labour - DEn | N/C | N/C | SHAFIK SHAIKH | 133 | 2024-05-31 | Phase 2 Department Labour | 46.5 | 650 | 0 | 30225 | 0 | 2024-08-12 | Charges for Male Coolie for Departmental work (Cube casting, Curing, Dewatering, Material Loading & unloading, etc) for Phase-2 for the month of JULY-2024. | 100 |  | 109818 | 2024-08-12 | 30225 | 1900-01-01 | 0 | SHAFIK SHAIKH
Department Labour - DEn | N/C | N/C | SHAFIK SHAIKH | 133 | 2024-05-31 | Phase 2 Department Labour | 42.5 | 650 | 0 | 27625 | 0 | 2024-08-18 | Charges for Male Coolie for Departmental work (Cube casting, Curing, Dewatering, Material Loading & unloading, etc) for Phase-2 for the month of AUGUST-2024. | 100 |  | 109894 | 2024-08-19 | 27625 | 1900-01-01 | 0 | SHAFIK SHAIKH
Plot Boundary & Contour Survey | N/C | N/C | YOGESH BALU ICHAKE | 137 | 2024-06-03 | Kondhawa Plot 36 Contour Survey | 4.1 | 1500 | 0 | 6150 | 0 | 2024-08-12 19:47 | Charges for Kondhawa plot no 36 revised survey work due to short area | 100 |  | 109898 | 2024-08-19 | 6150 | 2024-08-21 10:43 | 0 | YOGESH BALU ICHAKE
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 142 | 2024-06-05 | A-Bldg 3rd Slab Total Station Survey point Making | 100 | 100 | 0 | 10000 | 0 | 2024-08-16 | Charges for Total Station point marking work for A Building Aluform RCC Work. | 100 |  | 109889 | 2024-08-19 | 10000 | 1900-01-01 | 0 | VECTOR SURVEYORS
Total Station Point marking. | N/C | N/C | VECTOR SURVEYORS | 142 | 2024-06-05 | A.Bldg 4th Slab Total Station Survey point Making | 100 | 100 | 0 | 10000 | 0 | 2024-08-22 | Charges for Total Station point marking work for A Building Aluform RCC Work. | 100 |  | 110025 | 2024-08-26 | 10000 | 1900-01-01 | 0 | VECTOR SURVEYORS
M.S. Ghodi | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 150 | 2024-06-13 | A - MS Ghodi Work | 30 | 4450 | 0 | 133500 | 24030 | 2024-08-21 | Labour and Material Charges for MS Ghodi for A Building.(Sqaure pipe 32 x 32 x 2mm,Checkered sheet 3mm thickness,12 inch x 48 inch,Height 1.2 meter) | 100 |  | 110003 | 2024-08-21 | 133500 | 2024-08-24 11:19 | 0 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
M.S. Ghodi | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 151 | 2024-06-13 | B - MS Ghodi Work | 25 | 4450 | 0 | 111250 | 20025 | 2024-08-21 | Labour and Material Charges for MS Ghodi for B Building.(Sqaure pipe 32 x 32 x 2mm,Checkered sheet 3mm thickness,12 inch x 48 inch,Height 1.2 meter) | 100 |  | 110002 | 2024-08-21 | 111250 | 2024-08-24 11:19 | 0 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 1 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 10 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 11 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 12 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 13 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 14 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 15 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 16 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 17 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 18 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 19 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 2 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 20 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 21 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 22 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 23 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 24 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 3 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 4 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 5 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 6 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 7 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 8 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B- Parking Shop No 9 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 2 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 3 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 4 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 5 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 6 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 7 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 8 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 9 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 1 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 10 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 11 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Electrical Work (Labour) | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-LG Shop No 12 Electrical Work | 1 | 750 | 0 | 225 | 0 | 2024-08-19 | Conduiting work for RCC Shear wall & Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -12675 | TAHA ELECTRICALS
Light Point - DSP | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-2nd SLAB ELECTRICAL WORK | 49 | 250 | 0 | 3675 | 0 | 2024-08-19 | Conduiting Work for RCC Shear wall and Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -9225 | TAHA ELECTRICALS
Light Point - DSP | N/C | N/C | TAHA ELECTRICALS | 157 | 2024-06-17 | B-SHOP LOBBY ELECTRICAL WORK | 15 | 250 | 0 | 1125 | 0 | 2024-08-19 | Conduiting Work for RCC Shear wall and Slab | 30 |  | 109940 | 2024-08-19 | 12900 | 1900-01-01 | -11775 | TAHA ELECTRICALS
Transit Mixer | N/C | N/C | VIKAS GARADE | 16 | 2023-08-25 | TM Charge | 52.8571 | 350 | 0 | 18499.985 | 0 | 2024-08-19 | Charges for TM weight for the month of May, June & July-2024 | 100 |  | 109980 | 2024-08-20 | 18499.99 | 1900-01-01 | -0.005 | SATISH RAMCHANDRA JAGTAP
Site Expenses -SO | N/C | N/C | MANGESH ASHOK KSHIRSAGAR | 179 | 2024-07-06 | Phase 2 Site Expenses | 0.6282 | 10000 | 0 | 6282 | 0 | 2024-08-17 | Petty cash Site Expenses for the month of AUGUST-2024 for Phase-2 | 100 |  | 109982 | 2024-08-20 | 6282 | 1900-01-01 | 0 | MANGESH ASHOK KSHIRSAGAR
Anti Termite Treatment (M+L) | N/C | N/C | S.R.Enterprises | 183 | 2024-07-06 | New HO 2nd Floor Anti-Termite Treatment for walls | 1200 | 4 | 0 | 4800 | 864 | 2024-08-12 19:51 | Material & Labour charges for Anti-Termite Treatment work for walls using Fipronil chemical for New HO. | 100 |  | 109886 | 2024-08-19 | 4800 | 1900-01-01 | 0 | S.R.Enterprises
Miscellaneous Expenses. - SO | N/C | N/C | SATISH RAMCHANDRA JAGTAP | 184 | 2024-07-06 | Site Staff Misc. Expenses | 0.5621 | 15000 | 0 | 8431.5 | 0 | 2024-08-26 | Charges for Miscellaneous Site Expenses for JULY-2024 | 100 |  | 110164 | 2024-08-26 | 8431.5 | 1900-01-01 | 0 | SATISH RAMCHANDRA JAGTAP
Miscellaneous Expenses. - SO | N/C | N/C | SATISH RAMCHANDRA JAGTAP | 184 | 2024-07-06 | Site Staff Misc. Expenses | 0.8083 | 15000 | 0 | 12124.5 | 0 | 2024-08-03 | Charges for Miscellaneous Site Expenses for APRIL-2024 | 100 |  | 109497 | 2024-08-05 | 41457 | 1900-01-01 | -29332.5 | VIKAS GARADE
Door Making Fabrication Work | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 2 Labour Camp Room Fabrication,FRP toilet fixing Work | 12 | 600 | 0 | 7200 | 1296 | 2024-08-26 | Labour Charges for Door making and fixing work for Phase 2 labour camp at B Building. | 100 |  | 110166 | 2024-08-26 | 38639.2 | 1900-01-01 | -31439.2 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
Window Making & Fixing | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 1 Labour Camp & godown Fabrication Work | 1 | 300 | 0 | 300 | 54 | 2024-08-24 | Charges for Window making & fixing for Labour Hutment, store godown, etc. | 100 |  | 110028 | 2024-08-26 | 44178.54 | 1900-01-01 | -43878.54 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
GI Sheet Fixing (L) | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 2 Labour Camp Room Fabrication,FRP toilet fixing Work | 2418.4 | 13 | 0 | 31439.2 | 5659.06 | 2024-08-26 | Labour Charges for GI Sheet with all frame fixing work including self tapping screw for Phase 2 labour camp at B Building. | 100 |  | 110166 | 2024-08-26 | 38639.2 | 1900-01-01 | -7200 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
Door making & fixing-SOSB | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 1 Labour Camp & godown Fabrication Work | 11 | 600 | 0 | 6600 | 1188 | 2024-08-24 | Charges for Door Making & fixing for Labour Hutment , Store Godown, etc | 100 |  | 110028 | 2024-08-26 | 44178.54 | 1900-01-01 | -37578.54 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
Door making & fixing-SOSB | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 1 Labour Camp & godown Fabrication Work | 16 | 600 | 0 | 9600 | 1728 | 2024-08-26 | Charges for Door Making & fixing for Labour Hutment , Store Godown, etc | 100 |  | 110161 | 2024-08-26 | 47075.3 | 1900-01-01 | -37475.3 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
G.I. Sheet Fixing - BC | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 1 Labour Camp & godown Fabrication Work | 2867.58 | 13 | 0 | 37278.54 | 6710.14 | 2024-08-24 | Labour charges for GI Sheet fixing with framing including self tapping screws for Labour Hutment & Store Godown. | 100 |  | 110028 | 2024-08-26 | 44178.54 | 1900-01-01 | -6900 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
G.I. Sheet Fixing - BC | N/C | N/C | CHINTAMANI ENTERPRISES (Prop.Sonawane) | 189 | 2024-07-10 | Phase 1 Labour Camp & godown Fabrication Work | 2882.715 | 13 | 0 | 37475.295 | 6745.56 | 2024-08-26 | Labour charges for GI Sheet fixing with framing including self tapping screws for Labour Hutment & Store Godown. | 100 |  | 110161 | 2024-08-26 | 47075.3 | 1900-01-01 | -9600.005 | CHINTAMANI ENTERPRISES (Prop.Sonawane)
MS Pipe (L) | N/C | N/C | SHAFIK SHAIKH | 200 | 2024-07-26 | SRA New Labour Camp Room & Staircase Fabrication Work | 346.77 | 29.25 | 0 | 10143.0225 | 0 | 2024-08-18 | Labour charges for Fixing of MS Square Pipe 40x40x1.5mm for Labour camp- 11 Rooms at B-Bldg | 100 |  | 109896 | 2024-08-19 | 22923.02 | 1900-01-01 | -12779.9975 | SHAFIK SHAIKH
Precoated Sheet Fixing - DEn | N/C | N/C | SHAFIK SHAIKH | 200 | 2024-07-26 | SRA New Labour Camp Room & Staircase Fabrication Work | 2556 | 5 | 0 | 12780 | 0 | 2024-08-18 | Labour charges for Fixing of Precoated sheet for Labour camp- 11 Rooms at B-Bldg | 100 |  | 109896 | 2024-08-19 | 22923.02 | 1900-01-01 | -10143.02 | SHAFIK SHAIKH
MS Pipe (M) | N/C | N/C | SHAFIK SHAIKH | 201 | 2024-07-26 | SRA New Labour Camp Room & Staircase Fabrication Work | 346.77 | 65 | 0 | 22540.05 | 0 | 2024-08-18 | Material supply charges of MS Square Pipe 40x40x1.5mm for Labour camp- 11 Rooms at B-Bldg | 100 |  | 109897 | 2024-08-19 | 59440.05 | 1900-01-01 | -36900 | SHAFIK SHAIKH
Aldrop Fixing (M+L) | N/C | N/C | SHAFIK SHAIKH | 201 | 2024-07-26 | SRA New Labour Camp Room & Staircase Fabrication Work | 22 | 150 | 0 | 3300 | 0 | 2024-08-18 | Material supply and Labour charges for Fixing of 4 inch Aldrop for Labour camp- 11 Rooms at B-Bldg | 100 |  | 109897 | 2024-08-19 | 59440.05 | 1900-01-01 | -56140.05 | SHAFIK SHAIKH
Precoated Sheet (M) | N/C | N/C | SHAFIK SHAIKH | 201 | 2024-07-26 | SRA New Labour Camp Room & Staircase Fabrication Work | 28 | 1200 | 0 | 33600 | 0 | 2024-08-18 | Material supply charges of Precoated Sheet for Labour camp- 11 Rooms at B-Bldg | 100 |  | 109897 | 2024-08-19 | 59440.05 | 1900-01-01 | -25840.05 | SHAFIK SHAIKH
Site Expenses -SO | N/C | N/C | RANJEET BANDU DALAVI | 203 | 2024-07-30 | Site Expenses | 0.9357 | 10000 | 0 | 9357 | 0 | 2024-08-26 | Petty Cash Expenses for Month of JULY-2024 | 100 |  | 110165 | 2024-08-26 | 9357 | 1900-01-01 | 0 | RANJEET BANDU DALAVI
Hiring Charges | N/C | N/C | SATISH RAMCHANDRA JAGTAP | 206 | 2024-08-14 | SRA-Crane Services | 0.804 | 100000 | 0 | 80400 | 14472 | 2024-08-20 | Charges of Rent of Crane, Hydra& Pharana for unloading site material as per site requirement. | 100 |  | 110024 | 2024-08-26 | 80400 | 1900-01-01 | 0 | M M CRANE SERVICES
Security Supervisor-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 24 To June 25 Security Guard & Supervisor (Day) | 31 | 516.12 | 0 | 15999.72 | 2879.94 | 2024-08-18 | Charges for Security Supervisor for Month JULY-2024 | 100 |  | 109893 | 2024-08-19 | 143998.72 | 1900-01-01 | -127999 | SHRI RAJMUDRA ENTERPRISES
Security Supervisor-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 24 To June 25 Security Guard & Supervisor (Night) | 31 | 516.12 | 0 | 15999.72 | 2879.94 | 2024-08-18 | Charges for Security Supervisor for Month JULY-2024 | 100 |  | 109893 | 2024-08-19 | 143998.72 | 1900-01-01 | -127999 | SHRI RAJMUDRA ENTERPRISES
Security Guard-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 24 To June 25 Security Guard & Supervisor (Day) | 124 | 451.61 | 0 | 55999.64 | 10079.94 | 2024-08-18 | Charges for Security Guard for Month JULY-2024 | 100 |  | 109893 | 2024-08-19 | 143998.72 | 1900-01-01 | -87999.08 | SHRI RAJMUDRA ENTERPRISES
Security Guard-SMS | N/C | N/C | SHRI RAJMUDRA ENTERPRISES | 27 | 2023-09-08 | July 24 To June 25 Security Guard & Supervisor (Night) | 124 | 451.61 | 0 | 55999.64 | 10079.94 | 2024-08-18 | Charges for Security Guard for Month JULY-2024 | 100 |  | 109893 | 2024-08-19 | 143998.72 | 1900-01-01 | -87999.08 | SHRI RAJMUDRA ENTERPRISES
R & D Purpose | N/C | N/C | SUNIL VASANTRAO PATIL | 29 | 2023-09-21 | Quality Lab Setup- R&D Purpose | 0.0042 | 100000 | 0 | 420 | 75.6 | 2024-08-14 | Charges for Testing and Certification of Various material as per requirement. | 100 | INVOICE NO: CPL242501768 | 109887 | 2024-08-19 | 420 | 1900-01-01 | 0 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Department Labour-Dev | N/C | N/C | SHAFIK SHAIKH | 39 | 2023-10-17 | Departmental Labour for Misc. site work (Mason and Male Cool | 111.5 | 650 | 0 | 72475 | 0 | 2024-08-10 | Charges for Male Coolie for Cube casting, Curing, Dewatering, Material loading & Unloading work for JULY-2024 (5 M/C per day). | 100 |  | 109707 | 2024-08-12 | 72475 | 1900-01-01 | 0 | SHAFIK SHAIKH
RCC Mi-van Labour (B-up Basis)BC | No category | N/C | KRISHNA CONSTRUCTION (Prop BHISE) | 40 | 2023-10-24 | A-3rd Floor (4th Slab) Aluform RCC on Built-up Area Basis | 5423.16 | 160 | 0 | 867705.6 | 156187 | 2024-08-20 | Labour charges for Aluform Shuttering/Reinforcement/Concreting for Slab Beam, Staircase & All Shear walls. | 100 |  | 110023 | 2024-08-26 | 867705.6 | 1900-01-01 | 0 | KRISHNA CONSTRUCTION (Prop BHISE)
MS Pipe (L) | N/C | N/C | SHAFIK SHAIKH | 42 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 186 | 29.25 | 0 | 5440.5 | 0 | 2024-08-18 | Labour charges for Fixing of MS Square Pipe 40x40x1.5mm for Labour camp room. | 100 |  | 109892 | 2024-08-19 | 7537.44 | 1900-01-01 | -2096.94 | SHAFIK SHAIKH
MS Pipe (L) | N/C | N/C | SHAFIK SHAIKH | 42 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 63.22 | 29.25 | 0 | 1849.185 | 0 | 2024-08-18 | Labour charges for Fixing of MS Square Pipe 90x20x4mm for Labour camp room. | 100 |  | 109892 | 2024-08-19 | 7537.44 | 1900-01-01 | -5688.255 | SHAFIK SHAIKH
MS Pipe (L) | N/C | N/C | SHAFIK SHAIKH | 42 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 8.47 | 29.25 | 0 | 247.7475 | 0 | 2024-08-18 | Labour charges for Fixing of MS Round Pipe 25mm Dia. & 1.5mm thick for Labour camp room. | 100 |  | 109892 | 2024-08-19 | 7537.44 | 1900-01-01 | -7289.6925 | SHAFIK SHAIKH
MS Pipe (M) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 186 | 65 | 0 | 12090 | 0 | 2024-08-17 | Material supply charges of MS pipe 40 x 40 x 1.5mm for Labour camp room. | 100 |  | 109891 | 2024-08-19 | 50439.85 | 1900-01-01 | -38349.85 | SHAFIK SHAIKH
MS Pipe (M) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 63.22 | 65 | 0 | 4109.3 | 0 | 2024-08-17 | Material supply charges of MS pipe 90 x 20 x 4mm for Labour camp room. | 100 |  | 109891 | 2024-08-19 | 50439.85 | 1900-01-01 | -46330.55 | SHAFIK SHAIKH
MS Pipe (M) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 8.47 | 65 | 0 | 550.55 | 0 | 2024-08-17 | Material supply charges of MS pipe 25mm Dia. and 1.5mm thick for Labour camp room. | 100 |  | 109891 | 2024-08-19 | 50439.85 | 1900-01-01 | -49889.3 | SHAFIK SHAIKH
Aldrop Fixing (M+L) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 26 | 150 | 0 | 3900 | 0 | 2024-08-17 | Material supply and Labour charges for 4inch Aldrop fixing work for Labour camp room. | 100 |  | 109891 | 2024-08-19 | 50439.85 | 1900-01-01 | -46539.85 | SHAFIK SHAIKH
Precoated Sheet (M) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 24 | 1200 | 0 | 28800 | 0 | 2024-08-17 | Material supply charges for Precoated sheet for Labour camp room. | 100 |  | 109891 | 2024-08-19 | 50439.85 | 1900-01-01 | -21639.85 | SHAFIK SHAIKH
Hinges (M+L) | N/C | N/C | SHAFIK SHAIKH | 43 | 2023-10-24 | SRA New Labour Camp Room & Staircase Fabrication Work | 33 | 30 | 0 | 990 | 0 | 2024-08-17 | Material supply and Labour charges for 4inch Hinges fixing work for Labour camp room. | 100 |  | 109891 | 2024-08-19 | 50439.85 | 1900-01-01 | -49449.85 | SHAFIK SHAIKH
Total Station Point marking- BC | N/C | N/C | VECTOR SURVEYORS | 49 | 2023-11-06 | Phase 1 UGWT Total Station Visit | 3 | 4500 | 0 | 13500 | 0 | 2024-08-16 | Labour charges for Total Station Survey work in B-Bldg & UGWT | 100 |  | 109888 | 2024-08-19 | 13500 | 1900-01-01 | 0 | VECTOR SURVEYORS
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 60 | 2023-12-09 | Site Electricity expenses | 0.6729 | 100000 | 0 | 67290 | 0 | 2024-08-14 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109871 | 2024-08-14 | 67290 | 2024-08-14 18:15 | 0 | MSEDCL
AMC Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 75 | 2024-02-06 | 40 kVA DG Servicing Work (L) | 12 | 736 | 0 | 735.9971 | 132.48 | 2024-08-23 | AUG-2024 | 8.3333 |  | 110027 | 2024-08-26 | 736 | 1900-01-01 | -0.002944 | MEGAPOWER SOLUTION PVT LTD
B Check Service Kit | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 77 | 2024-02-06 | 40 kVA DG Servicing Work (L) | 1 | 7454.76 | 0 | 7454.76 | 1341.86 | 2024-08-18 | Material Supply Charges for B-Check Servicing kit (Lubricant oil-10 Ltr, Coolant-01 Ltr, Distill water, -01 Ltr, Oil Filter-01 Nos, Fuel Filter- 02 Nos) for 40 kva DG set Servicing work | 100 |  | 109901 | 2024-08-19 | 8190.76 | 1900-01-01 | -736 | MEGAPOWER SOLUTION PVT LTD
Transport Charges | N/C | N/C | MEGAPOWER SOLUTION PVT LTD | 77 | 2024-02-06 | 40 kVA DG Servicing Work (L) | 1 | 736 | 0 | 736 | 132.48 | 2024-08-18 | Transportation Charges for Material Delivery for 40kva DG set Servicing work. | 100 |  | 109901 | 2024-08-19 | 8190.76 | 1900-01-01 | -7454.76 | MEGAPOWER SOLUTION PVT LTD
Surveying Work. | N/C | N/C | YOGESH BALU ICHAKE | 91 | 2024-04-05 | Wadgown Sheri Sr.no 23A Survey Work | 1 | 4500 | 0 | 4500 | 0 | 2024-08-12 19:48 | Charges for Topographical & Contour Surveying work by using DGPS/Total station for Periphery line, ground area, structures, compound wall, fencing, electric/telephone poles, manholes, nalas, roads, temporary sheds,trees,etc | 100 |  | 109899 | 2024-08-19 | 4500 | 1900-01-01 | 0 | YOGESH BALU ICHAKE