## Work_Completion_Browse638603540
Work Completion Browse
Project : WTC NAGPUR
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 113 Records 1 to 113
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Rental Charges. | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Maching Rental Charges | 1 | 8000 | 0 | 8000 | 1440 | 2024-08-24 | Photocopy Machine Rental Charges for JULY-2024 (Rate include Upto 10000 No of Print after that 0.4 Rs/Print) | 100 |  | 110065 | 2024-08-26 | 12468 | 1900-01-01 | -4468 | JP OFFICE EQUIPMENTS
Xerox Printout | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Printouts | 1970 | 0.4 | 0 | 788 | 141.84 | 2024-08-24 | Extra Printout Charges for AUG-2023 to JULY-2026 (if limit of 10000 number of Print per month exceed) | 100 |  | 110065 | 2024-08-26 | 12468 | 1900-01-01 | -11680 | JP OFFICE EQUIPMENTS
Colour Printout | N/C | N/C | JP OFFICE EQUIPMENTS | 1140 | 2020-08-25 | Xerox Printouts | 736 | 5 | 0 | 3680 | 662.4 | 2024-08-24 | Charges for Colour Printout from AUG-2023 to JULY-2026 | 100 |  | 110065 | 2024-08-26 | 12468 | 1900-01-01 | -8788 | JP OFFICE EQUIPMENTS
Rental Charges - So | N/C | N/C | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS) | 1142 | 2020-09-11 | Monthly charges for canteen materal | 1 | 2500 | 0 | 2500 | 450 | 2024-08-03 | Machine Rental Charges for the month of JULY-2024 | 100 |  | 109519 | 2024-08-05 | 2500 | 2024-08-19 13:51 | 0 | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS)
Canteen Material | N/C | N/C | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS) | 1142 | 2020-09-11 | Monthly charges for canteen materal | 0.467 | 10000 | 0 | 4670 | 233.5 | 2024-08-03 | Canteen Material Expenses for the month of JULY-2024 | 100 |  | 109520 | 2024-08-05 | 4670 | 1900-01-01 | 0 | SS ENTERPRISES - (PROP. SARANG DEEPAK FADNAVIS)
Pest Control | N/C | N/C | PEST CONTROL INITIAL | 1204 | 2020-12-15 | Pest control For technical office part A LG & GF | 1 | 12000 | 0 | 12000 | 2160 | 2024-08-03 | Charges for Sales office,Lobby 6,Kalibar,Technical office,Store & Labour Camp Pest Control for JULY-2024 (8 Visit in Month) | 100 |  | 109521 | 2024-08-05 | 12000 | 1900-01-01 | 0 | PEST CONTROL INITIAL
Security Supervisor-SMS | N/C | N/C | BABA | 1221 | 2021-01-20 | Security Service - (Jan24 - Dec24) | 22 | 548.387 | 0 | 12064.514 | 2171.62 | 2024-08-02 | Charges for Security Supervisor for the month of JULY-2024 | 100 |  | 109500 | 2024-08-05 | 193999.63 | 2024-08-19 13:49 | -181935.116 | BABA
Security Guard-SMS | N/C | N/C | BABA | 1221 | 2021-01-20 | Security Service - (Jan24 - Dec24) | 376 | 483.87 | 0 | 181935.12 | 32748.32 | 2024-08-02 | Charges for Security Guard Services for the month of JULY-2024 (14 Security Guard for L.G., 1st, 2nd, 3rd Floor) | 100 |  | 109500 | 2024-08-05 | 193999.63 | 2024-08-19 13:49 | -12064.51 | BABA
HVAC Consultancy | N/C | N/C | ICEBERG HVACR ENGINEERS | 1300 | 2021-03-22 | HVAC Consultancy | 1533300 | 1.9 | 0 | 145663.5 | 26219.44 | 2024-08-06 | On 4th Floor BOQ | 5 |  | 109649 | 2024-08-06 | 145663.5 | 2024-08-08 11:25 | 0 | ICEBERG HVACR ENGINEERS
Housekeeping (M) | N/C | N/C | SPICK AND SPAN SERVICES | 1397 | 2021-07-13 | Housekeeping work | 1 | 7000 | 0 | 7000 | 1260 | 2024-08-03 | Charges for Machinery used for Housekeeping work for the month of MAY-2024 | 100 |  | 109515 | 2024-08-05 | 38000 | 1900-01-01 | -31000 | SPICK AND SPAN SERVICES
Housekeeping (M) | N/C | N/C | SPICK AND SPAN SERVICES | 1397 | 2021-07-13 | Housekeeping work | 1 | 7000 | 0 | 7000 | 1260 | 2024-08-03 | Charges for Machinery used for Housekeeping work for the month of JUNE-2024 | 100 |  | 109515 | 2024-08-05 | 38000 | 1900-01-01 | -31000 | SPICK AND SPAN SERVICES
Housekeeping (M) | N/C | N/C | SPICK AND SPAN SERVICES | 1397 | 2021-07-13 | Housekeeping work | 1 | 12000 | 0 | 12000 | 2160 | 2024-08-03 | Material Supply Charges for Housekeeping work for the month of MAY-2024 | 100 |  | 109515 | 2024-08-05 | 38000 | 1900-01-01 | -26000 | SPICK AND SPAN SERVICES
Housekeeping (M) | N/C | N/C | SPICK AND SPAN SERVICES | 1397 | 2021-07-13 | Housekeeping work | 1 | 12000 | 0 | 12000 | 2160 | 2024-08-03 | Material Supply Charges for Housekeeping work for the month of JUNE-2024 | 100 |  | 109515 | 2024-08-05 | 38000 | 1900-01-01 | -26000 | SPICK AND SPAN SERVICES
Supervision Charges | N/C | N/C | SPICK AND SPAN SERVICES | 1425 | 2021-08-12 | Housekeeping work | 0.9677 | 18000 | 0 | 17418.6 | 3135.34 | 2024-08-03 | Charges for Supervision of Housekeeping work for the Month of JULY-2024 | 100 |  | 109524 | 2024-08-05 | 17418.6 | 1900-01-01 | 0 | SPICK AND SPAN SERVICES
Rent for Guest House- AIE | N/C | N/C | MILINDKUMAR WAMANRAO SALWE | 1556 | 2022-02-12 | Rent for Guest House | 12 | 40793 | 0 | 40792.8368 | 0 | 2024-08-03 | AUG-2024 | 8.3333 |  | 109472 | 2024-08-03 | 40792.84 | 2024-08-03 19:08 | -0.003172 | MILINDKUMAR WAMANRAO SALWE
Blockwork 8" - BC | GLAZING SERVICES | N/C | SHOBHNATH | 1594 | 2022-03-15 | Misc Blockwork,Plaster,&Repairing Work | 138.31 | 18 | 0 | 2489.58 | 0 | 2024-08-06 | Labour Charges for- New Blockwork 8 inch | 100 |  | 109715 | 2024-08-12 | 2766.2 | 1900-01-01 | -276.62 | NEBU LAL
8" Blockwork Rate Diff. | N/C | N/C | SHOBHNATH | 1594 | 2022-03-15 | Misc Blockwork,Plaster,&Repairing Work | 138.31 | 2 | 0 | 276.62 | 0 | 2024-08-06 | Rate Differance for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 109715 | 2024-08-12 | 2766.2 | 1900-01-01 | -2489.58 | NEBU LAL
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 2 | 2633.55 | 0 | 1053.42 | 189.62 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -203032.62 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 2 | 2633.55 | 0 | 3686.97 | 663.66 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -200399.07 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 5 | 1811.96 | 0 | 1811.96 | 326.16 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -202274.08 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 5 | 1811.96 | 0 | 6341.86 | 1141.54 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -197744.18 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 20 | 1881.8 | 0 | 7527.2 | 1354.9 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -196558.84 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 20 | 1881.8 | 0 | 26345.2 | 4742.14 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -177740.84 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 54 | 1577.22 | 0 | 17033.976 | 3066.12 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -187052.064 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 54 | 1577.22 | 0 | 59618.916 | 10731.4 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -144467.124 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 2 | 1215.41 | 0 | 486.164 | 87.5 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -203599.876 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 2 | 1215.41 | 0 | 1701.574 | 306.28 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -202384.466 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 16 | 1732 | 0 | 5542.4 | 997.64 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -198543.64 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 16 | 1732 | 0 | 19398.4 | 3491.72 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -184687.64 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 20 | 1229 | 0 | 4916 | 884.88 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -199170.04 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 20 | 1229 | 0 | 17206 | 3097.08 | 2024-08-07 | Before Material Dispatch | 70 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -186880.04 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 44 | 1020 | 0 | 8976 | 1615.68 | 2024-08-07 | Advance | 20 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -195110.04 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1612 | 2022-04-08 | Ground Floor HVAC Work | 44 | 1020 | 0 | 22440 | 4039.2 | 2024-08-07 | Before Material Dispatch | 50 |  | 109721 | 2024-08-12 | 204086.04 | 1900-01-01 | -181646.04 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 54 | 533.5 | 0 | 28809 | 5185.62 | 2024-08-07 | Installation of Ball Valve 40 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1358947.26 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 1.8 | 533.5 | 0 | 960.3 | 172.86 | 2024-08-07 | Installation of Ball Valve 32 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1386795.96 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 9 | 533.5 | 0 | 4801.5 | 864.28 | 2024-08-07 | Installation of Ball Valve 40 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1382954.76 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 14.4 | 645.05 | 0 | 9288.72 | 1671.96 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 50 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1378467.54 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 149.4 | 1843 | 0 | 275344.2 | 49561.96 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 150 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1112412.06 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 45.81 | 1304.65 | 0 | 59766.0165 | 10757.88 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 100 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1327990.2435 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 250 | 1052.45 | 0 | 263112.5 | 47360.26 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 80 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1124643.76 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 76.41 | 845.84 | 0 | 64630.6344 | 11633.52 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 65 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1323125.6256 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 125 | 514.1 | 0 | 64262.5 | 11567.26 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 40 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1323493.76 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 3.86 | 441.35 | 0 | 1703.611 | 306.64 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 32 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1386052.649 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 140.4 | 1561 | 0 | 219164.4 | 39449.6 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 125 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1168591.86 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 125 | 1052.45 | 0 | 131556.25 | 23680.12 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 80 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1256200.01 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 207 | 514.1 | 0 | 106418.7 | 19155.36 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 40 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1281337.56 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 6.5 | 1052.45 | 0 | 6840.925 | 1231.36 | 2024-08-07 | All chilled water piping as per IS 1239 along with hangers, clamps, supports & complete fittings like elbows, tees, reducers, mating flanges, sockets; 35mm insulated Microban Class O Nitrile rubber/EPDM/XLPE insulation; 80 NB; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1380915.335 | NEPTUNE ENGINEERS PRIVATE LIMITED
Insulation for Supply Air Duct (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 692.42 | 170 | 0 | 117711.4 | 21188.06 | 2024-08-07 | Installation of 19 mm Thick Nitrile Rubber/EPDM/XLPE Class O insulation for supply Air Duct. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1270044.86 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 1 | 1212.5 | 0 | 1212.5 | 218.26 | 2024-08-07 | Installation of Butterfly Valve 150 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1386543.76 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 3.6 | 1212.5 | 0 | 4365 | 785.7 | 2024-08-07 | Installation of Butterfly Valve 125 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1383391.26 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 2 | 824.5 | 0 | 1649 | 296.82 | 2024-08-07 | Installation of Butterfly Valve 100 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1386107.26 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 19.8 | 824.5 | 0 | 16325.1 | 2938.52 | 2024-08-07 | Installation of Butterfly Valve 65 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1371431.16 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 1.8 | 824.5 | 0 | 1484.1 | 267.14 | 2024-08-07 | Installation of Butterfly Valve 50 NB. | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1386272.16 | NEPTUNE ENGINEERS PRIVATE LIMITED
Acoustic Insulation (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1613 | 2022-04-08 | Ground Floor HVAC Work | 64.23 | 130 | 0 | 8349.9 | 1502.98 | 2024-08-07 | Installation of 25mm Thick Fibre Glass, Density 48Kg/cum; Finished with FRP Tissue; Covered with 0.4 mm Perforated Al. sheet for supply air duct; | 100 |  | 109720 | 2024-08-12 | 1387756.26 | 1900-01-01 | -1379406.36 | NEPTUNE ENGINEERS PRIVATE LIMITED
Cleaning work- SO. | N/C | N/C | RIYA SUNIL MAHATO | 1668 | 2022-07-26 | Labour Camp Cleaning Work | 0.9353 | 3000 | 0 | 2805.9 | 0 | 2024-08-02 | Charges for Basement Labour Camp cleaning & Garbage collection for the month of JULY-2024 | 100 |  | 109502 | 2024-08-05 | 2805.9 | 2024-08-19 13:49 | 0 | RIYA SUNIL MAHATO
Site Expenses -SO | N/C | N/C | ZAK BUSINESS SERVICES PVT LTD | 1720 | 2023-01-04 | Site Expenses.. | 12 | 11250 | 0 | 11249.955 | 0 | 2024-08-13 | AUG-2024 | 8.3333 |  | 109845 | 2024-08-13 | 11249.96 | 2024-08-13 12:50 | -0.005 | ZAK BUSINESS SERVICES PVT LTD
Toilet Cleaning- S.O. | N/C | N/C | RIYA SUNIL MAHATO | 1723 | 2023-01-10 | Labour Camp Toilet Cleaning | 0.9357 | 3500 | 0 | 3274.95 | 0 | 2024-08-02 | Charges for Basement Labour Camp Toilet cleaning work for th e month of JULY-2024 | 100 |  | 109503 | 2024-08-05 | 3274.95 | 2024-08-20 18:56 | 0 | RIYA SUNIL MAHATO
Security Guard-SMS | N/C | N/C | ALLEVIATE MANAGEMENT SERVICES PRIVATE LIMITED | 1724 | 2023-01-10 | Security Service . (Jan 24 . Dec 24) | 341 | 451.61 | 0 | 153999.01 | 27719.82 | 2024-08-03 | Charges for Security Guard Services for the month of JULY-2024 (14 Security Guard at Day & 14 Security Guard at Night) | 100 |  | 109517 | 2024-08-05 | 153999.01 | 2024-08-19 13:50 | 0 | ALLEVIATE MANAGEMENT SERVICES PRIVATE LIMITED
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1728 | 2023-01-13 | New Sales Office Housekeeping Work | 90 | 491.93 | 0 | 44273.7 | 7969.26 | 2024-08-03 | Charges for manpower for Housekeeping work (3 M/C) for the month of JULY-2024 | 100 |  | 109526 | 2024-08-05 | 44273.7 | 1900-01-01 | 0 | SPICK AND SPAN SERVICES
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1729 | 2023-01-13 | Housekeeping - Ground Floor & First Floor | 58 | 491.93 | 0 | 28531.94 | 5135.74 | 2024-08-03 | Charges for manpower for Housekeeping work (6 M/C) for the month of JULY-2024 | 100 |  | 109528 | 2024-08-05 | 69362.13 | 1900-01-01 | -40830.19 | SPICK AND SPAN SERVICES
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1729 | 2023-01-13 | Housekeeping - Ground Floor & First Floor | 83 | 491.93 | 0 | 40830.19 | 7349.44 | 2024-08-03 | Charges for manpower for Housekeeping work (6 M/C) for the month of JULY-2024 | 100 |  | 109528 | 2024-08-05 | 69362.13 | 1900-01-01 | -28531.94 | SPICK AND SPAN SERVICES
Cleaning work.-SO | N/C | N/C | SPICK AND SPAN SERVICES | 1730 | 2023-01-13 | LG-Common toilet cleaning at part A & C - 1 No. | 120 | 491.935 | 0 | 59032.2 | 10625.8 | 2024-08-03 | Charges for Common toilet and shops Cleaning work(4 M/C) at part C LG Floor for the month of JULY-2024. | 100 |  | 109529 | 2024-08-05 | 59032.2 | 1900-01-01 | 0 | SPICK AND SPAN SERVICES
Cleaning work.-SO | N/C | N/C | SPICK AND SPAN SERVICES | 1731 | 2023-01-14 | Part C Mezzanine Floor common toilet housekeeping work | 120 | 491.935 | 0 | 59032.2 | 10625.8 | 2024-08-13 | Charges for Basement Labour Camp Toilet cleaning work for th e month of JULY-2024 | 100 |  | 109909 | 2024-08-19 | 59032.2 | 1900-01-01 | 0 | SPICK AND SPAN SERVICES
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1732 | 2023-01-14 | Housekeeping work | 90 | 491.935 | 0 | 44274.15 | 7969.34 | 2024-08-03 | Charges for Housekeeping work for site office for the month of JULY-2024 | 100 |  | 109530 | 2024-08-05 | 44274.15 | 1900-01-01 | 0 | SPICK AND SPAN SERVICES
Professional Fees | N/C | N/C | P B SADRANI AND CO | 1733 | 2023-01-16 | Professional fees for Audit of rent charged | 1 | 6000 | 0 | 6000 | 1080 | 2024-08-24 | Professional Charges for work related to audit of rent charged to vendor Ashish NX for Month of JUNE-2024 | 100 |  | 110072 | 2024-08-26 | 6000 | 1900-01-01 | 0 | C S P S AND ASSOCIATES
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.2747 | 30000 | 0 | 8241 | 0 | 2024-08-24 | Milk and Food supply for Guest of sales office & Company Employees for month of JULY -2024 | 100 |  | 110062 | 2024-08-26 | 20451 | 1900-01-01 | -12210 | OAM INDUSTRIES INDIA PRIVATE LIMITED
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.407 | 30000 | 0 | 12210 | 0 | 2024-08-24 | Milk and Food supply for Guest of sales office & Company Employees for month of AUGUST -2024 | 100 |  | 110062 | 2024-08-26 | 20451 | 1900-01-01 | -8241 | OAM INDUSTRIES INDIA PRIVATE LIMITED
Food Expenses. | N/C | N/C | OAM INDUSTRIES INDIA PRIVATE LIMITED | 1735 | 2023-01-16 | Admin Expense - Milk & Food Charges | 0.0362 | 30000 | 0 | 1086 | 54.3 | 2024-08-03 | Milk and Food supply for Guest of sales office & Company Employees for month of JULY -2024 | 100 |  | 109844 | 2024-08-13 | 1086 | 2024-08-19 13:51 | 0 | OAM INDUSTRIES INDIA PRIVATE LIMITED
Miscellaneous Expenses - Month | N/C | N/C | HOTEL PRESIDENT | 1736 | 2023-01-16 | Admin Expenses Guest Hospitality | 0.058 | 30000 | 0 | 1740 | 87 | 2024-08-24 | Guest Hospitality and Guest from Pune HO for the month of JULY-2024 | 100 |  | 110068 | 2024-08-26 | 1740 | 1900-01-01 | 0 | HOTEL PRESIDENT
Miscellaneous Expenses - Month | N/C | N/C | HOTEL PRESIDENT | 1736 | 2023-01-16 | Admin Expenses Guest Hospitality | 0.8 | 30000 | 0 | 24000 | 2880 | 2024-08-24 | Guest Hospitality and Guest from Pune HO for the month of JULY-2024 | 100 |  | 110070 | 2024-08-26 | 24000 | 1900-01-01 | 0 | HOTEL PRESIDENT
Admin Expenses | N/C | N/C | DARVEKAR GENERAL STORES | 1741 | 2023-01-21 | Admin Expense - Material Charges | 0.78 | 7000 | 0 | 5460 | 0 | 2024-08-24 | Material Supply for Sales Office (Paper cup and Coffee Powder ) for the month of AUGUST-2024. | 100 |  | 110060 | 2024-08-26 | 5460 | 1900-01-01 | 0 | DARVEKAR GENERAL STORES
Professional Fees | N/C | N/C | TALENTAX RENAISSANCE PRIVATE LIMITED | 1748 | 2023-01-25 | GST Consultancy | 1 | 5000 | 0 | 5000 | 900 | 2024-08-03 | Professional Fees towards GST Related Service for the month of JUN-2024 | 100 |  | 109476 | 2024-08-03 | 5000 | 2024-08-03 19:08 | 0 | TALENTAX RENAISSANCE PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1751 | 2023-01-28 | Ground Floor HVAC Work | 56 | 724 | 0 | 8108.8 | 1459.58 | 2024-08-07 | Advance | 20 |  | 109838 | 2024-08-12 | 83372.4 | 1900-01-01 | -75263.6 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1751 | 2023-01-28 | Ground Floor HVAC Work | 56 | 724 | 0 | 28380.8 | 5108.54 | 2024-08-07 | Before Material Dispatch | 70 |  | 109838 | 2024-08-12 | 83372.4 | 1900-01-01 | -54991.6 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1751 | 2023-01-28 | Ground Floor HVAC Work | 4 | 10982 | 0 | 8785.6 | 1581.4 | 2024-08-07 | Advance | 20 |  | 109838 | 2024-08-12 | 83372.4 | 1900-01-01 | -74586.8 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1751 | 2023-01-28 | Ground Floor HVAC Work | 4 | 10982 | 0 | 30749.6 | 5534.92 | 2024-08-07 | Before Material Dispatch | 70 |  | 109838 | 2024-08-12 | 83372.4 | 1900-01-01 | -52622.8 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1751 | 2023-01-28 | Ground Floor HVAC Work | 4 | 2041 | 0 | 1632.8 | 293.9 | 2024-08-07 | Advance | 20 |  | 109838 | 2024-08-12 | 83372.4 | 1900-01-01 | -81739.6 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (M) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1751 | 2023-01-28 | Ground Floor HVAC Work | 4 | 2041 | 0 | 5714.8 | 1028.66 | 2024-08-07 | Before Material Dispatch | 70 |  | 109838 | 2024-08-12 | 83372.4 | 1900-01-01 | -77657.6 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 3.6 | 1213 | 0 | 4366.8 | 786.02 | 2024-08-07 | Labour charges for Installation of Butterfly Valve- 200 NB | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -785072.71 | NEPTUNE ENGINEERS PRIVATE LIMITED
Butterfly Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 4 | 825 | 0 | 3300 | 594 | 2024-08-07 | Labour charges for Installation of Butterfly Valve- 80 NB | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -786139.51 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 221.823 | 2614 | 0 | 579845.322 | 104372.16 | 2024-08-07 | Charges for all Chilled Water (M.S.) Piping as per IS 1239 along with Hangers,Clamps,Supports and Complete Fittings like Elbows,Tees,Reducers,Mating Flanges, Sockets etc.35mm insulated with Microban Class O Nitrile Rubber/ EPDM / XLPE Insulation 200 NB | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -209594.188 | NEPTUNE ENGINEERS PRIVATE LIMITED
MS Piping (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 122.31 | 359 | 0 | 43909.29 | 7903.68 | 2024-08-07 | Charges for all Chilled Water (M.S.) Piping as per IS 1239 along with Hangers,Clamps,Supports and Complete Fittings like Elbows, Tees, Reducers, Mating Flanges, Sockets etc.35mm insulated with Microban Class O Nitrile Rubber/ EPDM / XLPE Insulation 25 NB | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -745530.22 | NEPTUNE ENGINEERS PRIVATE LIMITED
GI Ducting for Fresh Air(0.63 mm thick) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 223.78 | 195 | 0 | 43637.1 | 7854.68 | 2024-08-07 | Labour charges for Factory fabricated G. I. Ducting with Splitters, Frames, Flanges,Threaded rod Supports and channel, Gaskets etc. and as per specification For Fresh Air 0.63 mm Thick | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -745802.41 | NEPTUNE ENGINEERS PRIVATE LIMITED
GI Ducting for Fresh Air(0.63 mm thick) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 503 | 195 | 0 | 98085 | 17655.3 | 2024-08-07 | Labour charges for Factory fabricated G. I. Ducting with Splitters, Frames, Flanges,Threaded rod Supports and channel, Gaskets etc. and as per specification For Fresh Air 0.63 mm Thick | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -691354.51 | NEPTUNE ENGINEERS PRIVATE LIMITED
Ball Valve (L) | N/C | N/C | NEPTUNE ENGINEERS PRIVATE LIMITED | 1752 | 2023-01-28 | Ground Floor HVAC Work | 56 | 291 | 0 | 16296 | 2933.28 | 2024-08-07 | Labour charges for Installation of Ball Valve- 25 NB | 100 |  | 109722 | 2024-08-12 | 789439.51 | 1900-01-01 | -773143.51 | NEPTUNE ENGINEERS PRIVATE LIMITED
Drawing Printing Charges | N/C | N/C | TRUE COPY CENTRE PRIVATE LIMITED | 1754 | 2023-01-31 | Admin Expense - Drawing Printing | 0.128 | 10000 | 0 | 1280 | 230.4 | 2024-08-03 | Charges for Auto CAD Drawing printing A1, A2 size pages for the Month of JULY-2024 | 100 |  | 109504 | 2024-08-05 | 1280 | 2024-08-19 13:51 | 0 | TRUE COPY CENTRE PRIVATE LIMITED
Housekeeping (M) | N/C | N/C | ORIGAMI CELLULO PVT LTD | 1777 | 2023-02-22 | Part C Mezzanine Floor common toilet housekeeping work | 0.6375 | 20000 | 0 | 12750 | 2295 | 2024-08-03 | Housekeeping Material (Tissue papers, Multifold Towel & Soap Refill) supply charges for the month of JUNE-2024. | 100 |  | 109678 | 2024-08-08 | 12750 | 2024-08-19 13:49 | 0 | ORIGAMI CELLULO PVT LTD
Housekeeping (M) | N/C | N/C | ORIGAMI CELLULO PVT LTD | 1777 | 2023-02-22 | Part C Mezzanine Floor common toilet housekeeping work | 0.6335 | 20000 | 0 | 12670 | 2280.6 | 2024-08-03 | Housekeeping Material (Tissue papers, Multifold Towel & Soap Refill) supply charges for the month of JULY-2024. | 100 |  | 109679 | 2024-08-08 | 12670 | 1900-01-01 | 0 | ORIGAMI CELLULO PVT LTD
Fabrication work (L) No. | N/C | N/C | ANAND KAMALAKANT SHIRSAT | 1874 | 2023-06-03 | Miscellaneous Fabrication work | 0.1154 | 100000 | 0 | 11540 | 2077.2 | 2024-08-07 | Charges for Miscellaneous MS Fabrication work of Various activity. | 100 |  | 109717 | 2024-08-12 | 11540 | 1900-01-01 | 0 | NEW ADITY ENTERPRISES
DumperTrips | N/C | N/C | PVR TRADERS AND SERVICES | 1914 | 2023-08-09 | Dumper on trips for shifting of debris out of premises at LG | 12.5 | 500 | 0 | 6250 | 1125 | 2024-08-02 | Charges for Debris removing from site (Gypsum, blockwork, etc) & shifting it outside of premises for month of JULY-2024 | 100 |  | 109501 | 2024-08-05 | 9250 | 1900-01-01 | -3000 | PVR TRADERS AND SERVICES
Dumper 6 Brass with JCB | N/C | N/C | PVR TRADERS AND SERVICES | 1914 | 2023-08-09 | Dumper on trips for shifting of debris out of premises at LG | 1 | 3000 | 0 | 3000 | 540 | 2024-08-02 | Charges for Tipper 4 Brass with JCB Debris Removing from site (Gypsum, Blockwork, etc) & Shifting it outside of Premises for month of JULY-2024 | 100 |  | 109501 | 2024-08-05 | 9250 | 1900-01-01 | -6250 | PVR TRADERS AND SERVICES
Single Coat Plaster (L) | N/C | N/C | NEBU LAL | 1930 | 2023-09-06 | First Floor ST-1 to ST-9 extra coat plaster | 780.11 | 17 | 0 | 13261.87 | 0 | 2024-08-06 | Labour charges for extra coat plaster for Staircase-1 to Staircase-9 . | 100 |  | 109716 | 2024-08-12 | 55521.32 | 1900-01-01 | -42259.45 | NEBU LAL
Single Coat Plaster (L) | N/C | N/C | NEBU LAL | 1930 | 2023-09-06 | Second Floor ST-1 to ST-9 extra coat plaster | 776.86 | 17 | 0 | 13206.62 | 0 | 2024-08-06 | Labour charges for extra coat plaster for Staircase-1 to Staircase-9 . | 100 |  | 109716 | 2024-08-12 | 55521.32 | 1900-01-01 | -42314.7 | NEBU LAL
Single Coat Plaster (L) | N/C | N/C | NEBU LAL | 1930 | 2023-09-06 | Third Floor ST-1 to ST-9 extra coat plaster | 914.19 | 17 | 0 | 15541.23 | 0 | 2024-08-06 | Labour charges for extra coat plaster for Staircase-1 to Staircase-9 . | 100 |  | 109716 | 2024-08-12 | 55521.32 | 1900-01-01 | -39980.09 | NEBU LAL
Single Coat Plaster (L) | N/C | N/C | NEBU LAL | 1930 | 2023-09-06 | Fourth Floor ST-1 to ST-9 extra coat plaster | 321.34 | 17 | 0 | 5462.78 | 0 | 2024-08-06 | Labour charges for extra coat plaster for Staircase-1 to Staircase-9 . | 100 |  | 109716 | 2024-08-12 | 55521.32 | 1900-01-01 | -50058.54 | NEBU LAL
Single Coat Plaster (L) | N/C | N/C | NEBU LAL | 1930 | 2023-09-06 | Fourth floor Part B Single coat plaster on Block work | 473.46 | 17 | 0 | 8048.82 | 0 | 2024-08-06 | Labour charges Sand Face plaster (Single coat) in Cement , crush sand mortar with specified proportion with scaffolding with proper joint preparation between RCC (column beam) & Block -work using Chicken mesh, nails, drill machine etc for 4th Floor Part-B | 100 |  | 109716 | 2024-08-12 | 55521.32 | 1900-01-01 | -47472.5 | NEBU LAL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1993 | 2023-12-09 | WTC Electricity expenses | 0.5786 | 1500000 | -27 | 867900 | 0 | 2024-08-07 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109668 | 2024-08-07 | 867873 | 2024-08-07 18:48 | 27 | MSEDCL
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 1993 | 2023-12-09 | WTC Electricity expenses | 0.0583 | 1500000 | -30 | 87450 | 0 | 2024-08-20 | Charges for Electricity Bills for Year 2023-24 | 100 |  | 109992 | 2024-08-20 | 87420 | 2024-08-20 19:04 | 30 | MSEDCL
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 0.0638 | 45000 | 1 | 2871 | 0 | 2024-08-01 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 |  | 109462 | 2024-08-01 | 2872 | 1900-01-01 | -1 | BHARTI AIRTEL LIMITED
Telephone Bills | N/C | N/C | NITIN D PARDESHI | 1995 | 2023-12-19 | Telephone, mobile & water supply expenses | 0.0324 | 45000 | 1 | 1458 | 0 | 2024-08-01 | Charges for Telephone & Mobile Bills from DEC-2023 to NOV-2024. | 100 |  | 109463 | 2024-08-01 | 1459 | 2024-08-01 18:36 | -1 | BHARTI AIRTEL LIMITED
Water Supply | N/C | N/C | NITIN D PARDESHI | 1996 | 2023-12-19 | Telephone, mobile & water supply expenses | 1.2156 | 40000 | 1 | 48624 | 0 | 2024-08-10 | Charges for Water Supply (Municipal corporation) from DEC-2023 to NOV-2024. | 100 |  | 109697 | 2024-08-10 | 48625 | 2024-08-10 17:08 | -1 | EXECUTIVE ENGINEER WATER WORKS DEPARTMENT NMC NAGPUR
Housekeeping Work- | N/C | N/C | SPICK AND SPAN SERVICES | 1999 | 2024-01-02 | Housekeeping work | 137 | 491.935 | 0 | 67395.095 | 12131.12 | 2024-08-03 | Charges for Housekeeping work for Extra man power required at 2nd &3rd floor for the month of JULY-2024 | 100 |  | 109531 | 2024-08-05 | 67395.1 | 1900-01-01 | -0.005 | SPICK AND SPAN SERVICES
Consultancy Charges | N/C | N/C | S.K.MISHRA | 2004 | 2024-01-12 | Proffessional Consultancy (HO Admin) | 1 | 400000 | 0 | 400000 | 0 | 2024-08-03 | Professional Consultancy Charges for the month of JULY-2024 | 100 |  | 109471 | 2024-08-03 | 400000 | 2024-08-03 19:08 | 0 | S.K.MISHRA
Consultancy Charges | N/C | N/C | DHARIA LABOUR LAW CONSULTANCY PVT. LTD.(OPC) | 2039 | 2024-07-06 | Proffessional Consultancy (HO Admin) | 12 | 3000 | 0 | 2999.988 | 540 | 2024-08-05 | JULY-2024 | 8.3333 |  | 109480 | 2024-08-05 | 2999.99 | 2024-08-05 12:48 | -0.002 | DHARIA LABOUR LAW CONSULTANCY PVT. LTD.(OPC)
Motor Rewinding | N/C | N/C | JAVED ELECTRICALS | 473 | 2017-11-15 | Basement ventilation fan1HP motor rewinding | 4 | 2500 | 0 | 10000 | 0 | 2024-08-03 | Charges for Motor Rewinding work and Fixing charges. | 100 |  | 109525 | 2024-08-05 | 10000 | 2024-08-19 13:51 | 0 | JAVED ELECTRICALS
Security Services. | N/C | N/C | SHREE GANESH SECURITY SERVICES | 485 | 2017-12-06 | Glocal Square Security Services | 8.3399 | 150000 | 0.42 | 104244.5801 | 18764.1 | 2024-08-06 | JULY 2024 | 8.333 |  | 109635 | 2024-08-06 | 104245 | 2024-08-06 11:06 | -0.41995 | SHREE GANESH SECURITY SERVICES
DG Hiring Charges | N/C | N/C | K.R.S. HEAVY EQUIPMENT SERVICES | 634 | 2018-07-09 | 320 KVA DG Hiring for Ashish NX | 1 | 90000 | 0 | 90000 | 16200 | 2024-08-05 | Hiring Charges for DG Set of 320 KVA for Ashish NX Shop LG Floor for JULY-2024 | 100 |  | 109532 | 2024-08-05 | 102000 | 2024-08-19 13:48 | -12000 | K.R.S. HEAVY EQUIPMENT SERVICES
Operator Charges. | N/C | N/C | K.R.S. HEAVY EQUIPMENT SERVICES | 634 | 2018-07-09 | 320 KVA DG Hiring for Ashish NX | 1 | 12000 | 0 | 12000 | 2160 | 2024-08-05 | Operator Charges for DG Set of 320 KVA for Ashish NX Shop LG floor for JULY-2024 | 100 |  | 109532 | 2024-08-05 | 102000 | 2024-08-19 13:48 | -90000 | K.R.S. HEAVY EQUIPMENT SERVICES
Blockwork 8" - BC | GLAZING SERVICES | N/C | SHOBHNATH | 843 | 2019-08-22 | B part 8" & 6" Block work for B part (L) | 1890.88 | 18 | 0 | 34035.84 | 0 | 2024-08-06 | Construction of 8 inch thick Blockwork in Extra fine joining mortar to fix block including Striking joints,Raking out joints and Scaffolding with plumb bob Vertical & Right Angle at corner with proper joint filling etc. Complete. | 100 |  | 109711 | 2024-08-12 | 34035.84 | 1900-01-01 | 0 | NEBU LAL
8" Blockwork Rate Diff. | N/C | N/C | SHOBHNATH | 844 | 2019-08-22 | B part 8" & 6" Block work for B part (L) | 1890.88 | 2 | 0 | 3781.76 | 0 | 2024-08-06 | Rate Differance Charges for Construction of 8 Inch Blockwork in extra fine joining mortar to fix block including striking joints, Raking out joints & Scaffolding with plumb vertical and right angle at corner with proper joint filling etc complete. | 100 |  | 109712 | 2024-08-12 | 3781.76 | 1900-01-01 | 0 | NEBU LAL
Blockwork 8" - BC | GLAZING SERVICES | N/C | SHOBHNATH | 845 | 2019-08-22 | Part C Mezzanine Floor 8" Blockwork (L) | 293 | 18 | 0 | 5274 | 0 | 2024-08-06 | Construction of 8 inch thick Blockwork in extra fine jointing mortar to fix block including striking joints, raking out joints and scaffolding with Plumb (Valamba) Vertical & Right angle (Gunya) at corner, with proper joint filling etc. complete | 100 |  | 109713 | 2024-08-12 | 5274 | 1900-01-01 | 0 | NEBU LAL
Single Coat Plaster (L) | N/C | N/C | YAYATI RAMESH PATIL | 917 | 2019-11-21 | Basement floor part A Single coat plaster | 213.34 | 16 | 0 | 3413.44 | 0 | 2024-08-06 | Single Coat Plaster work with specified proportion incl.scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using Chicken mesh,Nails.drill machine incl.Loading,shifting & unloading of raw material at required place. | 100 |  | 109710 | 2024-08-12 | 3413.44 | 1900-01-01 | 0 | NEBU LAL
Single Coat Plaster (L) | N/C | N/C | SHOBHNATH | 920 | 2019-11-21 | Basement floor part C Single coat plaster | 343.48 | 16 | 0 | 5495.68 | 0 | 2024-08-06 | Single Coat Plaster work with specified proportion incl. scaffolding fixing & removing with proper joint preparation between RCC & Blockwork using Chicken mesh,nails,drill machine inclu.Loading,Shifting & unloading of raw material at required place. | 100 |  | 109714 | 2024-08-12 | 5495.68 | 1900-01-01 | 0 | NEBU LAL