## Work_Completion_Browse638603540
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : YADAV GANGA SAGAR
From Date : 19/08/2024 To date: 19/08/2024
Page 1 of 1
Total Records: 10 Records 1 to 10
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
1st Coat Satin Matt Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 1602 Walls Satin Matt Painting | 293.94 | 1.5 | 0 | 440.91 | 0 | 2024-08-24 11:43 | Labour Charges for Applying of 1st coat Satin matt paint for internal walls of flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for brush Cleaning. | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -1753.56 | YADAV GANGA SAGAR
1st Coat Premium Emulsion Paint (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 1602 Ceiling Premium Emulsion Painting | 144.453 | 1 | 0 | 144.453 | 0 | 2024-08-24 11:43 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat series 2 including Brush,Pattra,Roller,Ghoda,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -2050.017 | YADAV GANGA SAGAR
Water Base Primer | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Ceiling Premium Emulsion Painting | 144.453 | 1 | 0 | 144.453 | 0 | 2024-08-24 11:04 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flat series 2 | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -2050.017 | YADAV GANGA SAGAR
Oil base Primer-BC | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Walls Satin Matt Painting | 293.94 | 1 | 0 | 293.94 | 0 | 2024-08-24 11:04 | Labour Charges for Applying Oil Base primer for internal walls of flat series 2 | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -1900.53 | YADAV GANGA SAGAR
Astar Coat | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Walls Satin Matt Painting | 293.94 | 0.5 | 0 | 146.97 | 0 | 2024-08-24 11:04 | Labour Charges for Applying of Astar coat for internal walls of Flat series 2. | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -2047.5 | YADAV GANGA SAGAR
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Ceiling Premium Emulsion Painting | 144.453 | 1 | 0 | 144.453 | 0 | 2024-08-24 11:04 | Labour Charges for Applying of 2nd Coat of lambi putty for ceiling of internal flat series 2. | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -2050.017 | YADAV GANGA SAGAR
2nd Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Walls Satin Matt Painting | 293.94 | 1 | 0 | 293.94 | 0 | 2024-08-24 11:04 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat series 2 | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -1900.53 | YADAV GANGA SAGAR
Touch up Lambi | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Walls Satin Matt Painting | 293.94 | 0.5 | 0 | 146.97 | 0 | 2024-08-24 11:04 | Labour Charges for Touch up lambi work for internal flat series 2 painting work. | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -2047.5 | YADAV GANGA SAGAR
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Walls Satin Matt Painting | 293.94 | 1 | 0 | 293.94 | 0 | 2024-08-24 11:04 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series 2 | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -1900.53 | YADAV GANGA SAGAR
1st Coat Lambi Putty (L) | N/C | N/C | AAKRUTI ENTERPRISES | 1613 | 2023-05-04 | A 502 Ceiling Premium Emulsion Painting | 144.453 | 1 | 0 | 144.453 | 0 | 2024-08-24 11:04 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat series 2 | 100 |  | 110102 | 2024-08-26 | 2194.47 | 1900-01-01 | -2050.017 | YADAV GANGA SAGAR