## Work_Completion_Browse638603547
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : R K INTERIOR
From Date : 19/08/2024 To date: 19/08/2024
Page 1 of 1
Total Records: 16 Records 1 to 16
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Living,Dining,Passa. Marble Flooring | 1.6475 | 60 | 0 | 98.85 | 17.8 | 2024-08-26 11:57 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14347.66 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Master Bed Marble Flooring | 1.725 | 60 | 0 | 103.5 | 18.64 | 2024-08-26 11:57 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14343.01 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Guest Bed Marble Flooring | 1.895 | 60 | 0 | 113.7 | 20.46 | 2024-08-26 11:57 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14332.81 | R K INTERIOR
Italian marble Skirting - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Parents Bed Marble Flooring | 4.967 | 60 | 0 | 298.02 | 53.64 | 2024-08-26 11:57 | Italian Marble Skirting Cutting & Fixing (L) | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14148.49 | R K INTERIOR
Vitrified Skirting BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Kitchen Vitrified Flooring | 38.673 | 28 | 0 | 1082.844 | 194.92 | 2024-08-26 11:40 | 1200 x 800 Vitrified Skirting | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -13363.666 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Dry Balcony Vitrified Flooring | 8.612 | 21 | 0 | 180.852 | 32.56 | 2024-08-24 16:46 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14265.658 | R K INTERIOR
Vitrified Flooring -BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Staff Toilet Vitrified Flooring | 21.726 | 24 | 0 | 521.424 | 93.86 | 2024-08-26 11:40 | 600 x 600 Vitrified Flooring,Floor Gaurd Sheet Laying & Removing & Acid Wash | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -13925.086 | R K INTERIOR
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Kitchen dado | 42.759 | 22 | 0 | 940.698 | 169.32 | 2024-08-24 16:32 | 600 x 600 Dado Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -13505.812 | R K INTERIOR
Dado BC | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Dry Balcony dado | 74.547 | 22 | 0 | 1640.034 | 295.2 | 2024-08-24 16:32 | 600 x 600 Dado Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -12806.476 | R K INTERIOR
L Groove - BCV | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Kitchen dado | 13.878 | 20 | 0 | 277.56 | 49.96 | 2024-08-24 16:32 | Dado L Groove in Vitrified Tile | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14168.95 | R K INTERIOR
L Groove - BCV | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Dry Balcony dado | 5.022 | 20 | 0 | 100.44 | 18.08 | 2024-08-24 16:32 | Dado L Groove in Vitrified Tile | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14346.07 | R K INTERIOR
I Marble Patti - BCo | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Toilet & Dry Balcony Devider Patti | 29.98 | 60 | 0 | 1798.8 | 323.78 | 2024-08-26 12:01 | Italian Marble Divider Patti Cutting & Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -12647.71 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 1302 Powder Toilet Counter wash Basin | 2.54 | 750 | 0 | 1905 | 342.9 | 2024-08-25 | Italian Marble Counter Shifting,Cutting & Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -12541.51 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Master Toilet Counter wash Basin | 0.287 | 800 | 0 | 229.6 | 41.32 | 2024-08-26 11:53 | Italian Marble Counter Shifting,Cutting & Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14216.91 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2102 Powder Toilet Counter wash Basin | 0.254 | 800 | 0 | 203.2 | 36.58 | 2024-08-26 11:53 | Italian Marble Counter Shifting,Cutting & Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -14243.31 | R K INTERIOR
Italian Marble Counter - Mkt | N/C | N/C | MONIKA ENTERPRISES | 537 | 2019-04-04 | A 2302 Parents Toilet Counter wash Basin | 6.19 | 800 | 0 | 4952 | 891.36 | 2024-08-25 | Italian Marble Counter Shifting,Cutting & Fixing | 100 |  | 110090 | 2024-08-26 | 14446.51 | 1900-01-01 | -9494.51 | R K INTERIOR