## Work_Completion_Browse638603595
Work Completion Browse
Project : GANGA DHAM TOWERS
Executed By : YADAV GANGA SAGAR
From Date : 19/08/2024 To date: 19/08/2024
Page 1 of 1
Total Records: 15 Records 1 to 15
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Sanding Gattu (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 0.5 | 0 | 138.736 | 0 | 2024-08-24 11:17 | Labour Charges for Applying of Sanding Gattu for internal walls of flat Series No. 4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2874.254 | YADAV GANGA SAGAR
Touch up Lambi | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 0.5 | 0 | 138.736 | 0 | 2024-08-24 11:17 | Labour Charges for Touch up lambi work for internal flat painting work for Flat Series no.4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2874.254 | YADAV GANGA SAGAR
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 1 | 0 | 277.472 | 0 | 2024-08-24 11:17 | Labour Charges for Applying 1st coat lambi putty for internal walls of flat series No.4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2735.518 | YADAV GANGA SAGAR
1st Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 0 | 2024-08-24 11:17 | Labour Charges for Applying of 1st Coat of lambi putty for ceiling of internal flat Premium emulsion paint. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2871.54 | YADAV GANGA SAGAR
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 0 | 2024-08-24 11:17 | Labour Charges for 2nd Coat Lambi putty for ceiling premium emulsion paint for internal flat Series no.4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2871.54 | YADAV GANGA SAGAR
2nd Coat Lambi Putty (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 1 | 0 | 277.472 | 0 | 2024-08-24 11:17 | Labour Charges for Applying 2nd coat lambi putty for internal walls of flat Series No. 4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2735.518 | YADAV GANGA SAGAR
Astar Coat | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 0.5 | 0 | 138.736 | 0 | 2024-08-24 11:17 | Labour Charges for Applying of Astar coat for internal walls of Flat Series No.4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2874.254 | YADAV GANGA SAGAR
1st Coat Satin Matt Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 504 Walls Satin Matt Painting | 55.4944 | 1.5 | 0 | 83.2416 | 0 | 2024-08-24 10:59 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2929.7484 | YADAV GANGA SAGAR
1st Coat Satin Matt Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1204 Walls Satin Matt Painting | 277.472 | 1.5 | 0 | 416.208 | 0 | 2024-08-24 11:28 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2596.782 | YADAV GANGA SAGAR
1st Coat Satin Matt Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 1.5 | 0 | 416.208 | 0 | 2024-08-24 11:17 | Labour Charges for Applying of 1st coat satin matt paint for internal walls of flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2596.782 | YADAV GANGA SAGAR
Water Base Primer | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 0 | 2024-08-24 11:17 | Labour Charges for Applying of Water base perimer for Premium emulsion paint for ceiling of internal flats Series No.4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2871.54 | YADAV GANGA SAGAR
1st Coat Premium Emulsion Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 504 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 0 | 2024-08-24 10:59 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2871.54 | YADAV GANGA SAGAR
1st Coat Premium Emulsion Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 0 | 2024-08-24 11:17 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2871.54 | YADAV GANGA SAGAR
1st Coat Premium Emulsion Paint (L) | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 1204 Ceiling Premium Emulsion Painting | 141.45 | 1 | 0 | 141.45 | 0 | 2024-08-24 11:28 | Labour Charges for Applying of 1st coat Premium emulsion paint for Ceiling of internal flat including Brush,Pattra,Roller,Ghoda,Jula,clothes,sand paper,Terpentine for Brush cleaning. | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2871.54 | YADAV GANGA SAGAR
Oil base Primer-BC | N/C | N/C | POONA PAINTING | 1612 | 2023-05-03 | A 704 Walls Satin Matt Painting | 277.472 | 1 | 0 | 277.472 | 0 | 2024-08-24 11:17 | Labour Charges for Applying Oil Base primer for internal flat Series No. 4 | 100 |  | 110071 | 2024-08-26 | 3012.99 | 1900-01-01 | -2735.518 | YADAV GANGA SAGAR