## Work_Completion_Browse638603601
Work Completion Browse
Project : GANGA ALTUS
Contractor : ROHIT CONSTRUCTION
From Date : 16/12/2023 To date: 16/12/2023
Page 1 of 1
Total Records: 6 Records 1 to 6
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
RCC Work - DEn | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work F-Entrance Gate RCC Labour | 0.4 | 300000 | 0 | 48000 | 8640 | 2024-01-23 16:28 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 104851 | 2024-01-29 | 96000 | 2024-03-07 11:22 | -48000 | ROHIT CONSTRUCTION
RCC Work - DEn | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work F-Entrance Gate RCC Labour | 0.6 | 300000 | 0 | 72000 | 12960 | 2024-02-03 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 105066 | 2024-02-05 | 144000 | 2024-03-02 12:25 | -72000 | ROHIT CONSTRUCTION
RCC Work - DEn | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work F-Entrance Gate RCC Labour | 0.8 | 300000 | 0 | 144000 | 25920 | 2024-04-08 | After Completion of all RCC Work Above Slab-Column, Beam,Elevation including shuttering,Deshuttering,Reinforcement & Concreting. | 60 |  | 106714 | 2024-04-08 | 324000 | 2024-04-25 11:25 | -180000 | ROHIT CONSTRUCTION
RCC Work - DCH | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work D& E-Entrance Gate RCC Labour | 0.4 | 300000 | 0 | 48000 | 8640 | 2024-01-23 16:28 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 104851 | 2024-01-29 | 96000 | 2024-03-07 11:22 | -48000 | ROHIT CONSTRUCTION
RCC Work - DCH | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work D& E-Entrance Gate RCC Labour | 0.6 | 300000 | 0 | 72000 | 12960 | 2024-02-03 | RCC Work for Footing,Stub column,Plinth Beam,Column,Inverted Beam up to Slab at Security Cabin | 40 |  | 105066 | 2024-02-05 | 144000 | 2024-03-02 12:25 | -72000 | ROHIT CONSTRUCTION
RCC Work - DCH | N/C | N/C | ROHIT CONSTRUCTION | 867 | 2023-12-16 | RCC Work D& E-Entrance Gate RCC Labour | 1 | 300000 | 0 | 180000 | 32400 | 2024-04-08 | After Completion of all RCC Work Above Slab-Column, Beam,Elevation including shuttering,Deshuttering,Reinforcement & Concreting. | 60 |  | 106714 | 2024-04-08 | 324000 | 2024-04-25 11:25 | -144000 | ROHIT CONSTRUCTION