## Work_Completion_Browse638603764
Work Completion Browse
Project : GANGA ALTUS
Labour : Texture Paint (L)
Executed By : SAI NIRMAL COLOURS & TEXTURES
From Date : 27/07/2024 To date: 27/07/2024
Page 1 of 1
Total Records: 16 Records 1 to 16
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 10th Floor Northside Acrylic Texture Paint | 840.57 | 7.5 | 0 | 6304.275 | 1134.78 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178592.025 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 11th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 12th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 13th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 14th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 15th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 16th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 17th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 18th Floor Northside Acrylic Texture Paint | 893.87 | 7.5 | 0 | 6704.025 | 1206.72 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -178192.275 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 19th Floor Northside Acrylic Texture Paint | 1340.45 | 7.5 | 0 | 10053.375 | 1809.6 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -174842.925 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 1st Floor Northside Acrylic Texture Paint | 433.9 | 7.5 | 0 | 3254.25 | 585.76 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -181642.05 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 20th Floor Northside Acrylic Texture Paint | 1340.45 | 7.5 | 0 | 10053.375 | 1809.6 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -174842.925 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 21st Floor Northside Acrylic Texture Paint | 1340.45 | 7.5 | 0 | 10053.375 | 1809.6 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -174842.925 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 22nd Floor Northside Acrylic Texture Paint | 1340.45 | 7.5 | 0 | 10053.375 | 1809.6 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -174842.925 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 23rd Floor Northside Acrylic Texture Paint | 1340.45 | 7.5 | 0 | 10053.375 | 1809.6 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -174842.925 | SAI NIRMAL COLOURS & TEXTURES
Texture Paint (L) | N/C | N/C | RAHUL PATIL | 909 | 2024-01-19 | D-Bldg 24th Floor Northside Acrylic Texture Paint | 1340.45 | 7.5 | 0 | 10053.375 | 1809.6 | 2024-08-25 | Labour charges for Applying Texture paint including joint putty,Grinding & Touchup for D-Bldg North side External Texture Painting work. | 100 |  | 110132 | 2024-08-26 | 184896.3 | 1900-01-01 | -174842.925 | SAI NIRMAL COLOURS & TEXTURES