## Work_Completion_Browse638604451
Work Completion Browse
Project : GANGA ALTUS
Executed By : INNOVADOOR PRODUCTS PRIVATE LIMITED
From Date : 01/06/2024 To date: 01/06/2024
Page 1 of 1
Total Records: 86 Records 1 to 86
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-001-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-002-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-003-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-004-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-005-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-006-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-007-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-008-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1001-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1002-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1003-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1004-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1005-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1006-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1007-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-1008-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-101-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-102-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-103-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-104-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-106-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-107-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-108-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-201-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-202-2BHK(Near Refuse Area) Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-203-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-204-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-205-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-206-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-207-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-208-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-301-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-302-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-303-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-304-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-305-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-306-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-307-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-308-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-401-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-403-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-404-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-405-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-406-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-407-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-408-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-501-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-502-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-503-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-504-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-505-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-506-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-507-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-508-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-601-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-602-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-603-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-604-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-605-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-606-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-607-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-608-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-701-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-702-2BHK(Near Refuse Area) Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-703-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-704-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-705-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-706-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-707-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-708-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-801-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-802-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-803-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-804-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-805-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-806-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-807-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-808-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-901-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-902-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-903-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-904-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-905-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-906-3BHK Door Frame Fixing Work | 2.1 | 1980 | 0 | 4158 | 748.44 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -289674 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-907-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED
Installation of Bedroom door set with frame | N/C | N/C | INNOVADOOR PRODUCTS PRIVATE LIMITED | 446 | 2022-06-16 | D-908-2BHK Door Frame Fixing Work | 1.4 | 1980 | 0 | 2772 | 498.96 | 2024-06-28 | Labour charges for Installation of Door set with Frame for Bedroom (set size- 2250 mm x 1000 mm) for D-Building | 100 |  | 108681 | 2024-07-01 | 293832 | 1900-01-01 | -291060 | INNOVADOOR PRODUCTS PRIVATE LIMITED