## Work_Completion_Browse638607012
Work Completion Browse
Project : GANGA ASMI
From Date : 01/08/2024 To date: 01/08/2024
Page 1 of 1
Total Records: 80 Records 1 to 80
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Fogging work-SO | N/C | N/C | S.R.Enterprises | 166 | 2021-09-16 | Sales Office,Lab Camp,Site Office area-Fogging Work | 1 | 8000 | 0 | 8000 | 1440 | 2024-08-01 | Sales office area, Labour camp, Site office Pest control & Fogging work (8 times in month) for the Month of JULY-2024. | 100 |  | 109546 | 2024-08-05 | 8000 | 2024-08-21 10:40 | 0 | S.R.Enterprises
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 174 | 2021-10-22 | Site Infra Soil Test-Site Visit Wing-1,2,3 | 4 | 7500 | 0 | 15000 | 2700 | 2024-08-21 | Advance along with work order | 50 |  | 110041 | 2024-08-26 | 30000 | 1900-01-01 | -15000 | GLOBAL GEOTECHNICS
Visiting Charges-AIE | N/C | N/C | GLOBAL GEOTECHNICS | 174 | 2021-10-22 | Site Infra Soil Test-Site Visit Wing-1,2,3 | 4 | 7500 | 0 | 15000 | 2700 | 2024-08-21 | On submission of Report | 50 |  | 110041 | 2024-08-26 | 30000 | 1900-01-01 | -15000 | GLOBAL GEOTECHNICS
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.024 | 100000 | 0 | 240 | 43.2 | 2024-08-22 | Testing and Certification of Construction material and structure test. | 10 |  | 110047 | 2024-08-26 | 30240 | 1900-01-01 | -30000 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110047 | 2024-08-26 | 30240 | 1900-01-01 | -20240 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110047 | 2024-08-26 | 30240 | 1900-01-01 | -20240 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110047 | 2024-08-26 | 30240 | 1900-01-01 | -20240 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110044 | 2024-08-26 | 55440 | 1900-01-01 | -45440 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110044 | 2024-08-26 | 55440 | 1900-01-01 | -45440 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110044 | 2024-08-26 | 55440 | 1900-01-01 | -45440 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110044 | 2024-08-26 | 55440 | 1900-01-01 | -45440 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110044 | 2024-08-26 | 55440 | 1900-01-01 | -45440 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.544 | 100000 | 0 | 5440 | 979.2 | 2024-08-22 | Testing and Certification of Construction Material and Structure Test. | 10 |  | 110044 | 2024-08-26 | 55440 | 1900-01-01 | -50000 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 1 | 100000 | 0 | 10000 | 1800 | 2024-08-06 | Testing and Certification of Construction material and structure test. | 10 |  | 109730 | 2024-08-12 | 11200 | 1900-01-01 | -1200 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Testing & Certification Charges | N/C | N/C | VIKAS GARADE | 257 | 2022-03-04 | Testing & Certification of const.material & structure test | 0.225 | 100000 | 0 | 2250 | 405 | 2024-08-12 | Testing and Certification of Construction material and structure test. | 10 |  | 109734 | 2024-08-12 | 6450 | 1900-01-01 | -4200 | CONSTROLOGIX ENGINEERING AND RESEARCH SERVICE PVT. LTD.
Total Station Point marking. | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 299 | 2022-04-25 | Survey work (Wing 2) | 84 | 100 | 0 | 8400 | 1512 | 2024-08-05 | Charges for Total Station point marking for Column at plinth level. | 100 |  | 109583 | 2024-08-05 | 8400 | 2024-08-30 12:11 | 0 | SP ENGINEERS AND LAND SURVEYORS
Rent for Tent | N/C | N/C | B.S. KATURE | 30 | 2020-07-20 | Sales Office&Show Flats -Rent for Mandap | 1 | 100000 | 0 | 100000 | 18000 | 2024-08-01 | Rent for Sales office Mandap for the month of JULY-2024 | 100 |  | 109554 | 2024-08-05 | 100000 | 1900-01-01 | 0 | B.S. KATURE
Garbage Collection UGC | N/C | N/C | VIKAS GARADE | 315 | 2022-06-06 | Site Infra Misc Work | 1 | 1000 | 0 | 1000 | 0 | 2024-08-01 | Labour charges for Collection of Garbage from sales office & Labour camp 1,2 & 3 for month of JULY-2024 | 100 |  | 109565 | 2024-08-05 | 2000 | 2024-08-24 11:12 | -1000 | VIKAS GARADE
Maintanance Work - SMS | N/C | N/C | VIKAS GARADE | 315 | 2022-06-06 | Site Infra Misc Work | 1 | 1000 | 0 | 1000 | 0 | 2024-08-01 | MSEB Maintenance for month of JULY-2024 | 100 |  | 109565 | 2024-08-05 | 2000 | 2024-08-24 11:12 | -1000 | VIKAS GARADE
Security Services. | N/C | N/C | SHREE GANESH SECURITY SERVICES | 333 | 2022-07-09 | H.O. Admin Security Services | 0.1485 | 140873 | 5.36 | 20919.6405 | 3766.5 | 2024-08-06 | Security services for the month of JULY-2024 | 100 |  | 109636 | 2024-08-06 | 20925 | 2024-08-06 11:07 | -5.3595 | SHREE GANESH SECURITY SERVICES
Site Expenses -SO | N/C | N/C | VIKAS GARADE | 38 | 2020-09-24 | Site Expenses | 1 | 10000 | 0 | 10000 | 0 | 2024-08-01 | Petty Cash expenses for the month of JULY-2024 | 100 |  | 109561 | 2024-08-05 | 10000 | 1900-01-01 | 0 | VIKAS GARADE
Architectural Consultancy | N/C | N/C | SPACE DESIGNERS SYNDICATE | 394 | 2023-01-20 | Phase-A Wing-2 Architectural Consultancy | 40000.136 | 19 | 0 | 200000 | 36000 | 2024-08-03 | PREPARATION OF WORKING DRAWING | 26.3157 |  | 109477 | 2024-08-03 | 200000 | 2024-08-03 19:09 | -2.312e-06 | SPACE DESIGNERS SYNDICATE
Professional Fees | N/C | N/C | TALENTAX RENAISSANCE PRIVATE LIMITED | 399 | 2023-01-25 | GST Consultancy | 1 | 2000 | 0 | 2000 | 360 | 2024-08-03 | Professional Fees towards GST Related Service for the month of JUN-2024 | 100 |  | 109474 | 2024-08-03 | 2000 | 2024-08-03 19:09 | 0 | TALENTAX RENAISSANCE PRIVATE LIMITED
Rent Charges | N/C | N/C | JAIPRAKASH RAMRATAN BAJAARI | 402 | 2023-02-01 | H.O. Admin Rental Charges | 12 | 166668 | 0 | 166667.3333 | 0 | 2024-08-03 | AUG-2024 | 8.3333 |  | 109479 | 2024-08-03 | 166667.33 | 2024-08-03 19:09 | 0.003328 | JAIPRAKASH RAMRATAN BAJAARI
Marketing Operating Expenses | N/C | N/C | SUMIT SATISHCHANDRA SHARMA | 406 | 2023-02-09 | Marketing Expenses | 4.965 | 10000 | 0 | 3309.669 | 0 | 2024-08-05 | JULY 2024 | 6.666 |  | 109591 | 2024-08-05 | 3309.67 | 2024-08-13 12:47 | -0.001 | SUMIT SATISHCHANDRA SHARMA
Marketing Operating Expenses | N/C | N/C | SUMIT SATISHCHANDRA SHARMA | 406 | 2023-02-09 | Marketing Expenses | 6.993 | 10000 | 0 | 4661.5338 | 0 | 2024-08-19 | AUG 2024 | 6.666 |  | 109919 | 2024-08-19 | 4661.53 | 2024-08-20 17:12 | 0.0038 | SUMIT SATISHCHANDRA SHARMA
Pocklain with Breaker- DTR | N/C | N/C | DRAUPADA EARTHMOVERS | 420 | 2023-02-22 | JCB/ Poclain/ Crane Charges For Misc Dev.Work | 4 | 2200 | 0 | 8800 | 1584 | 2024-08-24 | Poclain Hiring charges with Breaker for Bolder Breaking for plinth filling NTA, Old PCC Breaking & Spreading on road. | 100 |  | 110050 | 2024-08-26 | 40300 | 1900-01-01 | -31500 | DRAUPADA EARTHMOVERS
Pocklain with Bucket-DTR | N/C | N/C | DRAUPADA EARTHMOVERS | 420 | 2023-02-22 | JCB/ Poclain/ Crane Charges For Misc Dev.Work | 17.5 | 1800 | 0 | 31500 | 5670 | 2024-08-24 | Poclain Hiring charges for Dubber shifting during rainy session, Material shifting, Road Chaining for TM Movement, Double shifting of Murum & Dubber Wing-3,etc. Misc. work | 100 |  | 110050 | 2024-08-26 | 40300 | 1900-01-01 | -8800 | DRAUPADA EARTHMOVERS
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 421 | 2023-02-23 | Head Office Expenses | 12 | 32500 | 0 | 32499.87 | 5849.98 | 2024-08-07 | JULY-2024 | 8.3333 |  | 109665 | 2024-08-07 | 32499.87 | 2024-08-09 12:53 | 0 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Housekeeping -SM | N/C | N/C | SPRINGTIME MAINTENANCE SERVICES PVT LTD | 422 | 2023-02-23 | Head Office Housekeeping | 12 | 4500 | 0 | 4499.982 | 810 | 2024-08-07 | JULY-2024 | 8.3333 |  | 109666 | 2024-08-07 | 4499.98 | 2024-08-09 12:53 | 0.002 | SPRINGTIME MAINTENANCE SERVICES PVT LTD
Post Tensioning Work -BC | No category | N/C | STRESSTECH ENGINEERS PRIVATE LIMITED | 457 | 2023-03-24 | Wing 2 -1st (P2) slab Post Tensioning Work | 3.47 | 143000 | 0 | 248105 | 44658.9 | 2024-08-05 | After delivery of strands | 50 |  | 109587 | 2024-08-05 | 248105 | 1900-01-01 | 0 | STRESSTECH ENGINEERS PRIVATE LIMITED
Garden Maintenance | N/C | N/C | SITARAM GANGADHAR AUTI | 477 | 2023-04-14 | Garden Work | 1 | 20000 | 0 | 20000 | 0 | 2024-08-01 | Charges for Garden and all plants/trees Maintenance including cutting,trimming,watering,cleaning of all area for month JULY-2024. | 100 |  | 109550 | 2024-08-05 | 20000 | 2024-08-19 13:54 | 0 | SITARAM GANGADHAR AUTI
Professional Fees | N/C | N/C | SUNITA S MISHRA | 487 | 2023-05-01 | Professional Fees | 1 | 500000 | 0 | 500000 | 90000 | 2024-08-01 | Professioanl Consultancy Charges for the month of JULY-2024. | 100 |  | 109456 | 2024-08-01 | 500000 | 2024-08-02 12:20 | 0 | SUNITA S MISHRA
RCC Superstructure (B-up area) | N/C | N/C | KSHITEEJ ENTERPRISES | 508 | 2023-05-30 | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | 5037.032 | 195.232 | 0 | 983389.8314 | 177010.16 | 2024-08-01 | Charges for- P5 Level 4th Slab Shuttering, Reinforcement Concreting work for Slab,Beam, Staricase & All Shearwalls. | 100 |  | 109457 | 2024-08-01 | 983389.83 | 2024-08-05 13:41 | 0.001424 | VINAYAKA ASSOCIATE
Legal Consultancy | N/C | N/C | UMESH SHANTARAM VASTE | 510 | 2023-06-06 | Legal Consultancy | 1 | 35000 | 0 | 35000 | 0 | 2024-08-05 | Professional Consultancy Charges for the month of JULY-2024 | 100 |  | 109490 | 2024-08-05 | 35000 | 2024-08-05 12:51 | 0 | UMESH SHANTARAM VASTE
Anti-termite Treatment - No. | N/C | N/C | S.R.Enterprises | 554 | 2023-08-26 | Goel House Anti Termite Treatment (Inside/Outside) | 30 | 4000 | 0 | 120000 | 21600 | 2024-08-12 20:01 | Charges for Termite Baiting System for Goel House. | 100 |  | 109903 | 2024-08-19 | 120000 | 1900-01-01 | 0 | S.R.Enterprises
Total Station Point marking. | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 583 | 2023-10-12 | Wing-2 1st Slab Total Station Suvey Point Marking | 21 | 100 | 0 | 2100 | 378 | 2024-08-05 | Labour charges for Total station Point Marking work for Wing-2 Each Slab 100 Points. | 100 |  | 109585 | 2024-08-05 | 21400 | 2024-08-30 12:10 | -19300 | SP ENGINEERS AND LAND SURVEYORS
Total Station Point marking. | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 583 | 2023-10-12 | Wing-2 2nd Slab Total Station Suvey Point Marking | 38 | 100 | 0 | 3800 | 684 | 2024-08-05 | Labour charges for Total station Point Marking work for Wing-2 Each Slab 100 Points. | 100 |  | 109585 | 2024-08-05 | 21400 | 2024-08-30 12:10 | -17600 | SP ENGINEERS AND LAND SURVEYORS
Total Station Point marking. | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 583 | 2023-10-12 | Wing-2 3rd Slab Total Station Suvey Point Marking | 55 | 100 | 0 | 5500 | 990 | 2024-08-05 | Labour charges for Total station Point Marking work for Wing-2 Each Slab 100 Points. | 100 |  | 109585 | 2024-08-05 | 21400 | 2024-08-30 12:10 | -15900 | SP ENGINEERS AND LAND SURVEYORS
Total Station Point marking. | N/C | N/C | SP ENGINEERS AND LAND SURVEYORS | 583 | 2023-10-12 | Wing-2 4th Slab Total Station Suvey Point Marking | 100 | 100 | 0 | 10000 | 1800 | 2024-08-05 | Labour charges for Total station Point Marking work for Wing-2 Each Slab 100 Points. | 100 |  | 109585 | 2024-08-05 | 21400 | 2024-08-30 12:10 | -11400 | SP ENGINEERS AND LAND SURVEYORS
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-501 (3BHK) Electrical Work (L) | 0.9 | 16792 | 0 | 5289.48 | 0 | 2024-08-05 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109580 | 2024-08-05 | 14727.2 | 1900-01-01 | -9437.72 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-502 (3BHK) Electrical Work (L) | 0.9 | 16792 | 0 | 5289.48 | 0 | 2024-08-05 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109580 | 2024-08-05 | 14727.2 | 1900-01-01 | -9437.72 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Electrical Work (Labour) | N/C | N/C | LAXMI ELECTRICALS | 587 | 2023-10-23 | Flat No-503 (2BHK) Electrical Work (L) | 0.9 | 13169 | 0 | 4148.235 | 0 | 2024-08-05 | PVC Conduiting work for RCC Shear wall & Slab | 35 |  | 109580 | 2024-08-05 | 14727.2 | 1900-01-01 | -10578.965 | LAXMI ELECTRICALS (Prop.Mayur Raskar)
Safety Barrication | N/C | N/C | PARTH ENTERPRISES | 607 | 2023-11-08 | Wing 1 - Window hard barrication work (Typical - 10 Floor) | 308.6 | 12 | 0 | 3703.2 | 0 | 2024-08-06 | Labour charges for Fixing of MS Pipe 40 x 40 x 2mm for safety barrication work for 10 floor Window . | 100 | 3rd floor Barrication | 109731 | 2024-08-12 | 3703.2 | 1900-01-01 | 0 | PARTH ENTERPRISES
Housekeeping-SMS | N/C | N/C | KARAN JAGRAM BALMIKI | 619 | 2023-11-18 | Site Expenses Curing & House Keeping | 1 | 25000 | 0 | 25000 | 0 | 2024-08-01 | Charges for all Labour Camp Cleaning & Housekeeping work for Month JULY-2024. | 100 |  | 109557 | 2024-08-05 | 25000 | 2024-08-24 11:12 | 0 | KARAN JAGRAM BALMIKI
Joint Filling with Putty | N/C | N/C | RAHUL PATIL | 637 | 2023-11-30 | Wing-1 Parking-2 (2nd Slab) Ceiling(OBD) Painting | 4108.3 | 1 | 0 | 4108.3 | 739.5 | 2024-08-27 | Labour Charges for Joint Filling with putty for Parking Ceiling Paint including proper cleaning. all tools & equipments. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | ANIL MAHTO ENTERPRISES
Joint Filling with Putty | N/C | N/C | RAHUL PATIL | 637 | 2023-11-30 | Wing-1 Parking-3 (3rd Slab) Ceiling(OBD) Painting | 4108.3 | 1 | 0 | 4108.3 | 739.5 | 2024-08-27 | Labour Charges for Joint Filling with putty for Parking Ceiling Paint including proper cleaning. all tools & equipments. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | ANIL MAHTO ENTERPRISES
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 641 | 2023-11-30 | NTA -1st Slab (Parking-2) RCC (L) | 3055.1316 | 155 | 0 | 473545.398 | 85238.18 | 2024-08-24 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Non Tower Area) | 100 |  | 110052 | 2024-08-26 | 947090.8 | 1900-01-01 | -473545.402 | SAIRAJ CONSTRUCTION
RCC Superstructure (B-up area) | N/C | N/C | SAIRAJ CONSTRUCTION | 641 | 2023-11-30 | NTA -1st Slab (Parking-2) RCC (L) | 3055.1316 | 155 | 0 | 473545.398 | 85238.18 | 2024-08-24 | Labour Charges for- Shuttering, Reinforcement & Concreting Work for Slab, Beam, Column & Staircase.(Non Tower Area) | 100 |  | 110052 | 2024-08-26 | 947090.8 | 1900-01-01 | -473545.402 | SAIRAJ CONSTRUCTION
Website Maintainence - | N/C | N/C | WORLD WEB SOLUTIONS | 648 | 2023-12-08 | ONLINE / DIGITAL Social / Digital Activity | 12 | 90000 | 0 | 89999.64 | 16199.94 | 2024-08-16 | 3) JUNE 2024 | 8.3333 | GGG + GOOGLE MY BUSINESS + YOUTUBE+ OFFPAGE / ONPAGE SEO+ e-PROMOTION (PUNEDIARY.COM/MAJHEGHAR.COM ) + EMAILERS/NEWSLETTERS + REAL RIC + WTC NAGPUR + EAST POINT ETC WEBSITE DEVELOPMENT & MAINTENANCE MONTLY BASIS CHARGES @ 90000/- + TAX | 109879 | 2024-08-16 | 89999.64 | 2024-08-22 12:18 | 0 | WORLD WEB SOLUTIONS
Website Maintainence - | N/C | N/C | WORLD WEB SOLUTIONS | 648 | 2023-12-08 | ONLINE / DIGITAL Social / Digital Activity | 12 | 90000 | 0 | 89999.64 | 16199.94 | 2024-08-16 | 4) JULY 2024 | 8.3333 | GGG + GOOGLE MY BUSINESS + YOUTUBE+ OFFPAGE / ONPAGE SEO+ e-PROMOTION (PUNEDIARY.COM/MAJHEGHAR.COM ) + EMAILERS/NEWSLETTERS + REAL RIC + WTC NAGPUR + EAST POINT ETC WEBSITE DEVELOPMENT & MAINTENANCE MONTLY BASIS CHARGES @ 90000/- + TAX | 109880 | 2024-08-16 | 89999.64 | 2024-08-22 12:18 | 0 | WORLD WEB SOLUTIONS
Vehical Service & Repair | N/C | N/C | NITIN D PARDESHI | 651 | 2023-12-09 | Vehicle Fuel, Maintenance & Insurance | 0.1906 | 25000 | 1 | 4765 | 0 | 2024-08-24 | Charges for Vehicle Service & Repairing work for Year 2023-24 | 100 |  | 110021 | 2024-08-24 | 4766 | 2024-08-24 18:04 | -1 | ACE KUDALE CAR PVT LTD
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 652 | 2023-12-09 | Goel House Electricity expenses | 0.5985 | 75000 | 2.5 | 44887.5 | 0 | 2024-08-07 | Charges for Electricity Bills for Goel House for Year 2023-24 | 100 |  | 109670 | 2024-08-07 | 44890 | 2024-08-07 18:49 | -2.5 | MSEDCL
Membrane Vertical Waterproofing (M) | N/C | N/C | AQUARIUS WATERPROOFING | 654 | 2023-12-09 | UGWT Waterproofing Membrane W/P (Vertical) | 3613.32 | 30 | 0 | 108399.6 | 19511.92 | 2024-08-29 | Material Supply Charges for UGWT Vertical Waterproofing work with Rigidex-F Membrane. | 100 |  | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | AQUARIUS WATERPROOFING
Hoarding display charges | N/C | N/C | SHUBHANGI ADVERTISING | 671 | 2023-12-16 | PRINTING PRINTING-NO.-(NA) | 12 | 50000 | 0 | 49998 | 8999.64 | 2024-08-26 | 8) DURATION 20/07/2023 TO 19/08/2024 | 8.333 | WAKAD - HINJEWADI RD , NR BAJAJ SHOWROOM, WAKAD CHOWK, WAKAD FACING AUNDH, SIZE 30 X30 NON LIT HOARDING . | 110140 | 2024-08-26 | 49998 | 2024-08-28 13:45 | 0 | SHUBHANGI ADVERTISING
Rental Charges. | N/C | N/C | NITIN D PARDESHI | 675 | 2023-12-19 | Photocopy-Xerox Machine Rental Charges. | 7.8363 | 15000 | 0 | 9794.9832 | 0 | 2024-08-05 | Rental Charges for JULY 2024 | 8.333 |  | 109533 | 2024-08-05 | 9794.98 | 2024-08-05 17:38 | 0.003185 | CANAN ENTERPRISES
Electricity Bills | N/C | N/C | NITIN D PARDESHI | 677 | 2023-12-19 | Site Electricity expenses | 0.8132 | 350000 | 0 | 284620 | 0 | 2024-08-10 | Charges for Electricity Bills from DEC-2023 to NOV-2024 | 100 |  | 109695 | 2024-08-10 | 284620 | 2024-08-10 17:02 | 0 | MSEDCL
Tea Expenses-SO | N/C | N/C | ANIL SHRIHARI MEDHAKE | 685 | 2023-12-30 | Site Expenses | 0.9466 | 9000 | 0 | 8519.4 | 0 | 2024-08-01 | Tea Expenses for the month of JULY-2024 | 100 |  | 109571 | 2024-08-05 | 8519.4 | 2024-08-24 11:12 | 0 | VIKAS GARADE
Housekeeping (M) | N/C | N/C | VIKAS GARADE | 698 | 2024-01-18 | Sales office & Sample flat Housekeeping Material | 1 | 2000 | 0 | 2000 | 0 | 2024-08-01 | Charges for Housekeeping material for the month of JULY-2024 | 100 |  | 109575 | 2024-08-05 | 2000 | 2024-08-24 11:12 | 0 | VIKAS GARADE
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | RED TREE DESIGN STUDIO PRIVATE LIMITED | 734 | 2024-04-02 | ONLINE / DIGITAL Social / Digital Activity | 12 | 300000 | 0 | 299999.88 | 53999.98 | 2024-08-03 | 4) MONTH OF JULY 2024 | 8.3333 |  | 109478 | 2024-08-03 | 299999.88 | 2024-08-03 19:09 | 0 | RED TREE DESIGN STUDIO PRIVATE LIMITED
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | ANIMOTIONSZ | 746 | 2024-04-22 | ONLINE / DIGITAL Social / Digital Activity | 3 | 15000 | 0 | 14998.5 | 2699.74 | 2024-08-13 | 1) JULY 2024 | 33.33 | WTC NAGPUR - MANAGING THE CAMPAIGN FOR INCREASING THE ROI + CREATION OF ADS + LANDING PAGE + FACEBOOK PAIND CAMPAING = MONITORING CHARGES 15,000/-RS PER MONTH + TAX | 109855 | 2024-08-13 | 14998.5 | 2024-08-13 17:28 | 0 | ANIMOTIONSZ
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | ANIMOTIONSZ | 747 | 2024-04-22 | ONLINE / DIGITAL Social / Digital Activity | 3 | 7500 | 0 | 7499.25 | 1349.86 | 2024-08-13 | 1) JULY 2024 | 33.33 | WTC NAGPUR - MANAGING THE CAMPAIGN FOR INCREASING THE ROI + CREATION OF ADS + LANDING PAGE + FACEBOOK PAIND CAMPAING = MONITORING CHARGES 7,500/-RS PER MONTH + TAX | 109856 | 2024-08-13 | 7499.25 | 2024-08-13 17:28 | 0 | ANIMOTIONSZ
Snake Treatment | N/C | N/C | S.R.Enterprises | 779 | 2024-05-24 | Goel House Pest Control | 1 | 3000 | 0 | 3000 | 540 | 2024-08-12 19:58 | Charges for Snake Control Spraying and Granules Spreading for Goel House | 100 |  | 109902 | 2024-08-19 | 3000 | 1900-01-01 | 0 | S.R.Enterprises
Shuttering Ply | N/C | N/C | VINAYAKA ASSOCIATE | 780 | 2024-05-24 | Wing 1 - Ply Shuttering Material | 42 | 2200 | 0 | 92400 | 16632 | 2024-08-01 | Material supply charges for Shuttering i.e., Shuttering Ply (8 feet x 4feet ) for Wing-01 | 100 |  | 109577 | 2024-08-05 | 133225 | 1900-01-01 | -40825 | VINAYAKA ASSOCIATE
Shuttering Patti | N/C | N/C | VINAYAKA ASSOCIATE | 780 | 2024-05-24 | Wing 1 - Ply Shuttering Material | 355 | 115 | 0 | 40825 | 7348.5 | 2024-08-01 | Material supply charges for Shuttering i.e., Shuttering Patti (8 feet x 4inches x 1.5 inches) for Wing-01 | 100 |  | 109577 | 2024-08-05 | 133225 | 1900-01-01 | -92400 | VINAYAKA ASSOCIATE
Lumpsum work- DCW | N/C | N/C | IMRAN NISAR ANSARI | 790 | 2024-06-06 | Ganga Satellite B1 Bldg. 11th Floor Bedroom painting | 1 | 10000 | 0 | 10000 | 0 | 2024-08-12 20:07 | Charges for B1 Bldg Bedroom wall painting work (Royal Luxury Emultion), Ceiling painting (Royal Luxury Emultion) & Goel House Cabin no-1, Cabin-3 Painting work. | 100 |  | 109904 | 2024-08-19 | 10000 | 1900-01-01 | 0 | IMRAN NISAR ANSARI
Unloading charges | N/C | N/C | ANANDI ENTERPRISES | 797 | 2024-07-04 | Tower Crane | 1 | 12000 | 0 | 12000 | 2160 | 2024-08-01 | Charges for Tower Crane Potent MCT85 Unloading work with supervision & Skilled Trained Manpower (Transfer from Ganga Altus to Ganga Asmi) | 100 |  | 109601 | 2024-08-05 | 12000 | 1900-01-01 | 0 | ANANDI ENTERPRISES
Professional Fees | N/C | N/C | PRITESH SURESH BANSAL | 799 | 2024-07-10 | Professional Fees | 1 | 150000 | 0 | 150000 | 0 | 2024-08-05 | Professional Consultancy charges for Month MAY-2024 | 100 |  | 109495 | 2024-08-05 | 150000 | 2024-08-05 13:36 | 0 | PRITESH SURESH BANSAL
Professional Fees | N/C | N/C | PRITESH SURESH BANSAL | 799 | 2024-07-10 | Professional Fees | 1 | 150000 | 0 | 150000 | 0 | 2024-08-05 | Professional Consultancy charges for Month JUNE-2024 | 100 |  | 109496 | 2024-08-05 | 150000 | 2024-08-05 13:37 | 0 | PRITESH SURESH BANSAL
Professional Fees | N/C | N/C | PRITESH SURESH BANSAL | 799 | 2024-07-10 | Professional Fees | 1 | 150000 | 0 | 150000 | 0 | 2024-08-05 | Professional Consultancy charges for Month JULY-2024 | 100 |  | 109489 | 2024-08-05 | 150000 | 2024-08-05 13:05 | 0 | PRITESH SURESH BANSAL
Aluminium angle | N/C | N/C | FURNITURE ZONE | 803 | 2024-07-17 | Goel House Pelmet For Monsoon Blinds | 3 | 7246.5 | 0 | 21739.5 | 3913.12 | 2024-08-13 15:48 | Charges for Aluminium Angle 4 x 4 x 5mm x 12 ft fixing for Pelmet for Monsoon Blinds for Goel House. | 100 |  | 109905 | 2024-08-19 | 38000.64 | 2024-08-30 12:17 | -16261.14 | FURNITURE ZONE
Powder Coating-Bco | N/C | N/C | FURNITURE ZONE | 803 | 2024-07-17 | Goel House Pelmet For Monsoon Blinds | 3 | 386.48 | 0 | 1159.44 | 208.7 | 2024-08-13 15:48 | Charges for Powder coating work for Pelmet for Monsoon Blinds for Goel House. | 100 |  | 109905 | 2024-08-19 | 38000.64 | 2024-08-30 12:17 | -36841.2 | FURNITURE ZONE
Fabrication work (L) No. | N/C | N/C | FURNITURE ZONE | 803 | 2024-07-17 | Goel House Pelmet For Monsoon Blinds | 1 | 6280.3 | 0 | 6280.3 | 1130.46 | 2024-08-13 15:48 | Charges for Fabrication work for Fixing Pelmet for Monsoon Blinds for Goel House. | 100 |  | 109905 | 2024-08-19 | 38000.64 | 2024-08-30 12:17 | -31720.34 | FURNITURE ZONE
Carpentary work (L)-BC | N/C | N/C | FURNITURE ZONE | 803 | 2024-07-17 | Goel House Pelmet For Monsoon Blinds | 1 | 2415.5 | 0 | 2415.5 | 434.8 | 2024-08-13 15:48 | Charges for Carpenter Labour for Fixing Pelmet for Monsoon Blinds for Goel House. | 100 |  | 109905 | 2024-08-19 | 38000.64 | 2024-08-30 12:17 | -35585.14 | FURNITURE ZONE
Transport Charges | N/C | N/C | FURNITURE ZONE | 803 | 2024-07-17 | Goel House Pelmet For Monsoon Blinds | 1 | 1449.3 | 0 | 1449.3 | 260.88 | 2024-08-13 15:48 | Charges for Transport Labour for Fixing Pelmet for Monsoon Blinds for Goel House. | 100 |  | 109905 | 2024-08-19 | 38000.64 | 2024-08-30 12:17 | -36551.34 | FURNITURE ZONE
Contractor Profit-Mkt | N/C | N/C | FURNITURE ZONE | 803 | 2024-07-17 | Goel House Pelmet For Monsoon Blinds | 1 | 4956.6 | 0 | 4956.6 | 892.18 | 2024-08-13 15:48 | Charges for Contractor Profit for Fixing Pelmet for Monsoon Blinds for Goel House. | 100 |  | 109905 | 2024-08-19 | 38000.64 | 2024-08-30 12:17 | -33044.04 | FURNITURE ZONE
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | MAGICBRICKS REALTY SERVICES LIMITED | 811 | 2024-08-21 | ONLINE / DIGITAL Social / Digital Activity | 0.52 | 504000 | 0 | 259459.2 | 46702.66 | 2024-08-29 | 1) ASMI - 900 LEADS IN 120 DAYS | 99 |  | 110175 | 2024-08-29 | 259459.2 | 1900-01-01 | 0 | MAGICBRICKS REALTY SERVICES LIMITED
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | MAGICBRICKS REALTY SERVICES LIMITED | 811 | 2024-08-21 | ONLINE / DIGITAL Social / Digital Activity | 0.27 | 504000 | 0 | 134719.2 | 24249.46 | 2024-08-29 | 1) ASMI - 900 LEADS IN 120 DAYS | 99 |  | 110176 | 2024-08-29 | 134719.2 | 1900-01-01 | 0 | MAGICBRICKS REALTY SERVICES LIMITED
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | MAGICBRICKS REALTY SERVICES LIMITED | 811 | 2024-08-21 | ONLINE / DIGITAL Social / Digital Activity | 0.2 | 504000 | 0 | 99792 | 17962.56 | 2024-08-29 | 1) ASMI - 900 LEADS IN 120 DAYS | 99 |  | 110177 | 2024-08-29 | 104832 | 1900-01-01 | -5040 | MAGICBRICKS REALTY SERVICES LIMITED
DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | N/C | N/C | MAGICBRICKS REALTY SERVICES LIMITED | 811 | 2024-08-21 | ONLINE / DIGITAL Social / Digital Activity | 1 | 504000 | 0 | 5040 | 907.2 | 2024-08-29 | 2) PROJECT LISTING, 6 BIGSHOT BANNER, PROJECT SPOTLIGHT VERIFIED LOCALS. | 1 |  | 110177 | 2024-08-29 | 104832 | 1900-01-01 | -99792 | MAGICBRICKS REALTY SERVICES LIMITED