## rptGTN638601771111184639_00001.
Goods Testing Note
From 25-07-2024 To 25-08-2024
GTN_SrId | GTN_No | Project_Name | Supplier | PO_No | Material_Category | Material_Name | Test_Date | Challan_No | Challan_Date | Vehicle_No | Test_Name | Test_result | Test_Status | Test_Remark | Tested_Qty | Rejected_Qty
54758 | 110874 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 052365 | 45502.5 | MH12KP7717 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54758 | 110875 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 052365 | 45502.5 | MH12KP7717 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54759 | 110876 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 052392 | 45502.5 | MH11AL5997 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54759 | 110877 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 052392 | 45502.5 | MH11AL5997 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54760 | 110878 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 052415 | 45503.5 | MH11AL5998 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54760 | 110879 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 052415 | 45503.5 | MH11AL5998 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54761 | 110880 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 2609 | 45503.5 | MH12KP7717 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54761 | 110881 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 2609 | 45503.5 | MH12KP7717 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54762 | 110882 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 2610 | 45503.5 | MH11AL5997 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54762 | 110883 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 2610 | 45503.5 | MH11AL5997 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54763 | 110884 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 2610 | 45503.5 | MH11AL5997 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54763 | 110885 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45503.5 | 2610 | 45503.5 | MH11AL5997 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54773 | 110900 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 053523 | 45504.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 1.495 | 0
54773 | 110901 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69267 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 053523 | 45504.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 1.495 | 0
54774 | 110902 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 053523 | 45504.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 4.505 | 0
54774 | 110903 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 053523 | 45504.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 4.505 | 0
54775 | 110904 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 053571 | 45504.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54775 | 110905 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 053571 | 45504.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54776 | 110906 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 20809 | 45505.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54776 | 110907 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 20809 | 45505.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54777 | 110908 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 20816 | 45505.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 2.753 | 0
54777 | 110909 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 20816 | 45505.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 2.753 | 0
54778 | 110910 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 20816 | 45505.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 3.25 | 0
54778 | 110911 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45505.5 | 20816 | 45505.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 3.25 | 0
54811 | 110973 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054516 | 45506.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54811 | 110974 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054516 | 45506.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54812 | 110975 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054540 | 45507.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54812 | 110976 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054540 | 45507.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54813 | 110977 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054552 | 45507.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 2.745 | 0
54813 | 110978 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054552 | 45507.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 2.745 | 0
54814 | 110979 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054552 | 45507.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 0.26 | 0
54814 | 110980 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45507.5 | 054552 | 45507.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 0.26 | 0
54820 | 110989 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69389 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 054917 | 45507.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 1.42 | 0
54820 | 110990 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69389 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 054917 | 45507.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 1.42 | 0
54821 | 110991 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 054917 | 45507.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 4.58 | 0
54821 | 110992 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 054917 | 45507.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 4.58 | 0
54822 | 110993 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 21981 | 45507.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54822 | 110994 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 21981 | 45507.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54823 | 110995 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 054947 | 45508.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 4 | 0
54823 | 110996 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45509.5 | 054947 | 45508.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 4 | 0
54824 | 110997 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45510.5 | 055592 | 45509.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54824 | 110998 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45510.5 | 055592 | 45509.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54825 | 110999 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45510.5 | 055607 | 45510.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54825 | 111000 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45510.5 | 055607 | 45510.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54826 | 111001 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45510.5 | 055633 | 45510.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5 | 0
54826 | 111002 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45510.5 | 055633 | 45510.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 5 | 0
54830 | 111008 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 056600 | 45511.5 | MH12KP7719 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54830 | 111009 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 056600 | 45511.5 | MH12KP7719 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54831 | 111010 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 056614 | 45511.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5 | 0
54831 | 111011 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 056614 | 45511.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 5 | 0
54832 | 111012 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 2683 | 45512.5 | MH12KP7715 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54832 | 111013 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 2683 | 45512.5 | MH12KP7715 | Should be as per Mix design & batch report |  | Pass |  | 6.5 | 0
54833 | 111014 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 2685 | 45512.5 | MH12KP7717 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54833 | 111015 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45512.5479 | 2685 | 45512.5 | MH12KP7717 | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54839 | 111025 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45513.6715 | 057227 | 45513.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 3.66 | 0
54839 | 111026 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69385 | RMC | Sand-Metal Mix M25 (Downpour) | 45513.6715 | 057227 | 45513.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 3.66 | 0
54840 | 111027 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45513.6715 | 057227 | 45513.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 2.832 | 0
54840 | 111028 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45513.6715 | 057227 | 45513.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 2.832 | 0
54740 | 110843 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45502.5 | 051437 | 45501.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54740 | 110844 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69326 | RMC | Sand-Metal Mix M25 (Downpour) | 45502.5 | 051437 | 45501.5 | By Truck | Should be as per Mix design & batch report |  | Pass |  | 6.5 | 0
54893 | 111135 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45519.3924 | 060456 | 45519.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54893 | 111136 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45519.3924 | 060456 | 45519.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54894 | 111137 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45519.3924 | 060380 | 45518.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54894 | 111138 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45519.3924 | 060380 | 45518.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54895 | 111139 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45519.3924 | 060428 | 45518.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54895 | 111140 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45519.3924 | 060428 | 45518.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54897 | 111142 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45521.7993 | 21463 | 45521.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 4.168 | 0
54897 | 111143 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45521.7993 | 21463 | 45521.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 4.168 | 0
54898 | 111144 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45521.7993 | 21463 | 45521.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 1.832 | 0
54898 | 111145 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45521.7993 | 21463 | 45521.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 1.832 | 0
54899 | 111146 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45521.7993 | 21464 | 45521.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5 | 0
54899 | 111147 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45521.7993 | 21464 | 45521.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 5 | 0
54939 | 111227 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45525.7778 | 062810 | 45524.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 4.5 | 0
54939 | 111228 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45525.7778 | 062810 | 45524.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 4.5 | 0
54940 | 111229 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45525.7778 | 062874 | 45525.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54940 | 111230 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69508 | RMC | Sand-Metal Mix M25 (Downpour) | 45525.7778 | 062874 | 45525.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54852 | 111051 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45515.4674 | 058183 | 45514.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54852 | 111052 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45515.4674 | 058183 | 45514.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6.5 | 0
54853 | 111053 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45515.4674 | 058222 | 45514.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54853 | 111054 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45515.4674 | 058222 | 45514.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6.5 | 0
54854 | 111055 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45515.4674 | 058251 | 45515.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54854 | 111056 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45515.4674 | 058251 | 45515.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54869 | 111085 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45517.459 | 2751 | 45517.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54869 | 111086 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69420 | RMC | Sand-Metal Mix M25 (Downpour) | 45517.459 | 2751 | 45517.5 | NEW TM | Should be as per Mix design & batch report |  | Pass |  | 6 | 0
54889 | 111128 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45518.6618 | 059728 | 45517.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54889 | 111129 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45518.6618 | 059728 | 45517.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54890 | 111130 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45518.6618 | 059727 | 45517.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54890 | 111131 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45518.6618 | 059727 | 45517.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54891 | 111132 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45518.6618 | 059760 | 45518.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54891 | 111133 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45518.6618 | 059760 | 45518.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54741 | 110845 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051409 | 45500.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54741 | 110846 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051409 | 45500.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6.5 | 0
54742 | 110847 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051412 | 45500.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54742 | 110848 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051412 | 45500.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6.5 | 0
54743 | 110849 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051419 | 45500.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54743 | 110850 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051419 | 45500.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6.5 | 0
54744 | 110851 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051422 | 45500.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54744 | 110852 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051422 | 45500.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6.5 | 0
54745 | 110853 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051426 | 45500.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54745 | 110854 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051426 | 45500.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54746 | 110855 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051444 | 45501.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54746 | 110856 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051444 | 45501.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6.5 | 0
54747 | 110857 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 18979 | 45501.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6.5 | 0
54747 | 110858 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 18979 | 45501.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6.5 | 0
54748 | 110859 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051448 | 45501.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 4.5 | 0
54748 | 110860 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051448 | 45501.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 4.5 | 0
54749 | 110861 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051447 | 45501.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5.5 | 0
54749 | 110862 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45502.5 | 051447 | 45501.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 5.5 | 0
54846 | 111039 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058188 | 45514.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54846 | 111040 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058188 | 45514.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54847 | 111041 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058196 | 45514.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54847 | 111042 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058196 | 45514.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54848 | 111043 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058264 | 45515.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54848 | 111044 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058264 | 45515.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54849 | 111045 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058230 | 45515.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 0.87 | 0
54849 | 111046 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058230 | 45515.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 0.87 | 0
54850 | 111047 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058230 | 45515.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5 | 0
54850 | 111048 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058230 | 45515.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 5 | 0
54851 | 111049 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058275 | 45515.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5 | 0
54851 | 111050 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69462 | RMC | Sand-Metal Mix M25 (Pumpable) | 45515.4674 | 058275 | 45515.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 5 | 0
54779 | 110912 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053545 | 45504.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 0.874 | 0
54779 | 110913 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69253 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053545 | 45504.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 0.874 | 0
54780 | 110914 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053545 | 45504.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 5.126 | 0
54780 | 110915 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053545 | 45504.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 5.126 | 0
54781 | 110916 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053561 | 45504.5 | MH12KP7717 | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54781 | 110917 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053561 | 45504.5 | MH12KP7717 | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54782 | 110918 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053567 | 45504.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54782 | 110919 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 053567 | 45504.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54783 | 110920 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 20811 | 45505.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 3.824 | 0
54783 | 110921 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69342 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 20811 | 45505.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 3.824 | 0
54784 | 110922 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 20811 | 45505.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 2.5 | 0
54784 | 110923 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 20811 | 45505.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 2.5 | 0
54785 | 110924 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 20818 | 45505.5 | By Truck | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54785 | 110925 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69371 | RMC | Sand-Metal Mix M25 (Pumpable) | 45505.5 | 20818 | 45505.5 | By Truck | Should be as per Mix design &batch report |  | Pass |  | 6 | 0
54870 | 111087 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69421 | RMC | Sand-Metal Mix M30 (Downpour) | 45517.459 | 2749 | 45516.5 | NEW TM | Chk slmp as per mix dsgn & max.wrkbility 2 hrs |  | Pass |  | 6 | 0
54870 | 111088 | GANGA DHAM TOWERS | HELLA INFRA MARKET PRIVATE LIMITED | 69421 | RMC | Sand-Metal Mix M30 (Downpour) | 45517.459 | 2749 | 45516.5 | NEW TM | Should be as per Mix design &batch report |  | Pass |  | 6 | 0