## 638596860511738348_00001.xlsx
Contractor Payment Report - Detail
Bill Date From : 01/01/2024 To : 20/08/2024
Contractor : ANAND PUNDLIK JADHAV
Page 1 of 1
Total Records: 18 Records 1 to 18
Project | Contractor | Bill_No | Bill_Date | Voucher_No | WO_SrNo | WO_Type | WOTotalAmt | Debit_Amount | Advance_Recovery | TDS_Amt | Retention_Amt | Bill Submitted | GrossBillAmt | Approved in Contract | Approved in Accounts | Total Payment Made | Balance Payment As On Today
GANGA ALTUS | ANAND PUNDLIK JADHAV | 106791 | 2024-04-15 |  | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 32100 | 32100 | 32100 | 0 | 0 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 108484 | 2024-06-22 | EV - 960 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 1550 | 1550 | 1550 | 1550 | 1550 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 104608 | 2024-01-15 | EV - 3023 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 36735 | 36735 | 36735 | 36735 | 36735 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 109654 | 2024-08-06 |  | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 39312 | 39312 | 39312 | 0 | 0 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107950 | 2024-06-03 |  | 376 | construction open | 989000 | 0 | 0 | 122 | 0 | 12118 | 12240 | 12118 | 0 | 0 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 105853 | 2024-03-11 |  | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 26001 | 26001 | 26001 | 0 | 0 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 108478 | 2024-06-21 | EV - 905 | 998 | construction open | 74500 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 108283 | 2024-06-11 | EV - 768 | 1012 | construction open | 65000 | 0 | 0 | 0 | 0 | 65000 | 65000 | 65000 | 65000 | 65000 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107113 | 2024-04-25 | EV - 624 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 34482 | 34482 | 34482 | 34482 | 34482 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107872 | 2024-05-30 | EV - 603 | 998 | construction open | 74500 | 0 | 0 | 0 | 0 | 24500 | 24500 | 24500 | 24500 | 24500 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 109239 | 2024-07-22 | EV - 1522 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 25998 | 25998 | 25998 | 25996 | 0 | 25996
GANGA ALTUS | ANAND PUNDLIK JADHAV | 109438 | 2024-07-29 |  | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 249 | 249 | 249 | 0 | 0 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107683 | 2024-05-20 | EV - 802 | 376 | construction open | 989000 | 0 | 0 | 45 | 0 | 4455 | 4500 | 4455 | 4500 | 4500 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107112 | 2024-04-25 | EV - 1218 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 12255 | 12255 | 12255 | 12255 | 12255 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 105072 | 2024-02-05 |  | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 26034 | 26034 | 26034 | 0 | 0 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107880 | 2024-06-01 | EV - 651 | 1004 | construction open | 63200 | 0 | 0 | 0 | 0 | 31600 | 31600 | 31600 | 31600 | 31600 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 104617 | 2024-01-15 | EV - 3113 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 16636 | 16636 | 16636 | 16636 | 16636 | 0
GANGA ALTUS | ANAND PUNDLIK JADHAV | 107626 | 2024-05-18 | EV - 554 | 376 | construction open | 989000 | 0 | 0 | 0 | 0 | 84600 | 84600 | 84600 | 84600 | 84600 | 0