## Project_Work_Order6385801694487
Project Work Order
From 01 Jul 2019 To 01 Aug 2024
Page 1 of 1
Total Records: 6 Records 1 To 6
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GANGA ALTUS | 724 | 0 | 13 Jul 2023 | HARISH CHANDRA JADHAV ELECTRICALS | Material Lift E-Bldg lift earthing work | Earthing work(m+l)- BC | No. | 2 | 4400 | 8800 | 1584 | 10384 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Jul 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 724 | 0 | 13 Jul 2023 | HARISH CHANDRA JADHAV ELECTRICALS | Material Lift E-Bldg lift earthing work | GI Strip 32x5mm (M+L) | Mtrs | 36 | 198 | 7128 | 1283.04 | 8411.04 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 |  |  |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Jul 2023 |  | No category | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 724 | 1 | 13 Jul 2023 | HARISH CHANDRA JADHAV ELECTRICALS | D-P1 to P5 Floor-Ceiling Light fixing & removing | Tube Light Fixing | No. | 160 | 100 | 16000 | 2880 | 18880 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Jul 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 724 | 1 | 13 Jul 2023 | HARISH CHANDRA JADHAV ELECTRICALS | D-P1 to P5 Floor-Ceiling Light fixing & removing | Tubelight Removing | No. | 160 | 30 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Jul 2023 |  | No category | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 724 | 1 | 13 Jul 2023 | HARISH CHANDRA JADHAV ELECTRICALS | D-P1 to P5 Floor-Ceiling Light fixing & removing | Lamp Fixing | No. | 160 | 80 | 12800 | 2304 | 15104 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Jul 2023 |  | No category | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 724 | 0 | 13 Jul 2023 | HARISH CHANDRA JADHAV ELECTRICALS | Material Lift E-Bldg lift earthing work | Earthing work(m+l)- BC | No. | 0 | 4400 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | ADITYA.CHOUGULE |  | construction open | 13 Jul 2023 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 13 Jul 2023 | 0