## Project_Work_Order6385804555294
Project Work Order
From 01 Jul 2024 To 01 Aug 2024
Page 1 of 1
Total Records: 2 Records 1 To 2
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GANGA ALTUS | 1052 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (M)- BCE | Sq.Ft | 247.52 | 110.7 | 27400.46 | 0 | 27400.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247.52 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 1052 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (M)- BCE | Sq.Ft | 247.52 | 110.7 | 27400.46 | 0 | 27400.46 | 0 | 247.52 | 27400.46 | 0 | 0 | 0 | 27400.46 | 0 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande |  | 100