## Project_Work_Order6385804904311
Project Work Order
From 01 Jul 2024 To 01 Aug 2024
Page 1 of 1
Total Records: 10 Records 1 To 10
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (L)- BCE | Sq.Ft | 169.1 | 45 | 7609.5 | 0 | 7609.5 | 2.5 | 169.1 | 7609.5 | 0 | 0 | 0 | 7609.5 | 0 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande |  | 100
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Riser (L)- BCE | R.Ft | 46.33 | 40 | 1853.2 | 0 | 1853.2 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 46.33 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Vertical Patta (L) | R.Ft | 21.67 | 45 | 975.15 | 0 | 975.15 | 2.5 | 21.67 | 975.15 | 0 | 0 | 0 | 975.15 | 0 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande |  | 100
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Edge Polish (L) | R.Ft | 39.17 | 10 | 391.7 | 0 | 391.7 | 2.5 | 39.17 | 391.7 | 0 | 0 | 0 | 391.7 | 0 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande |  | 100
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Tread | R.Ft | 22.92 | 40 | 916.8 | 0 | 916.8 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 22.92 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Flooring (L)- BCE | Sq.Ft | 169.1 | 45 | 7609.5 | 0 | 7609.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 169.1 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Vertical Patta (L) | R.Ft | 21.67 | 45 | 975.15 | 0 | 975.15 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 21.67 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Tread | R.Ft | 22.92 | 40 | 916.8 | 0 | 916.8 | 2.5 | 22.92 | 916.8 | 0 | 0 | 0 | 916.8 | 0 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande |  | 100
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | F-Entrance Gate(Security Cabin)-Tiling Work | Granite Riser (L)- BCE | R.Ft | 46.33 | 40 | 1853.2 | 0 | 1853.2 | 2.5 | 46.33 | 1853.2 | 0 | 0 | 0 | 1853.2 | 0 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Elevation Features | Approved | Swapnil Erande |  | 100
GANGA ALTUS | 1051 | 0 | 12 Jul 2024 | PAPPU BAGELA | D&E-Entrance Gate(Security Cabin)-Tiling Work | Granite Edge Polish (L) | R.Ft | 39.17 | 10 | 391.7 | 0 | 391.7 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 39.17 | 0 |  |  |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande |  | 0