## Project_Work_Order6385805567578
Project Work Order
From 02 Apr 2024 To 01 Aug 2024
Page 1 of 1
Total Records: 14 Records 1 To 14
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 50 Sqmm x 3.5 Core cable (M+L) | No. | 18 | 660 | 11880 | 2138.4 | 14018.4 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 120sqmm-UTI | Mtrs | 800 | 71.5 | 57200 | 10296 | 67496 | 2.5 | 394 | 28171 | 0 | 0 | 5070.78 | 33241.78 | 406 | 34254.22 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 49.25
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 120sqmm X 3.5 core cable (M+L) | No. | 24 | 990 | 23760 | 4276.8 | 28036.8 | 2.5 | 20 | 19800 | 0 | 0 | 3564 | 23364 | 4 | 4672.8 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 83.3333
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | 185 Sqmm x 3.5 Core Alu. Armoud jointing kit (M+L) | No. | 2 | 2800 | 5600 | 1008 | 6608 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 95sqmm X 3.5 core cable (M+L) | No. | 4 | 990 | 3960 | 712.8 | 4672.8 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 300sqmm-UTI | Mtrs | 2270 | 99 | 224730 | 40451.4 | 265181.4 | 2.5 | 2039 | 201861 | 0 | 0 | 36334.98 | 238195.98 | 231 | 26985.42 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 89.8238
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 50sqmm-UTI | Mtrs | 80 | 55 | 4400 | 792 | 5192 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | 120 Sqmm x 3.5 Core Alu. Armoud jointing kit (M+L) | No. | 3 | 2800 | 8400 | 1512 | 9912 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 185 Sqmm x 3.5 Core cable (M+L) | No. | 4 | 1540 | 6160 | 1108.8 | 7268.8 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Al. Arm. Cable laying 3.5C 95sqmm-UTI | Mtrs | 120 | 60.5 | 7260 | 1306.8 | 8566.8 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | 300 Sqmm x 3.5 core Alu. Armoud Jointing kit (M+L) | No. | 4 | 3300 | 13200 | 2376 | 15576 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | End Termination 300sqmm X 3.5 core cable (M+L) | No. | 54 | 1870 | 100980 | 18176.4 | 119156.4 | 2.5 | 8 | 14960 | 0 | 0 | 2692.8 | 17652.8 | 46 | 101503.6 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande |  | 14.8148
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | DTC Meter Fixing | No. | 4 | 2420 | 9680 | 1742.4 | 11422.4 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 0
GANGA ALTUS | 958 | 0 | 02 Apr 2024 | ADITI POWER CARE AND ENTERPRISES | HT & LT Cable Laying with pannel termination | Meter Panel (L) | No. | 32 | 3000 | 96000 | 17280 | 113280 | 2.5 | 14 | 42000 | 0 | 0 | 7560 | 49560 | 18 | 63720 |  |  |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Apr 2024 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande |  | 43.75