## Project_Work_Order6385821921448
Project Work Order
From 01 Jul 2024 To 03 Aug 2024
Page 1 of 1
Total Records: 28 Records 1 To 28
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 3.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 7.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 1.75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 5.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 11.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.63 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Scaffolding Fixing Work - DER | Sq.Ft | 0 | 5.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Schedule work- BC | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Texture Paint (L) | Sq.Ft | 0 | 11.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (L) | Sq.Ft | 0 | 2.63 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Final Cleaning & Housekeeping work (L) | Sq.Ft | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | S OH Conveyance & Transport | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Schedule work- BC | No. | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 03 Jul 2024 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 05 Jul 2024
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | D&E-Entrance Gate-External Texture Work | Labour lumpsum | No. | 1 | 48000 | 48000 | 8640 | 56640 | 2.5 | 0.6 | 28800 | 5184 | 33984 | 0.4 | 22656 |  | 60 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande
GANGA ALTUS | 1035 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES | F-Entrance Gate-External Texture Work | Labour lumpsum | No. | 1 | 48000 | 48000 | 8640 | 56640 | 2.5 | 0.9 | 43200 | 7776 | 50976 | 0.1 | 5664 |  | 90 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Jul 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande