## Project_Work_Order6385822018235
Project Work Order
From 01 Jul 2024 To 03 Aug 2024
Page 1 of 1
Total Records: 8 Records 1 To 8
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | Texture Paint (M) | Sq.Ft | 1718.73 | 8 | 13749.84 | 2474.98 | 16224.82 | 0 | 1546.857 | 12374.86 | 2227.48 | 14602.34 | 171.873 | 1622.48 |  | 90 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1718.73 | 1 | 1718.73 | 309.38 | 2028.11 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.25 | 3867.14 | 696.08 | 4563.22 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | D&E-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.5 | 4296.83 | 773.42 | 5070.25 | 0 | 0 | 0 | 0 | 0 | 1718.73 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | Texture Paint (M) | Sq.Ft | 1718.73 | 8 | 13749.84 | 2474.98 | 16224.82 | 0 | 1546.857 | 12374.86 | 2227.48 | 14602.34 | 171.873 | 1622.48 |  | 90 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | 1 Coat Primer (Water Base) (M) | Sq.Ft | 1718.73 | 1 | 1718.73 | 309.38 | 2028.11 | 0 | 1546.857 | 1546.86 | 278.44 | 1825.3 | 171.873 | 202.81 |  | 90 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | 1st Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.25 | 3867.14 | 696.08 | 4563.22 | 0 | 1546.857 | 3480.43 | 626.48 | 4106.91 | 171.873 | 456.31 |  | 90 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande
GANGA ALTUS | 1036 | 0 | 01 Jul 2024 | VEER BHADRA ENTERPRISES (MATERIAL) | F-Entrance Gate-External Texture Work | 2nd Coat Acrylic Paint (M) | Sq.Ft | 1718.73 | 2.5 | 4296.83 | 773.42 | 5070.25 | 0 | 1546.857 | 3867.14 | 696.08 | 4563.22 | 171.873 | 507.02 |  | 90 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Jul 2024 |  | 10 PAINTING WORK | Approved | Swapnil Erande