## Project_Work_Order6385853929700
Project Work Order
From 01 Jul 2000 To 07 Aug 2024
Page 1 of 1
Total Records: 5 Records 1 To 5
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 1 | 0 | 01 Feb 2020 | OM SAI CORP | PRINTING Flex Printing | Flex Printing & Pasting | Sq.Ft | 840 | 14 | 11760 | 2116.8 | 13876.8 | 0 | 0 | 0 | 0 | 0 | 840 | 0 | Site Project Hoarding Flex Print with Mount At Ganga Altus Kharadi Size as 42x20 Sq Ft Star Frontlit Flex | 0 |  | tejas | sunitas | construction open | 01 Feb 2020 |  | MKT. Media | Approved | sunitas
GANGA ALTUS | 1 | 1 | 01 Feb 2020 | OM SAI CORP | PRINTING Flex Printing | Flex Printing & Pasting | Sq.Ft | 360 | 8 | 2880 | 518.4 | 3398.4 | 0 | 360 | 2880 | 518.4 | 3398.4 | 0 | 0 | Site Project Hoarding Flex Print with Mount At Ganga Altus Kharadi Size as 18X20 Sq Ft Normal Flex | 100 |  | tejas | sunitas | construction open | 01 Feb 2020 |  | MKT. Media | Approved | sunitas
GANGA ALTUS | 1 | 2 | 01 Feb 2020 | OM SAI CORP | PRINTING Flex Printing | Flex Printing & Pasting | Sq.Ft | 2016 | 20 | 40320 | 7257.6 | 47577.6 | 0 | 146 | 2920 | 525.6 | 3445.6 | 1870 | 44132 | Ganga Altus Project Site Branding At Kharadi Frontlit Panel Star Frontlit Flex Print with Pasting Size as 8x6 Sq Ft Qty 42 Panels | 7.2421 |  | tejas | sunitas | construction open | 01 Feb 2020 |  | MKT. Media | Approved | sunitas
GANGA ALTUS | 1 | 3 | 01 Feb 2020 | OM SAI CORP | PRINTING Flex Printing | Flex Printing & Pasting | Sq.Ft | 1600 | 200 | 320000 | 57600 | 377600 | 0 | 320 | 64000 | 11520 | 75520 | 1280 | 302080 | Ganga Altus Project Site Branding At Kharadi Star Backlit Panel MS Frame Box with Tin Patra Side Covering Flex Print with Pasting with LED TubeLight Wire Size as 8x8 Sq Ft Qty 25 Panels Printing Pasting Installation with all material | 20 |  | tejas | sunitas | construction open | 01 Feb 2020 |  | MKT. Media | Approved | sunitas
GANGA ALTUS | 1 | 4 | 01 Feb 2020 | OM SAI CORP | PRINTING Flex Printing | Flex Printing & Pasting | Sq.Ft | 2200 | 20 | 44000 | 7920 | 51920 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | Ganga Altus Project Laundching Arch - Star Flex Print with Pasting Size as 30x3 Sq Ft Qty 6 Top Side, and Left - Right Arch Size as 17x3 Sq Ft Qty. 24 Total 3 Arch Making | 0 |  | tejas | sunitas | construction open | 01 Feb 2020 |  | MKT. Media | Approved | sunitas