## Project_Work_Order6385855451790
Project Work Order
From 07 Jul 2024 To 07 Aug 2024
Page 1 of 1
Total Records: 43 Records 1 To 43
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
TANGEWALA COLONY SRA PROJECT NEW | 1 | 0 | 11 Jun 2024 | SUPREME ENGINEERS | RAFT & RETAINING WALL | RCC Work - Mkt | Sq.Ft | 162.53 | 90 | 14627.7 | 2632.98 | 17260.68 | 2.5 | 0 | 0 | 0 | 0 | 162.53 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jun 2024 |  | MKT. Marketing Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 2 | 0 | 11 Jun 2024 | MAHALAXMI BUILDCON | RAFT & RETAINING WALL | Concrete work (M). | Cu.Mtrs | 109.38 | 6330.7 | 692451.97 | 124641.36 | 817093.33 | 0 | 0 | 0 | 0 | 0 | 109.38 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jun 2024 |  | No category | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 2 | 0 | 11 Jun 2024 | MAHALAXMI BUILDCON | RAFT & RETAINING WALL | Reinforcement (M) | Kgs | 14860.04 | 65 | 965902.6 | 173862.46 | 1139765.06 | 0 | 0 | 0 | 0 | 0 | 14860.04 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jun 2024 |  | 02 RCC WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 2 | 0 | 11 Jun 2024 | MAHALAXMI BUILDCON | RAFT & RETAINING WALL | Concrete work (M). | Cu.Mtrs | 6.99 | 6330.7 | 44251.59 | 7965.28 | 52216.87 | 0 | 0 | 0 | 0 | 0 | 6.99 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jun 2024 |  | No category | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 2 | 0 | 11 Jun 2024 | MAHALAXMI BUILDCON | RAFT & RETAINING WALL | Reinforcement (M) | Kgs | 768.72 | 65 | 49966.8 | 8994.02 | 58960.82 | 0 | 0 | 0 | 0 | 0 | 768.72 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 20 Jun 2024 |  | 02 RCC WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 4 | 0 | 11 Jun 2024 | MAHALAXMI BUILDCON | A & B Building Grade Slab & Soling Work | Soling Work -Mkt | Sq.Ft | 4582.77 | 22.3 | 102195.77 | 18395.24 | 120591.01 | 0 | 0 | 0 | 0 | 0 | 4582.77 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Jun 2024 |  | MKT. Marketing Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 23 | 1 | 01 Jul 2024 | SUPREME ENGINEERS | Excavation Work By Department Labour | Department Labour - DEn | No. | 16 | 900 | 14400 | 2592 | 16992 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Jul 2024 |  | DEV. Entrance Gate | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 23 | 1 | 01 Jul 2024 | SUPREME ENGINEERS | Excavation Work By Department Labour | Breaker | Day | 4 | 600 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Jul 2024 |  | B.C. Building Common Items | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 24 | 0 | 09 Jul 2024 | JIVAN DEVIDAS ADSUL | Tree Cutting Work | Tree cutting Work - LC | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2024 |  | Land Cost | Approved | Swapnil Erande
TANGEWALA COLONY SRA PROJECT NEW | 25 | 0 | 09 Jul 2024 | NITIN D PARDESHI | Site Electricity expenses | Electricity Bills | No. | 7 | 100000 | 700000 | 0 | 700000 | 0 | 0.5308 | 53080 | 0 | 53080 | 6.4692 | 646920 |  | 7.5829 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Jul 2024 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande
TANGEWALA COLONY SRA PROJECT NEW | 26 | 0 | 12 Jul 2024 | SUKHAKARTA ENTERPRISES | Admin & Office Expenses | Internet Connection | Month | 12 | 700 | 8400 | 0 | 8400 | 0 | 12 | 8400 | 0 | 8400 | 0 | 0 | 50 MBPS | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2024 |  | 14 MISC WORK | Approved | Swapnil Erande
TANGEWALA COLONY SRA PROJECT NEW | 26 | 0 | 12 Jul 2024 | SUKHAKARTA ENTERPRISES | Admin & Office Expenses | ONU Syrotech | No. | 1 | 1200 | 1200 | 0 | 1200 | 0 | 1 | 1200 | 0 | 1200 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 19 Jul 2024 |  | No category | Approved | Swapnil Erande
TANGEWALA COLONY SRA PROJECT NEW | 27 | 0 | 16 Jul 2024 | MAHALAXMI BUILDCON | Partition Wall | Reinforcement (M) | Kgs | 2042.46 | 65 | 132759.9 | 23896.78 | 156656.68 | 0 | 0 | 0 | 0 | 0 | 2042.46 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 02 RCC WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 27 | 0 | 16 Jul 2024 | MAHALAXMI BUILDCON | Partition Wall | Concrete - M20 | Cu.Mtrs | 30.54 | 5487 | 167572.98 | 30163.14 | 197736.12 | 0 | 0 | 0 | 0 | 0 | 30.54 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 02 RCC WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 28 | 0 | 18 Jul 2024 | SUPREME ENGINEERS | Partition Wall | RCC Work - Mkt | Sq.Ft | 3288.94 | 150 | 493341 | 88801.38 | 582142.38 | 2.5 | 0 | 0 | 0 | 0 | 3288.94 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | MKT. Marketing Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 30 | 650 | 19500 | 0 | 19500 | 0 | 30 | 19500 | 0 | 19500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 31 | 650 | 20150 | 0 | 20150 | 0 | 31 | 20150 | 0 | 20150 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 30 | 650 | 19500 | 0 | 19500 | 0 | 30 | 19500 | 0 | 19500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 31 | 650 | 20150 | 0 | 20150 | 0 | 31 | 20150 | 0 | 20150 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 31 | 650 | 20150 | 0 | 20150 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 30 | 650 | 19500 | 0 | 19500 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 31 | 650 | 20150 | 0 | 20150 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 30 | 650 | 19500 | 0 | 19500 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 29 | 0 | 19 Jul 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 31 | 650 | 20150 | 0 | 20150 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 01 Aug 2024 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 30 | 0 | 27 Jul 2024 | S.R.Enterprises | Fogging work | Fogging work-SO | Month | 1 | 3000 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 31 | 0 | 27 Jul 2024 | SUPREME ENGINEERS | A- Murum filling, Bobcat & Compactor | Murrum Filling | Brass. | 400 | 715 | 286000 | 51480 | 337480 | 0 | 0 | 0 | 0 | 0 | 400 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 01 EARTHWORK & ROADWORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 31 | 0 | 27 Jul 2024 | SUPREME ENGINEERS | A- Murum filling, Bobcat & Compactor | Bobcat Hiring Charges | Hrs | 120 | 900 | 108000 | 19440 | 127440 | 0 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 01 EARTHWORK & ROADWORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 31 | 0 | 27 Jul 2024 | SUPREME ENGINEERS | A- Murum filling, Bobcat & Compactor | Roller for Levelling -SOS | Day | 5 | 4500 | 22500 | 4050 | 26550 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | S OH Infrastructure | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 32 | 0 | 03 Aug 2024 | PRAKASH CONTRACTOR | Department Labour | Department Labour- BC | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 03 Aug 2024 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 03 Aug 2024
TANGEWALA COLONY SRA PROJECT NEW | 33 | 0 | 06 Aug 2024 | AQUARIUS WATERPROOFING | A & B Building- Membrane W/P Vertical & Horizontal | Membrane Horizontal Waterproofing (L) | Sq.Ft | 1315.68 | 13 | 17103.84 | 3078.7 | 20182.54 | 10 | 0 | 0 | 0 | 0 | 1315.68 | 0 | Membrane Waterproofing work for A & B-Bldg Retaining wall, Raft and Footing area. | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 06 WATERPROOFING WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 33 | 0 | 06 Aug 2024 | AQUARIUS WATERPROOFING | A & B Building- Membrane W/P Vertical & Horizontal | Membrane Vertical Waterproofing (L) | Sq.Ft | 6655.55 | 15 | 99833.25 | 17969.98 | 117803.23 | 10 | 0 | 0 | 0 | 0 | 6655.55 | 0 | Membrane Waterproofing work for A & B-Bldg Retaining wall, Raft and Footing area. | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 06 WATERPROOFING WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 34 | 0 | 06 Aug 2024 | AQUARIUS WATERPROOFING | A & B Building- Membrane W/P Vertical & Horizontal | Membrane Horizontal Waterproofing (M) | Sq.Ft | 1315.68 | 34 | 44733.12 | 8051.96 | 52785.08 | 0 | 0 | 0 | 0 | 0 | 1315.68 | 0 | Membrane Waterproofing work for A & B-Bldg Retaining wall, Raft and Footing area. | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 06 WATERPROOFING WORK | Un-Approved
TANGEWALA COLONY SRA PROJECT NEW | 34 | 0 | 06 Aug 2024 | AQUARIUS WATERPROOFING | A & B Building- Membrane W/P Vertical & Horizontal | Membrane Vertical Waterproofing (M) | Sq.Ft | 6655.55 | 40 | 266222 | 47919.96 | 314141.96 | 0 | 0 | 0 | 0 | 0 | 6655.55 | 0 | Membrane Waterproofing work for A & B-Bldg Retaining wall, Raft and Footing area. | 0 |  | ADITYA.CHOUGULE |  | construction open |  |  | 06 WATERPROOFING WORK | Un-Approved